## IDT PORTFOLIO LOGFRAME
PROJECT NAME | Strategic collaboration with UK statistics system
IMPACT | Impact Indicator 1 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
Quality, timely, reliable and disaggregated data is available and used worldwide to support delivery of the Global Goals and ensure no one is left behind. | World Bank Statistics Capacity Building Score for primary partner countries: - Kenya (KNBS) - Ghana (GSS) - Rwanda (NISR) | Planned | Kenya 57.8 Ghana 68.9 Rwanda 77.8 | (No target documented) | Kenya 57 Ghana 73 Rwanda 80 | Kenya 58 Ghana 74 Rwanda 81 | Kenya 59 Ghana 75 Rwanda 82
|  | Achieved |  | Kenya 55.6 Ghana 77.8 Rwanda 65.6 | Kenya 57.8 Ghana 77.8 Rwanda 65.6
Source
World Bank Statistics Capacity Building Score http://datatopics.worldbank.org/statisticalcapacity/
| Impact Indicator 2 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of SDG indicators with at least one data point in the last five years (for primary partner countries): - Ethiopia (ACS, part of UNECA) - Kenya (KNBS) - Ghana (GSS) - Rwanda (NISR) | Planned | Rwanda 56
Achieved
Source
SDG team
OUTCOME1 | Outcome Indicator 1.1 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March) | Assumptions
Increased availability and frequency of high quality disaggregated data | Cumulative number of case studies of changes in quality, frequency or coverage of national data sets in partner countries which demonstrate some contribution from ONS and moderate or major impact (see methodology) | Planned | 0 | 1 | 5 | 10 | 12
|  | Achieved |  |  | 11 | 8
Source
ONS case studies, reviewed and scored by FCDO, according to methodology
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£)
INPUTS (HR) | FCDO (FTEs)
OUTCOME2 | Outcome Indicator 2.1 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March) | Assumptions
Increased capability of partner NSOs | Cumulative number of case studies of capacity building in partner countries which demonstrate some contribution from ONS and moderate or major impact (see methodology) | Planned | N/A | N/A | N/A | 10 | 12
|  | Achieved | N/A | N/A | N/A | 10
Source
ONS case studies, reviewed and scored by FCDO, according to methodology
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£)
INPUTS (HR) | FCDO (FTEs)
TIER 1 PARTNERSHIPS
OUTPUT 1 | Output Indicator 1.1 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March) | Assumption
Kenya National Bureau of Statistics increases the availability and quality of SDG data, and capacity is built, with ONS support | Measure of partner commitment towards establishing and maintaining an effective partnership with ONS (see partnership indicators tab) | Planned | 0 | 2 | 3 | 3 | 3 | Senior leadership changes do not throw partnership aims off course. Partner able to engage with remote assistance.
|  | Achieved |  | 1 | 3 | 3
Source
FCDO and ONS joint assessment
| Output Indicator 1.2 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of national statistical strategies / sectoral modernisation plans / guidelines or equivalent developed informed by ONS support and advice (cumulative) | Planned | 0 | 0 | 2: (communications strategy and strategic plan) | 4; (cumulative - + Code of Practice and NSDS) | 5 (cumulative)
|  | Achieved |  |  | 2 | 3 (2 complete 1underway)
Source
KNBS/ONS reporting; Indicator added in 18/19
| Output Indicator 1.3 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of Case Studies and stories of change where ONS support in the 5 partnerships objectives (Leadership; Statistical Operating Frameworks; Data Visualisation & Dissemination; Census, Surveys & Admin Data; and Data Science & Development) has helped improve KNBS operations. (cumulative) | Planned | 0 | 0 | 2 | 4 | 6
|  | Achieved |  |  | 2 | 5
Source
KNBS/ONS reporting; Indicator added in 18/19
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
15% | Number of people trained with ONS support and rating training as effective (cumulative) | Planned | 0 | 0 | 5 | 15 | 30
|  | Achieved |  |  | 0 | 21
|  | Source | [5 empty] | RISK RATING
|  | KNBS/ONS reporting; Indicator added in 18/19 | [5 empty] | Medium
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
550000
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March) | Assumptions
Ghana Statistical Service increases the availability and quality of SDG data, and capacity is built, with ONS support | Measure of partner commitment towards establishing and maintaining an effective partnership with ONS (see partnership indicators tab) | Planned | 0 | 2 | 3 | 3 | 3 | Strategic Adviser is able to remain engaged remotely with GSS and FCDO Senior leadership changes do not throw partnership aims off course. GSS commitment to partnership remains high given changing modality. Partner able to engage with remote assistance.
|  | Achieved |  | 1 | 3 | 4
Source
FCDO and ONS joint assessment
| Output Indicator 2.2 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of cases of where ONS have provided advice on strategic policy documents: (e.g. Statistical Bill, communications strategy, other policy documents) and there is evidence that this advice has had an influence on the final product (cumulative) | Planned | 0 | 0 | 2 | 3 | 5
|  | Achieved |  |  | 4 | 7
Source
ONS reporting: Indicator added in 2018 AR
| Output Indicator 2.3 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of leaders mentored and/or trained by ONS support, and rating training as effective (cumulative number of individuals) | Planned | 0 | 0 | 20 | 50 | 60
|  | Achieved |  |  | 41 | 70
Source
ONS reporting Indicator added in 2018 AR
| Output Indicator 2.4 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of stories of where ONS support has enabled GSS to fill SDG data gaps, using admin data or other sources (cumulative). | Planned | 0 | 0 | 3 (2 from the following examples: SDGs NRP, data templates (inc metadata) and new data sources groundwork ) | 5 | 7
|  | Achieved |  |  | 2 | 7
Source
ONS reporting Indicator added in 2018 AR
IMPACT WEIGHTING (%) | Output Indicator 2.5 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
15% | Examples of where ONS support has led to more rigorous statistical infrastructure and systems; that are sustainable and promote good practice (e.g. statistical standards and concepts, adoption of national or international standards, programmes to upskill staff etc) | Planned | 0 | 0 | 2 | 3 | 5
|  | Achieved |  |  | 3 | 6 - but all partial
|  | Source | [5 empty] | RISK RATING
|  | ONS reporting Indicator added in 2018 AR | [5 empty] | Medium
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
550000
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March) | Assumptions
Rwanda Statistics Office increases the availability and quality of SDG data, and capacity is built, with ONS support | Measure of partner commitment towards establishing and maintaining an effective partnership with ONS (see partnership indicators tab) | Planned | 0 | 2 | 3 | 3 | 3 | GoR support for legal reforms. Supportive environment for innovation in NISR and broader GoR. Engagement from stakeholders also involved in data science in Rwanda (other government departments, universities etc) NISR are able to recruit dedicated data science staff World Bank and GoR commitment to complete training centre Partner able to engage with remote assistance.
|  | Achieved |  | 3 | 3 | 3
Source
FCDO and ONS joint assessment
| Output Indicator 3.2 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of cases where ONS has provided advice on strategic douments (eg. national statistical strategies, sectoral modernisation plans, NISR strategies and policies or equivalent) (cumulative) | Planned | 0: NSDS 2 evaluation supported by ONS in 2017, concluded that NSDS 3 needs to integrate data revolution policy | 1: NSDS3 drafted by June 2018 with clear integration of data revolution strategy as informed by ONS advice in areas such as capability, IT and legal frameworks | 1: Final NSDS published with clear evidence of ONS inputs. Progress towards NSDS3 objectives being made | Target: 5 Total: NSDS from previously plus 3 first drafts + 1 completed document. First drafts: Security Strategy, Data Protection law, Data Management Policy Complete: QA protocol for SDG indicators published and being implemented (adapted, increased) | Target: 8 examples where ONS has advised on the draft of a new policy or refine an existing policy or draft policy.
|  | Achieved |  | 2: Two completed documents, plus ongoing advice on legal framework that is shaping NISR’s approach but has not yet resulted in a published document - NSDS3 finalised with clear evidence of ONS inputs. - Terms of Reference for ICT infrastructure tender published online in July 2019 | 2 | 6
Source
NISR / ONS reporting Target was added just prior to 2018 annual review and didn’t count for scoring
| Output Indicator 3.3 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of active or complete data science projects ONS has supported (e.g. scoping, mentorship) (cumulative) | Planned | None | One project underway | One published and one more underway | Target: 5 2 scoped (GIS visit) 2 with active mentorship 1 complete (BNR visualisation). | Target: 8 3 scoped 2 with active mentorship 3 complete
|  | Achieved |  | One project (SDG platform) underway and two more being scoped | 1 | 5 Three complete and two scoped/with active mentorship. ONS has also designed processes to improve the effectiveness and sustainability of mentor projects.
Source
NISR / ONS reporting Target was added just prior to 2018 annual review and didn’t count for scoring
| Output Indicator 3.4 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of case studies where ONS has supprted the development of training materials/learning resources (cumulative) | Planned | 0 | 1: milestones towards establishing NISR Training Centre and Data Hub on track | 1: milestones towards establishing NISR Training Centre and Data Hub on track | Target: 3 - Training facilitators for L&C training - Develop induction materials for new data science team | Target: 4 - Revised capability-building plan for data science
|  | Achieved |  | 1: in 2018 ONS data science campus undertook training needs assessment and developed a draft capability plan | 1 | 5. Train the trainer Leadership and Commmunication Training Visualising data in R online training Data Science Induction materials A bank of online learning resources and advice on delivering online training (responding to COVID)
Source
NISR / ONS reporting Target was added just prior to 2018 annual review and didn’t count for scoring
| Output Indicator 3.5 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of instances where people are trained with ONS support, and rated training as effective (cumulative) Note: if one person attends 2 different courses they will be counted twice (once for each course) | Planned | 0 | 180 | 270 | 100 | 150
|  | Achieved |  | 1 | 50 | 131
Source
NISR / ONS reporting Target was added just prior to 2018 annual review and didn’t count for scoring
| Output Indicator 3.6 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of SDG indicators where ONS has provided methodological advice to either fill a data gap or improve the quality of existing data for that indicator | Planned | N/A | N/A | N/A | 1 | 3
|  | Achieved | N/A | N/A | N/A | 3 partial
Source
NISR / ONS reporting
IMPACT WEIGHTING (%) | Output Indicator 3.7 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
15% | Number of staff upskilled by ONS to update SDG indicators in SDMX format, and publish on Open SDG platform (e.g. virtual training sessions/ demos, coaching, facilitation of staging site for testing, provision of ‘how to’ guides and resources, troubleshooting support e.g. in relation to SDMX structure of data) | Planned |  |  |  | 0 | 2
|  | Achieved |  |  |  | 0
Source
NISR / ONS reporting. Additional SDG indicator for March 2021 reflecting NISR prioritisation of ONS SDG support
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%) | RISK RATING
| 576355 | [5 empty] | 100% | Medium
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March) | Assumptions
UNECA provide an enabling environment for African National Statistics Offices, with ONS support | Measure of partner commitment towards establishing and maintaining an effective partnership with ONS (see partnership indicators tab) | Planned | 0 | 2 | 3 | 3 | 3 | Return to work in Addis of UNECA and ONS team. No further shut downs of Ethiopian internet connections. FCDO is supportive of support of ONS in non partner countries via UNECA. Partner able to engage with remote assistance.
|  | Achieved |  | 2 | 2 | 3
Source
FCDO and ONS joint assessment
| Output Indicator 4.2 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of Examples where ONS and UNECA have supported improvements to national statistics through support on specific topics (e.g. census, economic statistics, or CRVS ) | Planned | 0 | 0 | 3 | 8 | 11
|  | Achieved |  |  | 2 | 8
Source
ONS reporting: Indicator added in 2018/19
| Output Indicator 4.3 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of Africa Statistical Leaders mentored or trained through UNECA led, ONS supported training, and rated training as effective | Planned | 0 | 0 | 30 | 60 | 89
|  | Achieved |  |  | 0 | 64
Source
ONS reporting: Indicator added in 2018/19
| Output Indicator 4.4 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of Case Studies of where ONS support and delivery of the workplan has helped deliver changes to how UNECA operates | Planned | 0 | 0 | 2 | 5 | 8
|  | Achieved |  |  | 2 | 5
Source
ONS reporting: Indicator added in 2018/19
IMPACT WEIGHTING (%) | Output Indicator 4.5 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
15% | Number of examples where ONS has supported UNECA to build its data science capacity OR supported UNECA or member states in the application of data science techniques OR jointly worked with African countries on data science projects, either active or complete | Planned | 0 | 0 | 1 | 2 | 4
|  | Achieved |  |  | 0 | 1 and 1 partial
|  | Source | [5 empty] | RISK RATING
|  | ONS reporting: Indicator added in 2018/19 | [5 empty] | Medium
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
550000
INPUTS (HR) | FCDO (FTEs)
GLOBAL PROGRAMMES | 5A) International Cooperation: influencing on statistical modernisation | [6 empty] | Assumptions
OUTPUT 5 | Output Indicator 5.1 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March) | Reputation of ONS continutes to drive interest in global products beyond core partner countries. Effective remote advice is possible.
| Weighted average (by spend) of scores for flexible facility activities related to ONS engagement in key data for development international events | Planned | Not measured | A | A | A | A
|  | Achieved |  | A++ | A+ | A
Source
Each relevant flexible facility project will set out clear targets and indicators in the terms of reference, which must be agreed by the FCDO/ONS steering committee. These will be monitored after the event and reported back to the steering committee. A weighted average of the scores (on the scale A++, A+, A, B, C) using FCDO output scoring methodology will be calculated as part of the annual review.
5B) SDGs: ; advice and TA on SDG monitoring, reporting, and data disaggregation
| Output Indicator 5.2 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Number of case studies of partner countries successfully cloning and using UK/US SDG platform as a direct result of ONS support (cumulative) | Planned | 0 | 1 | 3 | 5 | 6
|  | Achieved |  | 2 | 3 | 5
Source
Case Studies to be documented by ONS and verified by national NSO. Case studies count if ONS provided direct inputs and they have gone on to use / publish / further develop the tool.
| Output Indicator 5.3 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Expert advice on data disaggregation to support the SDGs and the leave no one behind agenda provided to champions in the implementation of their IDC action plans. | Planned | N/A | N/A | N/A | 1 | 3
|  | Achieved | N/A | N/A | N/A | 2
Source
Case Studies to be documented by ONS and verified by national NSO. Case studies count if ONS provided direct inputs and they have gone on to use / publish / further develop the tool.
C) Economic Stats (leadership and effective TA);
| Output Indicator 5.4 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Effective progress towards targets in workplan for project to improve the quality consistency and dissemination of statistics on employment and productivity | Planned | N/A | A | A | A | A
|  | Achieved |  | B | B | A
Source
Progress towards milestones as set in project TORs documented by ONS and verified by FCDO technical lead on this project
| Output Indicator 5.5 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Effective participation of ONS in ICP technical working groups | Planned | No participation | Workplan developed and participation initiated. Targets for future years set. | A | A | NO TARGET - de-prioritised by partner and steering committee
|  | Achieved |  | Targets for ONS participation have been set and participation has been initiated. | A | N/A - wasn’t required by partner
Source
Progress towards milestones as set in project TORs documented by ONS and verified by FCDO technical lead on this project
D) Data Science; awareness raising, projects and capability building
| Output Indicator 5.6 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
| Effective delivery of data science capability for international development via the campus hub in FCDO (see matrix of targets for project delivery, mentoring and capacity building) | Planned | N/A | N/A | A | A | A
|  | Achieved |  | N/A | A+ | A+
Source
Progress towards milestones as set in project TORs documented by ONS and verified by FCDO technical lead on this project
| Output Indicator 5.7 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March)
IMPACT WEIGHTING (%) | Effective progress towards developing a new tool for storing, and analysing results data | Planned | N/A | N/A | A | A | A
30% |  | Achieved |  | N/A | A | A
|  | Source | [5 empty] | RISK RATING
|  | Progress towards milestones as set in project TORs documented by ONS and verified by FCDO technical lead on this project | [5 empty] | Medium
| FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (£) | £2.3 million?
FCDO (FTEs)
INPUTS (HR)
TIER 2 PARTNERSHIPS
OUTPUT 6 | Output Indicator 6.1 |  | Baseline 2017 (June) | Milestone 2018 (June) | Milestone 2019 (June) | Milestone 2020 (June) | Target 2021 (March) | Assumptions
Deliver effective TA to Tier 2 partner countries in identified areas: | Number of Tier 2 MoUs signed, with partners satisfied or very satisfied with support provided | Planned | N/A | N/A | N/A | N/A | 3 | Support of FCDO in country to forge new light touch MoUs with interested NSOs. Ability to work remotely.
Achieved
Source
ONS reporting: Indicator added in 2018/19
IMPACT WEIGHTING (%) | Output Indicator 6.2
10%
RISK RATING
Medium
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)

## Ref Outcome 1.1 Method
1.1 Cumulative number of case studies of changes in quality, frequency or coverage of national data sets in partner countries which demonstrate some contribution from ONS and moderate or major impact (see methodology)
| Contribution of ONS | Major |  | Count these for narrative reporting but not scored towards the target | Score case studies in this area
Moderate
Some Minor
Insignificant
|  |  | Insignificant | Minor | Moderate | Major
Impact on national data sets

## Ref Partnership indicators
Measure of partner commitment towards establishing effective partnership with ONS
| 4 | 3 | 2 | 1 | 0
| Agenda being fully driven by partner: setting the priorities, pushing ONS to deliver in a timely way | Partner engages positively and proactively ensures that ONS support is being channelled to their most pressing needs | Partner engaged with ONS, respond positively and quickly to suggestions for support, provides their views openly and in a timely way e.g on the priorities and timings for the activities | Agreement that a partnership would be beneficial, but limited evidence of commitment from partner so far, content of partnership and timings for visits largely being driven by ONS. | Only very preliminary indication of commitment from partner for a partnership with ONS
Partner | 2017 (baseline) | 2018 (target) | 2018 (actual) | 2019 (target) | 2019 (actual) | 2020 (target) | 2020 (actual) | 2021 target | 2021 actual
Rwanda | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3
Kenya | 0 | 2 | 1 | 3 | 3 | 3 | 3 | 3
Ghana | 0 | 2 | 1 | 3 | 3 | 3 | 4 | 3
UNECA | 0 | 2 | 2 | 3 | 2 | 3 | 3 | 3

## Ref DS Campus Method
PCR (March 2021) Targets for the data science hub (indicator 5.6) - each row is assessed independently and an average taken, with the adminisration row having lower weight in calculation of the average
| C | B | A | A+ | A++
Decision support tool scoping | No ideas ready for Discovery and no real sense of prioritisation or links to the theory of change. | A long list of project proposals ready, prioritised, with a short list of scoped projects ready for exploratory work. Projects underway. | As B, and at least one demonstrator project that illustrates the unique offers of the Data Science Hub and can be used in decision making for those in the International Development community. | As A, plus more than one demonstrator project, or at least one which demonstrated real impact through its use in the international development community. | The Hub is a ubiquitous brand for Data Science, with multiple tools that are used widely in decision making across the SDG-delivery community.
Mentoring and consultancy | At most some of the data science staff engaging periodically with only FCDO staff. | Each of the Data Scientists recruited has established a relationship with an external organisation through face to face contact, and has regular contact with FCDO staff. | Each of the data scientists recruited also has a strategic mentoring relationship through which they are helping to automate the use of data in a partner organisation. The team have provided commercial advice within FCDO. | A demonstrated impact on automating the use of data in a partner organisation, due to these mentoring relationships can be seen. The team have provided strategic and commercial advice to other organisations. | The Hub is widely recognised as leading transformation of the SDG-delivery community towards evidence based decision making.
Capacity | Some or no assessments made of learner needs for Data Science training generally, without an assessment of suitability for SDG-delivery. | Assessments made of learner needs in some areas of data science, for both producers and consumers of data science in the SDG-delivery community. Some materials prepared and adapted, in line with needs. | A comprehensive report on available materials, and the adaptations needed to use them in international development context, plus some adapted materials and methodologies. Training is being delivered to external organisations. | A comprehensive report, and a full suite of new and adapted materials. Training is being rolled out to other organisations as part of preparing them to take over maintenance of some decision support tool. | The Hub is widely recognised as leading transformation of the SDG-delivery community towards evidence based decision making.
Administration | Some or none of the key planning documents developed, and not used in decision making. | Theory of change, risk register, issue register and stakeholder map all developed in a consultative way and being periodically used and updated. | Theory of change, risk register, issue register and stakeholder map all developed in a consultative way and being regularly used and updated. | All documents in place, and evidence that these are really driving decisions and enabling the hub to be most effective. | The Hub’s processes and history can be used as an exemplar to other organisations for how to run a capability building programme.
PCR (March 2021) Targets for 5.7:
C | B | A | A+ | A++
The REX project has not allowed the Climate portfolio’s 2021 Results Commission to complete according to plan, and a contingency approach has had to be adopted. | The REX generic tool has met the fundamental expectations of the Climate portfolio’s 2021 results commission, with some manual data collection needed alongside, beyond levels needed for the current Knowledge Platform solution. | REX has been used successfully to capture the Climate portfolio’s 2021 results commission, meeting all the data needs of the portfolio representatives. Theory of Change and Contribution Mapping functionality is working and Governance portfolio users can input data. | As with (A), and the tool has seen sufficient data input from the Governance and Syria portfolios to demonstrate potential analyses. User needs have been established for further pilot portfolios. Discussions with external organisations about adoption of the REX standard have early agreement. | As (A+) and REX has been adopted as part of plans to systematically record the contribution of FCDO activities to strategic objectives.
Decision support tool scoping
Mentoring and consultancy
Capacity

## AR 2019
Strategic collaboration with UK statistics system
Results Chain |  |  |  | Indicators | Planned | Achieved | Score |  | Source
2019
IMPACT | Quality, timely, reliable and disaggregated data is available and used worldwide to support delivery of the Global Goals and ensure no one is left behind. |  | World Bank Statistics Capacity Building Score for primary partner countries: - Kenya - Ghana - Rwanda |  | 0% | 0% |  | #N/A | 0
|  |  | Number of SDG indicators with at least one data point in the last five years (for primary partner countries): - Kenya - Ghana - Rwanda |  | 0 | 0 |  |  | 0
OUTCOME | Increased availability and frequency of high quality disaggregated data |  | Cumulative number of case studies of changes in quality, frequency or coverage of national data sets in partner countries which demonstrate some contribution from ONS and moderate or major impact (see methodology) |  | 5 | 0 |  | #N/A | ONS reporting
|  |  | 0 | [5 empty] | 0
OUTPUTS | Kenya National Bureau of Statistics increases the availability and quality of SDG data, with ONS support | 15% | 1.1 | Progress towards establishing an effective project workplan (see partnership indicators tab) | 4 | 0 |  | #N/A | DFID and ONS joint assessment
|  |  | 1.2 | Measure of partner commitment towards establishing effective partnership with ONS (see partnership indicators tab) | 3 | 0 |  |  | DFID and ONS joint assessment
|  |  | 1.3 | Number of national statistical strategies / sectoral modernisation plans or equivalent developed informed by ONS support and advice | 2: (communications strategy and stratgic plan) | 0 |  |  | KNBS/ONS reporting; Indicator added in 18/19
|  |  | 1.4 | Number of stories of change of where ONS support and delivery of the workplan has helped deliver changes to how KNBS operates | 3 | 0 |  |  | KNBS/ONS reporting; Indicator added in 18/19
|  |  | 1.5 | Number of people trained with ONS support and rating training as effective | 5 | 0 |  |  | KNBS/ONS reporting; Indicator added in 18/19
| Ghana Statistical Service increases the availability and quality of SDG data, with ONS support | 15% | 2.1 | Progress towards establishing an effective project workplan (see partnership indicators tab) | 4 | 0 |  | #N/A | DFID and ONS joint assessment
|  |  | 2.2 | Measure of partner commitment towards establishing effective partnership with ONS (see partnership indicators tab) | 3 | 0 |  |  | DFID and ONS joint assessment
|  |  | 2.3 | Number of cases of where ONS have provided advice on strategic policy documents: (e.g. Statistical Bill, communications strategy, other policy documents) and there is evidence that this advice has had an influence on the final product (cumulative) | 0 | 0 |  |  | ONS reporting: Indicator added in 2018 AR
|  |  | 2.4 | Number of stories of where ONS support has enabled GSS to fill SDG data gaps, using admin data or other sources (cumulative). | 20 | 0 |  |  | ONS reporting Indicator added in 2018 AR
|  |  | 2.5 | Number of stories of where ONS support has enabled GSS to fill SDG data gaps, using admin data or other sources (cumulative). | 3 | 0 |  |  | ONS reporting Indicator added in 2018 AR
|  |  | 2.6 | Examples of where ONS support has led to more rigorous statistical infrastructure and systems; that are sustainable and promote good practice (e.g. statistical standards and concepts, adoption of national or international standards, programmes to upskill staff etc) | 0 | 0 |  |  | ONS reporting Indicator added in 2018 AR
| Rwanda Statistics Office increases the availability and quality of SDG data, with ONS support | 15% | 3.1 | Progress towards establishing an effective project workplan (see partnership indicators tab) | 4 | 0 |  | #N/A | DFID and ONS joint assessment
|  |  | 3.2 | Measure of partner commitment towards establishing effective partnership with ONS (see partnership indicators tab) | 3 | 0 |  |  | NISR / ONS reporting Target was added just prior to 2018 annual review and didn’t count for scoring
|  |  | 3.3 | Number of national statistical strategies / sectoral modernisation plans or equivalent informed by ONS advice | 1: Final NSDS pubished with clear evidence of ONS inputs. Progress towards NSDS3 objectives being made | 0 |  |  | NISR / ONS reporting Target was added just prior to 2018 annual review and didn’t count for scoring
|  |  | 3.4 | Number of joint data science projects, with published results | One published and one more underway | 0 |  |  | NISR / ONS reporting Target was added just prior to 2018 annual review and didn’t count for scoring
|  |  | 3.5 | Number of Stories of change of where ONS has helped NSOs to develop training materials / capacity development approaches | 1: milestones towards establishing NISR Training Centre and Data Hub on track | 0 |  |  | NISR / ONS reporting Target was added just prior to 2018 annual review and didn’t count for scoring
|  |  | 3.6 | Number of people trained with ONS support, and rating training as effective (cumulative) | 270 | 0 |  |  | NISR / ONS reporting Target was added just prior to 2018 annual review and didn’t count for scoring
| UNECA provide an enabling environment for African National Statistics Offices, with ONS support | 15% | 4.1 | Progress towards establishing an effective project workplan (see partnership indicators tab) | 3 | 0 |  | #N/A | DFID and ONS joint assessment
|  |  | 4.2 | Measure of partner commitment towards establishing effective partnership with ONS (see partnership indicators tab) | 3 | 0 |  |  | DFID and ONS joint assessment
|  |  | 4.3 | Number of examples of where ONS and UNECA have supported improvements to national statistics through support to the census office on specific topics (e.g. economic statistics, CRVS or gender data) | 3 | 0 |  |  | ONS reporting: Indicator added in 2018/19
|  |  | 4.4 | Number of Africa Statistical Leaders mentored or trained through UNECA led, ONS supported training, and rated training as effective | 30 | 0 |  |  | ONS reporting: Indicator added in 2018/19
|  |  | 4.5 | Number of stories of change of where ONS support and delivery of the workplan has helped deliver changes to how UNECA operates | 2 | 0 |  |  | ONS reporting: Indicator added in 2018/19
|  |  | 4.6 | Number of examples where ECA have supported African countries in the use/application of data science techniques or jointly worked with African countries on data science projects. | 1 | 0 |  |  | ONS reporting: Indicator added in 2018/19
|  |  | 4.7 | Number of examples of where ONS and UNECA have supported improvements to national statistics through support to the census office on specific topics (e.g. economic statistics, CRVS or gender data) | 3 | 0 |  |  | ONS reporting: Indicator added in 2018/19
| Flexible short term technical assistance delivers effective results | 40% | 5.1 | Weighted average (by spend) of scores for flexible facility activities related to ONS engagement in key data for development international events | A | 0 |  | #N/A | Each relevant flexible facility project will set out clear targets and indicators in the terms of reference, which must be agreed by the DFID/ONS steering committee. These will be monitored after the event and reported back to the steering committee. A weighted average of the scores (on the scale A++, A+, A, B, C) using DFID output scoring methodology will be calculated as part of the annual review.
|  |  | 5.2 | Number of case studies of partner countries successfully cloning and using UK/US SDG platform as a direct result of ONS support (cumulative) | 3 | 0 |  |  | Stories of change to be documented by ONS and verified by national NSO. Case studies count if ONS provided direct inputs and they have gone on to use / publish / further develop the tool.
|  |  | 5.3 | Effective participation of ONS in ICP technical working groups | A | 0 |  |  | Progress towards milestones as set in project TORs documented by ONS and verified by DFID technical lead on this project
|  |  | 5.4 | Effective progress towards targets in workplan for project to improve the quality consistency and dissemination of statistics on employment and productivity | A | 0 |  |  | Progress towards milestones as set in project TORs documented by ONS and verified by DFID technical lead on this project
|  |  | 5.5 | Effective progress towards targets in workplan for establishment of data science campus hub in DFID East Kilbride | A | 0 |  |  | Progress towards milestones as set in project TORs documented by ONS and verified by DFID technical lead on this project
#REF!
#REF!

## Ref Scoring
The below explains the meaning of the letter-based scoring approach. If, for example, an output is exceeded by 50% of the stated target, so achieves 150% or 1.5 times its intended value, it would lead to an A++ score at Annual Review.
A++ | 150%
A+ | 125%
A | 100%
B | 75%
C | 50%