## Annual Review Template – from April 2020

Title: Humanitarian protection for vulnerable refugees and host communities in Jordan
Programme Value £ (full life): £15,000,000		Review date:
Programme Code: 300537	AMP start date: 06/06/2018	AMP end date: 31/03/2021

Summary of Programme Performance
Year	2019	2020
Overall Output Score	A	A+
Risk Rating	Minor	Moderate

DevTracker Link to Business Case:	Business Case
DevTracker Link to results framework:	Logframe

A. SUMMARY AND OVERVIEW

Description of programme
The Syrian refugee crisis has placed a significant burden on Jordanian services at a time that the country is facing its own economic and social challenges. Syrian refugees and other vulnerable groups (including people lacking documentation, people with disabilities or mental health conditions, female-headed households, and children) can face significant difficulties in accessing the health, protection and other services they require to ensure their rights and wellbeing are protected. The protection programme is part of the DFID Jordan humanitarian programme which also includes multi-purpose cash assistance to the most vulnerable refugees. The combination of delivering both cash assistance and protection services (responding to needs such as lack of civil documentation, children at risk, or people with disabilities) ensures that the most vulnerable are able to cover their basic needs while having access to specialised services. The synergies between both programmes are important as neither one alone is sufficient in protecting refugee rights and supporting the resilience of vulnerable communities. These communities are particularly vulnerable as they do not have regular access to livelihoods opportunities or may be have members in their households who are disables or in need of other services which they are not able to receive. Supporting people to obtain civil documentation, for example, ensures they have a legal status in Jordan and can also support them in accessing public health services.

Through this programme, DFID is providing up to £15 million over three years to International Medical Corps (IMC), Norwegian Refugee Council (NRC), and Humanity and Inclusion (HI) to deliver life-changing activities to address basic protection needs of 62,167 of the most vulnerable Jordanians and refugees (including Syrians), in a way that promotes sustainability and resilience, and which also builds the capacity of local actors. Activities include:
- Legal counselling and case management (e.g. to enable people to obtain marriage and birth certificates);
- Health support for people in remote communities including persons with disabilities (PwD) requiring physical rehabilitation, mental health support, and psychosocial services;
- Child protection case management;
- Training for health professionals, community leaders and local NGOs on a wide range of topics including safeguarding and needs assessments; and
- Awareness-raising and advocacy on refugee rights through continuous community outreach and social media campaigns.

This programme is a result of an open call for proposals conducted in 2017 out of which these three partners were selected. The programme was then designed alongside the partners mentioned above. Providing protection services with the aim of improving people’s wellbeing is an area of focus deemed important to engage in; the needs in Jordan for these services are great.

While the programme consists of different components, DFID is seeking to strengthen how partners work together holistically on these issues in Jordan.

The major change in context over the period covering this Annual Review (AR) is the COVID-19 pandemic and associated lockdown measures introduced in Jordan. However, as these were introduced on March 17th 2020, and this AR covers the period until March 31st 2020, the effects of the lockdown are not covered extensively in this review.
[note] The AR was due in June 2020, but received an extension until September due to the COVID-19 crisis.

This review is based on partner narrative and financial reporting, quarterly meetings and field visits across Jordan, and feedback from beneficiaries.

Summary supporting narrative for the overall score in this review
Over the period covered by this review, the second year of the programme, partners exceeded expectations and the overall programme score is therefore an A+. Implementation is on track, with the majority of output indicators achieved or moderately over-achieved. The limited number of moderately under-achieved indicators are on track to be rectified and we are confident they will catch up in the last year of this programme.

Major lessons and recommendations for the year ahead
A number of lessons were learned during the past year of operation. A key lesson is the importance of the role of community volunteers and outreach teams which have proven to be effective in raising awareness among communities of available services, as well as referring cases to partners. This has helped improve trust with communities and expanded outreach to more remote areas. Similarly, investing in the capacity of local partners is beginning to show positive results with specific activities being conducted fully by downstream partners and local service providers. This not only ensures sustainability but lays the ground for stronger national systems that can provide services to both refugees and host communities.

Recommendations for the year ahead:
1. IMC to look at ways to engage with the new mental health and psychosocial support (MHPSS) department in the Ministry of Health (MoH), perhaps using training and capacity building as a way to contribute to building more sustainable national services.
2. DFID to follow-up closely with NRC on how research reports and policy briefs are being used, and if NRC can develop a tool to track any policy changes related to them to better measure their effectiveness.
3. All partners to cement the work done with local organisations throughout the project period, focusing efforts on building sustainability and enabling downstream partners to begin operating more independently where possible by applying learning from capacity building efforts. Capacity building should go beyond just training to real engagement and coaching where that is not already taking place, particularly on administrative functions like finance, HR, and M&E.
4. DFID to continue closely monitoring delivery risks related to COVID-19 lockdown (or possible return to lockdown), liaising with partners to ensure beneficiary needs continue to be met and protection of vulnerable people is maintained.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
This programme’s theory of change (ToC) is based on the delivery of specialised protection services to vulnerable households (including support to people with disabilities, child protection, mental health, and legal assistance) whereby improving the protection situation of vulnerable families and individuals will lead to an improvement in their wellbeing and social participation, and build their resilience towards future shocks. The programme also works on strengthening the capacity of national systems to respond to the needs of vulnerable groups; contributing to the enhanced wellbeing of refugees where they can live in safety and dignity. The assumptions that underpin this ToC are still valid; the Government of Jordan (GoJ) has granted authorisations for these activities to take place, the security environment remains stable, and refugee populations are not returning to Syria in large numbers. There has been no new evidence that challenges this ToC; partners continue to deliver on outcomes and impact as planned. No changes were made to agreed impact and outcome indicators, but a new outcome indicator was added to reflect additional activities that DFID is funding through Humanity and Inclusion (HI). This indicator tracks progress on HI’s work with the GoJ on the early detection and early intervention (ED/EI) of disabilities, where HI is working on updating and developing guidelines on ED/EI, to be approved by the GoJ by September 2020 subject to any required changes as a result of the Covid-19 situation. A review of output indicators took place in December 2019 with minor changes done to targets and wording (specifics changes are indicated in section C of this review). This was approved by the programme’s Senior Responsible Owner (SRO) with consultation with the lead Humanitarian Adviser/ Humanitarian Team Leader.
[note] Due to travel and movement restrictions related to COVID-19, HI has indicated that this work might be delayed until March 2021. No formal logframe changes have taken place yet as we await HI’s official request and justification.

In the period concerned the programme continued to be effective with partners delivering on outcomes as planned (as this review covers the period up until March 2020, COVID-19 effects on outcome delivery are not yet known. Outcome indicators and results are outlined below:
- Outcome indicator 1: Percentage of beneficiaries who report exercising their legal rights- 89% achieved out of a target of 75%
- Outcome indicator 2: Percentage of beneficiaries who rate the service provided positively- 83% achieved out of a target of 80%
- Outcome indicator 3: Percentage of beneficiaries showing improvement in functional independence- 80% achieved out of a target of 75%
- Outcome indicator 4: Number of instances where partner recommendations are reflected in targeted policies, decisions, and/or other arenas by GoJ- 14 achieved out of a target of 4
The DFID team continues to meet regularly with partners and have discussions with beneficiaries during field visits to ensure that the ToC is still relevant in this context. Feedback received reflects the positive results captured above.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme is on track to achieve the outcomes and impact set out in the Business Case (BC). Most outcome indicators are overachieved as shown above, albeit partners didn’t have robust baseline data on which to set targets as some activities were new. This is continuously reviewed as data becomes available but there is no immediate need to review targets. On outcome indicator 4, the overachievement is attributed to more work being done by NRC and HI on advocacy and policy. Particularly, NRC worked on producing more reports than planned and actively engaged in advocacy on topics related to refugee rights. Moreover, HI worked with a number of working groups within the Jordan Response Plan (JRP) to reflect disability inclusion within planning; a key element of the HI programme.

One impact indicator that is underachieving is one related to an increase in social participation by beneficiaries receiving rehabilitation services through HI. This has achieved 60% out of a target of 75% by March 2021. This is due to many external factors affecting social participation that are difficult to change in the medium term, such as cultural norms or certain disabilities that cause limited movement. HI has nonetheless increased this from 45% achieved in the first year of the project and continues to push for change through its community volunteers who have proven to be very effective.

There have been no significant unexpected outcomes to the programme and partners continue to deliver based on agreed budgets and timelines. The project is due to end in March 2021 with all indicators on track. The project also continues to deliver impact on gender equality as outlined in the BC through addressing the needs of women and girls through service delivery and referrals to other service providers providing counselling or psychosocial support. We continue to push partners to monitor the impact the programme is having on women and girls and ensure a ‘do no harm’ approach is applied consistently. This is partly achieved through influencing national policies that create an enabling environment for addressing protection needs. All partners are working with national service providers and coordinating with government bodies to contribute to that aim.

During the past year, both HI and NRC conducted external mid-term evaluations of the programme where recommendations and findings were discussed in detail with their teams. We also continue to follow-up on progress made against those recommendations. Findings from these evaluations showed that the interventions are efficient and respond to beneficiary needs. Particularly, NRC interventions to support people obtaining their legal and civil documentation have had significant impact where families now have birth certificates for their children and proof of parental links. The HI evaluation also showed that the programme has improved and expanded the quality of services available to people with disabilities at local and national levels.
IMC is planning for a project evaluation to take place towards the end of 2020. DFID has received the terms of reference (ToR) and has provided feedback on them to IMC.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
As the programme continues to deliver and the ToC still holds, we recommend that this programme should continue until its closure in March 2021. The DFID humanitarian team has also refreshed the humanitarian strategy for 2020-2023 where different programming options were evaluated based on UK commitments and policy priorities, overlaid with the context in Jordan. The strategy concludes that protection programming should continue, complemented by unconditional cash assistance to the most vulnerable; which is being delivered by another programme. Moreover, the work being undertaken to build the capacity and influence national service providers directly contributes to the wider portfolio’s trajectory of work on the humanitarian-development nexus; a key area of influence for DFID in Jordan.

## C. DETAILED OUTPUT SCORING

Output Title	Training and capacity building of key stakeholders including NGO staff, GOJ staff and community leaders
Output number:		1	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	Yes, up by 5%

Indicator(s)	Milestones for this review (March 2020)	Progress (March 2020)
1.1 # of national, local authorities, lawyers, jurists, law students and legal aid providers trained on access to justice issues for refugees	155	323 (208%)
1.2 # primary health care providers receive training, for example mhGAP, early detection/ early intervention (ED/EI) and mental health and psychosocial support (MHPSS)	185	303 (164%)
1.3 # of community actors and leaders that are empowered to support protection needs both in community settings and camps to influence service provision	275	302 (173%)
1.4 # of projects assessed and for which inclusion action plans have been developed for implementation	7	8 (1%)
1.5 % of training participants demonstrating an improved knowledge in topics covered	70%	90% (129%)
[note] All milestones are cumulative
[note] To support primary healthcare providers in identifying and referring mental health patients
[note] HI’s target is for the number of primary healthcare centres, the number of staff trained in the centres is extracted from the narrative reports
[note] This indicator was reworded and revised to better reflect the work that HI is doing. It previously measured the number of projects which reflect improved inclusion practices.

Briefly describe the output’s activities, and provide supporting narrative for the score.
This output combines different activities being undertaken by all three partners to train and build the capacity of national stakeholders with the aim of strengthening national systems to respond to the protection needs of vulnerable groups.
Partners have overachieved on all indicators under this output due to the increased demand for training which partners were able to accommodate. The increased demand is partly due to new staff joining and increased efforts by partners to improve skills and knowledge at national and local institutions. This demonstrates the flexibility of the programme to respond where needed and the importance of these activities. This also involves on-the-job coaching (as in the case of the mhGAP training) as well as close follow-up of implementation (as in the development of inclusion action plans). This output focuses on making services sustainable and building expertise.

The inclusion plans developed under output indicator 1.4 have improved how other agencies design their programmes to ensure that services are inclusive of people with disabilities (PwDs). The overachievement is because of the many requests received by HI from other agencies and the recognition of the need to improve on inclusion. The plans include training on the use of the Washington Group Questions as well as tailored technical advice on how to interact with and include people with functional limitations in programming.

All indicators are on track to achieve the targets by the end of the programme, going beyond original plans. Indicator 1.5 also demonstrates the effectiveness of the training where more participants than originally expected have demonstrated increased knowledge in the topics covered. It’s difficult to determine the exact reason for over-achievement on indicator 1.5 as it is based on pre and post evaluations of training participants, it does show, however, that these activities are delivering positive results.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Looking at the performance of this indicator over the past year, there were no major changes in input costs which mainly consist of venue rental and transportation costs, as well as staff salaries of those involved in delivering these activities. The cost for this output per beneficiary for NRC (as measured by NRC), for example, increased slightly from $212 in 2018 to $294 in 2019 due to a lower number of training beneficiaries targeted by staff in 2019. The efficiency of this output is demonstrated, however, by the ability of those trained to increase the outreach of protection activities, including assessment and referrals of cases. For example, HI trained community-based rehabilitation (CBR) volunteers work 4-6 hours per day, yet the fact that they are already known and trusted by communities enables them to identify and refer cases that HI staff from outside of those communities wouldn’t have been able to do in this amount of time. Investing in training costs thus produces efficient outputs. There is no evidence suggesting volunteers from outside the community will not be as efficient, however DFID noted the importance of community links during field visits which foster trust and enable the volunteers to navigate their role more efficiently.

With regards to the equity of this output, partners target different groups for capacity building and training, including women and people with disabilities. Going back to the HI example above, CBR volunteers trained include people with disabilities which not only empowers them but enables them to reach other people with disabilities (PwD) in their communities who are in need of services, complementing other outreach activities to PwDs. There has also been an improvement over the past year where IMC mhGAP training targeted mainly male health professionals (as they are nominated by the MoH) but after follow-up by IMC more female staff were being nominated and trained. This, in turn, can help increase the number of female beneficiaries if they feel more comfortable discussing mental health with female medical staff.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The only change in this output was on indicator 1.4 which was reworded in December 2019 to better reflect the work that HI is conducting. This was previously measuring the number of projects which reflect improved inclusion practices, but as that was difficult for HI to measure, it now captures the number of projects for which inclusion action plans have been developed for implementation (effectively the number of action plans developed). No progress was made on this indicator in 2018 mainly because of the length of time it took to embed inclusion practices in projects, but over 2019 HI has now delivered on the set targets.

There are no planned changes to this output as a result of this review.

The above and all other logframe changes were approved by the SRO as well as the humanitarian team leader.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Last year’s AR recommended that IMC strengthened advocacy with the MoH to develop guidelines and standard operating procedures (SoPs) for MHPSS patients. This came from the potential in doing so to contribute to the sustainability of the programme and building national systems on mental health. IMC did not undertake direct advocacy with the MoH but through its involvement and leadership in the MHPSS sector has explored other ways in which to strengthen national actors. This was mainly through the development of an internship scheme directly linked with universities in Jordan where psychology or related fields students can intern with IMC, learning practical skills and in turn providing an avenue for IMC to influence curricula in universities in relation to mental health. While not directly linked to the above recommendation, IMC has informed DFID that the MoH has now decided to create a separate mental health department within the MoH, separating it from the ‘special needs’ department. This will create new opportunities to influence MHPSS service provision on the national level. A recommendation for the coming year is therefore for IMC to look at ways to influence the new MHPSS department in the MoH, perhaps using training and capacity building as a way to engage and contribute to building more sustainable national services.

Another recommendation made last year is the need for HI to continue discussions with the MoH and MoSD on the development and implementation of ED/EI guidelines and protocols. Starting in September 2019, DFID signed a new accountable grant arrangement (AGA) with HI including planned work with both ministries to update and develop guidelines and referral pathways for ED/EI. This work is due to be completed in early 2021.

Lessons learned over the past year reflect the importance and key role that community volunteers play in terms of detection and referral of cases, as well as increasing the outreach of programmes. Having committed and passionate volunteers has contributed positively on the overall delivery of the programme.

Output Title	Awareness is raised amongst beneficiaries and other community members on protection issues
Output number:		2	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	Yes, down by 20%

Indicator(s)	Milestones for this review (March 2020)	Progress (March 2020)
2.1 # of direct beneficiaries and community members who received information	58,834	52,177 (89%)

Briefly describe the output’s activities, and provide supporting narrative for the score.
This output reflects activities undertaken by NRC and HI to raise community awareness of protection issues and available services, mainly around legal information and services available to people with disabilities. The underachievement is attributed to the time taken by HI to identify and train community leaders responsible for delivering these awareness sessions. NRC had also underachieved on this target in 2018 due to lower number of beneficiaries than expected attending sessions. NRC has now caught up with targets for 2019 and expanded reach through community-based organisations; the overall target is on track to be achieved by the end of the programme. HI did not achieve its targets but is expected to get back on track by the programme end date as more sessions are being held.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
There were no changes in input costs for this output that affected its economy or efficiency over the past year. Cost drivers are mainly staff costs of those delivering the information sessions and any associated rental or transportation costs. For NRC, for example, the cost per beneficiary for delivering legal information sessions reduced from $16 in 2018 to $15 in 2019. While this is a small change, it is attributed to NRC’s increased use of community-based organisations’ (CBO) staff and volunteers rather than delivering the sessions directly by NRC staff. This has resulted in reaching a larger number of beneficiaries with available resources.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Following a full logframe review with all delivery partners at the end of 2019, it was decided to split this output into two outputs, with output 3 (see below) covering advocacy and policy change and output 2 covering information and increase in awareness. This makes the distinction between the two outputs as they are different in nature and target different audiences and beneficiaries.

Another change was the reduction in NRC’s target which was revised down from 100,000 over 3 years to 80,000 over 3 years. The reason for that reduction, which was approved in December 2019, is NRC’s shift to focus its resources on complex legal cases related to civil legal documentation of refugees. NRC continues to provide information to beneficiaries, also utilising social media which is not counted towards results under this indicator.
[note] There is a specific indicator for social media campaigns run by NRC or its local partners, separate from this targeted legal information provision.

There are no planned changes to this output as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
There were no recommendations specific to this output from last year’s annual review.

A lesson learned this year is that increased engagement with CBOs and local volunteers is effective and increases reach and awareness of services within communities. INGOs don’t have the capacity or local presence and trust that CBOs or volunteers have with community members and information shared may not reach as many people as intended without working with local organisations.

Output Title	Research is produced to influence advocacy and policy change
Output number:		3	Output Score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	N/A new output

Indicator(s)	Milestones for this review (March 2020)	Progress (March 2020)
3.1 Number of periodic reports and policy briefs produced on barriers to rights for refugees in Jordan	5	9 (180%)

Briefly describe the output’s activities, and provide supporting narrative for the score.
Following three products produced by NRC last year, six were developed for the period covering this annual review. These are:
1. Legalising Labour Work Rights and Conditions for Syrian Refugees in Jordan- done jointly with Tamkeen (a local NGO).
2. Policy brief on legal challenges to return that are faced by Syrian refugees- done jointly with UNHCR.
3. A presentation on legal safety for durable solutions presented at an NRC regional donors’ breakfast in December 2019.
4. Recommendations presented, jointly with Tamkeen, at a learning event held by the Swiss Embassy in Jordan; focusing on how to promote decent working conditions for refugees, migrants, and nationals in Jordan and Lebanon.
5. Briefing note on the legal safety for returns preparedness- done jointly with UNHCR.
6. Briefing note on education pathways, looking at education documentation and equivalence between the Jordanian and Syrian education systems.
NRC has exceeded the target although products 3 and 4 may not strictly fall into the description of this output indicator. Nonetheless they are felt to be relevant because they were live advocacy events focusing on policy recommendations from completed products.

Overall, these reports and briefing notes are important sources of evidence but also tools for shaping the response for refugees in Jordan. The emphasis on work rights is feeding into wider discussions and advocacy to improve work rights, and the work related to returns preparedness is a key part of thinking through durable solutions for Syrian refugees.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
As this falls under the ‘advocacy’ component of NRC’s VfM framework, it is very difficult to assess its efficiency and economy. The main costs going into the reports are a combination of consultant fees, and staff costs related to data collection and analysis. As each piece of work requires a different combination of these and reports are designed for different audiences, it is a complex task to measure the efficiency of advocacy. However, as NRC has exceeded the target using resources budgeted for at the start of the programme without an increase in costs, then we can determine that this output continues to perform well in terms of VfM. NRC disseminates these products widely to relevant actors and utilises them in its programming, proving their importance to both build evidence and influence to improve the enabling environment for refugees.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This was previously part of output 2 but was split into a separate output in December 2019 to better distinguish between information dissemination related to services and those more targeted towards advocacy and research. There are no planned changes as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
A recommendation made in last year’s Annual Review highlighted the need to increase the awareness of employees of Syrian refugees on work rights. While this is not strictly part of NRC’s role in this programme, it has worked with Tamkeen on the production of the report mentioned above to highlight the need to legalise work rights and working conditions of Syrian refugees. The report made specific recommendations on promoting the compliance of work rights among employers, and DFID will follow-up with NRC and Tamkeen on the progress or work done on this issue.

A recommendation for the coming year is for DFID to follow-up closely with NRC on how these reports and policy briefs are being used, and if NRC can develop a tool to track any policy changes related to them to better measure their effectiveness.

Output Title	Vulnerable persons receive direct assistance, and have increased access to services
Output number:		4	Output Score:	A+
Impact weighting (%):		60%	Weighting revised since last AR?	Yes, increased by 5%

Indicator(s)	Milestones for this review (March 2020)	Progress (March 2020)
4.1 # of direct NRC beneficiaries who received (a) legal counselling and (b) direct legal services	(a) 31,060 / (b) 1,624	(a) 35,043 / (b) 3,807 / (119%)
4.2 # of vulnerable people who received comprehensive rehabilitation services	3,450	3,961 (115%)
4.3 # of IMC beneficiaries receiving specialised mental health (MH) and child protection (CP) case management services at static centres and at mobile medical units (MMUs)	3,666	3,823 (104%)
4.4 # IMC beneficiaries receiving the social assistance protection package for three months	200	204 (102%)
4.5 # of most vulnerable people referred by HI to external services	1,611	1,887 (117%)

Briefly describe the output’s activities, and provide supporting narrative for the score.
This output covers the specialised services delivered by partners, either directly or through downstream partners in different areas across Jordan. Activities conducted by NRC include legal counselling and direct legal services where counselling is done as a first step to understand the legal issue facing the beneficiary and give advice on how to move forward. The legal services are related to court representation of beneficiaries, mostly in cases related to legal and civil documentation. HI activities are related to rehabilitation services (physiotherapy and occupational therapy) where HI does not conduct this directly but works with local service providers on capacity building and referrals of beneficiaries to receive these services. Lastly, IMC activities covered by this output include MH and CP case management where specialists in either category assess beneficiary needs and work to manage their case through MH or CP sessions. This is also done at MMUs in collaboration with IMC’s downstream partner, JOHUD.

As demonstrated in the table, partners have moderately exceeded expectations on targets set. This is mainly due to additional needs not originally foreseen when planning, and also links to output 2 where partners reached out to communities to inform them of services which resulted in more people approaching the agencies in the field. The links between service delivery and outreach are made clear through this success and highlights the importance of involving communities and expanding the catchment area around service centres.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
These activities form the core of the intervention under this programme where the BC identified key cost drivers for all three partners to be staff costs, procurement of medication or assistive devices, and transfers to downstream partners. As the interventions are staff heavy, staff costs represent an average of 50% of the budget across all three partners. This has remained within the original budget with partners performing active recruitment when there are gaps and ensuring accurate forecasts throughout the programme. Partners continue to apply competitive procurement methods and source items locally to reduce shipping costs where possible.

Partners also continue to ensure programme efficiency while delivering these services, maximising output with the available inputs. For example, the cost of legal assistance for beneficiaries (implemented by NRC) went down from $213/beneficiary in 2018 to $129/beneficiary in 2019. This is mainly due to NRC increasing its capacity for the provision of legal assistance through the use of external lawyers who NRC contracts to handle straight-forward legal cases, as well as introducing new services like accompanying beneficiaries to the Ministry of Foreign Affairs to support in document validation. On a more organisational level, a recent HI move to consolidate offices across Jordan into one regional office has resulted in savings on administrative costs related to the programme (although not possible to quantify yet). IMC also continued to ensure project efficiency where cost per beneficiary for the entire intervention in year 2 of the programme was £306/beneficiary and was originally forecasted to be £348/beneficiary. This is both a result of reaching more beneficiaries, and at a lower cost than originally forecasted. As shown by the outcome assessment in section B, this has not affected project quality or effectiveness.

On equity, all partners continue to reach men and women equally, providing culturally sensitive settings and services where needed. Moreover, the project specifically targets people with both physical or mental disabilities; providing services to the most vulnerable in communities. Partners’ outreach through the MMU or activities in remote areas in informal tented settlements also ensure reaching people who would otherwise not be within the catchment areas of fixed spaces where activities are being delivered. HI uses the Washington Group Questions (WGQs) to assess people’s disabilities and supports other agencies to start introducing this tool within their assessments as well. DFID has communicated to all partners the importance and commitment made to disaggregate data by disability, and the gradual introduction of this tool will help in achieving this commitment.

Overall, the programme continues to demonstrate VfM, sometimes exceeding the assessment made in the BC.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
One change was made to this output in the past year, particularly on indicator 4.1 delivered by NRC. The target for legal assistance (b) was increased by 1,350 beneficiaries in December 2019 to reflect the increased need for the delivery of direct legal services by NRC and the shift in its focus to work on complex legal cases related to civil documentation.

No changes are planned to this output based on this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Last year’s AR made a recommendation for IMC to continue exploring ways to improve VfM of its delivery of cash assistance. After switching providers in 2018 from using the Jordan Post Office (JPO) to using mobile money, IMC reverted back to using the JPO despite it being a little more expensive in terms of overhead costs. This was because of delays and disagreements on the contract with the mobile money service provider, which meant that beneficiaries had to wait longer to receive payments and faced technical issues with withdrawing the cash. IMC has looked at all options and decided that since this is a relatively small caseload, it would continue with using JPO. DFID is supportive of this decision as it also ensures timely delivery of assistance and IMC oversight of the process.

Another recommendation was made for NRC to work with its local partners, JCLA and Tamkeen, on strengthening beneficiary feedback and complaints mechanisms as both organisations had limited capacity in that regard. NRC has taken this forward and is working with both organisations on ways to strengthen their own systems, while also developing tools for closely following up with cases that are referred by NRC.

A further recommendation made in last year’s AR is related to realistic setting of milestones and targets as partners had overachieved on all targets by high margins. This was discussed with partners and where unexpected needs sometimes result in overachievement, we stressed the need for reviewing targets if necessary. As referred to above, NRC reviewed targets accordingly and HI and IMC expressed no immediate need to review targets as they are on track to reach overall targets set for the programme. Partners have mostly recalibrated efforts and now working towards milestones while responding to emerging needs. We do not think that overachievement on targets is an ongoing issue and with 6 months remaining in the programme (at the time of submission of this review), there is no pressing reason to review targets.

A key lesson learned this year is the need for continuous engagement with both relevant government bodies and local service providers to ensure needs continue to be met. HI, for example, has faced some challenges in coordinating with the MoH although not at the central level, where specific hospitals can be more challenging to work with and resist change. Local non-governmental organisations have proved more open to change and welcome the support received by INGOs. Regular conversations with relevant ministries have been effective and both DFID and partners should continue this momentum going forward.

A recommendation for the coming year of operation is for all partners to cement the work done with local organisations throughout the project period; focusing efforts on building sustainability and enabling downstream partners to begin operating more independently where possible by applying learning from capacity building efforts. Capacity building should go beyond just training and real engagement and coaching, particularly on administrative functions like finance, HR, and M&E.

D: RISK

Overview of risk management
.

The risk table below covers programme risk, trends and drivers and how they are managed.

Table 1: Risk Categories
Risk Category	Programme Residual Risk	Comments
Safeguarding	Moderate	DFID ran sessions with partners on safeguarding risks and how to mitigate for them effectively. The programme also tackles safeguarding issues through case management services.
Context	Minor	There are 3 contextual risks that we are tracking, and all are minor. This reflects the stable operating environment in Jordan and no major contextual challenges related to delivering activities in this programme. We continue to monitor the context and reassess these risks periodically.
Delivery	Major	There are a number of delivery risks affecting this programme, ranging from minor to major. Major delivery risks are directly related to COVID-19 and were added in March 2020 to reflect the risks of slowing momentum on work with government as well as the risk of protection concerns being exacerbated during lockdown as a result of suspension of activities. We regularly discuss delivery risks with partners and corresponding mitigation measures. During lockdown, partners continued to deliver remotely where possible and sought permits for movement to deliver essential services.
Operational	Minor	Operational risk remains minor with clear distribution of tasks among the humanitarian team and timely resource planning across the office.
Fiduciary	Moderate	Aid diversion risks remain unlikely and partners have strong mitigation measures in place. The moderate residual risk is because of our assessment of there being moderate impact on the programme and beneficiaries should any risks materialise.
Reputational	Major	There are three reputational risks for this programme with residual risks ranging from minor to major. We continue to actively manage these risks with appropriate mitigating measures. No reputational risks to this programme have materialised.

Due Diligence assessments (DDAs) were conducted for all partners in 2018/2019, including enhanced DDAs (EDDAs) on safeguarding. Recommendations were shared with partners and followed-up. Moreover, the Internal Audit Department (IAD) looked at this programme as part of a DFID Jordan audit in September 2019. IAD recommended a number of actions which were taken forward by the team.

Conflict Sensitivity
During the past year of implementation, the DFID team followed-up closely on conflict sensitivity through regular discussions with partners as well as dedicated reporting on the issue through annual reports. Partners continue to prioritise the principles of do no harm in implementation by ensuring engagement with the community, assessing risks, and responding adequately. For example, during the last year NRC closed its field office in Jerash as part of their restructuring process. During the closure, NRC communicated this clearly to beneficiaries and the community, and Jerash cases are now covered by the Irbid office, along with regular NRC staff visits to Jerash. Additionally, NRC opened a new field office in Zarqa which was preceded by careful analysis of risks and corresponding mitigation measures of starting operations in a new area. Examples of mitigation measures taken are offering volunteering opportunities equally to refugees and Jordanians, giving priority to Zarqa residents while following recruitment policies, and engaging closely with local organisations to outreach to the community through trusted partners.

During the past year, HI requested DFID support on integrating conflict sensitivity within its regular monitoring exercises, as a result of which some questions are now included in post intervention monitoring surveys to get beneficiary feedback on any indications of conflict as a result of the presence of HI or any HI-supported service providers in their areas. HI has found this exercise useful, with no concerns raised to date. IMC is also focusing its efforts on staff training on conflict sensitivity, with training sessions run on preventing sexual exploitation and abuse. Moreover, project activities are regularly discussed with local authorities, communities, and local organisations to get feedback and keep the community involved. Emphasis is also placed on community cohesion where beneficiaries and community members of different nationalities are engaged in activities and volunteer opportunities. DFID field visits to different programme locations of all three partners reflect their commitment to mitigating any conflict sensitivity risks, with clear engagement with communities at different levels.

Update on Partnership Principles
Jordan continues to work with partners on poverty reduction and the realisation of the SDGs with important steps taken to implement reform and expand the private sector to grow the economy. The GoJ also remains committed to its international obligations towards refugees and is a role model in the region. COVID-19 could threaten progress but the government remains transparent in communicating measures taken to reduce the economic and social impact on the most affected and vulnerable groups. Good progress is also being made on disability rights and there is good engagement from relevant ministries with non-governmental bodies and partners to advance this agenda.

The UK continues to engage with the GoJ on refugee issues and on maintaining the protection space for agencies to operate and support the most vulnerable. We are also engaging on the Jordan Response Plan (JRP) to ensure a needs-based approach to the provision of services rather than it being status-based. The new comprehensive vulnerability assessment undertaken jointly by the UN and GoJ is a positive step forward in this regard, which will shape targeting going forward.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and DFID, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

All partner reports were submitted in a timely manner and were of good quality. Audited annual statements are also submitted by partners when finalised and published; there were no issues of concern flagged by external auditors in these statements. DFID and partners have regular discussions on risk and partners provide an updated risk matrix with each quarterly report, flagging any changes and updating mitigation measures. In addition to quarterly meetings held with each partner separately, where risks are a key part of the discussion, we also held programme meetings with all three partners to jointly discuss the overall programme risk matrix, focusing on changes in risk levels and mitigation measures. These have all been fruitful discussions with partners being transparent about risks. Additionally, partners update delivery chain risk maps regularly to capture specific risks related to working with their downstream partners. There have been no major changes to the risk assessments of downstream partners.

On financial management, partners also submit financial reports as part of quarterly reporting, explaining any over or underspend on budget lines. Forecasting has been generally accurate with the exception of HI’s work on ED/EI where there has been significant underspend on the agreed budget and forecast. This is mainly due to delays in recruiting consultants as HI faced difficulties finding people with the required skills. An EI consultant was eventually recruited but then was unable to travel to Amman due to COVID-19 travel restrictions. HI has not yet recruited an ED consultant but has re-advertised the opportunity. The work on this component is scheduled to end in September 2020, but HI has indicated a desire to ask for a no cost extension until March 2021 to allow enough time to complete the intended work. Partners also provide DFID with an updated asset register every quarter. Asset spot checks are conducted by DFID during field monitoring visits, where items checked were accounted for.

During 2019/2020, DFID also provided a small grant of £18,000 to ACTED, which was subcontracted to Impact Initiatives. This grant was used to supplement other funding for a multi-sector needs assessment of informal tented settlements (ITSs) in Jordan. The assessment was completed (with full spend on the grant) and is being used by different service providers to better target and serve this particularly vulnerable group.

All partners have their monitoring activities which are performed separate from their programme teams. These include regular monitoring and data collection, in addition to specific analysis of outcome and impact indicators. DFID also conducts field monitoring visits for partners, at least every 6 months. These visits usually include discussions with field staff and beneficiaries, and observing activities taking place in the field. DFID sought beneficiary feedback in all the visits where this was always overwhelmingly positive. Field visits also include visits to downstream partner activities and discussions with their staff on their reflections in relation to the partnerships. Partner response and feedback mechanisms also deal with feedback and complaints where most feedback is about the need for cash assistance. An example where partners have used feedback to influence programme delivery is NRC more actively following up with beneficiaries awaiting legal decisions where cases can sometimes take months to be resolved. Lawyers and case managers now communicate expected timelines for cases to be resolved at the beginning of the process to manage expectations.

VfM has been covered throughout the report in the sections above.

Date of last narrative financial report	April 2020	Date of last audited annual statement	NRC: 31 December 2019 / HI: 31 December 2019 / IMC: 30 June 2019