Type of Review: Annual Review

Project Title: Humanitarian Preparedness and Response Programme

Date started: 30 June 2011
Date review undertaken: 5 June 2012
## Acronyms
## DER Disaster Emergency Response working group
## DFID UK’s Department for International Development
MAF	Mission Aviation Fellowship
## NGO Non-Governmental Organisation
## WFP World Food Programme
## Introduction and Context

What support is the UK providing?
The UK will provide up to £20 million over 5 years to provide rapid humanitarian responses in Bangladesh, and strengthen planning and preparedness. / Our support focuses on three areas: / Rapid response to disasters – up to 75% of the fund (£15 million) is reserved for rapid humanitarian response when a disaster occurs – which happens frequently in Bangladesh. Decisions are made based on agreed criteria. So far UK supported 150,000 people for one month in January 2012, to meet a critical gap in food needs as part of a response to severe water-logging in the South West. / Preparedness and planning, and logistical support for key agencies who will be involved in response and recovery, especially in remote and vulnerable areas; and / Stronger evidence on what makes for an effective response.

What are the expected results?
As the fund is established to respond to urgent disaster needs, we cannot predict the exact numbers of people to be assist, as the scale of need is not predictable. UK support will focus on the following results areas: / Lives and livelihoods saved, and recovery and resilience enhanced through: / A faster, more flexible model for response based on better preparation by key organisations including Government, donors, NGOS, UN organisations etc. / Easier access to remote, inaccessible areas / 2. A more effective response, including a specific focus on: / Long term resilience and recovery including factoring in risks from climate change / Accountability to those affected by the disaster - especially the most vulnerable - women and girls, the elderly, sick and disabled, and socially excluded communities and individuals / More efficient funding channels (speed, quality, capacity) / Nutrition / Ensuring high quality support (e.g. meeting internationally agreed ‘Sphere’[1] standards) / 3. An enhanced evidence base and better analysis for an effective disaster management response in Bangladesh, and globally.
[1] Sphere Humanitarian Charter and Minimum Standards in Disaster Response

What is the context in which UK support is provided?
Bangladesh is one of the most disaster prone countries in the world (ranked 6th in the World Risk Report 2011). It is particularly vulnerable to climate related disasters – cyclones, floods and droughts have been frequent problems for centuries. Severe floods happen every 4 – 5 years, and cyclones happen almost every year, with severe cyclones on average every three years (most recently in 2007 and 2009). Climate change will worsen these climate related disaster risks, straining Bangladesh’s well known ability to adapt. Bangladesh is also at risk of earthquakes, which could have devastating consequences particularly in densely populated cities where very few buildings meet standards for earthquake resilience. / Previous responses globally and in Bangladesh have highlighted the importance of strong coordination and better preparedness. DFID is helping to fill an important niche in supporting key institutions (e.g. Government, UN Agencies, other donors and NGOs) to prepare for effective responses. This is included in DFID’s Operational Plan for Bangladesh.

## Section A: Detailed Output Scoring

Output 1: Provision of emergency assistance to households most affected by disasters
Output 1 score and performance description: A. Outputs met expectation. / Progress against expected results: / Delivery of assistance / In January, DFID provided support through the World Food Programme (WFP) to meet the immediate humanitarian needs of 150,000 people affected by waterlogging in Satkhira district. Each family received 1500 taka for the month (approximately £12). This was the fourth round of assistance to these households, previous support funded by the European Union’s Humanitarian department (ECHO). A one month gap in funding would have caused serious hardship for households, and the UK was able to step in and meet this need. WFP’s monitoring shows that the cash was used for a range of purposes including some food provision but also other immediate and vital needs including shelter repair. / Timeliness / The waterlogging began in August 2011. DFID monitored the situation and pressed for a common assessment and analysis of needs, and a coordinated response. This took some time. DFID and partners have since invested a lot of time in improving coordination and needs assessment for Bangladesh as a whole. These improved systems should provide the information, evidence and mechanisms for informed decision making by all partners in a swifter and more coordinated way in future. / DFID received the WFP proposal in December 2011, and it was approved in January 2012 – in time for distributions to be made in January-February with only slight delay on the planned timeframe. The support filled a key gap and was appreciated by partners. DFID Bangladesh is looking at further tightening processes for swift decision making in future responses. / There are no annual milestones for this component due to the unpredictable nature of disasters.
Recommendations: DFID should maintain the focus on needs based response and encourage other donors to do the same. This should be clearly and consistently communicated to potential response partners, to ensure proposals are timely and contain the information DFID (and other donors) require for informed decision making. DFID Bangladesh should also use opportunities during ‘normal time’ to prepare information on costs of key interventions, experiences from previous responses etc to ensure we are well prepared to complete paperwork required for approval of funds from this programme. / Impact Weighting (%): 70% / Revised since last Annual Review? Y – this was not explicit in original logframe , but has now been added / Risk: Medium / Revised since last Annual Review? N

Output 2: Improved coordination and information management
Output 2 score and performance description: A. Outputs met expectation.
Progress against expected results: / DFID has not invested financial resources in this output in the first year of the programme, but has invested significant staff time in policy dialogue and establishment of new coordination mechanisms. The logframe therefore has no specific target or milestone for this output, although the baseline was that no clusters were fully functioning (meeting regularly, with terms of reference, up to date mapping of who was doing what, where). / Clusters (sector working groups for humanitarian preparedness and response on theme such as shelter, water and sanitation etc) are now established in seven key sectors and meeting regularly. A group to coordinate across clusters - the Humanitarian Coordination Task Team – has also been established. How all these new mechanisms will function during a response has not yet been tested, but huge progress has been made in the last six months and good ground work is being laid. / DFID is awaiting the outcome of discussions within the Disaster Emergency Response coordination group before making funding decisions regarding this output. The DER (and its subgroups) need to map existing capacity for coordination and information management, and identify gaps. DFID has been heavily involved in this dialogue and has expressed willingness to provide additional capacity once gaps are identified. / Recommendations: DFID should await the outcome of DER discussions before making funding allocations, whilst continuing to invest staff time in driving those discussions. In coming months, funding may be used to support cluster coordination capacity, to boost capacity in the UN Resident Coordinator’s Office or to provide support to NGO or UN initiatives designed to build in-country capacity for preparedness and response. / Impact Weighting (%): 20% / Revised since last Annual Review? Y – this was not explicit in original logframe, but has now been added. / Risk: Medium / Revised since last Annual Review? Y – recommend raising to medium, because there are key factors outside DFID control that will help determine how these systems develop.

Output 3: Logistical support for NGO and other partners providing humanitarian, risk reduction and development support to disaster-prone and vulnerable regions.
Output 3 score and performance description: A. Output meeting expectations.
Progress against expected results: / Clear output indicators are not yet in place for this output. The suggested target of improved levels of NGO monitoring as a result of MAF support is not appropriate, as we have no baseline, nor clear means of monitoring. / DFID provides core support to an NGO called MAF (the Mission Aviation Fellowship) to support them in operating a seaplane shuttle service. This small aircraft can land on water in some of the most remote, vulnerable and inaccessible areas of Bangladesh. It allows humanitarian and other development partners to reach these areas during disasters (when roads are often blocked with fallen trees etc), as well as in normal times. The service greatly improves access to these areas, enabling improved implementation and monitoring of disaster response and other programmes in vulnerable regions. / MAF’s most recent report shows that over 75% of flights were for NGOs and other forms of relief or community organisation. 22% were medical and 2.5% were for other purposes. Over 64 organisations are using the shuttle service and demand for an increased service (a 3rd shuttle flight per week) is strong. Another key priority for DFID in its partnership with MAF is encouraging MAF to look for longer term solutions and reduce reliance on DFID core support. MAF have been in touch with a range of donors and at least one major donor has expressed interest in providing similar support. / Recommendations: DFID should change the logframe indicator to reflect the proportion of flights taken by humanitarian and development actors. This is more measurable year on year than the current logframe indicator which looks at indirect impact of those flights on access and improved programme implementation by those actors. No other specific actions. DFID will maintain its dialogue with MAF and encourage their efforts to reach a broader donor base. / Impact Weighting (%): 10% / Revised since last Annual Review? Y – this was not explicit in original logframe, but has now been added. / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
Has the logframe been updated since last review? No, but recommend updating it now and including clear output indicators, targets and milestones particularly for Output 3 where expenditure is already underway. / 1.2 Overall Output Score and Description: A. Outputs meeting expectations. / Output Scoring / Output number Output Description Impact Weight (%) Output Performance / 1 Provision of emergency assistance to households most affected by disasters 70% Outputs met expectation (A) / 2 Improved coordination and information management 20% Outputs met expectation (A) / 3 Logistical support for NGO and other partners providing humanitarian, risk reduction and development support to disaster-prone and vulnerable regions 10% Outputs met expectation (A) / Annual Output Scoring 100% All outputs scored / Overall Output Score: Outputs meeting expectations (A) / 1.3 Direct feedback from beneficiaries / Beneficiary feedback on the cash interventions was received during field visits in February again in June 2012. In February, it was clear that lack of income was the priority gap and that assistance was vital. In the use of the cash provided, beneficiaries have demonstrated that food security was one amongst many concerns. Some cash was used to meet food needs, but other priorities included house repairs as the waterlogging damaged so many homes. Longer term needs included shelter and a separate DFID programme has since been designed to respond to those longer term recovery needs for 11,000 households.
1.4 Summary of overall progress / Overall progress has been positive, both in terms of responses (one response this year), but also in terms of DFID contributions to improved coordination, helping drive the establishment of cluster groups for coordination etc. A team from DFID’s humanitarian department visited Bangladesh in late May, discussing DFID’s Bangladesh response and preparedness planning with DFID Bangladesh and external partners. The humanitarian team judged that the use of this programme to date has been proportionate and appropriate, and that the spend rate was well judged.
1.5 Key challenges / Key challenges in managing disaster response are anticipated to be timeliness and coordination. The lack of clearly agreed triggers for disaster response is a particular challenge for smaller or slow onset disasters. Recent investments by key players in improved preparedness and coordination mechanisms should help reduce these risks.
1.6 Annual Outcome Assessment / The interventions supported to date under this programme have contributed towards the outcome level targets. Disaster affected people have been assisted with cash support. Recovery support for the same affected population was then provided under a separate business case, for longer term recovery and resilience at a much higher investment per household and overall cost. This demonstrates that this programme is being used effectively to fill immediate humanitarian response gaps whilst being complemented by separate larger responses or longer term recovery programmes where appropriate. / The waterlogging in Satkhira in August was partly coordinated by the DER but also highlighted some serious gaps in national and local level coordination, the lack of agreed triggers for response and the lack of agreed process for needs assessment. Good progress has since been made in establishing improved systems. They are yet to be tested but we can be confident that coordination should be improved since 2011 if a disaster hits in 2012. This level of preparedness then needs to be enhanced and maintained throughout coming years, whether disasters hit or not. DFID support to improved logistics through MAF continues to be appreciated and receive positive feedback from partners.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes, because the programme had only forecast a small spent for 2011. It is agreed with the Head of Office that DFID Bangladesh will not forecast against the resources earmarked for rapid disaster response because needs are unpredictable. Spend will be forecast against the preparedness component once concrete activities are agreed. Spend on logistics (through the NGO MAF) is as per forecasts. / 2.2 Key cost drivers / Key cost drivers will be determined by the nature of future responses and will be affected by the scale of disaster. The impact of that disaster and response on local, national and international markets also affects costs. / 2.3 Is the project on-track against original timescale: Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project. / The evidence base for interventions remains fairly consistent. Evidence of needs for each response is established depending on the nature of the disaster and its impact. / 3.2 Where an evaluation is planned what progress has been made? Not planned this year.

4. Risk
4.1 Output Risk Rating: Low / 4.2 Assessment of the risk level / Risk level overall remains low, though recommend raising risk level for achieving output 2 to medium because achievement of the indicators relies on a series of assumptions which DFID is working to influence but does not control.
Risk of funds not being used as intended. / In any disaster response, misuse of funds is a risk. DFID therefore only works through partners with strong oversight systems (clear management and accountability structures, strong financial controls, regular audits, complaint mechanisms for communities and staff) to mitigate these risks. This should be taken into account when assessing value-for-money through various partners for disaster response – slightly higher administrative costs that result in stronger financial controls will represent better value for money than cheaper options with higher financial risks. / Climate and Environment Risk. / Low given small scale of planned spend to date. Risk assessment for any further spend to be covered in each submission for release of funds under Output 1.

5. Value for Money
Performance on VfM measures / The bulk of the WFP support, £360,000, went directly to beneficiaries. The rest was (£80,000) was for operational costs, including delivery through two NGO partners, a small WFP team on the ground to manage the response, transport and a small amount for local security and IT. This budget included reductions already agreed. The direct operational costs and direct costs came to £48,000 (11%). DFID’s Guidance on Measuring and Maximising Value for Money in Cash Transfer Programmes gives an operational cost benchmark of 5-15% for well-executed cash and in-kind transfer programmes. / A review in early 2011 of the NGO MAF’s operating model provided evidence that support to MAF represented good value for money. / 5.2 Commercial Improvement and Value for Money / Savings were negotiated on overhead costs for the WFP intervention. / MAF costs are determined primarily by international markets for fuel and maintenance. Savings are sought where possible. / 5.3 Role of project partners / Project partners are critical to delivery of Value for Money in this programme. DFID has already provided value for Money information and documentation to some key partners likely to be involved in humanitarian response in country (specifically the UN agencies. MAF is also fully aware of DFID’s priorities in this area, having undergone a VfM assessment during 2011 prior to approval of funding under this programme. / 5.4 Does the project still represent Value for Money: / Yes. Value for money for the rest of the programme will depend on the nature of selected interventions. Value for money in disaster response is a balance of cost, quality and speed – decisions have to be made swiftly, sometimes on imperfect information if lives are to be saved or secondary impacts of disaster mitigated. / No value-for-money indicators have been used to date in this programme, but DFID may look at including these in future responses. / 5.5 If not, what action will you take? n/a

6. Conditionality
6.1 Update on specific conditions / n/a

7. Conclusions and actions
The interventions supported to date under this programme have been successful and filled key gaps in delivering assistance to those affected by disasters. / The programme has been used as it was designed to be used, and the decision not to spend more was the appropriate one. New opportunities to improve capacity for response and coordination are expected to arise in coming months and DFID will be well placed to help fill gaps as requested.

8. Review Process
The humanitarian preparedness and response programme has only been in place one year and spend to date has been relatively low at £625,000. It was decided to do an internal review, drawing on consultations with a range of partners. The review team consisted of DFID Bangladesh Disaster Management Adviser and Climate Change team programme manager. / The review also drew heavily on advice and recommendations from an team of 3 staff from DFID’s humanitarian department who visited Bangladesh in late May 2012. The visit included consultations with: / Government of Bangladesh / United Nations / NGOs / Other donors / Other UK government Departments and the British High Commission.