## Template
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | COVID-19 Emergency Education Response
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Target (date)
1. Mitigation of immediate education risks to pupils - particularly girls and highly vulnerable populations 2. Preservation of education systems in the medium to long term, including maintaining school places. | Teachers supported provide support to learning, and health, nutrition, child protection and psyscho-social support to children in refugee settings | Planned |  | 5,669 (xx% female, xx% IDP) | 2021-04-01
Achieved
Source
| Impact Indicator 2 |  | Baseline | Milestone 1 | Target (date)
| Teachers supported continue to work in the education system during the COVID pandemic and preparations for school return | Planned | 0 | 5,669 (xx% female, xx% IDP) | 2021-04-01
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Target (date) | Assumptions
Continued education for the most marginalised children despite COVID-19 interruptions | Children continue to receive support to their education and wrap-around support such as MHPSS | Planned | 0 | 300,000 (xx% girls, xx% IDP, xx% with disabilities) | 2021-04-01 | * Children will continue to engage with support and learn despite COVID-19 interruptions * Immediate support to teachers will maintain education systems, and teachers will remain in education * Support services provided by refugee teachers will mitigate the risks children face, particularly in terms of safety and nutrition * breakdown in reporting to show % female, % IDPs and % with disabilities will be available in reporting.
Achieved
Source
UNHCR monitoring
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | DFID SHARE (%)
| 5.3m |  |  |  | 100%
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Target (date) | Assumptions
5,669 teachers are supported to stay in work, providing continued learning to refugee students | Teachers paid in timely manner | Planned | 0 | 5,669 (xx% female, xx% IDP) | 2021-04-01 | * Teachers in refugee settings can continue to be paid, and there is no disruption to banking services * Teachers continue to support education and other support to refugee children * breakdown in reporting to show % female, % IDPs and % with disabilities will be available in reporting.
Achieved
Source
UNHCR monitoring
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline | Milestone 1 | Target (date)
100% | Positive impact stories shared with DFID and published | Planned | 0 | 3 | 2021-04-01
Achieved
Source
Stories received and approved by DFID
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | DFID SHARE (%)
| 5.3m |  |  |  | 100%
INPUTS (HR) | DFID (FTEs)

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined e.g. DRF, OP, ICF KPIs, MDG indicators
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.