Annual Review - Summary Sheet

Title : Humanitarian Preparedness and Response Programme (HPRP)
Programme Value: £20 million		Review Date: August 2015
Programme Code: 202660	Start Date: 27 June 2011	End Date: 26 June 2016

Summary of Programme Performance

Year	2012	2013	2014	2015	2016
Programme Score	A	A	A	A
Risk Rating	Low	Low	Low	Low

Summary of progress and lessons learnt since last review
The programme is assessed as on track and performing well. Humanitarian interventions supported by DFID Bangladesh (DFID-B) from 2014-2015 have contributed to achievement of the business case outcome indictors. Through Output 1 the UK has provided effective humanitarian support to crisis affected communities. UK funds have played an important role in helping households (HHs) recover from disasters. Output 2, principally through the Joint Needs Assessment (JNA) programme, has allowed DFID-B to support the creation of an enabling environment for humanitarian actors. Outputs 3 and 4 have also provided a conducive environment for effective humanitarian action.

Delivery against recommendations from 2013-2014
Overall DFID-B took forward the majority of the recommendations made during the 2013-2014 annual review. There were some instances were DFID-B was not able to implement recommendations e.g. against output 1 DFID-B’s response to 2014 monsoon flooding was not delivered as quickly as required according to timelines set out in the recommendations. Going forward we will undertake further work to quicken the UK’s post-disaster responses.

Summary of recommendations for the next year to be undertaken by DFID-B
1. Ensure readiness for meeting potential humanitarian needs through 2015 and early 2016 via a programme cost extension (by October 2015); secure new multi-year programme funds for the next phase of humanitarian support (by April 2016).
2. Resource the JNA process in the next phase of programming in the context of performance improvements designed to facilitate more rapid responses (by April 2016).
3. Assess options for strengthening early action for example through multi-year pre-financing arrangements with humanitarian organisations (by April 2016).
4. Assess options for strengthening coordination arrangements including through investments in Clusters and other fora such as the iNGO Emergency Sub-Committee (by April 2016).
5. Update the logframe to reflect and capture financial inputs and operational outputs relating to Rohingya interventions (by December 2015).
6. Continue to support Rohingya activities, specifically seeking to address protection needs, especially those pertaining to women and girls, while targeting support for shelter requirements and the legitimate needs of communities hosting refugees; support for Rohingya related coordination fora and the capacity building activities of national NGOs should also be considered (by April 2016).
7. Identify options for leveraging long-term development support for Satkhira district within DFID-B and other donors with the objective of strengthening resilience to future flooding (by December 2015).
8. Consider initiating a whole-of-programme independent review as a means to generate lessons learned from this phase to inform the design of the next phase of DFID-B’s humanitarian assistance (by December 2015).

A. INTRODUCTION AND CONTEXT (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3717152.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4875545.xlsx

Outline of the programme
The UK will provide up to £20 million over a five year period (2011-2016) to support humanitarian preparedness activities and to deliver timely relief following disaster events. There are three components to the HPRP:

1. Rapid responses to disasters: Approximately £15 million earmarked for post-emergency relief activities to support recovery efforts.
2. Institutional preparedness and logistical planning: £4.5 million for preparedness activities to enable agencies to better respond to the cyclical nature of disaster events.
3. Building the evidence base: Approximately £500,000 towards developing a robust evidence base regarding humanitarian action.

Bangladesh is one of the countries most at risk of natural disasters. Evidence of need is strong. Earmarking resources in advance of need demonstrates DFID’s commitment to an anticipatory approach. It streamlines programme management processes for DFID and partners. It ensures that the maximum amount of information collection and dialogue is completed in advance of a rapid response, rather than in its midst.

There have been strong recommendations following previous responses globally and in Bangladesh that highlight the importance of strong coordination and better preparedness. DFID can help to fill an important niche in supporting this institutional preparedness, and this is included in DFID’s Operational Plan for Bangladesh.

Through the programme the UK will also invest in strengthening logistical preparedness particularly in regards to preparedness for major disasters. To this end the UK will support humanitarian actors to develop logistics-based capacity assessments to understand the capability of transportation and communications infrastructure that could be used to support disaster response activities.

Finally, there is a clear and direct benefit to DFID and other partners in investing in a better understanding of response in Bangladesh, focusing particularly on improving effectiveness and accountability. Again, an emphasis on filling gaps, not duplicating or undermining other initiatives.

Through these areas the programme will aim to deliver the following results:

Lives and livelihoods saved, and recovery and resilience enhanced through:
- A faster, more flexible model for response
- A better prepared system
- Easier access to remote, inaccessible areas

2. A more effective response, including a specific focus on :
- Long term resilience and recovery
- Accountability to those affected by the disaster
- More efficient funding channels (speed, quality, capacity)
- Taking greater account of the needs of the most vulnerable - particularly women and girls, the elderly, sick and disabled – and of socially excluded communities and individuals
- Nutrition
- Quality of support (internationally agreed standards such as ‘Sphere’[1])
  [1] Sphere Humanitarian Charter and Minimum Standards in Disaster Response

3. An enhanced evidence base and better analysis for an effective disaster management response in Bangladesh, and globally.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
Against its three outcome indicators the HPRP performed well during 2014-2015. Under outcome indicator one (Disaster affected people assisted with shelter, food, nutrition, water/sanitation or early livelihoods recovery), for example, approximately 175,000 people benefitted from UK funded humanitarian activities helping DFID-B to fulfil its overall priority on humanitarian relief. During the reporting period, as per outcome indicator two, humanitarian coordination fora remained active. UK support to the JNA programme was instrumental in this regard as was UK participation at coordination related meetings etc. For example, over the reporting period the UK represented other donors at humanitarian coordination fora. The UK also took a leading role amongst other donors in developing the 2015-2017 work-plan for the Local Consultative Group Disasters & Emergency Response (LCG-DER). UK support to the Logistics Cluster and Mission Aviation Fellowship (MAF) also helped to sustain logistics networks and so contributed to delivery against outcome indicator three (Emergency response and recovery logistics maintained and strengthened). We assess that the programme’s theory of change and assumptions are still valid.

Overall output score and description: A
The HPRP continues to perform soundly and is on track to meet objectives stated in the business case. During this implementation period 10 individual components were supported. DFID funded programmes have performed strongly at the output level.

Output 1; score A: Via the National Alliance for Risk Reduction and Response Initiatives (NARRI) consortium and World Food Programme (WFP), in response to flooding in the north west and waterlogging in the south west, DFID has responded to the humanitarian impacts of disaster events. UK support to WFP for its Rohingya related activities has also enabled the UK to deliver extensive food aid and nutrition support inside refugee camps in the south east.

Output 2; score A: UK support to the Logistics Cluster led to the production of a nationwide logistics capacity assessment along with a capacity atlas which shows their whereabouts and type of logistics related infrastructure across Bangladesh. Such outputs have provided an important planning resource to humanitarian actors in Bangladesh. The work of the Logistics Cluster also helps to support earthquake preparedness related work that other actors including the US military are undertaking.

Output 3; score A: MAF continues to exceed its targets. The seaplane service is the only one of its kind in Bangladesh and allows humanitarian partners to reach remote locations and supports programme monitoring and so contributes to beneficiary accountability.

Output 4; score A: DFID supported programmes have helped to establish systems and procedures that facilitate humanitarian action. Environment. The JNA, for example, provides all humanitarian actors in Bangladesh with a range of tools and reference documents related to the conduct of assessments and the impact of crises. A major achievement of the JNA programme has been in helping to establish a joined-up approach to humanitarian assessments; since its establishment the JNA ‘approach’ has been used by organisations in delivering multi-agency assessments.

Key lessons
The overarching lesson from 2014-2015 relates to the requirement to quicken the timeliness of post-disaster responses and how structural improvements to Bangladesh’s humanitarian system can help to effect efficiency savings. Given the recurrent and predictable nature of disaster events in Bangladesh it is possible to loosely forecast when and where individual events will occur. However, the ability of the humanitarian system to respond speedily is not commensurate with such predictability. Future DFID-B supported programmes should look to invest ahead of disasters with the aim of facilitating early action e.g. by pre-disaster efforts to agree trigger points and response indicators and response packages, mapping geographic profile of response agencies etc.

Has the logframe been updated since the last review?
Yes, in February 2015. The logframe was updated to better capture programme outputs and milestones.

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Output 1: Provision of emergency assistance and recovery support to households most affected by disasters
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	55%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Number of people receiving emergency food security assistance	No milestones set	33,000 people reached with emergency food aid in 2014/2015.
1.2 Number of people receiving early livelihood recovery assistance	94,000 targeted people (48,000 male and 46,000 female)	98,740 people reached by June 2014
1.3 Number of people receiving other forms of emergency assistance	No milestones set	12,743 HHs provided with hygiene kits in 2014/2015.

Key Points
- DFID provided £1.4 million WFP to help address the root causes of persistent waterlogging in south-west Bangladesh. DFID’s support to-date has reached some 7,500 beneficiaries through cash-for-work schemes and trainings on disaster risk management. Over 70% of beneficiaries are women.
- Following extensive flooding in northern Bangladesh in August 2014 DFID provided £1.6 million to WFP to support 19,463 HHs with a three month package of financial support of BDT9,000. At the conclusion of the intervention the ‘acceptable’ HH food consumption score increased from 36% to 59%. The proportion of HHs reporting ‘poor’ food consumption fell from 27% to 5%, representing an 81% reduction.
- Also in August 2014, £300,000 was provided to the NARRI consortium to support 12,743 flood affected HHs in Kurigram district. As with WFP, UK funding also helped to address immediate food insecurity in addition to sanitation needs.
- Over the period 1st April to 30th September 2015 the UK will provide £1.9 million to WFP to enable the organisation to support 33,000 refugees in Nayapara and Kutupalang refugee camps with a monthly food ration. The UK will also support four separate nutrition related activities.

Summary of responses to issues raised in previous annual reviews
DFID-B took action against major 2013-2015 recommendations made in relation to output one. Notable examples include the ‘real-time’ and field-based programme monitoring of all UK funded humanitarian activities in 2014-2015. response,.

Summary of recommendations for the next year to be undertaken by DFID-B
1. Ensure readiness for meeting potential humanitarian needs through 2015 and early 2016 via a programme cost extension (by October 2015); secure new multi-year programme funds for the next phase of humanitarian support (by April 2016).
2. Assess options for strengthening early action for example through multi-year pre-financing arrangements with humanitarian organisations (by April 2016).
3. Continue to support Rohingya activities, specifically seeking to address protection needs, especially those pertaining to women and girls, while targeting support for shelter requirements and the legitimate needs of communities hosting refugees; support for Rohingya related coordination fora and the capacity building activities of national NGOs should also be considered (by April 2016).
4. Identify options for leveraging long-term development support for Satkhira district with the objective of strengthening resilience to future flooding (by December 2015).

Output Title	Output 2: Improved co-ordination and information management
Output number per LF		2	Output Score	A
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Databases including ‘3W’ (who, what, where) matrix, contact lists and other key data, for every DFID-supported cluster	Logistics cluster matrix, maps, contact lists Updated and maintained	Whilst the Logistics Clusters maintains 3W matrixes, contact lists etc. these are not available via http://logcluster.org/countries/BGD
2.2 Number of agencies trained to support implementation of a JNA	10 trainings to be completed	Under the initial phase of the JNA programme the training target was achieved.

Key Points
- In 2014-2015 the UK provided £140,200 to the Logistics Cluster to strengthen logistical preparedness for a large-scale humanitarian crisis, such as an earthquake, affecting Bangladesh. This support led to the development of a nationwide logistics capacity assessment which provides an important planning resource to humanitarian actors in-country.
- The Logistics Cluster has also provided civil-military related training to more than 30 representatives from the Bangladesh Armed Forces and staff from humanitarian agencies.
- The UK also provided £350,000 to the International Organisation for Migration (IOM) for its work in relation to undocumented Rohingya. This funded the establishment of a ‘Coordination Support Unit’ in Cox’s Bazar and the recruitment of six staff as well as the development of a ‘3W’ matrix showing the delivery of humanitarian services in areas hosting Rohingya along with the design of an online information portal.
- Via UK funds IOM is currently implementing a mapping exercise to assess the delivery capability of local Bangladeshi NGOs which will be followed by the development of “capacity building roadmap”.

Summary of responses to issues raised in previous annual reviews
DFID-B took action against all major recommendations made in relation to output two. The Government of Bangladesh (GoB) refused to grant the NGO Care approval for a successor to the JNA programme meaning we were not able to take forward work related to this recommendation.

Summary of recommendations for the next year to be undertaken by DFID-B
1. Assess options for strengthening coordination arrangements including through investments in Clusters and other fora such as the iNGO Emergency Sub-Committee (by April 2016).
2. Continue to support Rohingya activities, specifically seeking to address protection needs, especially those pertaining to women and girls, while targeting support for shelter requirements and the legitimate needs of communities hosting refugees; support for Rohingya related coordination fora and the capacity building activities of national NGOs should also be considered (by April 2016).
3. Resource the JNA process in the next phase of programming in the context of performance improvements designed to facilitate more rapid responses (by April 2016).

Output Title	Output 3: Logistical support for NGOs and other partners providing humanitarian, risk reduction and development support to disaster-prone and vulnerable regions
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Proportion of MAF flights taken by NGO and other humanitarian or development actors.	over 70%	78% (and 8% medical; 14% other)
3.2 Number of customs officers in Bangladesh with increased awareness of customs processes – as related to humanitarian emergency supplies	15 target	Not met: The GoB is unwilling to sign the customs model agreement which if in place would facilitate the rapid importation of relief items in the event of a crisis.

Key Points
- Over the reporting period DFID-B provided £180,000 to MAF for its seaplane service. Overall, MAF continues to exceed stated programme objectives.
- Last year 1,942 passengers used MAF’s charter service - against a target of 1,800.
- MAF calculates that its seaplane service saved NGOs 3,152 days of travel time over the reporting period.
- MAF has also taken concrete steps to broaden its donor base efforts which the UK has supported.

Summary of responses to issues raised in previous annual reviews
MAF has worked to implement all of the recommendations made by DFID-B in last year’s annual review. For example, MAF convened a briefing and information session which brought together a range of relief and development actors. MAF used this event publicise its work and to highlight the impact its service has on remote and inaccessible communities across Bangladesh. MAF also took steps to more closely work with Clusters and the Humanitarian Coordination Task Team. During the latter half of the reporting period MAF initiated work to engage donors with a view to broadening its support base. To this end a meeting with DFID-B and the US Agency for International Development will take place in September 2015.

Recommendations
1. DFID-B should re-assess its relationship with MAF. It should do this with the aim of ensuring that any potential new support to MAF clearly contributes to the achievement of the UK’s humanitarian objectives for Bangladesh. For example, DFID-B should explore how MAF can support both rapid needs assessments and timely responses to disaster events. Any new support to MAF should be more targeted in nature with a view to transitioning from the current model of subsidising MAF’s general operations (by April 2016).
2. To-date the GoB has been unwilling to sign a customs agreement regarding the importation of relief items following a major disaster event. Experience from the Nepal earthquake shows that such agreements, if in place prior to an emergency, can facilitate swift international responses. DFID-B should continue to engage with the GoB on this issue including where necessary with the support of colleagues from the High Commission.

Output Title	Output 4: An enhanced evidence base and better analysis for an effective disaster response in Bangladesh, and globally.
Output number per LF		4	Output Score	A
Risk:		Low	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1 Number of reviews or studies commissioned to fill identified knowledge and information gaps in disaster planning and preparedness	Secondary Data Reviews (SDRs) maintained. Capacity review of GoB. Humanitarian impact of low level disaster events.	Engagement with the GoB regarding a possible continuation of the JNA programme commenced during the reporting period and is still underway. Due to senior staff changes in the Ministry of Disaster Management & Relief (MoDMR) work on the capacity assessment was delayed. JNA staff also supported the joint assessments in relation to monsoon flooding in 2014 and 2015.

Key Points
- DFID-B provided £39,548 to the Norwegian Refugee Council (NRC) and Care to support a short-term continuation of the JNA programme.
- UK funding helped to finance the implementation of a multi-agency assessment in August 2014 in north west Bangladesh following monsoon flooding.[2] This assessment contributed to the development a Joint Response Plan which DFID-B and the European Commission (EC) supported.[3]
  [2] See http://www.lcgbangladesh.org/HCTT/JNA%20materials%20update/2014%20Flood%20Assessment/0809_NW_Flooding_JNA_FinalFINAL.pdf
  [3] See http://foodsecuritycluster.net/document/joint-response-plan-food-security-nutrition-and-wash-clusters-august-2014
- Tools developed by the JNA were used to guide the implementation of an Food Security Cluster led assessment in the north west in late 2014.

Summary of responses to issues raised in previous annual reviews
As noted above, the GoB refused to grant the NGO Care approval for a long-term successor to the JNA programme. As a consequence work relating to sustainability of the Secondary Data Reviews (SDRs) was put on hold. However, SDRs continue to be used internally by DFID-B and have been shared across programme teams.

Recommendations
The principal recommendation pertaining to the JNA includes;
1. DFID-B should look to resource the JNA process in the next phase of programming in the context of performance improvements designed to facilitate more rapid responses.
2. Via a new JNA programme DFID-B should explore options for developing assessment tools that include a specific focus on the impact of disaster events on women and girls in addition to assessments tools for use in urban contexts.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
Administration costs, overheads and management fees levied by our implementing partners have been primary cost drivers of the HPRP. Such costs have largely remained static over the course of the review period. However, WFP has recently increased the amount it charges for Direct Service Costs (which include staff salaries and other costs) from 13% to 18%. Doing so brings WFP-Bangladesh in-line with policy established at HQ in Rome. Operational costs have differed slightly between implementing partners. Such changes can be explained by the differences in delivery modality and operating context.

Cost of relief supplies is also an important cost driver. We judge that programme partners in 2014/2015 purchased inputs at an acceptable price in relation to quality. For example, the 12,743 family sized hygiene kits which were supplied for NARRI as part of the 2014 monsoon floods response were in-line with relevant Cluster standards and at reasonable cost. The DFID funded kits were also procured centrally by Oxfam on behalf of NARRI members on the local market at unit cost of £7.20. Such costs compare favourably to the price of similar kits held by DFID at the UK’s humanitarian stockpile. Whilst a direct comparison is not possible due to the differences in the composition of kits broadly speaking we judge the NARRI kits offer good VfM.

UK resources allocated in 2014/2015 under the HPRP helped to leverage financial support from other donors. For example, in September 2014 MAF led an overflight of flood affected districts of northern Bangladesh which the EC took part in. The MAF flight helped to inform the subsequent JNA which in turn supported the development of the Joint Response Plan. The EC drew on the findings of the JNA when allocating response resources. Likewise, our support to IOM has also catalysed interest in the Rohingya issue from a range of donors.

VfM performance compared to the original VfM proposition in the business case
VfM in the context of humanitarian responses centres primarily on the effectives of the response. For rapid onset crises, speed of response is also of prime importance. Using these criteria and also considering the costs of delivery, the VfM performance of the interventions funded through the programme is considered to be strong.

Assessment of whether the programme continues to represent VfM
The programme has performed well against the ‘3E’ of the VfM framework. Economy - spending less: As outlined above, we judge that programme partners in 2014/2015 purchased inputs at an acceptable price in relation to quality. Efficiency - spending well: Programme partners continue to convert inputs into outputs in an efficient manner. For example, the use of mobile money transfers in the 2014 monsoon flood response and waterlogging programme in Satkhira district ensured that the beneficiaries received their entitlements in a safe, secure and speedy manner. Effectiveness – spending judiciously: For example, activities supported under Output 1 which accounted for the bulk of expenditure were successful in addressing the immediate needs of disaster affected communities.

Quality of financial management
Financial management and oversight of UK resources by programme delivery partners is assessed to be sound. DFID-B works closely with its partners including on forecasting and reporting. DFID-B conducted a risk exercise following a period of hartals in early 2015 to assess the ability of partners to manage UK finances effectively given the operational challenges that such events pose. DFID-B assessed that the programme partners had responded soundly to the changing operational context with no adverse impacts on UK funds.

Date of last narrative financial report	MAF: 28/04/2015. / WFP; Monsoon flooding 2014; 05/05/2015 / NARRI; Monsoon flooding 2014; 08/04/2015. / WFP; Logistics Cluster; 03/11/2014 / Care; JNA; 02/11/2014. / WFP; Satkhira waterlogging; 02/02/2015 / IOM; Rohingya coordination; 15/04/2015
Date of last audited annual statement	MAF; 03/07/2015 / NARRI; Monsoon flooding 2014; 23/08/2015 / Care; JNA; 02/07/2015 / IOM; Rohingya coordination; 22/07/2015 / WFP: Audit reports are published online. The last report of Bangladesh is for 2013. We do not receive separate audit reports for our individual projects with WFP.

E: RISK (½ page)

Overall risk rating: Low

Overview of programme risk
There have been no changes to the overall risk environment. No cases of fraud or corruption were reported during 2014/2015. Programme beneficiaries that DFID-B met with in June and August 2015 in the south-east and south-west respectively did not raise any fraud or corruption concerns. Generally speaking programme partners effectively managed the period of hartals although recurrent strikes and blockades did impede implementation.

Programme partners delivering assistance to Satkhira waterlogging and providing logistics cluster support have requested extensions to their end dates in order to deliver the agreed results. In agreeing to extensions partners were reminded of the importance of building in sufficient contingencies to deal with risks both foreseen (such as flooding) and unforeseen The delays have impeded delivery of results.

All partners (including their downstream partners) have been informed and are aware of DFID’s zero tolerance of fraud and corruption and have been made aware of the requirement to report to DFID immediately. This was evident from conversations held with implementing partners during monitoring visit undertaken by DFID-B officials. Beneficiary selection criteria is rigorously set following extensive consultation. UK funded programmes in 2014-2015 under output one included beneficiary feedback and complaint mechanisms in their design which programme beneficiaries were able to describe to DFID-B officials during programme monitoring. The programme team has also initiated a robust check against funding in advance of need and partners have been made aware of DFID’s requirement to not fund in advance.

Outstanding actions from risk assessment

Risk	Detail	Risk mitigation strategy
Risk of funds not used for purposes intended	No cases of fraud or corruption were reported to DFID-B during 2014/2015.	DFID-B should continue to emphasise to partners its intolerance of fraud and corruption. DFID-B should also look to support partners, including through the provision of financial assistance if necessary, in their efforts to strengthen risk management.
Political unrest and Hartals continue	There is a risk that the political instability and hartals of early 2015 could remerge	DFID –B should continue to work with partners to assess the prevailing risk posed by hartals should the need arise. However, DFID-B will be unable to influence the overall operating environment. DFID-B might consider developing a series of ‘trigger points’ related to hartals which if reached might necessitate the implementation of risk mitigation steps.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Hartals adversely impacted on the delivery of UK funded programmes during the first six months of 2015. During this period., DFID-B worked with implementers agencies to understand the operational impact of hartals and to adjust programme timelines as necessary.

Performance of partnership(s)
Implementing partners during the reporting period were iNGOs, WFP and IOM, with WFP receiving the bulk of funds.

All the programmes, aside from IOM, are implemented through downstream partners.

Support to WFP has been provided via a due diligence assessment conducted by DFID HQ. A local level due diligence assessment is currently underway.

The establishment of separate Project Advisory Committees (PAC), which DFID and other donors sit on, by WFP for Rohingya and Satkhira related work has helped to strengthen the UK-WFP relationship. The committee facilitates, frank, open and focussed discussions regarding project activities.

The NARRI consortium remains a valued partner of DFID-B. It demonstrated an ability to execute a programme with rigour. Consortium members during the course of 2014/2015 have also demonstrated a commitment to supporting coordination fora.

Support to IOM has contributed to improvements in the operating context in the south-east of Bangladesh. We assess that IOM continues to play an important and useful role in coordination and more broadly in facilitating open dialogue on the Rohingya issue.

An opportunity exists to strengthen the speed and efficiency of humanitarian responses to rapid onset crises through multi-year pre-financing for pre-qualified organisations. This will be explored through a second phase of funding following the end of the current programme.

Asset monitoring and control
WFP, NARRI, MAF and IOM have established policies for managing assets. A spot check of NARRI and MAF by the Programme Manager on 15 Jan 2015 and 27 July 2015 did not reveal any issues. An asset check of MAF is due this month. Partners have communicated with DFID in case of asset disposal or management.

G: CONDITIONALITY (½ page)

No conditionality was linked to this programme.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
Owing to the short-term nature of activities funded during 2014-2015 no evaluations of DFID-B’s humanitarian activities were conducted. For the WFP programme in Satkhira an “after action review” has been planned. For the IOM component a mid-term and ex post evaluation will be conducted “to assess the project’s overall achievements and recommendations for potential future needs to be addressed.” Consideration is being given to whether a whole-of-programme independent review would help generate lessons learned from this phase to inform the design of the next phase of DFID-B’s humanitarian assistance.

Monitoring progress throughout the review period
DFID-B receives quarterly narrative reports and finance reports for all interventions except for WFP programmes funded by the HPRP. For WFP funded programmes, as per the DFID-WFP framework agreement, we receive ‘Standard Project Reporting’ and updates through the quarterly PAC meetings. In addition, through attendance at PAC meetings DFID-B is able to garner verbal updates regarding implementation in Satkhira and the south-east and monitor performance of partner delivery.

DFID-B visited all programmes funded by the HPRP during the period 2014-2015. For example, DFID officials took part in a MAF overflight of flooded northern areas in August 2014. Later that year, in December, we undertook a monitoring visit to Bogra district where NARRI was working and met with programme beneficiaries.

DFID staff also attended a civil-military training session managed by the Logistics Cluster.

In the south-east, in June 2015, several DFID-B staff members visited Cox’s Bazar to appraise IOM’s work in relation to Rohingya. On this visit we also met with Rohingya refugees who are supported under the WFP intervention in Kutupalang refugee camp. More recently DFID officials undertook a monitoring visit of WFP’s work in Satkhira district.

Feedback from beneficiaries has provided invaluable insights into how UK funded humanitarian programmes are perceived by those we support. Generally speaking feedback regarding UK funded interventions was positive. However, feedback often focussed on the structural drivers of vulnerability. For example, in Kutupalang refugee camp residents spoke of the need for a “durable solution” to their displacement.

Annual Review process
The annual review for the HPRP took place during 10-19 August 2015. The review included a review of documentation such as the HPRP business case and logical framework, previous annual reviews, quarterly progress and monthly financial reports produced etc.

The review also included meetings with key stakeholders including GoB officials from the MoDMR, other donors and implementing partners.

In addition, DFID officials also undertook a three day visit to Satkhira district to assess WFP’s work and to meet with beneficiaries.