## Annual Review – Responding to the Nutrition Crisis in Yemen

Title: Responding to the Nutrition Crisis in Yemen (R2N)
Programme Value £ (full life): £120,300,000		Review date: 30 October 2020
Programme Code: 300525	AMP start date: 25 September 2018	AMP end date: 30 September 2021

Summary of Programme Performance
Year	2019	2020	2021
Overall Output Score	B	A
Risk Rating	Severe	Severe

DevTracker Link to Business Case:	http://iati.FCDO.gov.uk/iati_documents/36022579.odt
DevTracker Link to results framework:	http://iati.fcdo.gov.uk/iati_documents/57385334.xlsx

A. SUMMARY AND OVERVIEW

Description of programme
Why Nutrition in Yemen? / Nearly 80% of the population – 24 million people – require some form of humanitarian assistance and protection. / Malnutrition leaves individuals more vulnerable to health risks, but only half of Yemen’s health facilities are functioning and 17.8 million people, of whom 50% are children, lack access to clean water and sanitation. / At least 1.8 million children and 1.1 million pregnant or lactating women are acutely malnourished.
[note] https://reliefweb.int/sites/reliefweb.int/files/resources/2019_Yemen_HNO_FINAL.pdf
[note] https://reliefweb.int/sites/reliefweb.int/files/resources/20190402_Yemen_HNO_2019_Summary_V1.pdf, Page 4

As part of the wider UK Government objective to improve nutritional outcomes and health services for women and children in Yemen, the Foreign Commonwealth and Development Office (FCDO) is providing £120.3 million over 3 years to UNICEF, research initiatives as well as to the World Bank, a new partner for the programme. The programme is built around a life-cycle approach that aims to address the immediate and underlying causes of undernutrition in Yemen. These include addressing malnutrition, health, water and sanitation needs, while also supporting technical analysis and evidence to inform the humanitarian response in Yemen. Since 2018, this programme has contributed to over 3.7 million children under the age of 5 being screened for severe acute malnutrition.
FCDO investments have been structured across three areas.
Output 1: Immediate Actions - Critical Nutrition, Health, Water, Sanitation and Hygiene service delivery – provide lifesaving, improved quality nutrition, health and wash services for affected populations, complemented by a focus on protection for the most vulnerable.
Output 2: Remedial Actions - System strengthening and risk management – maintain and strengthen systems delivering nutrition, health and water and sanitation services at a sub-national level. Improve efficiency and effectiveness of health risk management through improved planning and financing.
Output 3: Increase contextual understanding - Knowledge and evidence generation – address the information and data gaps that exist in Yemen by improving the knowledge and evidence base for the context and supporting analytical products to improve decision making.
This Annual Review covers the period July 2019 to June 2020. It should be noted that whilst COVID-19 has hit Yemen this year, we will not assess progress against what we have funded for COVID-19 response activities until the next annual review in 2021 as activities were not funded before this reporting year ended on 30 June 2020.
A cost and time extension for this programme was submitted for approval and whilst FCDO Ministers were able to approve, HM Treasury (HMT) could only provide approval on the budget for this financial year (2020-21). FCDO Yemen will approach HMT early in 2021 to seek approval for the remainder of the cost extension.

Summary supporting narrative for the overall score in this review

The programme received an ‘A’ score in this annual review, meaning it met the expected level of results and performance. The outbreak of Covid-19 in spring 2020 has been a major challenge to the sectors addressed by this programme, but overall, the performance has been robust despite this. Targets were achieved or exceeded for 15 out of 24 indicators. Of the 9 missed targets, 6 of these were directly attributable to the impact of COVID-19, particularly in relation to health-seeking behaviour and restrictions imposed on outreach activities by the authorities. Some of these restrictions, especially in Houthi areas, exceeded those strictly necessary for outbreak suppression and were part of a wider set of new impediments to humanitarian access. Where targets were achieved, these were underpinned by strong operational performance in the first half of the reporting period and by efforts to improve reporting rates from the downstream service providers. This helped to mitigate for the constraints faced in the second COVID-19 affected period. Of the three activities that were off-track before COVID-19, the one of most concern is that for polio vaccination. A vaccine-derived polio outbreak was declared in Yemen in August 2020 – a result of long-term under-vaccination. A huge effort will be needed to increase vaccination coverage going forward. Evidence of good quality services provided with UNICEF support is also provided by Tahseen, FCDO’s independent monitor. In summary, UNICEF has worked hard to maintain and extend services to vulnerable children and women despite multiple and complex challenges.
[note] Vaccine-derived polioviruses (VDPVs) are rare strains of poliovirus that have genetically mutated from the strain contained in the oral polio vaccine.

Major lessons and recommendations for the year ahead

Key Recommendations

1. By 31 December 2020 UNICEF will have committed itself to a simple action plan aimed at developing a more rigorous approach to programme data – and especially the use of data for analysis. The Annual Review has exposed some weaknesses and inconsistencies in the use of data to generate results and to interpret data into meaningful findings. In some cases, deviations from expected results could not be clearly explained or were at odds with other reporting. This undermines confidence in reporting. If data collection is weak this needs to be strengthened or be flagged as a clear constraint. All data need to be handled objectively to ensure rigorous evidence generation. UNICEF should consider expanding its data handling and analytical capacity, using FCDO funding if required.
2. Polio vaccination was slightly off-track before the COVID-19 outbreak and was severely curtailed during the outbreak. There is now an outbreak of vaccine-derived Polio in Yemen which needs a massive and swift response. Outreach activities of all kinds have been constrained by COVID-19 and humanitarian access impediments in 2020. These activities must be prioritised for advocacy as soon as possible, with support from FCDO and other donors and other key stakeholders [N.B. progress was being made at the time of finalising this report but needs to be sustained].
3. UNICEF’s learning around adapting activities to COVID-19 should continue to be applied in the long term – both to maintain preparedness for any subsequent waves and to ‘lock in’ the enhanced practices around Infection, Prevention and Control (IPC), triage and disease surveillance. Adequate in-country buffer stocks of Personal Protection Equipment (PPE) must be maintained to protect health workers and service users and to ensure activities can continue.
4. Extending the coverage of Severe Acute Malnutrition management services to more health facilities is an important objective under the programme, especially at a time when IPC levels are deteriorating, and more children are likely to become severely malnourished. By 31 December 2020 UNICEF and FCDO should review the constraints involved in this objective with a view to increasing the level of ambition for providing malnutrition services and perhaps if appropriate move budget to this component of the programme from another spending area.
5. Indicators under output 3 (Knowledge and Evidence Generation) - should undergo further analysis by 31 December 2020 with a view to clarifying and ensuring FCDO are clear on what is being funded and how the products are informing and improving the overall humanitarian response.
6. Follow up with UNICEF by 31 December 2020 on issues highlighted by FCDO’s independent monitor in respect of beneficiaries being charged registration fees for some health services in some health facilities and visibility/existence of beneficiary feedback and complaints mechanisms. Both these issues have been recurrent themes in a health facilities visited so far.
7. Update logframe by 31 December 2020 to ensure funding to the World Bank, a new partner in this programme, includes indicators specific to our funding.
8. FCDO will follow up by 31 December 2020 with UNICEF to request disaggregated data where these can reasonably be made available.
9. UNICEF should continue to take advantage of the flexibility built into this programme by ensuring that budget is allocated as needed under each output to where it is needed most.
10. FCDO and UNICEF to review indicator 1.9b (number of Rapid Response Teams responding to cholera and emergencies) by 31 December 2020 to ensure it takes into account case incidence e.g. deployment of Rapid Response Team to X number of suspect cases – otherwise the indicator will always be missed when there is not a large disease outbreak.

Key Lessons

1. UNICEF learned ways to ensure the resilience and continuity of essential services during the COVID-19 outbreak. Measures, such as orientation sessions for health workers on COVID-19 transmission and Infection Prevention and Control, as well as ensuring the availability of Personal Protective Equipment, were vital to mitigate fear of infection not only among patients, but also health workers. The continuity of Mental Health and Psychosocial Support services was also ensured through the use or remote case management approaches, including online counselling. Generally, more use was made of remote methods e.g. for training and supervision and these may continue to be useful adaptations in a situation where access is constrained for various reasons.One specific adaptation to operations during the pandemic was taken forward by UNICEF in the period immediately following the period which is covered by this report [information received in November 2020]. This was an adapted approach to vaccine outreach campaigns, specifically a diphtheria campaign in July 2020 covering five governorates and a polio campaign conducted July-Aug 2020 in thirteen governorates. The key to this adaptation was the appropriate use of PPE for the vaccination teams, joint planning with the Ministry of Health and effective community engagement. This resulted in an estimated 75% coverage of the target population of children under 15 for diphtheria and 96% coverage of targeted children under 5 for polio combined with vitamin A supplementation. These campaigns and the lessons for vaccination outreach during infectious disease outbreaks have been written up in the Global Journal of Health Science (https://doi.org/10.5539/gjhs.v12n12p141)
2. FCDO has learned that it is sub-optimal to rely solely on performance data provided by the grantee. Independent triangulation with data from other sources e.g. clusters, health information system and third-party monitors has allowed for a more rounded picture and the ability to score the AR with more assurance. This approach can be strengthened even further in future.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

This programme is part of a wider, UK Government objective to avert famine in Yemen. The above diagram illustrates that with the right financial and technical inputs we will contribute to outputs that address nutrition needs working through health and water and sanitation (WaSH) interventions. The programme aims to strengthen Yemeni systems to ensure that Yemenis have access to life saving interventions leading to an overall improvement in nutrition status among the population. Evidence and learning will continue to be gathered and shared across the interventions to ensure that the best approaches are being taken.
The programme initially targeted 107 high-priority districts considered at heightened risk of famine, as identified jointly by the WASH, Nutrition, Health, and Food Security and Agriculture clusters. As the situation in Yemen is rapidly evolving and uncertain, the programme maintains flexibility to work in any of the 333 districts for emergency response if/when the situation arises. The evolving COVID-19 situation in country has challenged some of the assumptions within the theory of change. For example, due to severe access and movement restrictions, vaccination campaigns and other outreach activities have been suspended, resulting in some planned results being missed. In addition, the overall funding situation for Yemen in 2020 (HRP only 40% funded as of 6th October 2020) is also proving challenging resulting in for example, the reduction to the number of Rapid Response Teams (RRTs) particularly helpful during the COVID-19 pandemic. The flexibility in the programme enables UNICEF to adapt to the changing context and where that is not possible then challenges to date have not changed the overall impact or outcomes of the programme.

Although there have been changes to some milestone targets within the reporting period, this is mainly due to streamlining the logframe after the last annual review. In addition, UNICEF has failed to meet some milestones, particularly under the output 1, provision of direct lifesaving support, but this has been largely due to funding shortfalls and the rapidly evolving situation on the ground with COVID-19 impacting progress in some areas. Notwithstanding these challenges the programme is still delivering value for money (VFM), with UNICEF remaining one of FCDO’s key implementing partners on the ground in Yemen, particularly during the COVID-19 pandemic where it is critical that on-going support to the health system is maintained. The programme is flexible in that budget can be moved between different activities within an output. This helps to maximise VFM by ensuring that resources are directed to where they are most needed and where conditions allow them to be spent.

Although, some UNICEF activities are targeted at women, for example skilled childbirth attendance, other activities, under WaSH are targeted at men, women, boys and girls but these results are not disaggregated by age, sex, disability or geography. There is some disaggregation on age given that certain activities focus on a specific age groups e.g. children under 5 years old enrolled on severe malnutrition management programmes. In terms of accountability to affected people, we are making attempts through Tahseen, our third-party monitoring provider, to seek views/feedback from beneficiaries but this is proving challenging with access to beneficiary contact details being problematic. Our third-party monitors are working with UNICEF to try and resolve these issues. We will follow up with UNICEF to request disaggregated data where these can reasonably be made available.

It should be noted that a recent business case addendum for a cost and time extension has been approved by FCDO Ministers which will enhance the programme by increasing the coverage, scale and sustainability of health services in Yemen through the inclusion of a new partner, the World Bank. HMT however, were unable to approve spending beyond the current financial year due to a UK Government budget prioritisation exercise and the timing of the spending review and so full approval will be sought in due course.

A new partnership with the World Bank is also being negotiated. This will increase FCDO’s influence over development finance and provide access to more health data held by the World Health Organisation and the Yemeni authorities. This will further increase VFM by leveraging FCDO influence over broader health policy in Yemen for a relatively modest investment.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Overall, the programme remains on track to achieve the intended impact and outcomes.

The logframe describes an overall intended impact of improving nutrition status across the life course for all vulnerable populations in Yemen, to be measured through the proxy of GAM (global acute malnutrition) and under 5 mortality rates.

Outcomes are closely aligned to outputs and for many milestones these have been achieved. Broadly, UNICEF has performed well against 15 out of 24 output indicators and for indicators that they performed less well against this is attributed in many cases to the challenges faced as a result of the COVID-19 pandemic. In recognition of this some milestones have been reduced, whilst end targets are unchanged, meaning that overall, it is expected the UNICEF will catch up on results that have proved more challenging to achieve due to the pandemic. Since the outputs are closely aligned with the outcomes, then it is expected that were UNICEF to have gone slightly off track due to the impact of COVID-19 then this will impact on the outcomes, but only temporarily. UNICEF has been a key partner during the COVID-19 pandemic and although they have faced challenges, they have risen to these, keeping other health, nutrition and WaSH services (where feasible) going whilst dealing with the impact of COVID-19. This has helped achieve VfM by supporting the health system throughout the pandemic, ensuring that services that had been paused can restart at the appropriate time.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme should continue given the critical nature of the services provided and UNICEF’s continued ability to deliver results across a range of indicators. UNICEF as a partner also offers additional opportunities to leverage and influence the behaviour of other donor contributions to this sector, such as the World Bank. Our cost and time extension will increase the coverage, scale, and sustainability of health services and, through a new partnership with the World Bank, increase FCDO’s influence over development finance, thus achieving increased VfM.

## C. DETAILED OUTPUT SCORING

Output Title	Affected populations in Yemen are provided with life-saving nutrition, health, WASH and protection support
Output number:	1	Output Score:	A
Impact weighting (%):	50%	Weighting revised since last AR?	Yes – revised from 40% to 50%

Indicator(s)	Baseline	Milestone(s) (June 2020)	Progress (June 2020)	Score and Results Attribution to FCDO
Nutrition
Output Indicator 1.1a (cumulative) / # of children under 5 screened for Severe Acute Malnutrition (SAM)	3,113,421	5,254,412	6,818,571	EXCEEDED (130% achieved) / (FCDO attribution - 20% = 1,363,714)
Output Indicator 1.1b (cumulative) / # of children under 5 with SAM enrolled in management programmes	288,928	566,584	530,279	UNMET (94% achieved) / (FCDO attribution – 25% = 132,570)
Output Indicator 1.1c (cumulative) / % of under 5 children enrolled in SAM management programmes who default (expressed as an average and range min/max)	14.7%	<15%	12%	EXCEEDED / (FCDO attribution - 12%)
Output Indicator 1.2 (cumulative) / # of children at school age (10 - 19 years old) receiving weekly iron supplementation as part of anaemia prevention interventions	0	300,000	0	NOT MET (0% achieved) / (FCDO attribution – 100%)
Output Indicator 1.3 (cumulative) / # of pregnant and lactating women receiving counselling and education on infant and young child feeding (IYCF)	1,530,810	2,371,376	4,414,128	EXCEEDED (186% achieved) / (FCDO attribution – 25% = 1,103,532)
Health
Output Indicator 1.4 (cumulative) / # of primary health consultations provided to children under 5, caregivers and pregnant and lactating women through health facilities, outreach services, and mobile health teams	1,090,559	3,552,632	3,645,229	MET (103% achieved) / (FCDO attribution – 30% = 1,093,569)
Output Indicator 1.5 (cumulative) / # of women of reproductive age receiving skilled birth attendance (home/facilities)	35,452	195,466	258,405	EXCEEDED (132% achieved) / (FCDO attribution – 15% = 38,760)
Output Indicator 1.6a (non-cumulative) / % of targeted children who are vaccinated with three doses of DTP/Penta vaccine (Routine vaccination & Integrated Outreach rounds)	82%	1,063,325 (100%)	880,669 (82%)	UNMET (82% achieved) (FCDO attribution– 15% = 132,100)
Output Indicator 1.6b (non-cumulative) / % of children <5yrs vaccinated during each rounds of Polio Vaccination campaign (Total target=5,535,816)	89%	11,071,632 (100%)	4,548,829 (82%)	UNMET (82% achieved) (FCDO attribution – 4% = 181,953)
Output Indicator 1.7 (cumulative) / % of children <5yrs vaccinated during each rounds of Polio Vaccination campaign (Total target=5,535,816)	New indicator (COVID-19 funding) Not assessed this reporting year
WASH
Output Indicator 1.8 (cumulative) / # of people provided with access to drinking water through UNICEF support to operational and maintenance (O&M) and rehabilitation of public water systems	1,119,791	1,369,791	1,620,792	EXCEEDED (118% achieved) / (FCDO attribution– 100% = 1,620,792)
Output Indicator 1.9a (cumulative) / # of individuals provided with emergency WASH	668,154	1,053,154	1,911,136	EXCEEDED (181% achieved) / (FCDO attribution – 100% = 1,911,136)
Output Indicator 1.9b (cumulative) / # of Rapid Response Teams responding to cholera and emergencies	0	800	300	UNMET (37.5% achieved) / (FCDO attribution – 40% = 120)
Output Indicator 1.10 (cumulative) / # of household members who have benefitted from UNICEF hygiene promotion activities, observed practicing handwashing with soap at critical times	0	950,000	1,050,280	MET (111% achieved) / (FCDO attribution – 100% = 1,050,280)
Output Indicator 1.11 (cumulative) / # people supported through continuity of WASH service	New indicator (COVID-19 funding) Not assessed this reporting year
Output Indicator 1.12 / # WASH NFI kit distributed to self-isolated Household	New indicator (COVID-19 funding) Not assessed this reporting year
Health and Nutrition and Social Care
Output Indicator 1.13 (cumulative) / # of pregnant women and mothers with newborns receiving vouchers to cover transportation costs for delivery, postnatal care and medical care in case of	TBD	0	0	MET / (FCDO attribution – 12%)
Child Protection
Output Indicator 1.14a (cumulative) / # of identified children who receive support through case management/referrals	0	925	932	MET (101% achieved) / (FCDO attribution – 100% = 932)
Output Indicator 1.14b (cumulative) / # of children and caregivers receiving mental health and PSS inside HF	0	92,120	91,056	UNMET / (FCDO attribution – 100% = 91,056)

Briefly describe the output’s activities, and provide supporting narrative for the score.

This output scores an A reflecting that the majority of indicators have been met or exceeded.

The output covers a range of integrated activities aimed at improving access to - and coverage of - services which address and mitigate the multiple causes of malnutrition. These span health, nutrition, water and sanitation interventions. Performance against the output has to be seen in the light of the COVID-19 pandemic which was a major and unexpected challenge during the last three months of the reporting period. Although the targets were underachieved for 6 out of 15 performance indicators, two-thirds of these had been on track to meet the targets according to the reporting for the first half of the period (July-Dec 2019). There is strong evidence that COVID-19 was an independent variable giving rise to lower achievements against these sub-outputs - a force majeure in effect. Moreover, lower numbers of ‘people reached’ during the COVID-19 outbreak are partly due to the behaviour of the service-users themselves. Fear of infection during the outbreak had a large effect on health-seeking behaviour, even though service providers, including MOH, UNICEF, WHO and NGOs were largely successful in keeping services running. The major exceptions here were outreach activities. Immunisation was badly curtailed due to government-imposed access restrictions. The number of Rapid Response Teams also had to be reduced due to funding shortfalls and lower numbers of cholera cases. It was too late in the reporting year to amend milestones for these indicators in the logframe and the scale of underachievement only became apparent when the end of year reporting was received by FCDO. However, not all the underachievement of targets can be explained by the COVID-19 factor. Performance was moderately off-track in relation to polio vaccination (indicator 1.6b) and the provision of psychosocial support services in health facilities (1.14b). Overall, it is commendable that most services kept running and achieved their targets given the challenges faced by COVID-19. However, the FCDO has concerns over one apparent inconsistency in reporting i.e. that the uptake of primary healthcare did not seem to be affected by COVID-19 in the second half of the reporting year (1.4). This is at odds with other data presented by UNICEF on service utilisation during the outbreak.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

This output continues to deliver VfM through bulk procurement and transportation of supplies such as vaccines, plumpynut (brand name for a Ready-to-Use Therapeutic Food) etc to deliver lifesaving support through its health, nutrition, WaSH and protection activities. UNICEF report that in terms of the plumpynut they procure, the unit cost does not exceed the £37.12 per carton for one child as set out in the business case. The same has been reported for other VFM indicators set out in the business case for items such as hygiene kits or water tanks where the original costs remain relevant. In the case of consumable hygiene kits the cost is $6 which is judged to be good value for money if comparing to other partners funded under the Displaced Peoples programme where the cost of a hygiene kit is over $14 – however, it should be noted that in this case these kits include additional items such as clothes, shoes, dignity kit etc. The agency maintains Long Term Agreements with specific suppliers for standard items which the agency expects to order multiple times over the course of a year. These agreements are typically in place for one year at a time, securing predictable prices and speeding up procurement.
Competitive tendering processes are maintained throughout, but UNICEF also assesses the viability of procuring items in Yemen, to avoid delays with international procurement. The lack of availability of items of acceptable quality within the country nevertheless precludes local procurement in most cases.
In addition, UNICEF has increased the integration of hybrid solar energy systems into emergency water pumping for more cost-effective and climate-sensitive programming. In 2019 analysis demonstrated that the costs of solar energy interventions in the northern province of Sa’dah broke even against diesel-fed generator costs in less than six months of operation.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

In response to the challenges presented by COVID-19 (outlined above) and shortfalls in UNICEF’s complementary programme funding from other donors (the Humanitarian Appeal for Yemen for 2020 was underfunded by $2bn at the time of reporting) some milestones under this output will be reduced over the next reporting year:

- Output indicator 1.1b - number of children under five enrolled in SAM treatment programmes reduced from 742,345 to 654,243 but the end of the programme target remains the same.  This milestone change is simply aligning with the Nutrition cluster target (currently at 90%) and is subject to change, therefore the numerical value of the milestone is also subject to change. We have advised UNICEF to keep us updated on future changes to ensure we have the most up to date milestone showing at any given time.
- Output indicator 1.9 b - number of Rapid Response Teams responding to cholera and emergencies - milestone reduced from 800 for period Jul to Dec 2020 to 300.  This is due to challenges including severe funding constraints, a decrease in confirmed cholera cases in 2020 compared to 2019 and switching the modality to training community- based volunteer teams to reflect COVID-19 social distancing constraints.
- Output indicator 1.13 - number of pregnant women and mothers with newborns receiving  vouchers to cover transportation costs for delivery, postnatal care and medical care in case of complications - milestone removed for period Jan to June 2020 as UNICEF have been addressing the risks with such a scheme to ensure they are managed well under the Programme Management Unit.  In addition, UNICEF confirmed that the voucher programme did face even further delays because of COVID-19 but will be ready to launch in August 2020.
- Output indicator 1.14 a - number of identified children who receive support through case management/referrals - revision to be able to report the milestones cumulatively.
- Output indicator 1.14 b - number of children and caregivers receiving mental health and Psychological Support Services inside Health Facilities - readjusting to show cumulative milestones.

Although not impacting on this reporting year, along with the above revisions, several new indicators were added to the logframe to take account of additional funding provided to UNICEF’s for COVID-19 activities.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against last year’s annual review recommendations

Simplification of the Logframe - UNICEF and FCDO to agree an updated logframe, to include only critical indicators necessary to assess outputs and outcomea. Where there has been an underachievement or overachievement, all targets will be adjusted for 2019/20 to better reflect progress against indicators. Progress update – this recommendation is relevant to all outputs and has been implemented in full.
Key Lessons Learned

UNICEF learned ways to ensure the resilience and continuity of essential services during the COVID-19 outbreak. Measures, such as orientation sessions for health workers on COVID-19 transmission and Infection Prevention and Control, as well as ensuring the availability of Personal Protective Equipment (PPE), were vital to mitigate fear of infection not only among patients, but also health workers. The continuity of Mental Health and Psychosocial Support services was also ensured through the use or remote case management approaches, including online counselling. Generally, more use was made of remote methods e.g. for training and supervision.

Recommendations for Year Ahead

1. By 31 December 2020 UNICEF will have committed itself to a simple action plan aimed at developing a more rigorous approach to programme data – and especially the use of data for analysis. The Annual Review has exposed some weaknesses and inconsistencies in the use of data to generate results and to interpret data into meaningful findings. In some cases, deviations from expected results could not be clearly explained or were at odds with other reporting. This undermines confidence in reporting. If data collection is weak this needs to be strengthened or be flagged as a clear constraint. All data need to be handled objectively to ensure rigorous evidence generation. UNICEF should seriously consider expanding its data handling and analytical capacity, using FCDO funding if required.
2. Polio vaccination was slightly off-track before the COVID-19 outbreak and was severely curtailed during the outbreak. There is now an outbreak of vaccine-derived Polio in Yemen which needs a massive and swift response. Outreach activities of all kinds have been constrained by COVID-19 and humanitarian access impediments in 2020. These activities must be prioritised for advocacy as soon as possible, with support from FCDO and other donors and other key stakeholders [N.B. progress was being made at the time of finalising this report but needs to be sustained].
3. UNICEF’s learning around adapting activities to COVID-19 should continue to be applied in the long term – both to maintain preparedness for any subsequent waves and to ‘lock in’ the enhanced practices around Infection, Prevention and Control , triage and disease surveillance. Adequate in-country buffer stocks of Personal Protection Equipment (PPE) must be maintained to protect activities, health workers and service users.
4. Follow up with UNICEF by 31 December 2020 on issues highlighted by our third party supplier, in respect to beneficiaries being charged registration fees for some health services in some health facilities and visibility/existence of beneficiary feedback and complaints mechanisms. Both these issues have been recurrent themes in a health facilities visited so far.
5. Update logframe by 31 December 2020 to ensure funding to the World Bank, a new partner in this programme, includes indicators specific to our funding.
6. FCDO and UNICEF to review indicator 1.9b (number of Rapid Response Teams responding to cholera and emergencies) by 31 December 2020 to ensure it takes into account case incidence e.g. deployment of Rapid Response Team to X number of suspect cases – otherwise the indicator will always be missed when there is not a large disease outbreak.

Output Title	Nutrition, health and WASH services in Yemen are supported at a local level to be more efficient and effective
Output number:	2	Output Score:	B
Impact weighting (%):	45%	Weighting revised since last AR?	Yes – revised from 30% to 45%

Indicator(s)	Baseline	Milestone(s) (June 2020)	Progress (June 2020)	Score and Results Attribution to FCDO
Nutrition
Output Indicator 2.1 (annual) / % of functional health facilities supported by UNICEF that provide SAM management programmes	83%	90%	79%	UNMET / (FCDO attribution – 12%)
Output Indicator 2.2 (cumulative) / # of Therapeutic Feeding Centre (TFCs) and Outpatient Therapeutic Programme (OTPs) supported by UNICEF with functional child-friendly spaces (offering Early Childhood Development services)	0	120	83	UNMET (69% achieved) / (FCDO attribution – 50% = 42)
Health
Output Indicator 2.3 (cumulative) / % of clinics supported by UNICEF offering minimum initial service package (primary health care, reproductive health, sexual and gender-based violence support) (total=4500)	0	56%	56%	MET (FCDO attribution – 20%)
Output Indicator 2.4 (cumulative) / % of estimated pregnant women in Yemen that have received at one ante-natal visit by a community health worker	N/A	30%	11%	UNMET / (FCDO attribution – 25%)
Output Indicator 2.5 / # of Health Facilities provided with medical, preventive and protective supplies (PPE, IPC supplies, ventilators and related equipment, test kits etc) to continue	New indicator (COVID-19 funding) Not assessed this reporting year
WASH
Output Indicator 2.6 / # of UNICEF supported isolation units /health centres meeting WASH basic IPC standard	New indicator (COVID-19 funding) Not assessed this reporting year
Output Indicator 2.7a / # of water facilities supported by UNICEF that have a risk management plan for improvement of water services	0	2	3	MET (150% achieved) / (FCDO attribution – 100% = 3)
Output Indicator 2.7b / # of people provided with improved water services by water facilities with a risk management plan	0	850,000	929,523	MET (109% achieved) / (FCDO attribution – 100% = 929,523)

Briefly describe the output’s activities, and provide supporting narrative for the score.
This output has scored a B.

Activities under this output aim at improving the quality of services being offered to children and women of child-bearing age and building stronger systems. Most of the activities span nutrition, health, early childhood development and provision of clean drinking water, and are aimed at extending the range of services available to children and women of reproductive age and therefore contribute to mitigating the multiple causes of malnutrition. One of the most important of these is access to clean water. UNICEF ensures there are ‘business continuity plans’ in place to support the resilience of water delivery systems. Essentially these are contingency plans to ensure sustained access to water should part of the system fail.

Progress against this output has been more mixed than for Output 1, with only half of the performance indicators on-track. COVID-19 has been a factor (only one indicator was off-track in the first half of the reporting period), but the association between the outbreak and missed targets seems weaker than for Output 1. Slower than expected progress was made in providing child-friendly spaces (CFS) in nutrition management facilities and in extending the coverage of ante-natal visits made by Community Health Workers (CHWs). The CFS provision was off-track before the COVID-19 outbreak; and difficulties encountered in offering incentives to CHWs is cited as the reason for delays in that activity. This latter constraint is related to increased risk mitigation over payments made through governmental bodies – something donors supported and therefore a valid and acceptable explanation.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

This output has failed to meet many of its targets and it is therefore hard to say that this element is providing the same level of VfM as initially envisaged in design. This aspect of the programme is the most challenging but is a long-term investment that should ultimately deliver better value for money for Yemenis through more sustainable, resilient health services that are more able to manage shocks etc. UNICEF works to benefit all Yemenis working at the local level making for a more effective and efficient response when delivering against its nutrition, health and WaSH activities. UNICEFs approach of working through Local Government Health Offices and NGOs ensures a more comprehensive service in Yemen. Delivery through Government Health Offices makes use of the existing health infrastructure and exercises long term benefits by supporting systems resilience. The combined delivery mechanism ensures reach and helps harmonise and manage costs across different geographical areas.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

In response to the challenges presented by COVID-19 and UNICEF’s funding situation some milestones under this output will be reduced over the next reporting year:

Output indicator 2.1 - % of functional health facilities supported by UNICEF that provide SAM management programmes - milestone for period Jul to Dec 2020 reduced from 90% to 70%.  The reason for this is that the current context of COVID-19 has impacted on the functionality of health facilities.  The revision is based on the revised annual work plan for UNICEF for 2020.  It is a temporary revision with end target remaining unchanged.  The revised proposed milestone of 70% is the minimum target that UNICEF aim to maintain during COVID-19, but it does not mean that they will not reach more.

Although not impacting on this reporting year, along with the above, revisions to a number of new indicators were added to the logframe to take account of additional funding provided to UNICEF’s for COVID-19 activities.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against last year’s annual review recommendations

Simplification of the Logframe – complete (see output 1 for more details).
Key Lessons Learned

Continued advocacy and support from authorities to keep facilities open and operational for non-COVID-19 emergency services, is key to prevent the rise in mortality trends in Yemen, especially maternal and newborn babies who are most vulnerable. Ongoing advocacy within the community also plays an important role, to ensure community members continue to seek health services

Recommendations for Year Ahead

Extending the coverage of SAM management services to more health facilities is an important objective under the programme, especially at a time when IPC levels are deteriorating, and more children are likely to fall into SAM status. By 31 December 2020 UNICEF and FCDO should review the constraints involved in this objective with a view to increasing the level of ambition for providing SAM services.

Output Title	Evidence is generated by UNICEF to improve understanding of the context and influence the shape of the response in Yemen
Output number:	3	Output Score:	A
Impact weighting (%):	5%	Weighting revised since last AR?	Yes – revised from 30% to 5%

Indicator(s)	Baseline	Milestone(s) (June 2020)	Progress (June 2020)	Score and Attribution to FCDO
Learning
Output Indicator 3.1 / # of surveys and assessments conducted by UNICEF funded by FCDO	0	2	2	MET (100% achieved) / (FCDO attribution – 100% for Smart Surveys)
Output Indicator 3.2 / # of analysis conducted on how the response efficiency could be improved (e.g. return on investment analysis)	0	5	7	EXCEEDED (140% achieved) / (FCDO attribution – 25%)
Output Indicator 3.3 / # of risk analysis and preparedness and contingency plans updated and shared with FCDO	0	2	2	MET (100% achieved) / (FCDO attribution – 100%)

Briefly describe the output’s activities, and provide supporting narrative for the score.

This output has scored a A.

Activities under this output focus on improving the knowledge and evidence base which underpin the ongoing analysis of malnutrition risks and prevalence in Yemen and strategies to reduce morbidity and mortality. The output is part of a drive away from a purely reactive emergency response type programming and towards an approach which identifies high risk areas and populations and allows pre-emptive deployment of additional inputs and resources. Examples are FCDO-funded Cholera Risk Modelling (Universities of Florida and Maryland) and rainfall forecasting (Met Office) which are used to anticipate potential cholera outbreaks and flooding risks. Malnutrition prevalence surveys have also been used to map where malnutrition rates are above emergency threshold levels and analyse the factors behind this. UNICEF’s reporting indicates that the knowledge targets have been met and even slightly exceeded. An additional example they cited was evidence generation on the evolving COVID-19 situation in Yemen since the outbreak began in April 2020. Nonetheless there is scope to sharpen these targets going forward and make the links between evidence and action even clearer.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

This output continues to demonstrate VfM by producing analysis to help inform and ensure and effective and efficient response in Yemen. For example, UNICEF worked with FCDO and the UK Met Office and several universities, to use predictive models based on weather, epidemiology and immunisation programme data to help to better prepare for and target cholera outbreaks. This helped to ensure the response was targeted in a timely manner. It has been demonstrated that early interventions in disease outbreaks can save thousands of lives, disability adjusted life years (DALYs) and money spent in responding once an outbreak has taken hold. For instance, researchers found that intervening four weeks earlier to the 2014 Ebola outbreak in Sierra Leone might have saved 8,835 lives and $203m. The authors’ conclusions were that ‘investments in healthcare systems facilitating such responses are needed and can offer good value for money’ (https://resource-allocation.biomedcentral.com/articles/10.1186/s12962-020-00207-x).

SMART surveys are funded under this output. Although these surveys are expected to inform the humanitarian response by ensuring resources are targeted appropriately to reach the most vulnerable, there are some questions as to whether these surveys are appropriate in a context like Yemen. SMART surveys are resource-heavy and it is hard to ensure adequate coverage in order to yield statistically-valid data at the national of governorate levels. Complementary and alternative means of monitoring the nutritional status of populations are being explored, including with expertise provided through FCDO funding.

Overall, analysis produced under this output assesses the efficiency of the response and highlights areas for improvement.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

None

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress against last year’s annual review recommendations

There were no recommendations under this output last year.

Key Lessons Learned

None

Recommendations for Year Ahead

Indicators under output 3 to be reviewed by 31 December 2020 with a view to clarifying and ensuring FCDO are clear on what is being funded and how the products are informing and improving the overall humanitarian response.

D: RISK

Overview of risk management
This programme was rated major residual risk at the business case approval stage, given the complexity of delivering the programme and contextual risks. The humanitarian context in Yemen remains high risk and since the business case was approved the overall context has deteriorated, increasing delivery, fiduciary and safeguarding risks. In addition, there has been a lack of reporting from UNICEF on fraud/aid diversion, particularly given the large number of downstream partners. This has resulted in the residual risk being increased to severe. The programme still operates within FCDO Yemen’s risk appetite across the six different risk categories (external context, delivery, fiduciary, safeguarding, operational and reputational).

COVID-19 has further exacerbated conditions in Yemen and increased risk, particularly in terms of ensuring continuity of health, nutrition and WASH services due to access and movement restrictions. The funding situation this year has also impacted on UNICEF ability to continue some key activities, meaning a scale back in for example WASH. COVID-19 continues to test the already fragile Yemeni health system, therefore it remains vital that key services are protected and strengthened.
Risk mitigation
UNICEF continued to report throughout the reporting year that they have robust risk mitigation measures in place; office wide audits, Harmonised Approach to Cash Transfers (HACT) audits, micro-assessments of partners and Programme Monitoring Visits. These measures should help to mitigate the risk of fraud occurring. However, an internal audit completed by the Office of Internal Audit and Investigations in 2019 identified several weaknesses including:

- how HACT is applied – UNICEF has addressed this weakness by putting in place an appropriate risk mitigation strategy, based on a robust methodology that exceeds the requirements within the HACT framework;
- no cohesive risk management strategy including no comprehensive assessment of the risk of fraud and aid diversion – UNICEF have introduced a risk management strategy, framework and data and trend analysis mechanism which is helping to address concerns raised; and
- concerns with direct cash transfer to authorities in Aden and de facto authorities in Sana’s, as a result of issues with sourcing qualified NGO partners. UNICEF have strengthened the capacity of Implementing Partners to address this risk and has further introduced a new payment modality through direct payment to beneficiaries, effectively bypassing making payments through the authorities.
UNICEF has confirmed that all actions responding to the major findings of this internal audit have been actioned. We will explore whether our independent monitoring partner Tahseen can undertake a study to verify the actions being taken by UNICEF.
UNICEF report on risk through six monthly progress reports and quarterly partner meetings with risk also regularly discussed at other scheduled update meetings. We expect levels of fraud, aid diversion and issues surrounding safeguarding to be present and perhaps increase in the Yemen humanitarian context. This is particularly the case given the recent outbreak of COVID-19 and the World Food Programme’s decision in June 2019 to partially suspend their food aid due to significant levels of aid diversion in Houthi-held areas. It should be noted that there remains an on-going concern on the low levels of partner reporting in Yemen. We continue to remind partners through regular discussions and communication of the importance of reporting any credible cases of fraud, aid diversion or safeguarding to FCDO.

Our independent monitor, Tahseen, also helps FCDO to mitigate against risks as we have the partner reporting and can check on delivery.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

Performance of partners and FCDO, on commercial, and financial issues

Out of a total grant value of GBP £112.8 million (USD $149,008,800) to UNICEF, to date FCDO has disbursed approximately GBP £105 million (USD $138,705,000).   Of this amount, $94,026,667 has been spent leaving an unspent balance of $44,678,333 as of 8 October 2020. An additional $13,327,537 is committed in legally obligated expenditures, resulting in a total utilisation of $107,354,204, which amounts to 77 per cent of the funds received to date.

Delivery against planned timeframe
Timeliness of narrative and financial reporting has been adequate. However, in terms of quality and coherency of data there is room for improvement, ensuring that evidence provided can easily be triangulated against other sources of information that the partner issues or contributes towards e.g. UNICEF’s Socioeconomic Analysis of the Impacts of COVID-19 in Children in Yemen report (June 2020) or routine reporting by the Health Cluster. In terms of financial reporting UNICEF has submitted, on occasion, inaccurate financial reports/payment requests (e.g. with inaccuracies in forecasts not giving sufficient assurance that payments are justified at a given time) indicating a lack of internal quality assurance. FCDO Yemen continue to work with UNICEF Yemen to ensure financial reporting is accurate. We continue to see improvements but important to continue working closely with UNICEF to ensure progress is maintained.

Performance of partnership
Overall FCDO recognises the complexity and access constraints in delivering in Yemen further compounded this reporting year by COVID-19. FCDO sees UNICEF as one of the critical actors in Yemen whose programmes are essential in saving lives and maintaining systems.

UNICEF performance is currently seen as good; however, this can be affected by the transparency, and credibility of UNICEF reporting, whether in donor reports, fraud or research (e.g. SMART surveys). An improvement in UNICEF’s level of transparency is needed to improve the quality of the partnership.

Asset Monitoring and Control
UNICEF maintains an asset register (last updated and shared with FCDO in February 2020) which is formally reviewed by FCDO. Asset management is in line with UNICEF policy and procedures as agreed in the Framework Agreement between FCDO and UNICEF.

Monitoring

October 2018 – 30 June 2020
# programmatic monitoring visits	134 programme monitoring visits conducted
# micro-assessments	66 Micro Assessments Conducted for IPs and 14 Micro Assessments are in progress in 2020.
# audits	34 IPs are under audit 2020 covering the amount of $15.8M
# spot checks	7 Spot Check Conducted and 43 IPs are in the progress of the Spot Check in 2020

FCDO has contracted its own third-party monitoring service with in-depth and light touch reviews being conducted on this programme as part of the pilot phase. Monitors have so far visited five health facilities as part of these reviews. Key common issues noted were the absence of beneficiary feedback and complaints mechanism and registration fees being charged in some health facilities for some services. FCDO will seek to ensure these issues are looked at in more health facilities as more reviews get underway. This will help to build a picture of whether these issues are pertaining to only a small number of health facilities or whether there is a more significant issue that will need to be addressed.

Evidence

Examples were provided above under the Value for Money section of how FCDO-funded data collection and analysis is helping to inform partners in the health and WASH sectors about impending humanitarian risks such as flooding and cholera. The programme team is also drawing on wider FCDO expertise and services, such as contracted technical support to the Scaling Up Nutrition movement (scalingupnutrition.org) to review critical nutrition elements of the programme including the SMART nutrition surveys and the Nutrition Information System. These initiatives are expected to bear fruit by early 2021. Reports from data gathering and analysis entities like ACAPS and Catapult on COVID-19 are also helping to inform FCDO policy and provide insight to the health authorities and humanitarian actors about the course of the epidemic and possible mitigation measures in Yemen. Upon request, ACAPs and Catapult can supply the FCDO Yemen team with data analysis and satellite imagery to help us and our partners understand other dimensions to the humanitarian context in Yemen.

Value for Money

Economy - Inputs of the appropriate quality at the right price

UNICEF indirect costs are in line with other UN partners. FCDO’s contribution includes an indirect cost recovery charge of 8% (a standard board-approved rate), and on an approved overall budget of £112,800,000 this equates to just over £9 million. A further 11.7% in country management cost (which will remain under review to ensure it remains appropriate in an evolving context) has been applied which covers operations (6.5%), M&E (1.3%), emergency and field operations (0.9%) and security costs (2.5%). In addition, direct staff costs were projected to be 6.86% of the total budget, which is roughly the out-turn. In line with a newly approved office management policy in 2020 a 9% in country management cost (covering Operations 5%, M&E 1.2%, Field operations 1%, external communications 1%, security 0.8%) is being applied to an additional £10m we contributed for COVID-19 activities and the £6.8m from the crisis reserve for nutrition activities.

The key cost drivers continue to be supplies, field logistics and human resources. The VFM indicators set, continue to be broadly in line with what was set out in the business case with one exception: Cost of Community-Led Total Sanitation (CLTS) in one village (includes CLTS and water supply incentive to villages achieving open-defecation-free status). This was a carry-over from the previous business case. CLTS is no longer a part of the current programme and will therefore be removed as a VFM indicator.

Efficiency - How well are inputs converted into outputs?

UNICEF holds a position as market leader in the procurement of basic child vaccines, mosquito nets, etc. This gives UNICEF unparalleled leverage in negotiating the lowest prices with suppliers. UNICEF has long-term arrangements in place with suppliers for hundreds of products, ensuring quality items at highly competitive prices.

Equity
UNICEF works to benefit all Yemenis. As a UN agency, UNICEF has no political affiliation and has consolidated its reputation as a development agency working to benefit all vulnerable individuals and communities irrespective of their political, territorial or sectarian affiliations. Beneficiary needs are the guiding factors for responses. UNICEF interventions target youth and women since women and girls in conflict affected areas are the most vulnerable group. This business case also aims to improve the access to critical services for people with disabilities. This is likely to take the form of a regular assessment of services based on the Washington Group questions.

Taking a protracted crisis approach; Use of existing health facilities and structure

UNICEF’s approach of working through Local Governorate Health Offices (GHO) and NGOs continues to ensure a more comprehensive service in Yemen and enables FCDO to access programming throughout the country. Delivery through GHOs makes use of the existing health infrastructure and exercises long term benefits by supporting and strengthening systems resilience. The combined delivery mechanism ensures reach and helps harmonise and manage costs across different geographical areas.

Managing financial partnerships

UNICEF’s comprehensive policies and procedures to effectively and efficiently manage funds, including its HACT assurance system and the ERM. HACT includes assessment and strengthening of partner financial systems, spot checks and scrutiny of use of funds. Capacity building, monitoring and financial regulations such as limits on overhead costs help to limit mismanagement of funds. UNICEF staff also conduct programmatic visits to implementing partners and proactively support interventions especially capacity development efforts.

Specific VFM examples

Programmatically, UNICEF has VfM built into the design of programmes, for example:

- When undertaking rehabilitation of water systems, UNICEF installs solar pump systems, minimising reliance on fuel which is vulnerable to inflation and market availability and generates pollution. In tandem, UNICEF provides capacity building to local water authority technicians, to ensure sustainable and reliable access to clean and safe water for communities. Solar power investments are expected to break even in just over two yers and save over $500,000 at year 5 with a 15% return investment on year 10. This is based on an assumption that there is a one-year time lag in construction, that fuel costs will be held constant at $1/litre and they system is brought up to 100% capacity when previously running at 10% capacity. At the end of the 10 years the investment is expected to generate a $1.4m saving.
- Communication for development activities leverage mass media as well as community level communication structures. These modalities optimise reach, build off existing community relations to optimise impact and link to sustainability in furthering community knowledge and change behaviour in key family practices.

Date of last narrative financial report	23/09/2020	Date of last audited annual statement	01/01/2019 to 31/12/2019 (received 3rd July 2020)