## Annual Review 2020 – International Action Against Corruption

Title: International Action Against Corruption (I-ACT)
Programme Value £ (full life): £32.4 million		Review date: 22/11/20
Programme Code: [AMP ID#] 205181	AMP start date: 22/08/17	AMP end date: 30/06/21

Summary of Programme Performance
Year	2018	2019	2020
Overall Output Score	A	A	A
Risk Rating	MODERATE	MODERATE	MODERATE

DevTracker Link to Business Case:	http://iati.fcdo.gov.uk/iati_documents/18108311.odt
DevTracker Link to results framework:	http://iati.fcdo.gov.uk/iati_documents/47124770.xlsx

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

The International Action Against Corruption (I-ACT) programme provides up to £32.4m over four years (including £3m from the Prosperity Fund) to deliver specialist anti-corruption technical expertise which is not available at country level and access to international partnerships to help tackle cross-border corruption. It works to shift incentives by better prevention, detection and exposure of corruption and recovery of stolen assets. I-ACT supports a range of implementing partners who provide experts, for example in financial investigations, anti-money laundering and asset-tracing, to help countries prevent and expose grand corruption. The programme was approved by Ministers in July 2017 and is now in its final year. The programme has been extended by 3 months to June 2021, to allow partners to complete work affected by the global pandemic.

The COVID-19 pandemic significantly affected the international context for international anti-corruption work during 2020. States around the world removed controls on spending in order to rapidly procure health commodities and deliver emergency welfare. In many cases, this led to spikes in corruption, resulting in a wave of COVID-19 scandals, in developing and developed countries alike. IACT partners had to respond to this new trend rapidly, highlighting the problem and proposing solutions i.e. to prevent and mitigate risks by establishing or strengthening whistle-blower and reporting channels.

Due to reductions in the UK’s Gross National Income and consequently its budget for Official Development Assistance, partners had to cope with reduced resources as the overall programme budget for the 20/21 financial year (April 2020 to March 2021) was reduced from £8,234,318 to £5,270,107. IACT partners also found new ways of working as travel and in-person meetings became impossible due to global COVID-19 lockdowns.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

The programme is on track to achieve or exceed the targets in the logframe.

The programme has scored A in this review.

Output 1 scored B for various reasons including two items of work not being published yet but overall, the output is on track to achieve end of programme targets. The other four outputs scored either A or A+ and I-ACT has made significant progress over the past year across all components. Significant impact has been made in the asset recovery space, where 29 countries have been supported by the Stolen Asset Recovery Initiative (StAR) to introduce legislative or other reforms on asset recovery; and over £100m stolen assets have been recovered by the International Centre for Asset Recovery (ICAR) between 2017-20. This is remarkable given major COVID-19 related disruptions.

I-ACT components and projects have contributed to the following:
- 19 countries supported by the International Monetary Fund (IMF) on international Anti-money Laundering (AML) standards as part of the anti-money laundering project.
- 164 financial investigation units globally have access to training, resources and mentoring to better detect illicit financial flows and refer them to investigators.
- 7.6 million companies now registered on the global beneficial ownership register.
- I-ACT support to Transparency International (TI) has helped ensure that anti-corruption reforms are on the agenda of governments, high-level forums and organisations such as G20, OECD and the IMF.
- Several defence companies are making improvements to their publicly available information over the past six months. 58 companies provided responses to TI assessments, which reflects a 43% response rate, up from 32.5% in 2015.

Major lessons and recommendations for the year ahead [1/2 page]

Lessons learned
Remote and online learning is a cost-efficient means of delivering capacity building – while also being resilient to global events such as the pandemic that can interrupt in-person training models. Therefore, future capacity building programmes should aim to leverage more technology enabled training delivery methods.

I-ACT has demonstrated significant measurable results at output level. We need to better understand how the outputs are contributing to desired outcomes and impact, by framing and quantifying I-ACT outcome and impact level results. This will help us assess overall effectiveness and inform future anti-corruption work.

- The effectiveness and impact of I-ACT partners and other stakeholders working on anti-corruption can be maximised with enhanced collaboration and coordination. The technical solutions, however sound, cannot succeed without political will and I-ACT partners have been more effective when they have joined up efforts to engage on common issues with relevant stakeholders in country or internationally. TI and OpenOwnership’s work with STAAC (a bilateral FCDO programme in Ghana) is a good example of how joint working can help generate momentum for anti-corruption reforms.
- The current I-ACT structure in terms of components and contracts is complex and requires significant time from the anti-corruption team to manage. Any future centrally managed anti-corruption programming should be structured more efficiently to minimise administrative and management time to enable staff to focus more on policy engagement and coordination between programme components, bilateral FCDO anti-corruption programmes and other HMG initiatives. This will maximise impact of the programme delivery. COVID-19, while generating risks and operational difficulties that the I-ACT programme and its partners are still navigating, has also generated momentum for some policy and programme areas such as illegal wildlife trade and procurement transparency and reforms. The longer-term impacts of COVID will continue to pose challenges and opportunities for reforms and need to be closely monitored.
- Different government communication embargos over the course of 2019 and 2020, due to Brexit and elections, significantly affected the Business Integrity Initiative. BII requires a simplified approach to marketing to enable it to deliver its support to businesses on anti-corruption and bribery when trading and investing in developing countries.

Recommendations for the year ahead

Recommendation 1: Review and revise the I-ACT logical framework for all components to reflect pivoting and adaption by the partners due to changes to the context such as COVID-19 and ODA prioritisation.

Recommendation 2: Develop a coherent narrative, supported with as much quantitative data as possible, on IACT’s effectiveness as a programme.

Recommendation 3: Anti-corruption programming design and implementation should build in collaboration between programme partners, bilateral FCDO programmes, other HMG and donor’s initiatives from the beginning. This should include clear incentives and goals for coordination and collaboration; and be resourced appropriately across programme oversight and delivery chains especially staff time and resources within the anti-corruption team.

Recommendation 4: Increase coordination between I-ACT partners and with in-country stakeholders such as other donors and FCDO country programmes to maximise the impact of I-ACT interventions.

Recommendation 5: In future anti-corruption programming, FCDO should prioritise and link-up programme delivery with policy and influencing work in the UK and globally to generate political will for anti-corruption to enable the technical solutions delivered by the programmes to work.

Recommendation 6: U4 should continue improving the marketing of key services to enhance take-up by partners and wider community of anti-corruption practitioners.

Recommendation 7: Ensure partners report regularly on fee rates, to enable measurement of the agreed VFM metric, and on how they are addressing gender, and what that has achieved.

Recommendation 8: Future anti-corruption programming should aim to streamline number of components and management complexities.
List of Acronyms

AC – Anti-Corruption
AML – Anti Money Laundering
BEIS – The department for Business, Energy and Industrial Strategy
BI – Business Integrity
BOT – Beneficial Ownership Transparency
CFT – Combatting Financial Terrorism
CITES – Convention on international trade in endangered species of wild fauna & flora
CoSP – Conference of State Parties
DCI – Defence Companies Index
DIT – Department for International Trade
EACDS – Expert Advisory Call Down Services
ECOFEL – Egmont Centre of FIU Excellence and Leadership
FAST – Fiscal Accountability, Sustainability and Transparency
FATF – Financial Action Task Force
FCDO – Foreign, Commonwealth and Development Office
FIU – Financial Intelligence Unit
GDI – Global Defence Index
GI – Global Index
GOSAC – Governance Open Societies and Anti-Corruption
HMG – Her Majesty’s Government
I-ACT – International Action Against Corruption
ICAR – International Centre for Asset Recovery
ICRG – International Cooperation Review Group
IFF – Illicit Financial Flows
IMF – International Monetary Fund
IRCG – International Cooperation Review Group
IWT – Illegal Wildlife Trade
JACU – Joint Anti-Corruption Unit
MLA – Monitoring and Learning Agent
ODA – Official Development Assistance
OGP – Open Government Partnership
OO – Open Ownership
PM – Programme Manager
SME – Small and Medium-Sized Enterprise
StAR – Stolen Assets Recovery Initiative
TI – Transparency International
TI-DS – Transparency International Defence and Security
ToC – Theory of Change
TTF – Thematic Trust Fund
TRAFFIC – The Wildlife Trade Monitoring Network
UKTI – UK Trade and Investment
UNGASS – United Nations General Assembly Special Session
UNODC – United Nations Office on Drugs and Crime
VfM – Value for Money

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

I-ACT, along with two other centrally managed programmes Mobilising Data for Anti-Corruption (MODAC) and Fiscal Accountability, Sustainability and Transparency (FAST), were designed to complement each other. The theory of change in the Business Case was therefore at a high level covering all three programmes and highlighting complementarities.

The Theory of change (ToC) was redesigned in November 2019 with the support of our Monitoring and Learning Agent (MLA) and comprised of three main changes:
The inclusion of overall impact and outcome statements in the ToC with the overall outcome statement separated into two distinct elements: reducing incentives and diminishing impunity.

The inclusion of 3 ‘intermediate outcomes’ to demonstrate the ‘missing middle’ between the programme outcomes and outputs.

The 5 outputs in the logframe have been broken down into nine separate results areas to show how individual I-ACT components contribute to these results areas.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The programme is on track to achieve its expected outcomes, “ to reduce incentives for corruption due to international partners working better together across borders and in country to close down opportunities to hide the proceeds of corruption and increase transparency and integrity, and diminish impunity due to stronger cross-border financial investigations and greater accountability for compliance with international standards and commitments”.

The outcome indicators for the programme for the review year include two indicators: (i) one new collaboration by I-ACT partners, which leads to changes in international standards, policies or actions (e.g.; G20, UN, OGP) and, (ii) at least 50 SMEs have requested services through the online platform (hosted by DIT) of the BII hub. The programme has met indicator 1 where Transparency International, worked closely with other stakeholders, to influence IMF to include anti-corruption measures for the COVID-19 relief financing provided to affected countries.

Indicator 2: was partially achieved, where 14 businesses have requested services through BII. This indicator is not appropriate as an outcome indicator for I-ACT as it relates to a new/untested feature of BII. BII is a relatively small component of I-ACT and its outcome indicator should not be one of the key indicators of I-ACT outcome.
While the outcome statement is in line with the revised TOC, the indicators do not appropriately frame or measure the outcome statement or results of I-ACT components. I-ACT, with the support of the MLA, is working to improve framing and quantifying I-ACT effectiveness based on the 3 outcome areas identified in the TOC to be included in the programme completion report.

This year, COVID-19 provided a test for IACT’s partners with major challenges to their operations, due to partner country governments prioritising health and emergency response and partners’ budgets significantly reduced. Practically, all found a way to continue to deliver and were able to respond to the changed context, for example producing analysis (U4), adjusting advocacy (TI) and developing new guidance (ECOFEL).

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Surges in corruption following COVID-19 have only made anti-corruption programming more vital. In 2020, we have seen how corruption can prevent vital health commodities reaching health centres, and how it can undermine trust in Governments just when it is most needed. IACT is playing a vital, although less celebrated role in the UK Government’s global response to COVID-19. The programme is delivering effectively as referenced in a quote by the MLA “the I-ACT programme has been overall effective in establishing or extending basic elements of anti-corruption architecture to detect, expose, investigate, seize and recover Illicit Financial Flows” and remains on course to deliver final outputs. The programme has adapted effectively to the COVID-19 context, and partners have shown great flexibility in coping with reduced funding. For these reasons, the programme should continue to its planned end date.

C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Opportunities for corruption are reduced due to less vulnerability to money-laundering, UK company compliance with the Bribery Act and stronger mitigation of corruption risk in defence and security institutions especially in Summit countries
Output number:		1	Output Score:	B
Impact weighting (%):		25	Weighting revised since last AR?	N
Indicator(s)		Milestone(s) for this review		Progress
1.1 Number of technical assistance missions in low and lower middle-income countries conducted through International Monetary Fund (IMF) thematic trust fund on AML/FT.		15 additional technical assistance missions in low and lower middle-income countries conducted through IMF trust fund on AML/CFT.		Target substantially exceeded - 66 technical assistance missions conducted. 178 missions conducted since the beginning of the programme against a target of 50.
1.2 There is a lack of consistency in approach to the provision of business integrity support from UK missions, and the quality of that guidance varies.		Availability of study confirming the results to date for BII including satisfaction by SMEs, effectiveness of pilots and effectiveness of the Hub.		Target met - Evidence has been collated from the BII’s three pilots and UK activities, with average business satisfaction scores ranging between 3.3/4 and 3.9/4
		A second batch of pilots is started taking on board lessons learned from study		Target not met - A second round of pilots was not started due to COVID-19 operational difficulties and budget cuts resulting from ODA reprioritisation.
1.3 Increased number of investigations for corruption offences, including money-laundering linked to wildlife crime both in origin states and third-party states through which linked illicit financial flows may have passed.		6 ongoing/completed investigations, including at least 2 cases including an asset forfeiture element.		Target substantially exceeded - 37 ongoing/completed, including at least 14 cases with an asset forfeiture element.
		Typologies report available, increasing understanding on the financial movements related to wildlife crime and the business models used by wildlife criminals.		Target not met - A Case Digest report has been developed and soon to be published.
		Publication on sanctions available, providing guidance on alternative sanctions.		Target not met - A sanctions tool has been developed and is currently being developed as an online resource.
		FIUs selected to be mentored to improve their production of financial intelligence related to wildlife crime number and quality)		Target met – Mentorship programme now has 15 mentees.
		One regional event bringing together private sector and FIUs, to increase the quantity and quality of reporting and trigger a more proactive approach with the private sector on financial information that may relate to IWT cases.		Target not met – Due to the COVID-19 travel and gathering restrictions, no regional events of this nature were able to take place, but partner has plans for this to happen in early 2021.
1.4 Governments are better able to identify and mitigate corruption risks in their defence and security institutions (TI Defence and Security) measured by quality and engagement on the GI and its findings TI regularly publishing in-depth assessments of defence sectors' vulnerabilities to corruption and recommendations to improve defence governance.		25 Global Defence Anti-Corruption Index assessments and recommendations published with FCDO support.		Target not met - 21 assessments and accompanying county profiles published taking the overall cumulative number of assessments to 37 against the overall target of 40 assessments.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Output moderately did not meet expectation and scored B

Indicator 1.1 tracks IMF’s demand driven AML technical assistance missions to lower income or lower-middle income countries. The missions help countries to improve both design and implementation of anti-money laundering standards. 66 technical assistance missions were conducted since the 2019 annual review, supporting more than 20 countries. IMF have estimated that they have conducted an average of 60 missions per year over the last 11 years so this is slightly above that average. These missions were mainly in person and the impact of COVID will likely be seen in the next review. This means the milestone was substantially exceeded this year, meeting end-of-programme targets ahead of time. Highlights from this work include the passage of new AML/Combating the Financing of Terrorism law in Angola; development of domestic non-banking financial institution regulations in Sudan; and support to the Financial Intelligence Units (FIUs) in Sri Lanka that contributed towards Sri Lanka’s exit from the Financial Action Task Force (FATF) Grey List. In addition to technical assistance missions, a new capacity development management and administration programme (CDMAP) was established. And work to publish handbooks on ‘Combating the Financing of Terrorism’ and ‘Best Practices in the Use of Beneficial Ownership Registers’ continued, with publication expected in 2021. Phase 2 of the Thematic Fund is ending in 2020.

Indicator 1.2 tracks the development of the Business Integrity Initiative (BII) that meets demands from the private sector for practical advice on securing new trade and investment deals overseas without bribery. The first milestone met expectation; the second milestone did not meet expectation. The BII is not on track to meet its end of programme target of 70 SMEs as the Hub only received 14 applications to its consultancy service. Lower than expected demand for the service was due to limited marketing. BII was not able to implement its marketing plans due to HMG communications embargos arising from Brexit negotiations, 2019 elections and COVID-19. Any future iteration of the business integrity initiative will aim for a simplified approach to marketing. BII is undertaking an in-depth assessment of future needs of businesses to inform BII’s approach, including marketing, to delivering tailored advice to SMEs. Despite the lack of marketing, the BII overall has reached at least 250 SMEs through UK services and three country pilots. Evidence has been collated from the BII’s three pilots and UK activities, with high satisfaction scores from SMEs. There is also some evidence to show that activities and services provided have positively changed firms’ behaviour and ability to implement integrity measures. A second round of country pilots was not started because of pressure on budgets due to ODA cuts this year.

Indicator 1.3 tracks illegal wildlife trade (IWT) work implemented by UNODC and ECOFEL. It aims to increase the number of investigations of corruption offences, including money-laundering linked to wildlife crime both in origin and third-party states. The milestone did not meet expectations but is on track to meet end of programme targets. UNODC has significantly exceeded the target of ongoing or completed investigations due to the work done by the two primary consultants and the long inception phase helped to spark significant interest by government authorities. UNODC developed practical guidelines for the investigation and prosecution of financial offences linked to wildlife crime, drafted a guidance note on IWT business models and work has been ongoing on publishing a case digest report in partnership with TRAFFIC and this is expected to be published late 2020. ECOFEL ran workshops to raise awareness of the FIUs and other relevant bodies in Mauritius (January 2020) and in Bangkok (March 2020). The latter included stakeholders from eight Asian countries, with representation from a broad range of stakeholders (including CITES, Interpol, UNODC, environmental and customs agencies). It focused on supporting coordination and identifying options authorities can use to link IWT with financial crimes.

Indicator 1.4 tracks Transparency International’s implementation of their Defence and Security (TI-DS) Programme, which seeks to ensure governments are better able to identify and mitigate corruption risks in their defence and security institutions. This is measured by quality and engagement on the Global Defence Anti-Corruption Index and its findings. The milestone did not meet expectation but is on track to meet end programme targets. TI-DS will have completed 37 assessments in 2020 and are on target to meet the 40 assessments end of programme requirements. Over the past six months there has been high levels of engagement from the defence companies under assessment and several companies have made improvements to their publicly available information as a direct result of engagement and assessment. In total, 58 companies provided responses, which reflects a 43% response rate, up from 32.5% in 2015. Challenges relating to this indicator have been linked to the global pandemic which has affected national researcher recruitment and delivery of assessments.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

The business case provided VfM measurements to be tracked over the programme implementation relating to comparison of fee rates of I-ACT partners with private sector providers contracted by FCDO under Expert Advisory Call Down Services (EACDS), management and overhead charges of partners and unit costs for delivery. There is no standard set of metrics across all implementing partners as they have different cost structures and delivery mechanisms. Some have more in-house overhead and technical assistance staffing, others subcontract consultants or fund long-term technical assistance overseas, and some produce evidence products and training.

Economy – The fee rates and subsistence for this output are comparable with other similar international organisations based on current available information. These will continue to be monitored across the programme to ensure VfM is achieved. Monitoring will continue to be on a partner-by-partner basis rather than a standard approach, but we will work to improve this monitoring as a recommendation from this review. BII daily fee rates are generally under the £775 threshold apart from specialist legal experts who charge a maximum of £1,000 per day.

Equity – IMF has increased research and operational work on income and gender inequalities and this important work continues. UNODC is committed to gender equality and has strived to mainstream gender considerations into project activities, such as by requesting lists of potential candidates for training events in the early planning stages and making gender one of the criteria for the selection of participants. UNODC has sought to improve women’s active participation and, where possible, effective leadership throughout the project’s implementation.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

This was the last year of FCDO funding the IMF’s Topical Trust Fund on AML/CTF (indicator 1.1). Phase 3, which begins in November 2020, will not be funded by FCDO.
The IWT project (indictor 1.3) has moved from an inception phase into a fully operational phase. There has been enhanced political will and media interest over the last year regarding the illegal wildlife trade. UNODC and ECOFEL, in partnership, have moved from an inception phase into implementation and this partnership is setting the building blocks for enhanced transparency and collaborations in this area of corruption that has historically been a low risk and high reward sector for criminals.
The global pandemic has led to a more digitalised approach across the output. We will continue engaging with partners to monitor the effect the pandemic is having on their work and if alterations are required to the targets or indicators.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The annual review 2019 was a shortened version with no new recommendations.

Recommendation: Review and revise the I-ACT logical framework for all components to reflect pivoting and adaption by the partner due to changes to the context, such as COVID-19 and ODA prioritisation.

Recommendation: Ensure partners report regularly on fee rates, to enable measurement of the agreed VfM metric, and on how they are addressing gender, and what that has achieved.

Output Title	Corruption is exposed and detected through improved company beneficial ownership transparency and stronger financial intelligence units especially in London Anti-Corruption Summit countries passing cases to domestic and international investigations
Output number:		2	Output Score:	A+
Impact weighting (%):		25	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1 Open national registers of company beneficial ownership are established and compatible with international Open Ownership (OO) Register; Number of entries on global register	An additional 500,000 entries on OO Register. 1 Open national register developed in 1 additional Summit or FCDO priority country and compatible with OO register.	Target substantially exceeded – This indicator has already substantially exceeded the entire programmes milestones with 6.8m companies on the register as of June 2020, and 7.6m beneficial owners identified across 14.2m records. Target met for one open national register developed in Ghana.
2.2 Capacity and evidence on company beneficial ownership	Enhanced UK and international technical assistance capacity in place	Target met – OO have scaled up their TA to countries implementing BOT and established regional posts to facilitate technical assistance has been provided to a number of countries including Armenia, Ghana, Liberia, Mexico, Nigeria, Ukraine and Zambia.
2.3 Improvements in capacity and international collaboration by FIU members of Egmont	ECOFEL support results in improved capacity and cases passed to investigators from 2 summit/FCDO priority countries	Target met – Cases passed to investigators from 2 summit /FCDO priority countries (Nigeria and Afghanistan).

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Output moderately exceeded expectation and scored A+

Indicator 2.1 tracks FCDO’s support to the OpenOwnership (OO) Register which aims to accelerate corporate transparency by making it simple to publish and access high-quality data about who owns companies on an open global register. The milestone on the number of companies on the global register has been exceeded. OO have also met the milestone on new open national registers and is on track to meet end of programme targets. In the reporting period, an open national public register has gone live in Ghana with support from OO, who have also input into the sectoral registers of Nigeria and Myanmar in collaboration with the Extractive Industries Transparency Initiative. The OO Team continues to work with countries to develop national open registers with data compatible with the OO global register.

Indicator 2.2 tracks FCDO’s work on building capacity and evidence on company beneficial ownership. The milestone on technical assistance was met and is on track to meet end of programme targets. Open Ownership have scaled up their technical assistance to countries implementing beneficial ownership transparency and increased their staffing to create a regional presence which has facilitated the increase in assistance to a wider range of countries. The UK Overseas Territories have been given access to Open Ownership training and guidance materials, as they move towards opening their national registers by 2023. These ranges of technical assistance have reinforced the HMG Campaign to work towards a global norm of beneficial ownership transparency.
Indicator 2.3 tracks FCDO’s support to the Egmont Centre Of Financial Intelligence Unit Excellence and Leadership (ECOFEL). ECOFEL strengthens the capacity of financial intelligence units in developing countries. The milestone met expectation and is on track to meet end of programme targets. ECOFEL has focused on in-country capacity building activities as well as regional activities to enhance collaboration between FIUs. Over the past year, the eLearning platform, which includes more than 16,000 training courses and best practise papers, has continued to grow with over 2600 registered users. It is available in 40 languages. The LinkedIn Learning catalogue is a key addition to their training material. Mentorship, secondment and regional capacity building programmes are progressing well. ECOFEL has run webinars on topics such as AML/CFT which have been well received. The COVID-19 pandemic has caused a variety of challenges, however ECOFEL has adapted well to new working environment realities, reprioritising some work, adjusting its workplan and in some cases moving its events to later dates. The switch to an entirely digital way of working has led to switching in person workshops to webinar style sessions which has increased participant attendance.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

The fee rates and subsistence for this output are comparable with other similar international organisations, an example of this is ECOFEL who use the National Joint Council of Canada subsistence rates. These will continue to be monitored across the programme to ensure VfM is achieved. EACDS rates do not apply to this output as there are no contracts.

Building a transparent global register of who owns companies around the world could deliver high returns in facilitating corruption investigations by law enforcement and by reducing the amount of illicit financial flows through shell companies. OpenOwnership has achieved results due to its high-quality technical assistance and strong partnerships with other stakeholders, such as the Open Government Partnership, Open Contracting and EITI. UK government actions, such as the leadership of the Prime Minister’s Anti-Corruption Champion, the campaign for a global norm of beneficial ownership transparency (BOT), the creation of a leadership group of countries committed to BOT, together with the advocacy of OpenOwnership, have helped maintain and drive international action to implement national beneficial ownership registers. The COVID-19 pandemic has also highlighted the importance of knowing who owns companies that win public procurement contracts, in order to avoid corruption and cronyism. OpenOwnership remains committed to addressing gender inequality both internally and externally. Research shows that women are disproportionately affected by all dimensions of inequality, including that caused by corruption, which their external work explicitly aims to stem. Internally, they are developing a gender and marginalized communities’ policy to govern their hiring and other key functions.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Due to the ODA prioritisation exercise, £1.95m was reduced from ECOFE’s budget due to underspending against forecasted budget. This led to 6 activities being postponed including the hiring of two consultants and an IT service provider. The global pandemic has led to remote working and use of digital technologies to deliver activities however, this has not affected the progress of this output. We will continue engaging with partners to monitor the effect the pandemic is having on their work and if alterations are required to the targets or indicators, these alterations will be made.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The annual review in 2019 was a shortened version, with no new recommendations. The global interest in beneficial ownership has continued to grow, particularly with the increased importance of knowing the true owners of companies for fast procurement in the COVID-19 pandemic. It is important to build on this momentum through opportunities in international fora, by influence on individual countries and by new COVID-19 related work in the sister programme, GACP.

On the ECOFEL FIU component, the attention and interest their eLearning platform has gathered over the last year, shows that there is definite demand for anti-corruption products. The potential of the FIUs to fight money laundering, terrorist financing and predicate offences such as corruption, human trafficking etc, is not yet fully exploited. While much has been done to establish FIUs globally, there are differences with regards to the role FIUs play in each country. In some countries, they are leading on AML/CFT and anti-corruption efforts. In others, they have not yet reached a minimum of operational, analytical or functional capacities. This has been identified as a key lesson and a learning aim for the coming year and this work in ongoing.

Output Title	Corrupt actors are held to account and victims are reimbursed through the tracing, recovery and return of stolen public assets
Output number:		3	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of ICAR supported cases in FCDO target countries completed leading to conviction and/or recovery with return of assets.	48% have taken 4 or more steps towards conviction above Milestone 2	Target moderately exceeded – ICAR worked on a total of 87 active cases in 10 jurisdictions. 47 out of the 87 cases (54%) made four steps or more towards conviction or confiscation. / Over £100m stolen assets recovered with ICAR’s support between 2017 and 2020.
3.2 Number of policy events influenced on asset recovery through developing the knowledge base.	At least 1 knowledge product produced to address identified knowledge gap /emerging trend on asset recovery / and used at least at 2 global leadership events on asset recovery. / Cumulative target 4 events and 2 products.	Target met – 2 products produced by StAR: Going for Broke, Enhancing Government Effectiveness and Transparency: The Fight Against Corruption. / StAR held a day of workshops at the UN COSP and participated in 23 national level events.
3.3 Number of countries assisted by StAR have increased capacity to recover stolen assets.	3 additional countries improving legislative framework on asset recovery. / 3 additional asset recovery cases opened that include a proceeds of corruption component. / 2 additional countries with improved domestic co-ordination mechanisms adopted as asset recovery action plan / Cumulative target 16 countries cumulative assisted by StAR have increased capacity to recover stolen assets.	Target met – Countries improving asset recovery legislative frameworks 2 (Ukraine, Armenia) and ongoing process: 10 countries. / Asset recovery cases opened that include proceeds of corruption component: 4. / Countries improved domestic co-ordination mechanisms: 2 countries (Ecuador, Ethiopia) and ongoing process: 6 countries. / Cumulative total is 19 countries assisted by StAR, with 16 ongoing.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Output met expectation and scored A

Indicator 3.1 measures support to developing country institutions to prevent and detect laundering of the proceeds of corruption and to recover stolen public assets. The milestone moderately exceeded expectations and is on track to meet end of programme targets. There has been good progress in strengthening partner countries’ capacities to tackle grand corruption through training and mentoring programmes. ICAR’s own system to track cases is now much more robust as they have developed and launched a ‘Key Progress Chart’ which measures progress by steps taken towards conviction and asset recovery, rather than the end result which can take years. Between 2017 and 2020, ICAR have supported partner countries to recover over $100m in stolen assets.

Indicator 3.2 tracks the number of policy events influenced on asset recovery through developing a knowledge base to address identified knowledge gaps /emerging trends on asset recovery which are used at global leadership events on asset recovery. The milestone met expectations and overall programme targets. StAR’s reputation has been built on high quality knowledge products and they have been refocusing on this area. Both ICAR and StAR host and participate in global events on asset recovery and return. StAR hosted an event at the 8th Conference of the States Parties to UNCAC (CoSP) in December 2019, a full day of panel discussions on asset recovery. They made contributions on asset recovery policy issues in 23 national level events.

Indicator 3.3 tracks the number of countries who have been assisted by WB STAR in their efforts to increase the countries capacity to recover stolen assets. The milestone was met and on track to meet end of programme targets. Although some of the 2020 milestones were missed, the overall programme target has now been exceeded by 3 countries with 16 countries work ongoing.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

The fee rates and subsistence for this output are comparable with other international organisations, and these will continue to be monitored across the programme to ensure VfM is achieved. Monitoring will continue to be on a partner-by-partner basis rather than a standard approach, but as referenced in this report, work is needed to obtain up to date information on fee rates currently being used.

This output is one of the programme’s greatest VfM as between 2017-2020, ICAR helped in the recovery of $100m stolen assets. FCDO funding compared to the value of recovered assets, is very small whereas the value of assets returned to developing countries exceeds the entire contribution of I-ACT.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There have been no significant changes to this output in the past year. The global pandemic has led to adapting to working remotely and leveraging more digital technologies, however this has not affected the progress of this output which continues to perform exceptionally well. We will continue engaging with partners to monitor the effect the pandemic is having on their work and if alterations are required to the targets or indicators to enable achieving intended outcome and impact of I-ACT.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The work of ICAR and StAR provides capacity building through training, legislative and systems reform, and support on asset recovery cases. This combination of skill-building and practical case support is fundamental to fighting corruption. Both ICAR and STAR have adapted their work in the context of the Covid-19 pandemic and this needs to be reflected in the log-frame and future planning.

Output Title	IACT partners work effectively together internationally and in FCDO priority countries to close routes for corruption
Output number:		4	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1 Governments in Summit countries are held to account internationally and in country for delivering Summit commitments (TI-UK)	2 additional national Summit pledge trackers (8 in total) operational; National advocacy strategies implemented by TI chapters and partner organisations in 1 additional partner (5 in total and at least 2 FCDO ) countries; 1 additional governments (3 in total) have advanced their commitments on BOT, Asset Recovery and law enforcement, up at least one category since previous year	Target met – 8 Summit pledge trackers are operational in Afghanistan, Ghana, Kenya, UK, Jordan, Mexico, Nigeria and Sri Lanka. / Target Met – Advocacy strategies developed in 5 countries (Afghanistan, Sri Lanka, Jordan, South Africa, and UK). / Target exceeded by 1 – 4 additional country meeting commitment on beneficial ownership (Afghanistan, Ukraine, Mexico and Kenya). / Target Met – 3 additional country meeting commitment on asset recovery (Nigeria, Ghana and Jordan)

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Output met expectation and scored A

Indicator 4.1 measures progress in Summit/priority countries in meeting their commitments to develop better structures, processes and systems to tackle corruption. The milestones were met, and the component is on track to meet end of programme targets. Globally, the pledge tracker update in May 2020 reviewed 181 commitments from 20 countries, finding that 75.7% are ‘in play’ (defined as having seen progress in the last six months) while 24.3% were showing no progress. In terms of individual countries, Afghanistan started tracking new commitments, adding more commitments to the pledge tracker. Jordan made especially good progress on delivery - thanks to the cooperation between Rasheed (Transparency International Jordan) and the Jordanian Integrity and Anti-Corruption Commission, 8 out 11 commitments showed progress.

COVID-19 has been a challenge for the project, with several in-person activities stopped. However, TI-UK, in collaboration with TI-S and TI France, hosted an asset recovery event online to agree the international position and advocacy strategy on Victims Compensation. The partner also led a session on the impact of pledge tracking at the 2020 Civic Technology Conference (TICTeC).

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

TI Summit tracker is a well-run programme, with high-level events on a relatively small overall budget of approximately £1.3m. We have ensured that fee rates have not exceeded centrally agreed FCDO daily rates of £775.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There have been no significant changes to this output in the past year. The global pandemic has led to a more digitalised approach; however, this has not affected TI’s ability to monitor implementation of commitments through the tracker.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The annual review 2019 was a shortened version with no new recommendations. With a United Nations Special Session on Anti-Corruption planned for 2021, there is scope for the many lessons learned by TI’s overall ‘Promise to Practice’ programme to be shared and applied in the run-up to and wake of that conference.

Output Title	Evidence and lessons on how to reduce corruption are systematically collated, incorporated into the programme and used to evidence further UK and international action
Output number:		5	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
5.2 IACT partners' international collaboration to share lessons	MEL partner in place coordinating systematic lesson-sharing; U4 recording and disseminating lessons. / 2 learning events held for IACT partners to share lessons and form synergies (U4 recording and disseminating lessons).	Target Met – MLA and MEL partners has been contracted and is meeting all milestone expectations. / Target met – 2 learning events held, one in November 19 and one in June 20 (virtually).
5.3 Visits and repeat visits to U4 website and number of helpdesk responses	Visits: 105,000 visits / Repeat visits: 28% of visitors make repeat visits / Number of helpdesk responses: 20	Target substantially exceeded - 332,713 Visitors to the website. Target not met - 11.4% returning visitors same period. / Target substantially exceeded - 31 helpdesk responses.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Output met expectation and scored A

Indicator 5.2 captures the use of lesson learning and evidence in furthering UK and international action on corruption. The milestone met expectation and is on track to meet end of programme targets. We have two learning agents on the programme - the MEL agent has been contracted and the target of 2 learning days was met. The team also selected an MLA evaluation contractor for the programme who carries out routine monitoring of programme activities. They have engaged with the I-ACT partners and reviewed partner reports. They have produced several informative reports including a mid-term report which assessed the progress of I-ACT partners, as well as provided a think piece on broader findings of what is working and what is not. The first draft of a formative case study which assessed how relevant I-ACT (and FAST) has been to the political contexts of the countries it works in and how useful it has been in complementing country strategies on corruption, has been important work in guiding the current I-ACT programme.

Indicator 5.3 captures U4’s work for reducing the harmful impact of corruption on sustainable and inclusive development by providing development practitioners with anti-corruption knowledge and tools to design and implement their programmes in a more informed manner. The milestone exceeded expectation and is on track to exceed end of programme targets. Although the number of returning visitors milestone was not met, the number of visitors and helpdesk responses substantially exceeded expectations. Over the last year, U4 have published 13 COVID-19 related publications and blogs and their ’Anti-Corruption Essentials’ course has seen over 100 individual registrations. U4 responded rapidly to the increase in corruption risk after the spread of COVID-19, publishing high quality analysis and convening international donors to support their policy responses.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

We have ensured that fee rates have not exceeded centrally agreed FCDO rates, for example the highest daily fee rate applied to our MLA agent is £763 which is less than the maximum EACDS framework rate of £775. U4 have recently brought more work in-house, rather than out-sourcing to reduce costs. The two learning days held by our MLA agent has improved collaborations across the programme as partners were able to share information and exchange contact details. An example of this was ECOFEL providing an overview of their eLearning platform to BII Kenya. Gender equality was an important factor during the procurement of the MLA and the partner has an equal staffing split of male and female colleagues. U4‘s work on gender and corruption (see link here) continues to add to the global knowledge base on this subject.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There have been no significant changes to either output in the past year and no further alterations will currently be required to the logframe. We have ongoing conversations with the MLA regarding the quality of work they are producing and are working with them on a national clusters idea which will look at collaborations between I-ACT partners in a particular country. Both partners are used to digitalised working so the global pandemic has not significantly affected their delivery of the programme targets. We will continue engaging with partners to monitor the effect the pandemic is having on their work and if alterations are required to the targets or indicators, these alterations will be made.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The annual review 2019 was a shortened version with no new recommendations.

The MLA report stated “U4’s collective funding model continues to be efficient for FCDO and other contributing donors”. Their rapid analysis of the implications of COVID-19 on corruption was high quality and meant each of the 9 funding donors (plus countless other international organisations accessing the website) could rely on that analysis instead of each producing their own.
With the merger of DFID and FCO, U4’s services are now increasingly being offered to a wider range of UK Government staff in-country.
The influence of U4 on donors:
- Artificial Intelligence and anti-corruption. A U4 paper widely circulated among U4 Donors and used by Swedish SIDA for an interagency discussion on how they should respond to recommendations.
- Testing of “firedrill” for corruption cases. The OECD/DAC Anti-Corruption Task Force (ACTT) has over the last year developed a “firedrill” for donors to cooperate on handling larger corruption cases. U4 tested this out with donor agencies and field practitioners during two workshops, one in Uganda on donor coordination and one in Kenya on corruption risk management. The feedback from these sessions is helping to improve practice on this topic.

Recommendation: U4 should continue improving the marketing of key services to enhance take-up by partners and wider community of anti-corruption practitioners.

D: RISK [½ to 1 page]

Overview of risk management [1/2 page]

IACT has a high appetite for external context risk as we work in the most challenging environments to end corruption. This is complimented by our low-risk appetite for fiduciary, operational, reputational, safeguarding and delivery risks, which are managed through our active engagement with programme partnerships, and adherence to FCDO Smart rules. The programmes overall risk rating is Moderate.

There are 6 risk areas captured in the programmes risk register, with updates in the past year captured below.
Context: A risk has been added relating to the Business Integrity Initiative (BII) and future funding. This has been mitigated by plans relating to the spending review bids from both FCDO and the Department for International Trade. Two risks relating to BII have been removed as they related to the pilot phase which has now ended.

Delivery: A risk has been added relating to the ODA prioritisation budget cuts and partners who are reliant on UK funding. This has been mitigated by advising partners to seek out new donors and other sources of funding to ensure the future of their work is sustainable. Two delivery risks relating to BII pilot phase have been removed as the phase is now completed.

Safeguarding: There have been one safeguarding case raised over the past year relating to an I-ACT partner. The case is currently ongoing, with our internal audit department leading on this. We have added a COVID-related safeguarding risk relating to partners’ staff and their mental and physical health. This has been mitigated by a ban on non-essential travel, regular updates between partners and FCDO and regular check-in between partners and their staff to check on their wellbeing.

Operational: A COVID 19 related risk was added regarding the successful delivery of work during the pandemic as there is a possibility of staff contracting the virus and/or having to self-isolate. This has been mitigated by ensuring partners have plans for prioritising essential work/deliverables, keeping in touch regularly with staff, highlighting issues with the FCDO programme team and reviewing the FCDO supplier guidance on the pandemic. A risk relating to the business integrity initiative was added regarding staffing changes and potential funding issues which have been mitigated by regular contact, exploring future funding opportunities and working on a sustainability plan. A risk relating to the BII pilot phase has been removed as the phase has now ended.

Fiduciary: A risk regrading paying into trust funds has been removed as the funding phase to the relevant partner has ended.

Reputational: No new reputational risks have been added over the past year.

Due to these extensive mitigation measures, we have remained within our existing risk appetites across all six areas.

The Partnership Principles Assessment is not relevant here because all partners are international organisations and there are no direct partnerships with sovereign governments, or the transfer of funds to them under this programme.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency. [max 1 page]

By the beginning of October 2020, the programme has spent approximately £22.4m of its total approved budget of £32,4m which represents a 69.3% spend to date. Since the last annual review, spend has been £7,007,590 - reduced from £7,670,882. The difference relates to the ODA prioritisation budget cuts in 20/21, with the reminder of the £3.25m coming out of the budget for the remainder of this financial year.

The programme team, guided by the Senior Responsible Officer, are working with partners to improve the quality of reporting by organisations funded through IACT, including on areas such as risk, delivery chain mapping and results. Financial forecasting updates are made effectively and efficiently. The recent ODA prioritisation exercise increased the regularity of these partner conversations on finances and updates were made for the remainder of the 20/21 financial year and work has started on potential budgetary requirements for the 21/22 financial year.

Due to the global COVID pandemic, there have been no partner visits possible over the past year and all meetings have been held virtually. As referenced in the risk section of this report, risk conversations with partners are regular and reports include a section on risks and how they have been mitigated. The programme has carried out due diligence of all partners and recommendations have been agreed with them. The team monitors follow up actions using a traffic lights system on the delivery plan. Each funding agreement has a separate audit mechanism in place. There are currently no FCDO assets held by the partners funded through the I-ACT programme. If this changes, these assets will be recorded on an asset register, managed and tracked according to guideline expectations.

Reflecting on the business case and prior annual reviews VfM metrics, all fee rates, management and overhead charges from partners are regularly checked during our rigorous invoice checking procedure and are in line with similar international organisations to ensure unit costs for delivery represent good VfM. The limited number of contracts in this programme are conducted under the Expert Advisory Call Down Services (EACDS) guidelines. As referenced in this report, work is needed to ensure that more information on fee rates across the programme is obtained by the programme team. The partners have adapted well to the ongoing pandemic and we have seen savings made on travel and subsistence costs across the programme due to increased remote working.

Date of last narrative financial report	Last narrative and financial report by ECOFEL (3/11/20) and UNODC (9/11/20). / For some components, reports are sent monthly and for others they are sent quarterly. Finance data is sent as part of the payment authorisation process.	Date of last audited annual statement	U4: 16/10/2020 / ECOFEL16/10/2020 / UNODC:01/08/2020 / OO: 24/06/2020 / TI: 16/06/2020 / ICAR: 13/05/2020 / STAR: 05/02/2020