## Annual Review -2020

Title: Improving Reproductive Maternal and Child Health (RMNCAH) outcomes in Mozambique
Programme Value £ (full life): £ 39.85 million		Review date: November 2020
Programme Code: 205074	AMP start date: November 2016	AMP end date: November 2021

Summary of Programme Performance
Year	2017	2018	2019	2020
Overall Output Score	A	A	A	A
Risk Rating	Medium	Medium	Medium

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4833405.odt
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Description of programme

Despite progress in improving child health, the Maternal Mortality Ratio (MMR) in Mozambique has remained high and unchanged over the last decade, with a rate of 452 per 100,000 live births. The average age of women who die due to maternal-related causes is 27, while 20% of maternal deaths are below age 20.  The Infant Mortality Rate (IMR) is 67.3 per 1,000 live births (census 2017). These statistics reflect the high number of early pregnancies, as well as the broader service delivery challenges faced by the health system to address both the amount of services the patients want to use (demand) and provision of health services (supply).

Since September 2016, FCDO has been implementing a programme to improve Reproductive, Maternal, Neonatal, Child and Adolescent Health (RMNCAH) outcomes in Mozambique by tackling key health system constraints. This programme, worth £39.85 million, aims to contribute to reducing maternal mortality in Mozambique. It strongly aligns with the National Health Policy which has prioritised maternal and child health by formally approving the RMNCAH Investment Case, a five-year (2018-2022) Government Plan. It is the result of close consultation and collaboration between the Government of Mozambique (GoM) and partners. It is implemented throughout the country, using various mechanisms, including this programme, but also the health Common Fund (which includes donors such as the UN, Flanders, Italy and Switzerland) and the World Bank (WB)’s Primary Health Care Strengthening Programme (PHCSP) financed through the World Bank’s Multi-Donor Trust Fund (MDTF) via the Global Financing Facility (GFF) Platform.

This programme is delivered through the following components:

Component 1 is channelled through the UN Joint Programme (UNJP, made up of WHO, UNICEF and UNFPA) to support the RMNCAH Investment Case through provision of health services and technical assistance, which aim to prepare health facilities to provide a minimum level of basic obstetric and neonatal care. Interventions range from procuring commodities and equipment to supporting policy reforms, training health workers and delivering water, hygiene and sanitation (WASH) in health care facilities. The UN is well placed to partner with GoM to build their capacity to plan, provide technical support and prioritise interventions' at national and subnational level. This component ran from 2016 to 2019 (£23.5m) and has a costed extension of an additional £1.2 million until March 2021.

Component 2 (£5.5m) is a consortium led by Population Services International (PSI), including local organisations Nweti, Tuya, ThinkWell and Coalizão, to pilot approaches to increase family planning (FP) uptake among adolescents. This is achieved through interventions that stimulate demand for family planning services and goods from adolescent girls and young woman in their communities, working closely with community health promoters in rural areas and schools in Maputo, Gaza and Nampula provinces. This component will close in February 2021, as planned.

Component 3 was delivered by the WHO (£2.1m) and supported the Ministry of Health (MoH) to prepare for and respond to emergencies. This component provided technical assistance on climate- and disease-related disasters, which regularly disrupt health service delivery. This component allowed the MoH to respond to a polio outbreak in 2019, enabled three rounds of emergency oral vaccination campaigns in Zambezia, and provided the platform for the UK to be one of the first partners to support the response to COVID-19 (C-19) in March 2020. This component closed in March 2020.

Component 4 supports the Rapariga Biz (Busy Girl in Portuguese) programme from June 2018 – December 2019 (£2.9m), together with Sweden and Canada. This programme aims to prevent early marriage and pregnancies among adolescent girls and young women, working with five government ministries and with technical support from five UN agencies. The UK supported new components such as engaging boys and young men, greater inclusion of disability and an independent review in April 2019. Considering delays caused by the cyclone in central and northern Mozambique and the national elections in October 2019, a three month no cost extension was approved until March 2020, when UK support to the programme ended.

Component 5 is funding for technical assistance to provide research (£0.4m). This included consultancies (i) for the MoH to design a strategy for the attraction and retention of personnel in 2018 and (ii) to provide financial technical assistance to the Global Fund Unit of the MoH in 2019. This component also covered costs of the independent review of the UN Joint Programme that took place from October to December 2019 and an FCDO Demography Adviser from July 2019.

Component 6 is delivered through Village Reach (£0.3m), originally from October 2019 to September 2020, to test the use of Unmanned Aerial Vehicles (UAVs) to transport tuberculosis (TB) sputum samples. In close collaboration with the National Institute of Health, the pilot aims to improve the detection rate of TB cases which, at 38%, is one of the lowest in the world, due in part to difficulties in transporting samples to laboratories for testing. Frontier Technology Livestreaming (FTL) initially supported the pilot until October 2019, when the FCDO began support bilaterally. This component was added at the end of 2019 to to provide useful research for BHC Maputo's health programme, GFATM and other UK Aid investments in Mozambique, supporting the Global Fund to fight AIDS, TB and Malaria (GFATM) and other ODA-funded UK investments. GFATM had also indicated an interest in the research findings as an option to transport samples and medicines. Due to C-19, this component has been extended with no additional cost to March 2021.

Component 7: From July 2020, the UK is investing £2.5m in supporting the RMNCAH investment case with the Global Financing Facility (GFF) Platform (See above and below). The UK Government has contributed £2.5m to the GFF to support the RMNCAH investment case and maintain critical health services during the C-19 crisis.

This annual review covers progress over the period from November 2019 to October 2020.

Summary supporting narrative for the overall score in this review

The programme scored an A, highlighting good overall progress on the main components despite a challenging year with elections where the decision makers were not engaging as before in the sector, C-19 leading to limited access and disrupted health services, and conflict in the north slowing the pace of implementation, and delays in achieving milestones on two outputs. Out of five outputs, one output exceeded expectations (Output1); two outputs were met (Output 3 PSI/Rapariga Biz, Output 4 WHO/C-19 response). Output 2 moderately did not meet expectations, and output 5 did not meet expectations. The weighting of the outputs appropriately reflects the funding and relative importance of the intended and achieved results.

All components faced some delays due to contextual changes. Despite this, partners have been very resilient and responsive in proposing solutions to these changes as well as delivering the programme.

The main contextual changes include:

The national election in October 2019: Senior government officials were engaged in the pre-election campaign, slowing the implementation of the programme. A new government, including a new Minister of Health, was nominated in January 2020. The implementation of the new decentralisation process took several months at provincial level and has led to significant re-organisation of service delivery structures. These factors slowed down the decision-making process and the disbursement of funds to the local levels of the health system from January 2020 until now, and reduced opportunities for dialogue between partners and the government.

The C-19 pandemic had no precedent in the world and led to tremendous direct and indirect negative effects on the implementation of health programmes and basic health services in Mozambique. Due to fears of attending health facilities, the lack of personal protective equipment (PPE) for staff, and restrictions on movements following the State of Emergency measures (March–July 2020), patients had no access to non-essential health services from March to May 2020, outreach services including vaccinations stopped and in August 2020 at least 12% of health workers were reported to be infected with C-19. Cholera and measles outbreaks in the northern provinces are further indications that routine service delivery is failing.

The conflict in central and northern Mozambique has impaired partners’ activities due to rapid escalation of violence in 2020 and the need to adapt implementation methods. Routine service delivery has been delayed or stopped in the inaccessible areas and are under strain in districts and towns accommodating an estimated 400,000 Internally Displaced People (IDPs). FCDO already funds humanitarian support to IDPs, including improving C-19 isolation and treatment facilities, through other programmes.

Major lessons and recommendations for the year ahead

Adaptation to the C-19 Pandemic (by November 2021): A major lesson was the importance of flexible partnership agreements which allowed all partners to successfully adapt their programmes to the pandemic. The UN and PSI were able to immediately pivot programming to respond to the new context. WHO were able to re-programme funds to purchase PCR machines and thermal scanners before the programme phased out. Others like Village Reach had to delay activities from March to October 2020. The recommendation, as a result of the cyclone in 2019 and now the pandemic, is therefore to design future programmes so that they can adjust to a rapidly changing context. There should be scope for funds to be flexible and, on the basis of good value for money, be reallocated for emergencies through a contingency plan. Programmes could potentially include an emergency component to respond to unforeseen events.

Emergency response for the province of Cabo Delgado (by November 2021): The rapidly evolving violent insurgency in the northern provinces is increasingly demonstrating the need for development programmes to adapt and transition between development and humanitarian response more rapidly and with agility. There is a critical need to work with partners who have experience of conflict-affected areas in order to have a conflict lens in health and maintain critical services in hard-to-reach places. FCDO and partners will need to continue building an in-depth understanding of the drivers of the conflict and the political economy of the health sector and health interventions in Cabo Delgado to better adapt future programming to respond to insecurity but also make sure our interventions can seek to help build stability. Moreover, FCDO will continue to ‘work politically’, mobilising diplomatic and development expertise to enable a holistic response to the issues and evolving context.

Sustainability of the programme (to inform future programmes, 2021): Progress against outputs has been made (training the health workers and, the community health workers (CHWs), provision of equipment and service delivery to help mothers to deliver their babies), but deeper health system reforms have not followed. This is likely due to a combination of the fiscal crisis (2016 and onwards), the impact of two cyclones, and C-19 and the conflict in the north, and elections. The context has distracted the MoH from focusing and financing more systemic reforms. This changes the time frame over which the depth and breadth of reforms are feasible and suggests the need to continue a dual approach, with support to the delivery of services, whilst incentivising system changes. Investments in reforms agenda and in human resources, as well as new approaches such as the mentoring of the maternal and child health (MCH) nurses using professional associations, are already under way and will remain beyond the lifetime of the programme. The latter, for example, is now being supported by the US Government in Sofala. Over the next few years, the majority of service delivery and reform activities will continue through the WB’s PHCSP, which the UK hopes to support through a new demographic transition programme.

Sharing lessons learnt for future interventions (by end November 2021): The UK and programme partners will engage with the MoH and other partners to ensure that successes of and lessons learnt from the programme are shared and embedded more permanently and that interventions resulting from this programme continue to be implemented. A discussion about the UNJP’s achievements and how to continue with interventions has been planned for the Coordination Committee where partners meet with National Directors in November 2020. PSI and Rapariga Biz both documented lessons from implementation which will be shared with partners and inform future programmes. The WHO Regional Office as well as Switzerland with $1 million will continue to support the emergency response in health through WHO. It is also important to note that it will be important for programmes to build and use government structures in order to optimize interventions and measures realistic impact.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

There have been no changes to the outcome and impact indicators since the beginning of the programme. Most of the programme’s activities were in an advanced stage of implementation when the C-19 pandemic struck. There has been some reprogramming to respond and an additional indicator to measure the response from the UNJP programme. As this reprogramming happened in June 2020, it is too early to tell whether this will have an impact on the achievement of outcome indicators but implementing partners have tried to maintain service continuity despite C-19.

Does the theory of change hold and will the longer-term outcome be met?

The programme’s theory of change was built on the outcome of strengthening the responsiveness of health systems in Mozambique in relation to reproductive, maternal and child health. This was to be achieved through five outputs: equipping health facilities, responding to emergencies and disease outbreaks, enabling communities and health facilities to support reproductive and maternal health, delivering quality services and coordinating with other interventions in the sector. The programme’s theory of change remains relevant even though the programme delivered against a rapidly changing external context with the response to the C-19 pandemic since March 2020. For example, as part of the C-19 measures, schools closed down and PSI had to look for other places where they could reach adolescents such as markets, water points and bakeries. It also became challenging to visit the community and promote family planning, so the PSI team used social media and IT technologies (Zoom, SMS, WhatsApp) to reach out to beneficiaries and organised mobile brigades. Many of the UNJP’s planned activities were delayed because of the measures put in place to respond to C-19, yet as the programme was mostly on track, activities will resume and reach milestones as soon as C-19 restrictions are lifted.

The concept of health strengthening includes six components: governance/leadership, service delivery, health workforce, health information system, medical products, vaccines and technologies and health system financing. The programme succeeded in strengthening service delivery, drafting of reforms, and policy documents on strengthening HR and the health information system. The components of governance/leadership and health financing, however, depend on the commitment/willingness of the government to have a long-term vision. These are external factors that this programme cannot easily control. There would need to be significant progress in health sector financing and implementation of health sector reforms, in particular in state funding for positions and salaries for health workers, in order to be able to affirm that the capacity and resilience of the health system has durably improved, eventually reaching the health strengthening objective of the programme. The theory of change conceptualises health system strengthening but it remains complex to fully measure improvements and changes to the health system.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Will the outcomes directly related to the outputs of the programme be met?

The outcome of the programme, which is to “allow more people to equitably access and use quality health services” is likely to be achieved by March 2021.The outcome indicators are currently slightly off track, mostly due to the context constraints. But it is likely that these will be met by the end of the programme. The number of new users of contraceptives increased by 36% on average in 2019, reaching 80,978 new users. This equates to 81% of the target number for 2020 of new users from the UK’s contribution, consistent with the government’s target of 84% reached through the state budget. C-19 has also decreased new users in the first eight months of 2020 relative to the same period last year. 63% of health facilities have been accredited to deliver comprehensive emergency obstetric and new-born care against a target of 70%, but this indicator is likely to be met by the end of the programme as all the neonatal kits have been delivered, the planned number of nurses have been trained, and WASH facilities in health centres are on track to be completed.

The programme has successfully compensated for the lack of funding in the state budget and activities to support RMNCAH during a difficult financial and contextual period, starting in 2016. Some of the long-term outcomes and system changes have materialised with some reform and policy documents being submitted for approval by the GoM. Investments in the reform agenda and in human resources, as well as new approaches such as the mentoring of MCH nurses using professional local associations (as stated above), will remain beyond the lifetime of the programme. The programme has benefited women and children in a very concrete way and contributed to the country’s response to an unprecedented pandemic.

Despite the challenges outlined in the summary, implementing partners have successfully adapted to the changing context, pivoted activities and made progress. In the year ahead, the programme will focus on wrapping up interventions in order to close activities. This will include drawing lessons from implementation and establishing links with partners who can continue implementation. It is important to work on the exit strategy and advocate for the components of the programme to be taken over by other partners or become part of the national health policy. In order to guarantee programme sustainability and ownership, each output has an exit strategy in place. The interventions currently under the UNJP component will continue to be supported through the GFF. The GFF has designed different governance tools for ensuring sustainability (these are waiting approval from the government) and has developed a results-based payment mechanism to incentivise health system changes. The WB, through the GFF, will continue their technical support role for the community health workers. The WHO preparedness emergency programme will continue especially in the light on C-19 and the alarming humanitarian situation in Cabo Delgado. WHO is expected to coordinate the health cluster in the north of the country but also to continue the preparedness and response to outbreaks. It is important to continue to advocate for Mozambique to be reclassified with a priority of 2 in the humanitarian mechanism to enable WHO Mozambique to improve health emergency preparedness (Mozambique is currently priority 3). These classifications take into account the capacity, vulnerability and nature of emergencies a country is faced with and determine the staffing levels and structures in-country.

C-19 is likely to reinforce existing inequalities for women and girls and discrimination of other marginalised groups such as persons with disabilities and those in extreme poverty. The reprogramming of UNJP to respond to the C-19 context will closely follow and address the needs of these vulnerable groups.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme has been extended to March 2021 to enable the conclusion of: (i) interventions that were delayed as a result of C-19; (ii) support for the C-19 response; and (iii) support to areas affected by the conflict in northern Mozambique. The RMNCAH programme has scored an A since the beginning of its implementation.

This year there has been mixed performance across the outputs mainly due to the impact of the election, instability in the northern regions of the country, delays in government service delivery and more recently C-19 restrictions to movements and measures to reduce risk of transmission. However, the programme remains on track to deliver most outputs, and it is expected that those off-track components will deliver by March 2021.

Mozambique remains one of the countries with the highest maternal and child mortality rates, due to lack of infrastructure, access and skilled personnel, poor governance and lack of education and awareness. The RMNCAH programme tackled different angles of this problem with the general outcome to get health facilities ready and functional to deliver maternal, neonatal and children care. The RMNCAH programme is in its final year of implementation and has made significant progress towards a stronger health system for mothers and children. The magnitude of the impact of C-19 on the general healthcare of Mozambicans is not yet known, but the programme has already contributed to the efforts to mitigate the effects of C-19 on sexual, reproductive and child health. This programme will end in March 2021 and will concentrate on exit strategies to ensure sustainability of impact beyond the programme closure.

Finally, this programme provides a segue into the UK’s planned new demography programme tackling the factors driving poor youth development and opportunities, including early marriage and pregnancy. Learning from this programme and the experience of partners such as PSI or Rapariga biz will be very relevant to this next programme.

## C. DETAILED OUTPUT SCORING

Output Title	Enhanced availability and quality of trained midwifery workforce and improved facility readiness at national level by 2020 (UN Joint Programme)
Output number per LF		1	Output Score	A
Impact weighting (%):		40%	Impact weighting % revised since last AR?	Yes ↑

Indicator(s)	Milestone	Progress
1.1 Number of maternal and child health (MCH) nurses available in health facilities	320 additional nurses	Moderately Exceeded: Out of 320 MCH nurses initially targeted in the programme design, 344 students graduated by July 2020
1.2 Number of health facilities equipped with: / (i) ambulances, and / (ii) emergency obstetric and neonatal care (EmONC) kits, including safe abortion care and life-saving commodities	(i) 51 / (ii) 41	Moderately Exceeded: / (i) 53 ambulances (52 vehicles and one boat ambulance) / (ii) 41 kits received and handed over to MISAU

Briefly describe the output’s activities and provide supporting narrative for the score.

1.1 Moderately exceeded expectations. The programme has moderately exceeded this target with 344 students graduated by July 2020, against the initial target of 320 MCH nurses to be trained with UK funds. This contributed to the general increase of the numbers of Maternal and child health nurses in country: from 5,820 in 2017 to 6,175 in 2019 (all source of funding for training considered). UNFPA also supported strengthening training institutions’ capacity on the use of anatomical models for improved practice by MCH nurses. Mentorship initiatives have been developed with local professional organisations of obstetricians and gynaecologists (APARMO) to reinforce the sustainability of the training. Mentoring visits by APARMO to health facilities were conducted twice a week to ensure good practice amongst the newly graduated nurses. The implementation of this activity also faced challenges, including the complexity of the IT equipment and the mannequins/anatomic models, but also lack of availability of students at the beginning that slowed the start of the training.

The intention at the outset of the programme was that MoH would need to increase their capacity to formalize positions for the personnel within the health establishment at the same time as new nurses are trained. Unfortunately, not all MCH nurses are immediately absorbed into the system, with some waiting up to a year to be placed in a health centre. Dialogue between the Ministries of Health, State Administration and Economy and Finance are ongoing to ensure MCH nurses can be deployed more rapidly in the healthcare system.

1.2 Moderately exceeded expectations: This output had already been reached in the last annual review. UNFPA has successfully procured 53 ambulances throughout the country, which are being used to help pregnant women or new-borns with complications in district health centres to reach district hospitals where they can get specialised care. During various field visits the Programme Team saw the ambulances functioning at district capitals and rural hospitals. In order to deliver medicines and basic services to vulnerable women, girls and children in remote areas affected by Cyclone Kenneth last year and the current conflict in Cabo Delgado, a boat has been procured and delivered for the community in Ibo and surrounding islands off the coast of Cabo Delgado.

At the request of the Minister of Health, UNFPA has started the procurement of a larger ambulance boat that will allow for the transport of emergency patients from Ibo Island to Pemba. This is part of a package of services that will include an operating theatre for Ibo district, that will be delivered during the second half of 2020. The ambulance boat will serve as a referral vehicle for pregnant women requiring emergency obstetric and newborn care (EmONC) services and services that are more complex; while the operating theatre will offer EmONC services including Ceasarean (C) sections.

The programme also purchased EmoNC kits to equip maternity wards and surgical blocks to improve the quality of services including C-sections. The kits arrived in February 2019. 80% were distributed by March 2019 (as reported in the last annual review) and the 20% remaining have now also been distributed. The distribution criteria were aligned with the RMNCAH Investment Case approach of focusing on the capitals of the districts and reference hospitals with high demand, where most obstetric and neonatal complications occur (Zambézia province received the highest percentage of kits). UN agencies and MoH confirmed receipt of the kits and monitored their delivery to their destinations. These kits have contributed to health centres being better equipped and have therefore reduced mortality and morbidity. Yet the programme has lost the opportunity to require more robust data from GoM and the UN to calculate the impact of these kits. The RMNACH programme benefited 41 referral hospitals with the distribution of medical equipment (C-section, hysterectomy and tubal ligation kits) and 52 ambulances.  According to estimates from census data on population and strategic plan of the health sector updates (PESS) it is expected that every year 106,900 complications from pregnancy were treated in these health facilities, from which 5,345 were expected to be C-sections. The kits have been very helpful in saving babies’ lives as highlighted by this doctor in Lichinga: “with the support from British People, under the Joint United Nations Programme, Marquesa’s baby survived and came out of danger, thanks to the use of an automatic incubator that regulates the temperature and keeps the premature newborn in a heated environment.”

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The UN has not been reporting VfM indicators although these were agreed with the programme team 14 months ago. A summary of VfM based on observations and reports has been written for all UNJP outputs below. This section will focus on economy and efficiency.

Economy: The UN benefits from economies of scale through their use of a global procurement system to purchase quality equipment and commodities in bulk at the lowest price. Information from UNFPA demonstrates that the contraceptive intrauterine device (IUD) in 2018 cost US$0.35 for Mozambique when worldwide it was US$0.33, whereas implants were US$8.5 each both in Mozambique and internationally, the injectable Sayana Press costs US$1 and Depo provera was US$0.78 compared for Mozambique compared to US$0.8 and 0.8 for the UNFPA global prices. Both contraceptives were procured and used in Mozambique with the Government approving for Sayana Press to be distributed widely for women to self-inject in communities after a successful pilot earlier this year. The procurement of the ambulance boat was done through a competitive regional tender, thereby getting quality at the lowest price.
[note] UNFPA (2018) SRHR plan and gaps from 2018-2021 (excel spreadsheet shared with DFID Mozambique in May 2018
[note] UNFPA contraceptives price indicator year 2018

Efficiency in the programme is mixed. There has been efficiency in the timeliness with which the 344 maternal and child health nurses have been trained since the programme began which has largely followed the training plan. However, the UK-funded review of the programme undertaken in March 2020 showed that in 2019 only 20% of trained nurses had been deployed within a year of training because of a budget ceiling limiting the number of health workers that could be added to the payroll every year (capacity to integrate health workers into the health establishment, referred to above). There are two signs that this has improved in 2020: (i) discussions between the Ministries of Health and Finance has led to an increase in the number of health workers that could be added to the payroll from 2,100 in 2017 to 4,800 in 2020, and (ii) to respond to the increased demand for health workers in the context of C-19, the MoH has been using partner funds to hire nurses through one-year renewable contracts.
[note] Matsinhe C (20201) UNJP to support the Investment Case for improving reproductive, maternal, new-born, child and adolescent health. Mozambique.

Describe any changes to this output during the past year, and any planned changes as a result of this review

There was no change to this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendation from the previous AR
Progress against the two previous recommendations is mixed. See table in Annex 1.

Lessons learned
- The programme faced a series of procurement delays and much-needed training on the management of the supply chain was suspended due to the C-19 pandemic. There is a need to plan for adequate transport and to strengthen the management of the supply chain in order to deliver key inputs on time.
- The UN and health monitoring system do not capture data beyond the output level. The programme would have benefited from a more robust monitoring and evaluation system in order to better measure the outcome of the interventions This is a lost opportunity, but we will consider an evaluation of the impact of the material delivered to these health centers to the beneficiaries at the end of the programme.
- A study on the Evaluation of the Postpartum Haemorrhage Program (PPH) from the programme was used to generate recommendations for expanding to the rest of the country. The lessons from the study were included in activities planned for 2021 to strengthen service delivery.

Recommendations for the next year

The UN to include a budget for fuel and maintenance of the ambulances (led by MoH) from January to March 2021 and to develop the hospital management plan for all the equipment purchased by the programme. This is to be addressed before the end of the programme.

The programme was noted and recognized by MoH as very relevant in the context of the Investment case. The programme will be discussed at the Sector Coordinating Committee with all the National Directors to review its contribution to the Investment Case and decide which activities will continue with partners (for example by the PHCSP) or MoH. Lessons from the studies carried out by the programme including on neonatal health, community health workers, are to be integrated into the sector planning process for next year. This is an ongoing process that is happening now until 2021.

In order to understand better the impact of the programme, we recommend a final and external evaluation before the PCR to estimate how many people have benefited from the programme. This will be done through different methodologies including through the form of interviews of patients in low volume versus high volume health centres. This is to be addressed before the end of the programme.

Output Title	Platform for outreach through the community health worker (CHW) programme strengthened by 2020 (UN Joint Programme)
Output number per LF		2	Output Score	B
Impact weighting (%):		25%	Impact weighting % revised since last AR?	Yes - ↓ (from 30 % to 25%)

Indicator(s)	Milestone(s)	Progress
2.1. Proportion of CHW / (i) working in target districts of total needed / (ii) receiving at least 1 supervision visit per quarter	75% / 70%	(i) Moderately exceeded expectations. 79% working in target districts of total needed= 1,997 CHW candidates graduated and deployed to their communities (March 2020) (43% were female) / (ii) Exceeded expectations. 100% receiving at least 1 supervision visit per quarter. Total supervision visits (2019) = 40,356; average of supervisory visits: 8 contact/CHW/Year –

2.2 Proportion of CHW equipped and using UPSCALE mobile platform in (i) Cabo Delgado province (ii) Nampula province	30%	Moderately did not meet expectation / (i) Coverage: 20% / 700 CHWs from Cabo Delgado and Inhambane since 2018 / 613 CHWs trained in Zambezia since 2019

The output score is a borderline B because even if one indicator exceeds by 34% and the indicator that was not met fell short only by 10% we still consider these two indicators to have an independent weight and be as equally important for the CHWs to be operational

  1. Exceeded expectations: Community health workers have an essential role in delivering basic treatment and preventive healthcare in rural communities including nutrition, testing and treatment for malaria, delivery of FP and health education. The UNJP through UNICEF invested in increasing the number of community health workers (CHW). Firstly, this was supported through technical assistance to support the development and submission of the CHW National Strategic Plan (2018-2024), which emphasises the increase in overall numbers and proportion of female CHWs. Secondly, the UNJP supported the training of new CHWs from 5,200 in 2018 to 8,800 in 2020. UNICEF trained 864 new CHW by March 2019. As of March 2020, 1,997 CHW candidates had graduated and had been deployed to their communities. FCDO funds contributed to 64% of the national CHW expansion plan in 2019, with an increased female participation of 43% (456 female CHWs) trained in Nampula, Zambezia and Tete, a level which has never been achieved before. Furthermore, and in addition to the targets, during 2019 the programme supported the expansion of the CHW programme to remote communities, benefiting an estimated 2.5 million people living in remote areas of which 429,000 were children under five years who had no previous access to life-saving interventions. Compared to last year, more focus was given to strengthening supervision and improving the quality of service. The number of supervision visits performed by the nurses to the CHWs is eight per year, except in Cabo Delgado due to the instability caused by insurgency (where four visits per year are undertaken). The costs of supervisions were funded through this programme and through WB support to the GFF.

  1. Moderately did not meet expectations: Since the last AR, another 613 CHW in Zambezia district were trained and are utilising UPSCALE, a mobile phone platform that collects monitoring data and acts as a job aid. There was a plan for the other half of CHW in Zambezia province to start using UPSCALE in the first quarter of 2020, but due to restrictions caused by the COVID-19 State of Emergency, this was postponed. This delay also affected Nampula, Maputo and Gaza Provinces. FCDO funds supported the procurement of 1,700 mobile phones by UNICEF, which will be used to expand UPSCALE in four new provinces and replace old equipment in Inhambane and Cabo Delgado provinces. Although a technical advisor has been working to improve the national CHW programme since January 2019, the tool is still facing technical constraints including lack of adequate maintenance and insufficient spare equipment (batteries and charger). For these reasons the coverage of UPSCALE is only 20% of CHWs. There is a plan to expand the platform to reach 40% by March 2021. Now the concern is to address the cost effectiveness of UPSCALE before solving the technical problems and resuming implementation.

Progress on recommendation from the previous AR

The recommendation from last year was achieved. See table in Annex I.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Equity: As the beneficiaries of community healthcare consist largely of children, women and girls, the programme has focused on increasing the proportion of female CHWs from under 30% in 2017 to 43% in 2019. The deployment of CHWs is addressing regional disparities in access to health services with CHW coverage increasing from 49% of the country in 2017 to 79% by 2019. The deployment of CHWs has expanded the coverage of basic services in remote areas, following the government’s plan to ensure that the provinces with larger populations have more CHWs.

Economy: 90% of equipment and commodities purchased through the programme are through the UN’s global procurement system which benefits from economies of scale making it economical and effective. Where possible, the training of CHWs and MCH nurses was done using government training centres, reducing some of the direct costs.

Efficiency: For the government, the fact that this programme did not use government systems but set up parallel structures added to their transaction costs. UNFPA took 42 days to transfer funds from their headquarters to the different UN agencies in Mozambique. This figure decreased to 20 days for the second tranche in November 2019. We do not yet have the number of days for 2020. Progress on the 30 health facilities that will get WASH services is 76%. Reasons for the delay were the need for the WASH and health sectors to coordinate at both the national and provincial levels and the inability to bring in equipment from South Africa from March to August 2020 when the border was closed in the context of the pandemic. This activity should conclude by March 2021 when the programme ends. In future the UK will be working through the GFF that have identified the main bottlenecks for system strengthening such as coordination mentioned above and are tackling them at the same time that they are supporting service delivery.

One of the VfM indicators agreed for the programme is the cost of training each CHW and each MCH nurse. These are expected to be lower in high density provinces where there will be economies of scale as the number of CHWs and MCH nurses trained is larger. Although the cost of training each CHW in the programme is unknown, the World Bank has used international and national evidence to argue that CHWs in Mozambique are cost-effective because they deliver basic preventive and curative care at competitive costs in low income settings.
[note] World Bank (2015) Mozambique health public expenditure review 2009-2013.

Effectiveness:
The programme was effective at helping service delivery to continue. However, the system strengthening component faced considerable constraints due to the lack of coordination across the different departments at the MoH. For example, the lack of a management/plan for maintaining equipment poses a risk that equipment purchased by the programme may break down and decrease effectiveness over time. Although MCH nurses were trained, not all of them were immediately deployed. CHWs were trained but they still experience delays getting their monthly allowances and a shortage of supplies affecting morale and the quality of their service delivery. The programme has contributed to reforms to address these barriers such as the National Health Policy and dissemination of the Human Resources Retention Strategy. But delays in getting these documents approved has limited their effect considerably.

Lessons learned

- The advocacy and sensitisation commitment from UNICEF and its active engagement with provincial health directorates in Nampula, Zambezia and Tete provinces led to progress in recruiting and training female CHWs.
- Joint advocacy and collaboration between the UN and the WB brought together the Ministry of Finance and the Ministry of Health for fruitful discussions to ensure the Government starts to gradually take on the monthly allowances for the CHWs. This would imply a gradual phasing out direct support for the monthly allowances by partners.
- The findings of the malaria case management in Mozambique survey has been shared with the GFATM/National Malaria Programme and incorporated into the malaria programme to improve case management by the CHWs.
- Findings from the mentoring of the CHW nurses showed how much the knowledge and competencies of the MCH nurses had improved.
Recommendations for the next year

The UN has to do more to systematically track and report on value for money. For example, a recent review by the World Bank of the UPSCALE platform used by CHWs has shown that it is not as cost-effective as it could be, with recommendations made for the UN to reduce costs before the World Bank can scale it up. The UPSCALE platform will continue once the cost effectiveness is improved. This is to be addressed in next programmes.

The partners need to follow up on the development of a national costed CHW expansion plan for 2021-2022 inspired by the PHCSP programme. This will recommend a gradual transition for the government to pay for the CHWs while advocating for partners to continue supporting the programme given the country’s fiscal constraints.

Ensure that the momentum on the reform documents developed by the programme is maintained by getting other funding mechanisms such as the PHCSP, the Global Funds and USAID to be aware of and support them. At the moment, only the Essential Health Package has been shared. This is to be addressed beyond the end of this programme (end 2021)
[note] The programme has supported the development of the following documents: The National Health Policy; the Functional Analysis of the Health Sector; the Human Resource Retention Strategy; the Promotion of Health Professional Careers and the Definition of the Essential Health Package.

Output Title	Generating demand for family planning among adolescents (PSI and Rapariga Biz)
Output number per LF		3	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	Yes - ↓

Indicator(s)	Milestone	Progress
3.1 Additional FP users in the target areas as a result of FCDO interventions	Actions taken by key influencers to improve access to FP for adolescents and young women (no quantitative target available in the log frame)	Moderately exceeded expectations: 18,604 Community dialogues/ Meeting with leaders/ Meetings with parents
3.2 Improved knowledge, capacities and agency for SRHR	5,799 girls and young women trained as mentors by December 2019 in 20 target districts in Nampula and Zambezia	Met expectations: 5,609 young women trained as mentors: 97% of the target 5,799 of which Nampula (2,655) and Zambezia (2,953) are considered meeting expectations

3.1 PSI: Moderately exceeded expectations. The project seeks to generate FP demand through interventions that change social behaviours and beliefs. It does so by understanding the barriers, influencers, and the context faced by adolescent girls. PSI has done particularly well: since the beginning of the project, the total number of new users of FP is 80,978 among which 40,117 were during the period of this review, despite the C-19 pandemic. This has been done thanks to multiplying the interactions with key influencers (community dialogues, meeting with the leaders and parents) to support access to FP. The community dialogues have been instrumental in helping parents and influencers learn techniques and skills for supporting adolescents in making decisions about sexual reproductive health and rights (SRHR). Community leaders have also offered to use community meetings and church services to share information about the project and family planning messages for adolescents. Beneficiary feedback led to insights into the added value of the project: “Since the beginning of the project, we have seen improvements because the number of children who get pregnant have been reduced’ (community leader, Maputo). During the C-19 pandemic, leaders have been helpful in supporting the project team in situations where restrictions or beliefs have affected implementation. The meetings with parents are implemented in urban areas to improve parents’ skills for educating and communicating with their adolescents and youth, especially about their future, sexuality and reproductive health issues. After meetings, most parents commit to having more dialogue with their adolescents about these topics and continuing to encourage adolescents to focus on their futures. Moreover, parents are often more inclined to support the project because they already understand what will be taught and understand the value of/need for resources to educate adolescents about their futures, including family planning and reproductive health.

3.2 Rapariga Biz project: Met expectations. The mentoring numbers planned for this year were just about reached at 97%. Mentors are the backbone of the programme, providing safe spaces for girls. A total of 700,000 girls have been reached between 2016 and 2019, and over a third of them (37%) accessed family planning and counselling at Youth Friendly Centres linked to health facilities. Retention of the young female mentors is one of the challenges of the programme. Some are leaving their role as mentors due to the conclusion of their secondary school studies and the professional opportunities elsewhere, while others are offered higher stipends in other similar programmes. In addition, due to the programme's focus on increasing the number of mentors, it has proven to be a challenge to provide continuous learning opportunities. Initiatives to reinforce the capacity of the mentors were piloted in 2019 and demonstrated the importance of consistent and regular learning opportunities to keep the mentors motivated and ensure the quality of the mentorship sessions. The feedback from the mentors is very encouraging, such as, “I love my responsibility as a mentor and it is encouraging to help make a difference in the lives of the girls in my community” (Josina, 25, mentor).

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

PSI VfM

Economy: Total programme cost from September 2019 to September 2020 including direct and indirect costs as a proportion of total expenses was 68% which is slightly less than the plan of 71%.

Efficiency: The cost per FP ward in health facilities was £1,905. This includes the salaries of nurses, equipment, commodities, travel and promoter payments and promotional material for outreach services. This price is thought to be more than the cost of delivering through the health centre alone where health workers get paid less than the project nurses. However, patients prefer the private nurses due to better quality of services including privacy, counselling and not having to queue to get a service. The health facilities and PSI will have to discuss how to sustain the quality of these services once the project ends in February 2021. PSI have noted an increase of 45% usage on average in their FP wards over the last year.

Effectiveness: Cost per couple years of protection (CYP) had a target of £18 but cost less than planned at £13. Mozambique is relatively cost-effective according to PSI estimates: the cost per CYP in 2015 was £25 in Malawi, £20 in Zambia and £5 in Tanzania. Reasons for this include a more rapid uptake of long-acting methods of FP in Nampula than was originally unexpected and built into the VfM targets.
[note] CYP – the estimated protection provided by family planning services for a period of a year

Equity: PSI set a target of £35 for the cost per client under 20 years of age. This indicator tries to capture the cost of providing FP to adolescents who are harder to reach. The target was exceeded as the actual cost per client was £33. 26% of adolescents and youth reached by the project reported having a disability. The project aims to reach at least 40% of clients under 20 years of age. This was almost more or less met, as 37% were under 20 over the last quarter. The project has also reached many more rural (76%) clients than initially planned (63%). This means it is reaching poorer groups who did not previously have information on family planning, whereas FP uptake is easier and faster in urban areas where people have more information and higher levels of education.

Rapariga Biz VfM

Economy: The cost of training one mentor is $20 per person for an entire week from 2016-2018 is considered low when compared to the cost of training project employees in other countries. According to the independent evaluation of the project released in March 2020, the cost per unit of most indicators is difficult to calculate because these were not defined and therefore tracked from the beginning, and the results of interventions cannot be attributed only to the project
[note] leBlanc R, Calane A, Eltahir A, Bischler J, Grabaek S et al (2020) End of project evaluation of the One UN SRHR for girls and young women in Mozambique- Rapariga Biz Programme, 2016-2020. Submitted to Embassy of Sweden in Mozambique.

Efficiency: The cost per adolescent mentored is $3.30 which is considered low when considering the effects of mentoring, which lead to an increase in knowledge about family planning and agency to decide if they want to use family planning, education or justice services. The cost of training health staff in youth friendly centres is $400 per person, which is thought to be cost-effective based on an independent evaluation. The costs for the provision of health services in schools, income-generating activities and community dialogues are unknown. However, the need for adolescents to have parental consent when accessing longer-acting contraceptive methods, which is a new government policy, will have an effect on the uptake of this service and therefore the overall efficiency.
[note] leBlanc R, Calane A, Eltahir A, Bischler J, Grabaek S et al (2020) End of project evaluation of the One UN SRHR for girls and young women in Mozambique- Rapariga Biz Programme, 2016-2020. Submitted to Embassy of Sweden in Mozambique.

Effectiveness: The programme has led to delays in early marriage and pregnancy which are being measured at outcome level according to a UK funded review of the Programme and the Independent Evaluation undertaken earlier this year. However, both reports note that it is difficult to know which programme interventions are leading to this outcome. All government sectors (health, justice, gender and social welfare invested less than planned to the programme which undermined supervision and coordination activities, raising questions about sustainability.

Equity: The programme is not reaching the most vulnerable girls as the selection criteria include schools, thereby excluding out of school girls and women who tend to be poorer. The programme is therefore only reaching a small proportion of adolescents and young women with disabilities, who are married or who face problems in accessing services because they live in remote areas. Expanding the programme to reach more vulnerable girls will increase the cost per girl mentored.

Describe any changes to this output during the past year, and any planned changes as a result of this review
No change.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendation from the previous AR

A recommendation from last year was to decide whether or not to continue support to Rapariga Biz. FCDO decided to phase out after March 2020 due to our changing strategic approach to focus on demography but also due to the cost effectiveness of the interventions. It was impossible to measure the cost-effectiveness of interventions such as, for example, income-generating activities, community dialogue and a text message platform in mobile phones used by adolescents (SMS Biz) as the costing was not done at the beginning of the programme. Moreover, it was difficult to know which interventions led to preventing unwanted pregnancy and marriage. Canada and Sweden will continue to support the programme until September 2021 when the next phase starts.

Lessons learned

PSI
- The schools and pre-selected sites where mini-events and interaction with adolescents were conducted closed due to the C-19-related state of emergency. For this reason, the project has looked for beneficiaries in locations they frequent on an everyday basis, such as nearby markets, water points and bakeries. PSI showed flexibility in reaching out to adolescent girls.
- The implementation of community dialogues has helped to understand the extent to which engagement with influencers can support demand creation for contraceptives. Linking SRHR with other topics, such as financial stability, including the UK’s Financial Sector Deepening Programme which supports the poor to access financial services aligns with family priorities and encourages influencers to support the adolescents in seeking contraceptives.

Rapariga Biz
- The mentorship approach has proven relevant and effective to promote and influence a change in attitudes and behaviours in girls and young women related to SRHR, Gender-Based Violence (GBV), child marriage etc. The safe space sessions provide the girls and young women with a unique opportunity to acquire necessary knowledge, skills and social networks that can help them make healthy and informed decisions and demand their rights.
- The further from the district capitals the girls and young women live, the greater their unmet SRHR needs. Rapariga Biz therefore needs to expand to remote and hard-to-reach communities, rather than the current targeting.

Recommendation for the year ahead

The approach of PSI was extremely positive in generating demand for family planning. However, they will have to be more cost-effective and focus more on integration of FP within existing health services. This will be addressed beyond the end of this programme

The Rapariga Biz Steering Committee led by the Secretariat of Youth and Employment took place on the 26th October 2020. Representatives from all the stakeholders were present including the line ministries, civil society and main donors to the programme. The meeting reviewed performance in 2019, and progress in 2020 including findings from an independent evaluation of the programme. The UN and government are now in the process of implementing a roadmap which will consult and agree on which reforms from the evaluation will be incorporated in the next phase of programming of Rapariga Biz. This will be addressed beyond the end of this programme.

Output Title	Strengthen the health sector’s capacity to respond to emergencies
Output number per LF		4	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone	Progress
4.1 MoH's ability to prevent and respond to outbreaks is strengthened (through WHO's Emergency Preparedness project).	MoH preparedness and response to any disease outbreak in target areas	Met: MoH responded to cholera, measles and C-19 outbreaks using the preparedness plan and structure put in place through WHO
4.2 Institutional support to the MoH to advance the pandemic response to reduce the risk of mothers, newborn and children as well as health workers through the UN Joint Programme.	Institutional support to the health C-19 response plan	Met: UNJP has reprogrammed their activities around the C-19 pandemic: equipped health facilities with trained health workers, trained in case management of C-19, delivered life-saving medical equipment including PPE to respond to C-19, developed communication and awareness, and supported technical working groups with MoH

Briefly describe the output’s activities, and provide supporting narrative for the score

4.1 Met: WHO helped to respond to cholera outbreaks in northern Mozambique, measles in Sofala, Cabo Delgado and Nampula and C-19 from January 2020. The Integrated Disease Surveillance & Response (IDSR) guidelines issued by WHO were distributed and used as a basis for training of health professionals and were particularly useful in the C-19 pandemic response. WHO supported the MoH’s district and provincial rapid response teams to respond to the outbreaks with technical assistance, training and equipment. WHO also used UK funds to set up a public emergency operation centre (PHEOC) at the MoH to manage outbreaks. UK funds paid for 100% of the office and digital equipment for the PHEOC centre. UK funds to the PHEOC have phased out but the centre is used by technical working groups consisting of MoH staff and partners to follow the evolution of the pandemic and undertake day-to-day activities and strategic and operational planning at the provincial level. The PHEOC also provides capacity building to provinces and districts through video conferencing. UK funds were also used to finance technical assistance for preparedness activities, training, vehicles and staff.

WHO also facilitated transitioning out the electronic early warning alert and response disease surveillance system (EWARS) into a more robust electronic disease surveillance system (the eIDSR/m-Alert), now scaled up to all districts in Sofala province. eIDSR will allow the country to have real time data at different levels (district, province, centre) to guide timely decision and response. Training took place in December 2019 for health professionals in Sofala to improve case identification, public health threats, analysis and interpretation of data on priority diseases using standardised interoperable information systems within the context of Mozambique.

4.2 Met: The C-19 pandemic triggered a rapid and efficient response from the UNJP partners. FCDO has contributed by re-programming a total of £2,092,700 in early March 2020 to respond to C-19. UNFPA, UNICEF and WHO have been actively involved in the pandemic response, especially to reduce risks to mothers, newborns and children (MNCH). All three agencies had been actively involved in developing case management protocols for MNCH with the provincial health authorities and have supported training on C-19 infection, prevention and control protocols for health facility staff at all levels. The three UN agencies became the co-leads for the Service Continuity Technical Working Group to ensure that basic MNCH services would continue to be delivered in the context of C-19. They also worked extensively with provincial health authorities to apply the Live Saved Tool (LiST) analyses to assess the impact of the pandemic on MNCH care. The Lives Saved tool is a mathematical modeling tool which allows users to estimate the impact of coverage change on mortality in low- and middle-income countries. All three agencies have been supporting MoH and provincial offices for health centre monitoring to ensure service readiness. They have been actively involved in bringing in pandemic supplies (PPE, PCR tests, treatment kits) in coordination with the broader C-19 procurement plan coordinated by MoH. These commodities were purchased with UK funds as well as infrared thermometers, tablets for C-19 surveillance, medical equipment and consumables such as lab coats for hospitals and health centres. All three agencies are working together in the Service Delivery Working Group to ensure the mainstreaming of pandemic activities in emergency preparedness in the long run.

UNFPA programmes to prevent and respond to GBV are inclusive of women and girls with disabilities, supplying family planning commodities and promoting community and youth engagement. In the meantime, UNICEF ensured that children and adults with disabilities have access to appropriate prevention and response measures to C-19 and to mitigate risks associated with increased GBV and SRH.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Equity: The overall quality of the response was good due to having a dedicated Emergency Officer in the WHO country office, paid for by the project. This meant that support could be provided to adequately plan for, target and respond when there were disease outbreaks and reach all people in need.

Economy: Despite UK funds being used to pay for half of a full-time Programme Manager and full-time logistics staff to support the Emergency Officer, in practice, the Programme Manager dedicated little time to ensuring compliance with FCDO requirements as they were supporting other programmes in the country office. This affected the quality and timeliness of reports, with the FCDO Programme Team often having to call the Emergency Officer to get more information on the project’s performance. The inability of WHO to adequately address this issue contributed to the decision by FCDO to phase out our support to the Emergency Response project in March 2020. The UK has continued to support WHO through the UN Joint Programme which has more programme support from WHO.

Efficiency: WHO were able to learn from last year and set up a more efficient training arrangement with MoH staff. This led to greater engagement from the staff who had to travel outside their cities to attend the training. However, it also led to higher costs due to accommodation and transportation to the venue. The project was able to respond quickly to outbreaks including C-19 due to the availability of the emergency officer.

Effectiveness: The programme was effective at supporting the MoH to respond to disease outbreaks. Two of the major contributions were the setup of the PHEOC that has enabled the Government to manage outbreaks centrally, and the integration of a digital surveillance system. These have made emergency support more systematic and therefore less reactive.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
4.2 is a new output that was added in June 2020 to reflect the funds that were re-programmed to respond to C-19. The programme was mainly focused on RMNCAH, but funds were re-programmed for the C-19 response to keep health services active and avoid health workers being infected.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The recommendations from last year have not fully been achieved. See table in Annex I.

Lessons learned

- WHO regional support (especially the delay in recruiting staff) was compromised due to the number of simultaneous emergencies. This highlights the need for Mozambique to be prioritised for a higher number of WHO staff and support considering the frequency of emergencies it faces such as two category four cyclones, cholera and polio outbreaks in 2019 and C-19 and outbreaks of cholera and measles in northern Mozambique resulting from low coverage of immunisation services in 2020.
- It is crucial to maintain preparedness mechanisms and improve them over time through WHO support, with a gradual transition to MoH management in the long term.
- It will be important for the MoH to engage and take more accountability for the sustainability of the preparedness programme. For example, although WHO installed the PHOEC, a dedicated team to manage it was planned but never recruited.
Recommendations for the year ahead

WHO Mozambique needs to continue advocating to WHO headquarters for Mozambique to be reclassified as a country that requires additional regional resources to support all the health crises the country regularly faces. For example, due to the insurgency in northern Mozambique as well as C-19 there is an urgent need to assign a dedicated WHO Health Cluster coordinator in Cabo Delgado province. This will be addressed in the next programmes.

In future, it is necessary for partners to consider funding to reinforce surveillance in health centres and community-level surveillance. Community systems need to be strengthened on the coordination of the relay of data to the national level and on training CHWs on the new surveillance guidelines. This will be addressed in the next programmes.

FCDO and other partners should continue to advocate for continuation and sustainability of the WHO preparedness work. This will be addressed before the end of the programme

Output Title	Strengthen our central support towards innovation through drones for health by September 2020
Output number per LF		5	Output Score	C
Impact weighting (%):		5%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone	Progress
5.1 Number of test flights conducted for TB samples transportation	In-country UAS (drone) study flights conducted	Substantially did not meet expectations: The pilot flights were not conducted as planned due to C-19 pandemic

5.1 Outputs substantially did not meet expectations: This output was not met due to the C-19 pandemic. Initial test flights took place successfully outside of Maputo in March 2020. Unfortunately, the official TB study, which was planned for April 2020, was postponed due to travel restrictions arising from the C‐19 pandemic. However, whilst the flights were postponed, Village Reach carried out a community sensitisation study, continued engaging with the Civil Aviation Institute (Instituto de Aviação Civil de Moçambique - IACM) for flight authorisation, looked into other options, as including moving the official study flights to less populated areas, and finalised the procurement of all necessary laboratory material for TB lab sample analysis.

Village Reach requested a no‐cost extension from FCDO, which was granted, to do the study flights. The study, which initially aimed to demonstrate the feasibility of safe transport of TB lab samples, will now include C‐19 samples, which could increase the speed of analysis of C‐19 tests, contributing to the response and ensuring that routine supply chains remain intact. For C‐19 sample testing, the Health National Institute (Instituto National da Saude-INS) will cover the costs of all test kits and reagents, so no additional funding is being requested from FCDO. The pilot has already added value by mapping and costing current distribution routes for TB samples throughout the country. This information will be useful for GFATM and the regional TB programme supported by the World Bank f to cover a gap in rapid diagnostic and treatment of TB.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Economy: To reduce administrative costs, Village Reach worked closely with government staff whenever possible, enabling only one of their staff to engage with the project. Technical staff with expertise in flying UAV were brought in from neighbouring Malawi. Due to C-19, they had to quarantine in Mozambique for two weeks prior to undertaking the test flights, increasing the costs of the staff.

Efficiency: The project kept costs low by bringing in UAV from neighbouring Malawi for the test flights rather than purchasing UAV or bringing them from the United States or Australia where the technical team came from. Samples were taken from local laboratories with consent needed for the TB patients who provided them. For C-19, consent for the samples was waived following approval by the ethical board. This kept costs low and ensured that the test flights could be conducted within the agreed extension time. The project tested alternative transportation (trucks and motorbikes) for TB samples in Zambezia province. These will be assessed against the cost of transportation with the UAV.

Effectiveness: This project has buy-in from the government who are engaged in every part of implementation. Although this initially led to delays in implementation as approval had to be sought with different government counterparts such as National Aviation Authorities, community leaders and the National Institute of Health, it has meant that the programme has rapidly adjusted to C-19, carrying out the test flights in remote areas to prevent gatherings. Given government involvement, it is much more likely that the findings will be incorporated into the transportation options available in the health sector. However, it is still too early to identify the project’s full effectiveness, until the results of the study are available, and we understand what the uptake will be among partners or government. In any case, the learning will be disseminated, helping to inform options.

Equity: It remains to be seen whether this would be a cost-effective way of ensuring ‘last-mile’ diagnosis capacity to help reduce TB infection within hard to reach rural communities, who are often poorer than those with access to a testing facility.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This is a new output that was approved to take forward this innovative methodology, initially funded through a central FCDO fund, but then taken on by this programme to facilitate uptake locally.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lessons learned

C‐19 was an unforeseeable pandemic that ended up affecting the key deliverable of this output, including study flights and data collection for the cost‐benefit analysis. However, the pandemic is a reminder about the potential benefits of using new technologies. For example, the test flights that took place in October 2020 now include C-19 samples in addition to TB samples.

Recommendations for the year ahead

Although UAV may help to solve transport issues in Mozambique, it will be important to undertake a cost-benefit analysis and understand its sustainability, and to disseminate these findings. Local people need to be trained on maintenance and on recharging the drones as it has a range of only 131 km, if the government decides to use UAV in the future. Village Reach and the government will have to discuss how the project will continue after FCDO funding ends in March 2021.

D: RISK

Overview of risk management

The overall risk rating of the programme has been updated to major given the disruption to health services caused by C-19 and conflict in central and northern Mozambique. All partners have a risk matrix and provide regular updates in reports and review meetings. The overall programme risk management matrix (together with a mitigation plan) comprises delivery, safeguards, operational, fiduciary, environmental, and reputational risks. It has been updated regularly.

External risks management
The main risks about the external environment include (i) the emergencies, (ii) the weak capacity and commitment of government to drive health system strengthening and health reforms, (iii) an economic austerity leading to insufficient funding to the health sector, and (iv) the slow process of decentralisation which has had consequences on decision-making.

Fiduciary risks
Since the debt scandal in 2016, no UK funds have been channelled through the government at local or national level. Working through UN and NGO partners, subject to due diligence, provides good assurance that mitigation against fiduciary risks is in place.

Delivery/ Environmental risks
Since the last annual review, risk around disruption to routine delivery of health services due to emergencies (climate change, disease outbreaks and conflict/insecurity) have materialised with the exacerbation of violence in the central and northern provinces due to the elections, the conflict from the opposition party junta in central Mozambique, insurgency in Cabo Delgado but also the C-19 pandemic.

- Cabo Delgado conflict: It is harder to deliver in northern and central Mozambique where conflict has rendered entire districts inaccessible and led to approximately 500,000 IDPs. Essential services have been disrupted due to C-19 and the conflict itself. These services are resuming but additional safety requirements make it difficult to reach remote areas and are keeping patients away from health centres.
- C-19: UNJP and PSI were able to pivot programming to respond to C-19 but they still faced a lot of challenges such as cancelation of some activities that required people to gather in groups e.g. face-to-face training or community consultations. PSI came up with new activities such as use of e-learning platforms for training. The services were still disrupted but have adapted to “new normal”.
These have caused delays in implementation but RMNCAH partners put in place strong mitigation actions to get interventions back on track and established mechanisms to respond to these situations. They updated their risk registers regularly and adjusted their workplans accordingly. The multiple crises the country had to face created significant challenges in strengthening the health system for mother and child health.

Operational risks
The government challenges have consisted of low capacity and lack of senior level engagement in reforms resulting in slow progress to implement reforms such as the HR retention strategy. In order to mitigate these, the programme has invested in supervision of health personnel, or engaged in policy dialogue to ensure reforms took place and to deliver a health policy document on HR retention.

For the WHO emergency preparedness programme, organisational restructuring and delays in recruitment to essential positions were flagged as a moderate risk to the implementation of this programme. In order to mitigate this risk, partners have advocated for the state budget and other partners (e.g. GFF) to contribute to the sustainability of the main project interventions but also for health personnel positions to be maintained and included in the state payroll.

Delivery risks
Insufficient global supply/clearance processes during procurement and slow distribution once goods arrived in-country has been a recurrent issue in the UNJP programme. Nonetheless, UNFPA provided visibility and assurance regarding the adequate storage, management, and use for intended purpose of family planning, maternal health, and other programme supplies. All implementing partners have robust tracking systems in place to monitor their supply chains from procurement to distribution.

Safeguarding risks

 Sexual abuse and exploitation in partner organisations are a high risk when dealing with girls, women and children. Partners are putting in place measures to reduce these risks. For example, UNFPA has put in place mechanisms for people to report concerns, raise awareness in the community, reinforce the system with the police and Ministry of Justice and establish links with the Spotlight initiative, a global, multi-year partnership between the European Union and the UN to eliminate all forms of violence against women. A recent report from the Center for Public Integrity (Centro de Integridade Pública- CIP) reports allegations of women and girls facing sexual assault in the province of Cabo Delgado and a general call to government and organisations for more active denouncing of such cases. None of these allegations of abuse are linked to UK funding. UNFPA has expanded its services to raise awareness around GBV. Safeguarding issues are regularly picked up and referred to competent authorities (e.g. Rapariga Biz) but there is still an issue with UN reporting actions to the FCDO in a systematic manner. Other partners have shown willingness to strengthen their safeguarding reporting: as an example, the Rapariga biz programme in coordination with MoH and other sectors will strengthen GBV care services and prevention messages to girls who are victims of violence. The UNJP has safeguarding strategies in place but do not necessarily report concerns to us.

Update on partnership principles

The programme still does not channel any funding directly to government due to the debt scandal and subsequent corruption allegations. There is therefore no update on partnership principles.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

Table 1: Comparison between the budget and expenditure for the programme in the assessed period
Project	Budget	Spend	Balance	%Spend
UN Joint Programme - Capital	4,867,779	3,050,983	1,816,796	63%
PSI	3,140,437	963,840	2,176,597	31%
WHO	616,850	616,850	0	100%
Rapariga Biz	491,920	431,678	60,242	88%
VillageReach	300,000	170,983	129,017	57%
Total	9,416,986	5,234,334	4,182,652	56%

During the review period, there is a 44% (£4.12m) underspend in relation to the programme budget. The UN Joint Programme was affected by cyclone IDAI in 2019, forcing the project to move most of its deliverables and budget from the previous year to the assessed period. The underspend is also due to the fact that the WB, through the GFF, have contributed since 2018 to the outputs related to CHWs, generating a big saving.

PSI have exceeded their targets with lower than anticipated spend, so outputs were met despite the underspend. Additional spend would focus on translating these outputs into outcomes by ensuring lessons inform future implementation and decision-making/policy beyond each project. This will have an impact on the sustainability of interventions.

From March 2020 the UN Joint Programme, PSI and Village Reach projects were affected by the government restrictions necessary due to the C-19 pandemic which impacted negatively by slowing project implementation and reducing levels of budget expenditure. PSI suspended or delayed a large proportion of their interventions to manage the risk of transmission until these could be modified in the context of C-19, leading to only 31% spend. C-19 led to further delays in building WASH infrastructure in health facilities as the equipment could not be imported from neighbouring South Africa from March to September when the border was closed. As the CHW costs (subsidies and supervision) were covered by the MDTF/GFF funds, the UNJP programme was able to reprogramme savings of £1,612,700 to C-19. The UNJP (which has around 70% of the programme) spent 16% in administrative costs (15.5% in the previous AR).

Due to a changing context (C-19), partners revised their implementation plan. While some will not be able to achieve their deliverables, partners will be able to report on additional results linked to C-19 and overall, they will be able to achieve the majority of their intended objectives.

FCDO’s working relationship with all implementation partners continues to be collaborative. Implementing partners have been providing regular project progress updates based on agreed reporting schedules. The programme team continues to regularly engage with the partners.
All project compliance documents are up to date. The programme’s delivery plan is updated monthly and will be moved shortly to the online version of the Aid Management Platform (AMP). Regular internal meetings take place to follow up on programme compliance, and analysis of risks supports robust project cycle management. More recently these have been more frequent, in order to adapt the programme to C-19. Meetings with partners are organised every two weeks to review progress, for risk management and any adjustment of annual work plans that are necessary. This collaboration also helps in identifying areas of mutual interest in influencing policies.
FCDO mandatory requirements (including fraud, safeguarding, VfM, branding guidance, etc) have been shared with all the partners and are part of the subjects for regular updates. A discrepancy between the level of knowledge and the reporting strategy for safeguarding exists for UN partners. The project team has requested advice from the Safeguarding Unit in order to strengthen the reporting of any safeguarding issues.
The health programme team is actively engaged with five partners, three at implementation phase (UN Joint Programme, PSI and Village Reach) and two at closure phase (WHO Emergency Response and UNFPA – Rapariga Biz Programme). The UN Joint Programme was initially expected to end in March 2020 but due to the delays in implementations last year and further delays due to C-19 in the second quarter of this year, an extension of six months was granted.
A new Accountable Grant was signed with Village Reach in October 2019. A Due Diligence Assessment has been undertaken and recommendations are being followed up including compliance with all FCDO corporate requirements.

Quality of financial management
FCDO has established financial management processes and procedures that were followed to ensure all disbursements were initiated only after partners have showed evidence that they have spent previously disbursed funds. The FCDO team provided guidance on financial management to all delivery partners. Implementing partners’ annual work plans and detailed budgets are agreed and approved by FCDO and by the Ministry of Health in specific projects like the UN Joint Programme. The budgets are reviewed and monitored regularly to ensure that they are realistic and cost-effective. One of the parameters is to check financial execution versus programme progress but also how procurement lines are budgeted to avoid big underspends caused by UN advantages in global procurement prices. As set out in the business case, appropriate funding arrangements, disbursement schedules and reporting and monitoring schedules have been established and applied through the period of this assessment.
Two programmes were pivoted to respond to C-19. Funds that were no longer a priority in the context of C-19 such as face-to-face training or community consultations were redirected to activities such as surveillance, contact tracing, procurement of equipment to protect health workers and prevention and control training in health facilities. A table summarising this is set out below:

Programmes pivoted for C-19 Component	Pivoted amount (£)
UN Joint Programme	Total: 1,612,700
	UNFPA: 289,700
	UNICEF: 1,136,000
	WHO: 187,000
WHO Emergency response	480,000

Project Monitoring and Field Visits
The FCDO team have agreed and scheduled regular monitoring activities as part of the project agreements, including review meetings and field visits for beneficiary feedback. Review meetings with implementing partners have been carried out at least quarterly and, in some cases, monthly where deemed necessary to discuss project progress, risk management and VfM. The FCDO team carried out two field visits with implementing partners during the assessed period due to C-19 restrictions. The field visits were important to understand the implementation context, progress and constraints and to meet beneficiaries and government staff. Back to office reports from the field trips informed some programme adjustments such as the need to explore new partnerships in Cabo Delgado due to the new context of insecurity and the need to procure a bigger ambulance boat to support transfer of patients from the Quirimbas Islands to the mainland.
VFM Analysis
NGO suppliers (PSI, Village Reach and Rapariga Biz) who rigorously tracked VfM in the programme have demonstrated good VfM. VfM tracking for the UN was inconsistent across three programmes (Rapariga Biz, Emergency Response and UN Join Programme) even though we know that the UN, for example, benefits from economies of scale in procurement processes for medicines and commodities at the global level to secure lowest available prices at the best quality. It would be useful to compare the procurement costs for ambulances and EmONC kits against procurement agents that charge between 2-5% of total procurement costs. There is also some efficiency in the ability of the UN agencies to provide technical assistance and influence the government at policy level. It was not possible to compare the efficiency of technical assistance between years because the UN do not regularly track this. Further efficiencies were achieved through all implementing partners’ experience with local procurements. PSI and UNFPA ensured that the cost for distributing family planning methods at community level was below the estimated amount.
On equity, the programme continues to focus on increasing access to health services for the most vulnerable (pregnant or breastfeeding women and girls and children under five years of age) through community health workers in remote communities. One of the factors contributing to this has been increasing the proportion of community health workers that are female. However, the programme presented some issues in terms of timeliness regarding the construction of WASH infrastructure in health facilities that has been delayed by almost two years. There were also delays in the reform agenda necessary to strengthen health systems over time. These two factors and the lack of a platform for discussion of the overall Investment Case has undermined some of the programme’s effectiveness.
Recommendations
-FCDO to raise tracking of VfM with the UN at the representational level to ensure that it is consistently tracked across all programmes. For example, have the costs of EmONC kits so that these can be compared against the kits procured by private sector procurement agents.
-FCDO to support the ongoing review of the dialogue structures between the MoH and partners including the establishment of a platform to monitor implementation of the Investment Case.

Date of last narrative financial report(s)	Date: August and September 2020 / UN Joint Programme Vault ID: 56041683/58112815 / PSI Vault ID: 57944330 / VillageReach Vault ID: 58117377/58113037 / WHO Vault ID: 56938779 (Final) / UNFPA Rapariga Biz Vault ID: 57979379/58116450 (Final)
Date of last audited annual statement (s)	Date: August and September 2020 / WHO Vault ID: 57883125 (Final)

Annex I- Progress on the Recommendations from last year

Recommendation linked to Output 1 to 5	Status
1.Use the new Government as of January 2020 to advocate for reducing the effect of the fiscal crisis including the low absorption of health workers into the public system and having a maintenance budget for all districts that received equipment or ambulances.	Ongoing - The National Plan for Development of Human Resources for Health (2016-2025) and Retention Strategy (2018-2022) have been successfully disseminated in all provinces and the MoH encouraged all levels to develop a proposal of Salary Decompression for health technicians and a proposal for Professional Career Development. These documents are part of the reform agenda of the health sector and will lead to high impact in retaining health workers. / The proposed Hospital Equipment Management Plan for all the equipment purchased during the programme has not been prioritised. The UN and Government agreed to set aside funding to hire a consultant to support the development of the plan. This is still relevant as over $3 million worth of equipment has been purchased over the programme lifetime.
2.To advocate with the World Bank and other partners for the UN to maintain or even expand their technical assistance role in the sector.	Achieved - The UN have maintained their technical assistance to the CHWs and advocated strongly for their addition into the government system as state agents. This is under discussion with the Ministry of Economy and Finance.
3.Continue advocating for Mozambique to be reclassified by WHO so that the country gets additional resources for emergency preparedness.	Not achieved - Discussion and emails have been sent to ensure Mozambique is reprioritised as a country with priority 2 versus 3. This is an internal decision to WHO but escalating it to FCDO in Mozambique and UK could be useful
4. Agree an exit strategy for the Emergency Preparedness Project and UN Joint Programme with the UN agencies.	Achieved - Through discussion with partners like the World Bank who are managing the Global Financing Facility project (GFF) to support the RMNCAH investment case but also with the buy in and active participation of the government.
5. The UK must explore with UNFPA and other actors in the family planning sector how to improve coherence in the sector	Achieved - UNFPA were more proactive in over the last year by collaborating with other partners to resolve issues and keep SRHR services going in the context of COVID-19.
6. Continue to discuss safeguarding with the UN so that they are more proactive at sharing any incidents in the programmes.	Ongoing - Discussions with the UN have been ongoing. The project team has requested advice from the Safeguarding Unit in order to strengthen the safeguarding process.
7. Track how long UNFPA take to disburse to the other UN agencies by including this in the value-for-money (VfM) matrix.	Ongoing - This indicator has been inserted into the VfM matrix. However, we do not have updated figures to track if there have been improvements.
8. WASH and Health teams to work together to accelerate the implementation of WASH in health centres	Not achieved - This has not happened due to a change in the health and WASH teams at UNFPA since November 2019. All team members were in place by July 2020.