Annual Review Template – from April 2020

Title: Reducing Maternal and Neonatal Deaths in Kenya
Programme Value £ (full life): £64.69m		Review date: Oct 2020
Programme Code: 202549	AMP start date: 14/11/2013	AMP end date: 31/03//2023

Summary of Programme Performance
Year	2013/2014	2014/2015	2015/2016	2016/2017	2017/2018	2018/2019	2019/20
Overall Output Score	B	A	B	B	A	B	A
Risk Rating	Medium	Medium	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case: / DevTracker Link to BC addendum:	https://devtracker.fcdo.gov.uk/projects/GB-1-202549/documents / https://devtracker.fcdo.gov.uk/projects/GB-1-202549/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-1-202549/documents

A. SUMMARY AND OVERVIEW

Description of programme

The Reducing Maternal and Neonatal Deaths in Kenya programme (referred to as the Maternal and Newborn Health (MNH) programme) supports the delivery of essential health care to pregnant women and new-borns. It focuses on: i) improving the knowledge and skills of health workers to provide emergency obstetric and neonatal care (EmONC); and ii) improving the capacity of counties to plan and budget for health services and support health service delivery through their own budgetary allocation. The original programme budget was a £75.3 million over five-years (2013-2018), however following a DFID-wide Portfolio Quality Review (PQR) in 2017, the budget was reduced to £60.6 million. Following a five-year cost extension in 2018 (to March 2023), the budget was increased to £64.6 million.

The current phase of the programme is implemented through three partners: (i) the Liverpool School of Tropical Medicine (LSTM); (ii) Marie Stopes International/ Options Consultancy (Options); and, (iii) a Multi-Donor Trust Fund (MDTF) managed by the World Bank (WB). Funding to Program for Appropriate Technology in Health (PATH) to set up the first regional human milk bank in Kenya ended in November 2019. This annual review covers the period November 2019 to October 2020 and the three partners indicated above who implemented activities during the reporting period.
[note] Other donors to the MDTF are United States Agency for International Development (USAID) and Danish International Development Agency (DANIDA)

Key challenges in the review period

Covid-19 pandemic. The pandemic impacted the programme in several ways: i) movement restrictions as well as prohibitions on meetings, impacted negatively on training of health workers and on service delivery; ii) health workers were diverted from routine services to support the Covid-19 response; and iii) containment measures (including movement restrictions and a curfew) put in place by the Government, prevented pregnant women from accessing services in health facilities. This resulted in a decline in many health indicators and even though the utilisation subsequently improved following clarification that restrictions did not apply to accessing health services, in most cases, the indicators remain below levels of previous years.
.
County revenue allocation challenges. Insufficient financial allocation and delayed disbursement of funds from National Treasury to counties are major challenges. During the period under review, counties experienced significant delays in disbursement of funds from the National Treasury which was made worse by increased demand due to the Covid-19 pandemic. Many counties experienced health worker strikes and go-slows because of delayed payment of salaries and lack of personal protective equipment. At the time of review, counties were yet to receive their disbursements for Quarter 1 of the 2020/21 Fiscal Year (July 2020 – June 2021). These delays make it difficult for counties to deliver essential health services.
Summary supporting narrative for the overall score in this review

The programme performed well during the period under review and is assessed to have met expectations. However, improvements are required, especially in activities relating to sustainable financing, for the programme to achieve the desired outcomes and impact. Achieving financial sustainability beyond the life of the programme will require concerted efforts at both national and county level and should include high level engagement between the senior leadership at the High Commission and relevant officials in national and county government. It will also require collaboration with the work of the Public Finance Management (PFM) task team of the Development Partners Group (DPG) and the new FCDO Devolution Support Programme. This review provides recommendations on the changes necessary to maximise on the long-term impact of this programme.

While a few milestones were not achieved, most were achieved or surpassed. Interactions with health workers and county health management teams during this review confirmed the good performance of the programme and the impact it is having in improving the quality of maternal and newborn health services. It is commendable that the programme met expectations while also supporting the Covid-19 response and dealing with its negative impacts. The pandemic and associated containment measures affected both service delivery and access to services. For example, health workers were diverted from maternal and newborn health services to support the response and pregnant women could not access health facilities due to movement restrictions, stigma and fear of contracting Covid-19. However, on a positive note, the programme provided infection prevention and control supplies to some health facilities.

Major lessons and recommendations for the year ahead

Financial planning, budgeting and monitoring at county level is not enough: all counties reported that allocations from the National Treasury are constrained and disbursements often come late. Consequently, even with the best workplans and budgets, counties are still not able to provide essential health services. This review period was particularly difficult for counties – the Covid-19 pandemic affected counties’ own revenue generation, making them more reliant on allocations from the National Treasury. To ensure counties can sustain delivery of health services, it is important that: i) they have the capacity to plan, budget and monitor the utilisation of allocated resources; ii) bottlenecks to timely and effective fund flow from National Treasury to the counties and from the county funds to respective health facilities are addressed; and, iii) the overall allocation to counties is increased.

Partners should consider what counties can sustain in designing their activities: The review noted that the amount of resources partners are spending to facilitate some activities is high and counties will struggle to sustain them. For example, partners are providing transport and meal allowances for participants in mentorship programme. County health management teams met during this review confirmed that they will struggle to pay these allowances seeing as they are already struggling to pay salaries in time. The key lesson here is that partners need to be realistic and practical about what is affordable to counties to ensure smooth transition of activities from partner support.

Major recommendations for the year ahead:

1. FCDO should revise the Theory of Change by April 2021 to reflect concerns with GoK financing and engagement for MNH interventions supported under this programme.
2. FCDO and partners should review the various components and geographic locations to ensure complementarity of the different components and to consolidate resources where appropriate by April 2021.
3. FCDO and partners to review output indicators the contribution of all partners and any changes from (1) above by April 2021.
4. LSTM should document and disseminate the lessons learnt from the successful review of the Kenya Medical Training College (KMTC) curriculum to incorporate EmONC training by September 2021.
5. The Planning, Budgeting, Monitoring and Reporting (PBMR) element of the MDTF should seek to address bottlenecks at all stages of funds flow from national treasury to the health facility.
6. FCDO should have high level (High Commissioner and Development Director) engagement with relevant government departments to raise issues of PFM and bottlenecks to timely funds flow from national treasury to the counties and on to health facilities.
7. LSTM and Options should ensure the quality of care assessment tools are integrated into the Kenya Health Information System by September 2021 and capacity for analysis strengthened at facility, sub-county and county levels as appropriate.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The outputs in the Theory of Change (ToC) were revised as part of a cost extension in 2018. The extension sought to put greater emphasis on building sustainable capacity to deliver quality MNH services at national and county level. This is to be achieved through institutionalising systems and increasing domestic financing for health to reduce dependence on external support. The extension targeted health workers and county health management teams in counties with the worst MNH indicators, aiming to ultimately benefit pregnant women and new-borns.

The intended impact (reducing maternal and child mortality in Kenya) and outcome (increased and sustainable availability of quality MNH services) remained unchanged in the 2018 revision. The revised outputs included: sustainable health sector financing and strengthened systems at national level; increased county capacity to plan, budget for and manage MNH services; improved health worker knowledge and skills; institutionalised training, mentoring and monitoring of quality of MNH care; and, testing and dissemination of innovative approaches and interventions to address barriers to increasing access to and demand for MNH care.

The ToC logic and evidence on improving quality of MNH care remain valid and the programme is achieving its intended outcomes – skilled birth attendant rate has improved, number of facilities providing Basic and Comprehensive Emergency Obstetric and Newborn Care (BEmONC and CEmONC) services has exceeded expectation and obstetric case fatality rate has reduced. The programme continued to perform well even with the backdrop of the Covid-19 pandemic. Kwale county, for example, reported increased maternity services utilisation during the pandemic, as women feared that they could contract the disease from traditional midwives and chose to deliver in hospitals instead.

However, assumptions about domestic financing and counties’ ability to allocate resources for MNH services as well as assumptions about institutionalisation of mechanisms to ensure quality MNH services are not holding. County allocations from the National Treasury are constrained and, in most cases, disbursed late (at the time of review, counties had not received their allocations for Financial Year starting July 2020). Due to many competing priorities, counties are struggling to meet the recommended 30% allocation to health and most of their health allocations (almost 70% in counties like Kwale) go to personnel and operations/maintenance costs, leaving little to recruit necessary additional staff or support new interventions. As a result, interventions such as mentorship, reviews of maternal and perinatal deaths, development of annual work plans and even engagement with the county planning and budgeting process rely heavily on financial support from partners. This raises questions about the ability of counties to maintain these activities, which given high staff turnover, are important for sustaining the expected outcomes and impact of the programme.
[note] This target was recommended by the World Bank based on a 2018 assessment that found that, on average, counties allocated 21% of their budgets to health.

During the year under review, the programme seconded a health specialist/adviser to the World Bank to support the implementation of maternal health-focused activities under MDTF. The adviser is leading the Bank’s engagement with the Department of Family Health on RMNCAH including the Bank’s project that is supporting the MoH to develop a sustainable blood supply system. This will contribute to the achievement of the outcomes of this programme.

Supporting Maternal and Perinatal Death Surveillance and Reporting (MPDSR) at both national and county levels is a key aspect of this programme contributing to outputs 1 and 2. At national level, the programme supported the establishment of the MPDSR secretariat within the Department of Family Health in the Ministry of Health in 2016 and continues to support the operations of the secretariat. At county level, the programme supports the establishment of county, sub-county and health facility MPDSR committees and continues to facilitate their functionality by supporting review meetings and implementation of actions arising from the reviews, including health worker training and equipping health facilities. A functional national MPDSR secretariat and functional sub-national MPDSR committees are key to improving the quality of MNH services but, after more than four years, remain heavily dependent on the programme with little financial commitment from national and county governments.
[note] MPDSR is an approach aimed at improving quality of care for maternal and neonatal health by identifying the underlying causes of maternal and neonatal deaths and developing targeted interventions to address them.

However, those interventions that do not require much financial commitment from the government, are progressing well. For example, KMTC nursing and clinical medicine curriculum has been reviewed to include Emergency Obstetric and Newborn Care (EmONC). The new curriculum is expected to result in a better trained health workforce and improved quality of maternity services, without the need for further external support. Given that KMTC contributes about 85% of the middle level health workforce in Kenya, this will contribute significantly to sustainable health worker knowledge and skills development.
[note] KMTC website: https://kmtc.ac.ke/about-kmtc

While the programme has been successful and continues to overall provide, good value for money in increasing the availability of quality MNH services (demonstrated by improved indicators and quality of care assessments), there are interventions that are heavily supported and that counties will struggle to sustain after the programme ends.

The emphasis of sustainability of interventions is important and domestic financing is key. Because addressing the bottlenecks in domestic financing is beyond the scope of this programme, the theory of change and indicators should be revised to reflect parameters that the programme has influence over.

Recommendations:

FCDO to facilitate a review of the Theory of Change and the various interventions by April 2021 to determine:
1. Those that are sustainable and agree transition plans before the next review.
2. Those that are not sustainable as currently implemented but can be tweaked to make it easy for counties to take up and sustain when the programme ends.
3. Those that are not sustainable as currently implemented and cannot be tweaked. These should be dropped, and the resources allocated to support (a) or (b) above.

Recognising that ensuring sustainable financing is beyond the remit of this programme, FCDO and partners should work closely with FCDO’s new Kenya Devolution Support Programme (KDP) and the PFM task team of the DPG.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is delivering on two out of three outputs and remains on track to achieve its outcome of improving quality of MNH services and impact of reducing maternal and neonatal mortality. However, progress on the third output on improved capacity to plan, budget and manage MNH services is slow. The third output is crucial for sustaining the outcomes of the programme and expected impact. Most of the achievements on outputs 1 and 2 and the expected outcomes are due to heavy facilitation and funding by the programme and other donors.

Counties will find it difficult to sustain the interventions with their current level of resourcing and are unlikely to do so during the life of the programme. To address this, the programme will work closely with other initiatives aimed at supporting PBMR and PFM in general. Specifically, the programme will make use of the PFM task team currently co-chaired by FCDO to lobby the National Treasury and other relevant institutions to address funds flow concerns. The programme will also work closely with the FCDO’s new Kenya Devolution Support Programme (KDP) to ensure the respective PBMR activities are complementary.

Meanwhile, the programme will continue supporting counties to develop quality and evidence-based annual work plans (AWP) that are aligned to county resource planning, budgeting and allocation. At the same time, interventions will be adjusted to a level that counties will be able to afford and sustain. Where possible, plans for phasing out partner support should be agreed with relevant levels of government (national and county) before the final year of the programme.

Additionally, in the year ahead, the programme will review interventions and the geographical spread with a view to consolidating resources and focusing on interventions that are likely to have the greatest impact on the objectives of the programme and which the counties will be able to sustain. The programme will also revise the theory of change considering lessons around domestic financing for sustainability to ensure the programme ambition is realistic.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

This programme should continue because it is performing well against indicators and contributes to FCDO Kenya Country Business Plan’s strategic priority on sustainable development (reducing maternal and neonatal deaths) and the Sustainable Development Pillar of the UK - Kenya Strategic Partnership agreement. Through interventions like the curriculum review for pre-service training and mentorship programmes, it continues to represent good value for money. However, some adjustments are necessary to ensure greater complementarity between the different components and to consolidate resources on the interventions that will have the greatest impact and can be sustainable beyond the life of the programme.

## C. DETAILED OUTPUT SCORING

Output Title	Improved health worker knowledge and skills and sustainable systems for training and mentoring
Output number:		1	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress	Score
1.1: Number of health workers trained in EmONC skills (i) pre-service and (ii) in-service	(i) 32 (ii) 220	(i) 12 (ii) 381	A++
1.2: Numbers of (cumulative) pre-service-tutors trained to deliver EmONC training	National – 120 / Counties – 32	National – 59 / Counties - 12	B
1.3: Number of pre-service institutions delivering competency based EmONC training within the pre-service curriculum for (i) nurses, (ii) clinical officers.	33	35	A
1.4: Proportion of counties meeting at least 70% of training costs	100%	40%	C

Output 1 was designed to establish sustainable systems for improving health worker knowledge and skills through training and mentorship. LSTM is delivering pre-service training through the network of KMTC campuses across the country. Both LSTM and Options deliver in-service training through structured EmONC training sessions and through on-job mentorship. For sustainability, counties are expected to progressively increase their contribution to meet the training costs. Overall, this output is assessed to have met expectation and scores A.

Output indicator 1.1: EmONC training is a skills-and-drills competency-based training combining theory, practical demonstrations (on dummies) and supervised clinical work. The training is targeted at trainee health workers (pre-service) and health workers providing maternal and child health services (in-service). Whether delivered pre-service or in-service, the training is the same and imparts the same skills.

The pre-service component includes initial training of master trainers in five regional KMTC centres who are then expected to roll it out as part of the syllabus for the revised curriculum. The low achievement (12 trained against a target of 32) is due to closure of learning institutions as part of the containment measures against the spread of Covid-19 pandemic. The revision of the KMTC nursing and clinical medicine curriculum is an important achievement that will institutionalise quality improvement through health worker training. KMTC contributes about 85% of the middle level healthcare workers in the country. This achievement will also contribute to significant cost savings by reducing the need for in-service training and the associated high costs (financial and time healthcare workers are away from work attending trainings).

The in-service component is delivered through mentorship, where trained mentors train and supervise mentees based on identified training needs for the individual mentee or health facility nominating the mentee. Options and LSTM employ different approaches to mentorship.

LSTM’s approach seeks to improve the quality of care in selected high-volume facilities (five per county) with both the mentor and mentee coming from the same facility. The facility management determines which health workers need to be mentored and on what aspects of EmONC services, based on periodic data review and observations. Training is generally done through theoretical presentation, practical demonstrations using mannequins/ dummies and supervised clinical application. Mentees' performance is assessed on a monthly basis using a health facility log sheet which outlines actions to be undertaken by mentor and mentees. The actions are tracked monthly and followed up for completion

Options’ approach aims to improve the quality of care at peripheral facilities and reduce unnecessary referrals to high volume facilities. The sub-county health management teams (SCHMTs) identify training/ mentoring needs through MPDSR reviews. Identified facilities nominate health workers who are then assigned to trained mentors based at the high-volume facilities. Each mentor has an individual logbook that is used to assess their mentoring needs at the beginning and used to assess their mentorship progress. Mentees typically go through 10 – 15 sessions over a 3-month period.
In both approaches, county health teams and healthcare workers interviewed for this review appreciated that mentorship is relatively low-cost and provides hands-on capacity strengthening and credited the mentorship programme for improving quality of care. The quarterly assessments conducted by both LSTM and Options show improvement in quality of care. However, due to workforce constraints, both mentors and mentees are not able to take time out so end up training during their time off when they are meant to be resting. This raises concerns about potential health worker burnout that is detrimental to the welfare of the health workers and for patient care. This could undermine the very quality of care that the programme seeks to improve.

Despite these concerns, the programme has over-achieved on this indicator with a total of 393 health workers trained against a target of 252. The output substantially exceeded expectations and scores A++. While the pre-service activities were interrupted by closure of colleges due to Covid-19, numbers trained through the Options mentorship programme enabled the programme to over-achieve on this indicator.

Output indicator 1.2: The master trainers under indicator 1.1 were expected to cascade the training nationally to tutors across the network of 47 KMTC centres. The roll out of the trainings began in March 2020 with some 50 tutors before the Covid-19 restrictions came into effect. While the practical aspects of the training remain on hold until the restrictions are lifted, it is commendable that the partner found ways to deliver the theoretical training virtually. The indicator was on track during the first half of the review period before Covid-19 disruptions. Therefore, even though the programme only achieved 47% of the milestone under this indicator, the progress made is assessed to be satisfactory and the indicator is scored B. We are confident that the programme will deliver once colleges reopen.

Output indicator 1.3: The programme has supported capacity strengthening in 35 colleges (against a target of 33) to integrate the updated curriculum into midwifery and clinical medicine – reproductive health education programmes. Because of the current closure of all learning institutions, no pre-service institution is currently delivering any training but at the time of the review, the government had started easing the restrictions on learning institutions. This output met expectation and scores A.

Output indicator 1.4: This indicator tracks the ability of counties to meet part of the cost of EmONC training for their staff. This year only two counties (Uasin Gishu and Kilifi) met at least 70% of the cost of training for their staff. This is a reduction from last year’s three (Kilifi, Garissa, and Uasin Gishu). All counties cited delays in receiving their allocations from the national treasury as a major impediment to their operations. At 40%, this output did not meet expectation and in fact represents a drop from last year’s achievement of 60%. The indicator is therefore scored C.

Remedial measures: Options will continue supporting the target counties in developing annual work plans through a bottom-up approach to ensure training costs are appropriately budgeted for. Timely funds flow is key for the success of this intervention. This calls for concerted effort especially by PBMR element of the MDTF, Options and FCDO to address the bottlenecks in funds flow to the counties.

Progress on recommendations from the previous AR (if completed), lessons identified this year, and recommendations for the year ahead linked to this output:

The recommendation on fast tracking the approval of the revised curriculum has been successfully actioned. Health worker retention strategy and appropriate action plans have been agreed between LSTM and four out of five counties.

Going forward, it is recommended that:

1. For the next review, the target for indicator 1.1 be revised to factor Options’ contribution to in-service training through the mentorship programme.
2. LSTM document their experience and lessons learnt in successfully reviewing the KMTC curriculum and share with other health sectors like nutrition that are also grappling with the challenge of high cost of in-service training and interruptions to service delivery when health workers go on training.
3. LSTM and Options discuss with counties how mentors and mentees can undertake mentorship as part of their core duties without having to forfeit their time off to undertake mentorship.
4. All three programme partners and FCDO do more in engaging the counties to institutionalise resource allocation so that partners do not have to lobby for the same issues every year.
5. The MDTF component, through the PBMR element, consider supporting interventions to address challenges to funds flow from the national treasury to minimise disruptions in county operations and allow timely implementation of activities.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

The Business Case did not look at VfM metrics at output level, this has only recently been introduced to the Annual Review template. Under this output, economy was achieved in training by using institutional training facilities instead of hotels, eliminating the need to pay for training venues. The use of in-country faculty (local trainers) as opposed to international trainers further reduced the cost of travel and allowances. Peer reviews were also done virtually. As a result, the per capita cost of training reduced from £500 to £263 on average. Efficiency gains have also been made by working with counties to provide quality assurance of the trainings and the cost-share model, where counties and other partners contribute to the training cost. This cost sharing model resulted in savings of £17,693 which were reprogrammed to other activity budget lines. The programme has also promoted equity by benefitting women and young children from disadvantaged communities whose health outcomes are worse than the rest of the population. Trend analysis of data in the Kenya Health Information System shows improvements in skilled delivery and reduced maternal and perinatal deaths in target counties. The Kenya Demographic and Health Survey will give a better picture of progress made in this indicator at national and county levels.
[note] The Kenya Demographic and Health Survey is conducted every 5 years. The last one was in 2014. The next was due in 2019 but this was postponed due to concerns of survey fatigue following the 2018 national census. No date has been provided for the next KDHS.

Describe any changes to this output, and any planned changes as a result of this review.
The only change envisaged in this output is revision of indicator 1.1 targets to include Options contribution.

Output Title	Increased county and facility capacity to monitor and use data to improve MNH quality of care
Output number:		2	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress	Score
2.1. Percentage of (i) maternal deaths and (ii) perinatal deaths (facility level) for which review forms are submitted to the DHIS2 and (iii) % of health facilities that have made required adjustments to service provision or management practices based on MPDSR (17 counties: 9 WB, 4 Options, and 5 LSTM)	WB: / W. Pokot: (i) 100%; (ii) 22% / Bungoma: i) 100%; ii) 76% / Marsabit: (i) 87%; (ii) 40% / Samburu: (i) 85%; (ii) 30% / Garissa: i) 90%; ii) 7% / Lamu: (i) 60%; (ii) 20% / Mandera: (i) 71%; (ii) 20% / Tana River: (i) 80%; (ii) 30% / Wajir: (i) 84%; (ii) 30% / LSTM: / Uasin Gishu: i) 95%; ii) 6%; iii) 50% / Kilifi: i) 100%; ii) 9%; iii) 50% / Garissa: i) 90%; ii) 7%; iii) 50% / Vihiga: i) 95%; ii) 9%; iii) 25% / Taita Taveta: i) 90%; ii) 6%; iii) 50% / Options: / Kericho: i) 60%; ii) 30%; iii) 50% / Nandi: i) 60%; ii) 30%; iii) 50% / Kwale: i) 60%; ii) 30%; iii) 50% / Mombasa: i) 60%; ii) 30%; iii) 50%	WB: / W. Pokot: (i) 100%; (ii) no data / Bungoma: i) 95%; ii) 71% / Marsabit: (i) 50%; (ii) no data / Samburu: (i) 100%; (ii) 26.8% / Garissa: i) 100%; ii) 25.7% / Lamu: (i) 80; (ii) no data / Mandera: (i) 33.3%; (ii) no data / Tana River: (i) 50%; (ii) no data / Wajir: (i) 33.3%; (ii) no data / LSTM: / U/Gishu (i)100% (ii) 8.9% (iii) 86% / Kilifi (i) 96.2% (ii)9.8% (iii)67% / Garissa (i)100% (ii)28% (iii)89% / Vihiga (i) 100% (ii) 34% (iii)91% / T/Taveta (i)100%; (ii) 40.8% (iii)80% / Options: / Kericho: i) 100%; ii) 41%; (iii) 18% / Nandi: i) N/A; ii) 82%; iii) 56% / Kwale: i) 86%; ii) 40%; (iii) 26% / Mombasa: i) 75%; ii) 46%; iii) 13%	B
2.2. Number of counties with capacity to conduct facility readiness assessment	3	9	A++
[note] District Health System Software 2 – this is the MoH health information management system

Output 2 seeks to institutionalise the use of data to improve quality of MNH services. All counties are expected to review maternal and perinatal deaths and submit the reviews with other health data into the DHIS2. Counties are expected to address any issues raised or gaps identified in the reviews and to have the capacity to assess the readiness of health facilities to provide EmONC services. Both output indicators are equally important and are therefore weighted the same. This review finds this output to have met expectation and scores A.

Output indicator 2.1: Progress against the three sub-indicators under this output indicator is mixed. The low reported achievement by Options on sub-indicator iii (% of facilities that responded to issues identified by MPDSR) is due to the fact that they use the total number of facilities supported (70) as the denominator instead of only those facilities for which MPDSR raised issues. Data on perinatal death reviews submitted to DHIS2 for six counties is missing and another five sub-indicators were below target. Overall, 34 out 45 (76%) of the targets were achieved. This indicator is therefore assessed to have moderately not met expectation and scores B.

One of the major issues identified through the MPDSR reviews that the programme has sought to address is inadequate blood transfusion services. Kenya experienced a critical shortage of blood and blood products in October 2019 through to early 2020, prompting the need for a comprehensive assessment of the situation. The shortage was linked to the end of US funding to the Kenya National Blood Transfusion Services.

The World Bank, through the MDTF, facilitated an assessment of the situation to explore and identify any underlying challenges, and opportunities through a health systems lens to strengthen the blood transfusion services in Kenya. The World Bank has provided $10 million funding to the MoH this year to support the strengthening of the blood supply system through the COVID-19 emergency project. The FCDO-seconded health specialist/adviser is leading this work for the World Bank.

Options also conducted a rapid assessment of the capacity to collect, store, screen and utilize blood and hemovigilance processes in Kericho, Kwale, Mombasa and Nandi. Informed by the findings of the assessment, Options developed and delivered a haemovigilance training to over 120 health care workers and facilitated cross-county learning between Nandi and Kericho counties. They also supported blood donation drives through outreach and procured a test kit for Msambweni Satellite Blood Centre. Options is engaging the four counties to ensure the blood equipment and supplies activities are integrated in their annual work planning priorities and budget. Lastly, Options engaged the Kenya National Blood Transfusion Services (KNBTS) to address challenges with blood transfusion services at national level and to push for the revision of legislation/policy to allow county blood transfusion centres to screen blood.
[note] set of surveillance procedures covering whole transfusion chain from the collection of blood and its components to the follow up of its recipients to collect and access information on unexpected or undesirable effects resulting from the use of blood and blood products.
[note] The current policy requires that all blood samples are sent to Nairobi for screening which typically takes a few days. Lives have been lost as county blood transfusion centres wait for screening results from Nairobi.
Output indicator 2.2: Four counties (Kericho, Kwale, Mombasa and Nandi) have been supported to conduct EmONC facility readiness assessments using the Options’ Quality of Institutional Care (QuIC) assessment tool. Another five counties (Uasin Gishu, Kilifi, Garissa, Vihiga and Taita Taveta) are supported in conducting quarterly facility assessments using the LSTM’s EmONC Functionality Assessment (EFA). The assessments identify gaps and provide recommendations on what actions are required to address them. Healthcare workers confirmed assessments to be useful and provided examples of changes that had been made to address issues identified by the assessments. The review notes that both assessment tools are owned by the respective partners. While the QuIC assessments are conducted at facility level and health workers play a role in the analysis, the EFA analysis is undertaken in the UK and reports generated and shared with facilities every quarter. Discussions are ongoing at national level to determine what components of quality of care assessments should be integrated into DHIS2.

The over-achievement of this indicator is due to the milestone being determined with only one partner (LSTM) in mind. However, when Options conducted needs assessments in their target counties, this was identified as a gap. For this review the indicator is assessed to have substantially exceeded expectations and scores A++.

Progress on recommendations from the previous AR (if completed), lessons identified this year, and recommendations for the year ahead linked to this output:

Implementation of last AR’s recommendations – support for MPDSR, supporting counties to conduct facility readiness assessments, high level advocacy on funds flow from national treasury to counties and using MPDSR findings to lobby for budget allocation - on this indicator is an ongoing process. Going forward, it is recommended that:

1. FCDO ensures the formula for calculating achievements be consistently applied across all partners and partners should report against all sub-indicators.
2. The target for indicator 2.2 be revised upwards to reflect the increase in number of counties targeted.
3. For sustainability, the assessment tools be integrated into the DHIS2 where possible and health worker capacity strengthened to conduct these assessments without external help. Programme partners are encouraged to engage with the ongoing national dialogue on this integration.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

This output focuses on the counties’ capacity to monitor and use MNH data to improve quality of services. The programme provided technical support to establish and facilitate the MPDSR committees to function in 17 counties. While the Business Case did not look at VfM metrics at output level, the partners achieved economy following the outbreak of Covid-19 by shifting from physical to virtual meetings. The average cost of holding a meeting went down from £880 to £450. The savings were used to support virtual monthly mentorship and MPDSR meetings at the facility level. Participant feedback from an online evaluation indicated that the quality of the virtual meetings was just as good as the physical ones. In fact, most participants preferred the online training. Further, savings of £10,748 from the pre-service curriculum review, will support the mentoring of pre-service lecturers to implement the updated curriculum. Efficiency was achieved through stakeholder meetings, such as MPDSR Committee meetings, which were supported during the period under review. Through periodic review and timely feedback on the accuracy and completeness of data from facilities, the stakeholder meetings have resulted in better quality of data. The data provided by facilities is used to identify and address capacity gaps. This motivates health workers to provide quality data which has improved the understanding of underlying challenges and strengthened obstetric emergency preparedness and management of obstetric and neonatal complications.

Describe any changes this output, and any planned changes as a result of this review. No changes planned.

Output Title	Increased county capacity to plan, budget for and manage MNH services
Output number:		3	Output Score:	B
Impact weighting (%):		40%	Weighting revised since last ARA?	No

Indicator(s)	Milestone(s) for this review	Progress	Score
3.1. Proportion of counties allocating at least 30% of budget to health (WB only)	5 counties	7 counties	A
3.2. Percentage of facilities reporting stockouts of lifesaving MNH commodities (WB only)	40% in 9 counties	West Pokot – 86%; Bungoma – 50%; Marsabit – 80%; Samburu – 36%; Garissa – 76%; Lamu – 67%; Mandera – 68%; Tana River – 57%; Wajir – no data	C

Output 3 is about strengthening the capacity of County Departments of Health (CDoH) to engage with the planning and budgeting process to ensure that counties allocate adequate resources for health including essential commodities. While the programme overachieved on the indicator relating to allocation of budgets to health, this has not translated to availability of essential MNH commodities or increased capacity to undertake crucial quality improvement activities like trainings. This output is therefore scored B.

Output indicator 3.1: The programme is providing technical assistance (TA) to support County Departments of Health (CDoH) to develop quality and evidence based annual work plans (AWP) aligned to county resource allocation. The TA was aligned to the country planning and budgeting calendar. Among other things, the TA included public expenditure review and tracking and political economy analysis of the planning, budgeting, monitoring and reporting (PBMR) process. The programme, through the MDTF component, supported county health sector annual performance reviews (APR) in 18 counties and the development of county health sector annual work plans in those counties (17 AWPs were published in time). During the year under review, Options received additional funding for health system strengthening, part of which they used to support AWP development in Mombasa, Kwale, Nandi and Kericho. While, the milestones for this indicator have been exceeded, it is worth noting that none of the six World Bank supported counties (Embu, Kajiado, Kiambu, Kisii, Machakos and Meru) that met the 30% threshold are in the list of nine priority counties that were identified as having the worst MNH indicators. As such this indicator is assessed to score A. Going forward, it is important that this output pays more attention to the counties with the greatest needs.
[note] The MDTF provided TA to two groups of counties:(i) nine priority counties (Bungoma, Garissa, Lamu, Mandera, Marsabit, Samburu, Tana River, Wajir and West Pokot) with the worst MNH indicators and (ii) nine target counties (Embu, Kajiado, Kiambu, Kisii, Machakos, Meru, Murang’a, Nyamira and Uasin Gishu) selected based on capacity gaps in PBMR.

Domestic financing is key for the sustainability of health service delivery and other interventions supported under this programme. The PBMR TA has had promising results in increasing budgetary allocations to health and improved monitoring of budget execution and tracking of public expenditure in some counties. This success is partly due a better understanding of the political dynamics as a result of the political economy analysis (PEA) the World Bank conducts to better understand how to leverage ownership and support for sound and quality PBMR processes and outputs. The World Bank reports that counties supported under this component outperform other counties in many aspects of public finance management. There is, however, a disconnect between the counties targeted by the service delivery components of the programme and those targeted for PBMR support under the MDTF. Out of 27 counties supported by the programme, only one county (Garissa) is targeted for both service delivery and PBMR support.

But successful budgetary allocation is not enough if there are delays in disbursement of funds through the different steps in the funds flow. It is therefore important that efforts to support planning and budgeting are complemented by efforts to address bottlenecks in funds flow.

Output indicator 3.2: Under this output, the programme is providing technical assistance to strengthen county supply chain systems for reproductive, maternal, newborn, child and adolescent health (RMNCAH). The Supply Chain Management (SCM) for Health Products and Technologies (HPT) thematic area of the MDTF component supported: i) operationalisation of Commodity Security Technical Working Groups (CS TWG) at county level to strengthen governance mechanisms for HPTs; ii) training of health workers on quantification to strengthen county capacity for commodity management; iii) quantification, forecasting and supply planning; and, iv) deployment of a mobile solution for commodity management, reporting and requesting in 11 counties. This output seeks to minimise stockouts of essential commodities. This requires that counties allocate resources but also that KEMSA, the sole health supplies agency for counties, can supply the counties.

During the period under review, only one county (Samburu – 36%) had less than 40% of facilities reporting stockouts of essential commodities. This underachievement is attributed to four key factors: i) counties not prioritising RMNCAH commodities in their budgets; ii) KEMSA not servicing routine orders because it prioritised the four UHC pilot counties at the expense of other counties; iii) Even after the UHC pressure eased off, KEMSA could service the MDTF target counties because all of them, except Samburu and Tana River, had pending bills; and, iv) KEMSA prioritising Covid-19 response over RMNCAH commodities once the pandemic was confirmed in Kenya.

With only one out of nine counties reaching the milestone, this output indicator is scored C. This is the second year in a row this indicator substantially fails to meet expectations.

Remedial measures: To address the situation, the supply chain TA will collaborate with the PBMR TA and with other SCM partners to create synergies that will contribute towards increasing the availability of RMNCAH commodities. Further, the Supply Chain TA team has already joined the KEMSA Immediate Action Plan & Medium-Term Reforms Working Committee whose terms of reference include devising strategies to address the shortage of essential medicines and commodities at KEMSA.

Progress on recommendations from the previous AR (if completed), lessons identified this year, and recommendations for the year ahead linked to this output:

Implementation of the recommendation on high level advocacy with MoH and National Treasury on funds flow to counties and how the FCDO Kenya Devolution Programme can support the same are ongoing. Going forward, it is recommended that:

FCDO should have high level (High Commissioner and Development Director) engagement with relevant government departments to raise issues of PFM and bottlenecks to timely funds flow from national treasury to the counties and on to health facilities.

Given the importance of improved county budget allocation for health in ensuring sustainability of interventions programme interventions, FCDO and partners should review the geographical overlap between the service delivery components and the MDTF PBMR elements to ensure greater complementarity.

Indicator 3.1 should put emphasis on progress made in the nine priority counties.

Despite the remedial measures outlined above, FCDO and the World Bank should, by April 2021, examine the utility and justification for continued implementation of the SCM/HPT element of the MDTF component since this is the second year in a row that indicator 3.2 performs poorly.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

This output focuses on building the capacity of the counties through high quality technical assistance. While the Business Case did not look at VfM metrics at output level, the main VfM proposition under this output is effectiveness. This has been achieved by counties being able to develop evidence-informed annual work plans and budgets which have resulted in better prioritisation and resourcing of health interventions. This is a positive step towards sustainability as the programme continues to advocate for full transition to government funding. However, more needs to be done to ensure essential commodities are prioritised and that KEMSA has the capacity to support routine health programmes even during surge in demand as happens during outbreaks like Covid-19.

Describe any changes to this output, and any planned changes as a result of this review. This review recommends that PBMR component should be aligned to support counties targeted with service delivery and that the justification for the SCM/HPT element of the programme be reconsidered. The former will result in revision of targets while the latter may result in indicator 3.2 being dropped.

D: RISK

Overview of risk management

Overall risk rating for the programme has been maintained at Moderate. This is within the overall risk appetite for the programme. FCDO has a risk management policy in place that aims to ensure the effective mitigation of risks that could otherwise prevent FCDO from achieving its strategic objectives. The programme team meets implementing partners quarterly to discuss risks and update the risk registers. The implementing partners continuously identify, monitor and mitigate against risks that may impact on programme implementation at national and sub-national level. All partners implement directly. Further, all the current partners have their individual risk registers that are reviewed and updated quarterly.

Key risks of concern include:

Key Risk	Mitigation Strategy /Risk category
Delivery/Operational
Reduced access to quality MNH services due to Covid-19 restrictions and disruptions.	Implementing partners are working with counties to sustain community awareness on service availability and sending out communication of re-designation of service centres. / Implementing partners have supported national MoH to develop / adapt international guidelines on Covid-19 and to deliver and implement the guidelines and relevant messaging to counties. / (Major pre-mitigation, moderate post mitigation)
Blood shortage due to minimized blood drives in the county and lack of blood screening kits	Implementing partner is providing logistical support to satellite blood centres in the counties to access commodities from the Kenya National Blood Transfusion Service (KNBTS) and facilitating blood drives in line with Covid-19 guidelines. / (Major pre-mitigation, moderate post mitigation)
County health teams lacking skills for planning and budgeting resulting in inadequate budget allocation to priority activities. This would prevent the counties from fully taking up interventions at the end of the programme.	The programme provided TA to 18 counties on planning and budgeting. The programme supported both public and faith-based facilities for EmONC and MPDSR support. Implementing partners are supporting the counties to prepare for and respond to industrial action. / Fundamental challenges affecting the financial flow from the national level are not yet addressed. / (major pre-mitigation, moderate post-mitigation).
Safeguarding
Products and services targeting pregnant women fail to adhere to quality standards and a beneficiary experiences an adverse event	The GoK standard operating procedures have been used to manage adverse events and continuous training provided by the programme will ensure that all providers are aware of what to do in case of an adverse event. Referral mechanisms have also been put in place to ensure adverse events are referred to higher level facilities quickly and efficiently. / (Major pre-mitigation, minor post mitigation)

Materialised risk – During the period under review, the risk of blood shortage materialised occasioned by suspension of blood drives in the county due to Covid-19 restrictions and lack of blood screening kits. Options intervened and procured blood screening kits for Msambweni satellite blood transfusion centre. Options also organised refresher training for technicians at the Centre and resumed blood donation drives adhering to Covid-19 guidelines. Lesson learnt - As much as blood services are a national government function, it is important to support the capacity of counties to provide blood transfusion services.

Update on Partnership Principles

The last update of the FCDO Partnership Principles (conducted in June 2019) concluded that while GOK has a strong commitment to poverty reduction, FCDO Kenya will not channel bilateral funds directly through GOK financial systems until there is evidence of substantial improvements in the integrity of financial management systems. The World Bank, Options and LSTM have worked with national and county governments to deliver shared objectives but have not channelled programme funds directly through GOK systems.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

The programme is currently being implemented by three partners - Options, LSTM and the World Bank. Generally, FCDO’s relationship with all the partners has been positive and productive. FCDO coordinates joint partner meetings every quarter. These meetings have proved useful in getting programme updates, especially from partners such as the WB who submit annual reports as opposed to the other partners who submit quarterly. Three such meetings were held during the period under review. LSTM and Options have engaged in national and county coordination and technical committees, such as the National MPDSR committee and the Reproductive Health Technical Working Groups. They have also developed strong relationships with the county health management teams in the focus counties. This has allowed them to influence the delivery of maternal and newborn health services in these counties.

Delivery against planned timeframes

MSI/Options: Have demonstrated strong management and technical capacity. Reports are always on time and are clear, accurate and concise. An accountable grant was signed in April 2019 to support the quality of care in 70 high volume facilities in four target counties – Kwale, Mombasa, Kericho and Nandi. A supplier review commissioned in February 2020 by FCDO centrally scored them in the ‘Good Performance’ category with main positives around effective communication, timely reporting, accurate and timely responses, strong partnerships and good risk management. The partner submits quarterly financial and expenditure reports to FCDO.

LSTM: Their performance has been good, and their reports are always on time and clear. They have made good progress despite challenges related to covid-19. An accountable grant was signed with LSTM in April 2019 to continue promoting and supporting sustainable strategies to reduce maternal and perinatal mortality and morbidity in Kenya. LSTM focus counties are Garissa, Kilifi, Vihiga, Taita Taveta and Uasin Gishu. The partner submits quarterly financial and expenditure reports to FCDO.

The World Bank: An Administrative Agreement was signed with the Bank in 2018 to run till 2022 with a focus on technical assistance (TA) through the Multi-Donor Trust Fund. Through this programme, the World Bank supports nine counties - Samburu, West Pokot, Bungoma Marsabit, Garissa, Lamu, Mandera, Tana River and Wajir. The WB submits the MDTF report to FCDO annually. It was not possible for the world Bank team to participate in the field visits due to travel restrictions related to Covid-19.

Financial Management
The programme has been running in two five-year phases:

Phase one (2013-2017): The original programme budget, which was £79.8m, was reduced to £60.6m following the 2017 DFID Portfolio Quality Review. Some of the funds that became available following the end of the first phase were mainly reallocated to the World Bank, MSI (QoC) and LSTM. By the time phase one was ending in 2017, the programme had spent £48.2m.

Phase two (2018-2023): In this phase, the programme budget was increased to £64.7m. Programme spending is on track. To date, £59.23m has been spent by implementing partners with a balance of £5.02m committed to various partnerships and £0.44m set aside for monitoring and evaluation and health adviser seconded to the World Bank. The table below provides a detailed breakdown of spend for each implementing partner in this phase
Spend to date for partners in phase two

Component	Total Budget (£)	Spend to date (£)	Balance
LSTM	3,000,000	1,396,581	1,603,419
MSI/Options (QoC)	1,939,986	1,000,248	939,739
HERA	24,985	12,394	12,591
World Bank	4,000,000	2,000,000	2,000,000 (under consideration)

Overall quality of the financial management for all the above-mentioned partners has been satisfactory with each partner submitting quarterly financial and expenditure reports to FCDO (except the MDTF who report annually). Forecasting performance has been satisfactory for all the partners with minor variances.

Asset monitoring:

Both LSTM and Options have systems in place to record and monitor assets procured with FCDO funds. Both partners have submitted updated asset registers as required. During field visits for this review, all equipment and other assets procured with programme funds that were observed had a visible UKaid logo.

Date of last narrative financial report	LSTM October 2020, Options October 2020
Date of last audited annual statement	31 July 2019; Options for FY ending 31 December 2019

Summary information from recent audits was as follows:
MSI (Options) – The latest audited financial statement covers the period January-December 2019. The auditor’s opinion was that MSI's group financial statement and company financial statements give a true and fair view of the state of the group's and of the company's affairs as at 31 Dec 2019.
LSTM - The audited financial statements cover the period for the year ended 31 July 2019. The auditor’s opinion is that proper books of account have been kept and the accompanying financial statements, which are in agreement, give a true and fair view of the financial position of LSTM as at 31 July 2019.
Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio
The MNH programme represents good VfM and should continue. The programme in this second phase has shifted from providing direct service delivery to providing more strategic technical assistance to help counties allocate resources to health care. Domestic financing is key for sustainable delivery of quality RMNCAH services. The programme is making good progress, but challenges remain both at county (with allocation of resources to health and to essential commodities) and at national (with timely disbursement of funds to counties) levels. The programme partners will work closely with other partners and utilise appropriate fora to address the challenges. Further, the activities supported by the programme are key in maintaining quality essential services in the face of Covid-19 pandemic that is expected to continue into the next year.

Monitoring
All implementing partners have robust governance and management systems in place to ensure regular monitoring of the programme delivery. For example, Options uses Quality of Institutional Care (QuIC) as an approach to monitor facility readiness to provide EmONC services. This is a novel approach designed to fill the gap for a rapid, low-cost and scalable approach that enables stakeholders to make informed responses to improve and monitor quality of care. QuIC involves quarterly data-collection via short telephone interviews (approximately 20 minutes), with pre-prepared respondents at selected facilities, using a context- specific questionnaire. The questionnaires typically focus on enablers for EmONC services and capacity to provide safe EmONC services 24/7 with an aim of stimulating action to improve service quality. Also, all implementing partners conduct regular visits to counties to conduct follow-up visits to facilities and monitor programme activities. These programme visits were briefly interrupted by Covid-19 restrictions but resumed once movement restrictions were lifted.
FCDO programme team monitored the programme during this review period through quarterly programme management meetings with all partners. The meeting covered the progress on activities carried out during the quarter and planned future activities, programme risks, and progress on follow up action points from the previous annual review. Monitoring also included the submission of quarterly technical, and financial reports against the project logframe from all partners, except the MDTF which provided an annual report. Monthly catch up meetings were held between FCDO and all implementing partners.
A programme visit was carried out to three counties (Kwale, Mombasa and Kilifi) as part of this annual review by the FCDO programme team. The visit included meetings with county health management teams and health personnel at county and sub-county hospitals.
Annex 1
Progress on recommendations from previous reviews
Recommendation	Progress and status of implementation
R1) DFID to second technical advisory capacity into the World Bank to help in progressing HSS support at the national level, including looking at helping the GoK to develop a realistic national blood supply system. (Action for Human and Social Development Team Leader November 2019).	Achieved.
R2) Develop and present at the national level technical working group a county staff transfer strategy by February 2020, aiming at keeping skilled/ trained MNH staff in MNH departments - LSTM	Achieved. / Assessment to determine the proportion of EmONC-trained personnel that are retained in maternity units completed in LSTM focal counties / Dissemination of these findings to 4/5 county CHMTs completed / Action plans for retention of trained staff agreed upon in the 4/5 counties
R3) Conduct regular supportive supervision and mentorship, delivered in a manner that is fully integrated into existing systems for service provision and supervision: conduct post-training follow-up by supporting the counties to combine different training modalities, like classroom training with mentorship and on-the-job training as an effective, efficient, and less disruptive of capacity building – LSTM	Achieved. / Using the post-training follow-ups, supportive supervision and mentorship tools developed in the first project year, / LSTM has been actively involved in the development of national mentoring package. The package incorporates a lot of materials from LSTM mentoring approach and EmOC training programme. LSTM will be piloting some of the national mentoring tools and providing feedback to MoH, ahead of the national launch.
R4 Continue work through the Pre-Service Taskforce to ensure the inclusion of EmONC and maternal and perinatal death surveillance and response into the standard curricula for nursing/midwifery and clinical/medical officers	Achieved - Nursing & midwifery syllabus and Clinical Officers’ (CO) core curriculum revisions completed, and master trainers trained.
R5) Work towards full coverage of pre-service EmONC training in all KMTCs and universities training nurses, midwives, clinical and medical officers. Approach other partners to support equipping the skills labs - LSTM	Achieved: / Virtual training of Kenyan Super Master Facilitators (SMF) for the roll-out to tutors training has been completed. / All systems and processes for the training of ToT and tutors on the updated pre-service syllabi are in place.
R6) Push the MoH to fast track the approval of the revised curriculum to ensure the indicators that were not met in 2019 review year can be achieved by 2020 - LSTM	Achieved - Revised curriculum approved
R7) Sustainability of in-service training requires a county-based financing strategy, advocate with the counites to include a budget line - LSTM	Ongoing - At the national level, LSTM provided input to the World Bank-MDTF that supported counties’ annual work planning (AWP) for the 2020/21 financial year. LSTM’s input focused on EmONC and MPDSR components counties need to include in the AWPs and budget. In the focal counties, LSTM continues to advocate for allocation of health funds towards EmONC and MPDSR.
R8) Expand the activities under indicator 2.2 to all supported counties, since this is a useful process to assess the capacity of the health system regularly “health facility EmONC readiness assessment”	Achieved: / LSTM developed an electronic EmONC functionality assessment tool. Focal health facilities are using this tool to collect data that is used to assess facility EmONC functionality. / All focal facilities baseline EmONC readiness assessment completed and disseminated to the CHMT / Quarter 2 assessment completed; analysis is underway and results to be disseminated at facility and county levels
R9) Provide evidence-based technical support to counties during the annual budgeting and planning process to help them to use MPDSR findings to inform the budget allocation and use at the county level	Ongoing: / LSTM provides feedback to facilities and counties through the county Quarterly MPDSR Reports / LSTM provided input to the focal counties’ AWP and budgeting process to lobby inclusion of budget line on MPDSR.
R10) Support operationalization of Linda Mama and PFM Act in the counties with lessons learnt from Bungoma - Options	Ongoing: / Options is working with 2 counties – Nandi and Mombasa to finalize their draft FIF bills for approval at the county assemblies. / Both counties FIF bills are at review stage with the county legal teams
R11) Partners to train on Maternal Perinatal Death Surveillance and Response (MPDSR) at facility level.	Achieved / All 12 high volume facilities have been trained on MPDSR. / Programme is supporting 12 high volume facilities for monthly MPDSR reviews / Actions from MPDSR reviews are being used to improve quality of care and investments in health.
R12) Advocating for MNH budgets influence by MPDSR findings	Partially Achieved: / Nandi County has increased the proportion of the budget in 2020/2021 FY to 32.1%. / Options to continue advocating for increased funds in the rest of the focal counties.
R13) Assessment of blood availability in the counties	Ongoing / Training on hemovigilance conducted in all the 4 counties in Aug/Sept 2020. Options will assess the blood availability in the 4 counties and share report in Q4 2020. / The findings will inform year 2 interventions covering both blood supply and haemovigilance as part of Health systems strengthening (HSS).
R14) Still birth rate in Kenya is high despite MPDSR trainings and reviews in the counties.	Ongoing / 41% of perinatal deaths have been reviewed in year 1 from 0%. Options will continue to work with counties to increase the proportion of perinatal death reviews.