## Outputs 1 - 6
|  |  | YEAR ONE | [24 empty] | YEAR TWO | [24 empty] | YEAR THREE | [30 empty] | Total three years
|  |  | Quarter 1 | MEN | WOMEN | BOYS | GIRLS | DIS | Quarter 2 | MEN | WOMEN | BOYS | GIRLS | DIS | Quarter 3 | MEN | WOMEN | BOYS | GIRLS | DIS | Quarter 4 | MEN | WOMEN | BOYS | GIRLS | DIS | YEAR ONE TOTAL | Quarter 1 | MEN | WOMEN | BOYS | GIRLS | DIS | Quarter 2 | MEN | WOMEN | BOYS | GIRLS | DIS | Quarter 3 | MEN | WOMEN | BOYS | GIRLS | DIS | Quarter 4 | MEN | WOMEN | BOYS | GIRLS | DIS | YEAR TWO TOTAL | Quarter 1 | MEN | WOMEN | BOYS | GIRLS | DIS | Quarter 2 | MEN | WOMEN | BOYS | GIRLS | DIS | Quarter 3 | MEN | WOMEN | BOYS | GIRLS | DIS | Quarter 4 | MEN | WOMEN | BOYS | GIRLS | DIS | Quarter 5 | MEN | WOMEN | BOYS | GIRLS | DIS | YEAR THREE TOTAL | MEN | WOMEN | BOYS | GIRLS | DIS | Total achieved | Initial Target | Final Target | % Achieved Overall
Impact Indicator 1
| # of migrants, IDPs and host communities with humanitarian and protection needs | Planned
|  | Achieved | [81 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Source
Impact Indicator 2
| # of migrants provided with humanitarian and protection assistance | Planned
|  | Achieved | [81 empty] | 217542 | 18606 | 50054 | 5405 | 0 | 291607
Source
Impact Indicator 3
| # of IDPs and host community members provided with humanitarian and protection assistance | Planned
|  | Achieved | [81 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Source
Outcome Indicator 1
| % of supported IDPs and host communities reporting improved access to psychosocial support, referral and RH services | Planned
|  | Achieved | [86 empty] | 87%
Source
Outcome Indicator 2
| % of Humanitarian actors reporting improved planning as a result of DTM information packages | Planned
Achieved
Source
Outcome Indicator 3
| % of beneficiaries (disaggregated by sex, age and disability) reporting that humanitarian assistance is delivered in a safe, accessible and participatory manner | Planned
|  | Achieved | [86 empty] | 78.5%
Source
Output 1: Conflict affected migrants have improved access to humanitarian and protection services (IOM) | Output Indicator 1.1
| # of encountered migrants registered, identifying vulnerabilities and human rights abuses suffered services | Planned | 7383 | [5 empty] | 14766 | [5 empty] | 22149 | [5 empty] | 29532 | [5 empty] | 29532 | 7383 | [5 empty] | 14766 | [5 empty] | 22149 | [5 empty] | 29532 | [5 empty] | 29532 | 5859 | [5 empty] | 12716 | [5 empty] | 19573 | [5 empty] | 26430 | [11 empty] | 26430
|  | Achieved | 3415 | 2356 | 205 | 751 | 103 | 0 | 15486 | 11644 | 1286 | 2158 | 398 | 0 | 31399 | 23616 | 3020 | 4198 | 565 | 0 | 53036 | 39670 | 4987 | 7426 | 953 | 0 | 53036 | 16681 | 12885 | 1118 | 2404 | 274 | 0 | 34333 | 26272 | 1860 | 5577 | 624 | 0 | 55236 | 42027 | 2673 | 9646 | 890 | 0 | 72747 | 55735 | 3432 | 12510 | 1070 | 0 | 72747 | 13228 | 10523 | 421 | 2163 | 121 | 0 | 28269 | 11572 | 356 | 3055 | 58 | 1 | 45392 | 12976 | 541 | 3433 | 173 | 4 | 52116 | 5129 | 194 | 1315 | 86 | 0 | 55381 | 2767 | 226 | 222 | 50 | 0 | 55381 | 138372 | 10157 | 30124 | 2511 | 3 | 181164 | 96275 | 85494 | 211.9%
Source
|  | IOM | 3415 | 2356 | 205 | 751 | 103 | 0 | 11307 | 8653 | 1056 | 1310 | 288 | 0 | 11698 | 8912 | 1405 | 1228 | 153 | 0 | 15292 | 11503 | 1662 | 1842 | 285 | 0 | 41712 | 10933 | 8359 | 844 | 1512 | 218 | 0 | 9119 | 7296 | 220 | 1506 | 97 | 0 | 10095 | 8007 | 208 | 1814 | 66 | 0 | 7047 | 5799 | 87 | 1140 | 21 | 0 | 37194 | 8177 | 6454 | 204 | 1462 | 57 | 0 | 8481 | 6444 | 45 | 1980 | 12 | 1 | 9266 | 7075 | 173 | 1992 | 26 |  | 3407 | 2507 | 72 | 806 | 22 |  | 3265 | 2767 | 226 | 222 | 50 |  | 32596 | 86132 | 6407 | 17565 | 1398 | 0 | 111502
|  | DRC | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 376 | 19 | 42 | 3 | 0 | 2889 | 2256 | 311 | 316 | 6 | 0 | 3466 | 2701 | 269 | 467 | 29 | 0 | 6795 | 3784 | 2974 | 251 | 520 | 39 | 0 | 4277 | 3175 | 292 | 707 | 103 | 0 | 4725 | 3402 | 199 | 1064 | 60 | 0 | 3060 | 2412 | 115 | 506 | 27 | 0 | 15846 | 4071 | 3307 | 181 | 538 | 45 | 0 | 5729 | 4532 | 289 | 866 | 42 | 0 | 4230 | 3526 | 162 | 475 | 67 | 4 | 2356 | 1977 | 59 | 308 | 12 |  | 0 | [5 empty] | 16386 | 30638 | 2147 | 5809 | 433 | 1 | 39027
|  | INTERSOS | 0 | 0 | 0 | 0 | 0 | 0 | 324 | 259 | 6 | 55 | 4 | 0 | 1326 | 804 | 18 | 496 | 8 | 0 | 2879 | 1850 | 36 | 919 | 74 | 0 | 4529 | 1964 | 1552 | 23 | 372 | 17 | 0 | 4256 | 2916 | 230 | 960 | 150 | 0 | 6083 | 4346 | 406 | 1191 | 140 | 0 | 7404 | 5497 | 557 | 1218 | 132 | 0 | 19707 | 980 | 762 | 36 | 163 | 19 | 0 | 831 | 596 | 22 | 209 | 4 | 0 | 3627 | 2375 | 206 | 966 | 80 |  | 961 | 645 | 63 | 201 | 52 |  | 0 | [5 empty] | 6399 | 21602 | 1603 | 6750 | 680 | 2 | 30635
Output Indicator 1.2
| # of migrants receiving WASH, food, NFIs, temporary shelter and transportation | Planned | 4125 | [5 empty] | 8250 | [5 empty] | 12375 | [5 empty] | 16500 | [5 empty] | 16500 | 4125 | [5 empty] | 8250 | [5 empty] | 12375 | [5 empty] | 16500 | [5 empty] | 16500 | 13693 | [5 empty] | 28386 | [5 empty] | 43079 | [5 empty] | 57774 | [11 empty] | 57774
|  | Achieved | 5384 | 3715 | 323 | 1185 | 161 | 0 | 22236 | 16112 | 1767 | 3718 | 639 | 0 | 43785 | 29873 | 4814 | 7392 | 1706 | 0 | 80288 | 56141 | 7985 | 13801 | 2361 | 0 | 80288 | 25832 | 19281 | 1664 | 4452 | 435 | 0 | 58289 | 43586 | 3204 | 10382 | 1117 | 0 | 80939 | 59949 | 5119 | 14243 | 1628 | 0 | 116464 | 87836 | 6106 | 20648 | 1874 | 0 | 116464 | 18791 | 14373 | 779 | 3421 | 218 | 0 | 35931 | 13195 | 603 | 3216 | 126 | 3 | 63854 | 20562 | 1406 | 5607 | 348 | 3 | 79417 | 12684 | 707 | 1894 | 278 | 0 | 94855 | 12751 | 1020 | 1467 | 200 | 0 | 94855 | 217542 | 18606 | 50054 | 5405 | 0 | 291607 | 96275 | 90774 | 321.2%
Source
|  | IOM Food | 3848 | 2655 | 231 | 847 | 115 | 0 | 11112 | 8408 | 1015 | 1394 | 295 | 0 | 10790 | 7928 | 1344 | 1382 | 136 | 0 | 16287 | 11990 | 1896 | 2071 | 330 | 0 | 42037 | 11918 | 8895 | 930 | 1877 | 216 | 0 | 14621 | 11621 | 378 | 2325 | 297 | 0 | 5093 | 4288 | 106 | 643 | 56 | 0 | 15961 | 12685 | 202 | 3026 | 48 | 0 | 47593 | 11639 | 8884 | 215 | 2471 | 69 | 0 | 7076 | 5388 | 104 | 1556 | 28 | 1 | 11681 | 8637 | 460 | 2553 | 31 | 1 | 5274 | 4343 | 150 | 726 | 55 |  | 7985 | 6440 | 535 | 901 | 109 |  | 43655 | 102162 | 7566 | 21772 | 1785 | 0 | 133285
|  | IOM NFI | 1536 | 1060 | 92 | 338 | 46 | 0 | 4436 | 3039 | 241 | 985 | 171 | 0 | 5889 | 2652 | 1313 | 1016 | 908 | 0 | 6325 | 4214 | 585 | 1410 | 116 | 0 | 18186 | 2598 | 1845 | 76 | 642 | 35 | 0 | 2988 | 2254 | 141 | 553 | 40 | 0 | 2431 | 1758 | 243 | 366 | 64 | 0 | 2800 | 2225 | 189 | 359 | 27 | 0 | 10817 | 752 | 529 | 168 | 16 | 39 | 0 | 1765 | 1321 | 104 | 314 | 26 | 1 | 3447 | 2546 | 296 | 565 | 40 | 1 | 2418 | 1960 | 221 | 176 | 61 |  | 5960 | 5010 | 392 | 488 | 70 |  | 14342 | 30413 | 4061 | 7228 | 1643 | 0 | 43345
|  | IOM Shelter | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 151 | 29 | 47 | 13 | 0 | 333 | 40 | 13 | 0 | 27 | 0 | 0 | 179 | 129 | 9 | 41 |  | 0 | 51 | 24 | 10 | 16 | 1 | 0 | 34 | 21 | 8 | 5 | 0 | 0 | 304 | 291 | 169 | 90 | 22 | 10 | 0 | 33 | 15 | 4 | 8 | 6 | 1 | 34 | 17 | 5 | 6 | 6 | 1 | 110 | 52 | 21 | 24 | 13 |  | 29 | 16 | 6 | 2 | 5 |  | 497 | 700 | 182 | 198 | 54 | 0 | 1134
|  | IOM HK | 0 | 0 | 0 | 0 | 0 | 0 | 665 | 441 | 59 | 153 | 12 | 0 | 792 | 582 | 17 | 187 | 6 | 0 | 1856 | 1214 | 81 | 534 | 27 | 0 | 3313 | 1442 | 1039 | 40 | 338 | 25 | 0 | 3236 | 2491 | 121 | 589 | 35 | 0 | 3077 | 1766 | 722 | 413 | 176 | 0 | 3852 | 3076 | 151 | 609 | 16 | 0 | 11607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  | 1815 | 1627 | 87 | 76 | 25 |  | 1464 | 1285 | 87 | 76 | 16 |  | 3279 | 13521 | 1365 | 2975 | 338 | 0 | 18199
|  | Intersos Food | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1326 | 804 | 18 | 496 | 8 | 0 | 2879 | 2087 | 24 | 715 | 53 | 0 | 4205 | 3776 | 2866 | 188 | 620 | 102 | 0 | 5637 | 3938 | 439 | 1076 | 184 | 0 | 6418 | 4604 | 535 | 1156 | 123 | 0 | 3876 | 2989 | 53 | 805 | 29 | 0 | 19707 | 980 | 762 | 36 | 163 | 19 | 0 | 831 | 596 | 22 | 209 | 4 | 0 | 3627 | 2375 | 206 | 966 | 80 |  | 961 | 645 | 63 | 201 | 52 |  | 0 | [5 empty] | 6399 | 21666 | 1584 | 6407 | 654 | 0 | 30311
|  | Intersos NFI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 438 | 11 | 296 | 5 | 0 | 1950 | 1184 | 17 | 695 | 54 | 0 | 2700 | 1044 | 802 | 0 | 242 | 0 | 0 | 2684 | 1995 | 181 | 444 | 64 | 0 | 2395 | 1639 | 182 | 511 | 63 | 0 | 5172 | 4062 | 180 | 868 | 62 | 0 | 11295 | 467 | 321 | 34 | 95 | 17 | 0 | 824 | 591 | 22 | 207 | 4 | 0 | 3400 | 2226 | 188 | 914 | 72 |  | 943 | 628 | 63 | 200 | 52 |  | 0 | [5 empty] | 5634 | 13886 | 878 | 4472 | 393 | 0 | 19629
|  | Intersos Transport | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 34 | 26 | 1 | 3 | 4 | 0 | 38 | 25 | 25 | 0 | 0 | 0 | 0 | 63 | 31 | 10 | 10 | 12 | 0 | 98 | 61 | 11 | 18 | 8 | 0 | 114 | 64 | 21 | 20 | 9 | 0 | 300 | 4 | 4 | 0 | 0 | 0 | 0 | 8 | 7 | 0 | 1 | 0 | 0 | 13 | 9 | 2 | 2 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 25 | 231 | 45 | 54 | 33 | 0 | 363
|  | DRC Food | 0 | 0 | 0 | 0 | 0 | 0 | 546 | 416 | 129 | 1 | 0 | 0 | 622 | 495 | 52 | 75 | 0 | 0 | 3466 | 2701 | 269 | 467 | 29 | 0 | 4634 | 3784 | 2974 | 251 | 520 | 39 | 0 | 3049 | 1846 | 261 | 892 | 50 | 0 | 3087 | 2223 | 106 | 738 | 20 | 0 | 1389 | 1004 | 68 | 289 | 28 | 0 | 11309 | 1795 | 1389 | 79 | 307 | 20 | 0 | 3102 | 2449 | 107 | 522 | 24 |  | 2413 | 1952 | 93 | 314 | 54 |  | 1688 | 1452 | 43 | 183 | 10 |  | 0 | [5 empty] | 8998 | 18901 | 1458 | 4308 | 274 | 0 | 24941
|  | DRC DK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1376 | 858 | 292 | 222 | 4 | 0 | 3466 | 2701 | 269 | 467 | 29 | 0 | 4842 | 1205 | 822 | 179 | 186 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2327 | 1761 | 115 | 424 | 27 | 0 | 3532 | 2863 | 2315 | 157 | 347 | 44 | 0 | 3501 | 2828 | 240 | 399 | 34 |  | 3308 | 2800 | 156 | 287 | 65 |  | 2354 | 1977 | 59 | 308 | 10 |  | 0 | [5 empty] | 12026 | 16062 | 1467 | 2640 | 231 | 0 | 20400
Output Indicator 1.3
| # of migrants benefiting from life-saving health care | Planned | 1950 | [5 empty] | 3900 | [5 empty] | 5850 | [5 empty] | 7800 | [5 empty] | 7800 | 1950 | [5 empty] | 3900 | [5 empty] | 5850 | [5 empty] | 7800 | [5 empty] | 7800 | 20068 | [5 empty] | 40136 | [5 empty] | 60204 | [5 empty] | 80275 | [11 empty] | 80275
|  | Achieved | 5012 | 2292 | 1055 | 930 | 735 | 0 | 10595 | 6241 | 1970 | 1442 | 942 | 0 | 21342 | 14517 | 3358 | 2372 | 1095 | 0 | 27629 | 19297 | 4014 | 3066 | 1252 | 0 | 27629 | 2629 | 1933 | 316 | 324 | 56 | 0 | 12105 | 6710 | 2359 | 1892 | 1144 | 0 | 19670 | 12322 | 3093 | 2933 | 1322 | 0 | 32559 | 21486 | 4629 | 4710 | 1734 | 0 | 32559 | 9247 | 6597 | 1200 | 1187 | 263 | 0 | 19271 | 13812 | 2452 | 2495 | 512 | 0 | 28857 | 20805 | 3265 | 4021 | 766 | 0 | 36293 | 26626 | 3898 | 4926 | 843 | 0 | 45279 | 33345 | 4728 | 6266 | 940 | 0 | 45279 | 74128 | 13371 | 14042 | 3926 | 0 | 105467 | 19800 | 95875 | 110%
Source
|  | IOM MC | 4974 | 2265 | 1055 | 919 | 735 | 0 | 5583 | 3949 | 915 | 512 | 207 | 0 | 10103 | 7770 | 1385 | 804 | 144 | 0 | 5947 | 4539 | 654 | 597 | 157 | 0 | 26607 | 2501 | 1837 | 312 | 298 | 54 | 0 | 8564 | 4093 | 2037 | 1360 | 1074 | 0 | 6817 | 4997 | 734 | 911 | 175 | 0 | 11302 | 7830 | 1533 | 1531 | 408 | 0 | 29184 | 8748 | 6245 | 1199 | 1042 | 262 | 0 | 9164 | 6619 | 1249 | 1048 | 248 |  | 8426 | 6052 | 810 | 1310 | 254 |  | 5982 | 4657 | 622 | 631 | 72 |  | 8986 | 6719 | 830 | 1340 | 97 |  | 41306 | 67572 | 13335 | 12303 | 3887 | 0 | 97097
|  | IOM RH | 250 | 0 | 250 | 0 | 0 | 0 | 31 | 0 | 31 | 0 | 0 | 0 | 30 | 0 | 30 | 0 | 0 | 0 | 15 |  | 15 |  |  | 0 | 326 | 12 | 0 | 12 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 49 |  | 49 |  |  | 0 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 37 | 0 | 37 | 0 | 0 |  | 10 |  | 10 |  |  |  | 23 |  | 23 |  |  |  | 70 | 0 | 501 | 0 | 0 | 0 | 501
|  | IOM HA | 2665 | 1995 | 233 | 390 | 47 | 0 | 6301 | 4880 | 675 | 620 | 126 | 0 | 6136 | 4506 | 805 | 749 | 76 | 0 | 6285 | 4775 | 545 | 841 | 124 | 0 | 21387 | 3543 | 2690 | 350 | 433 | 70 | 0 | 8821 | 5754 | 1086 | 1718 | 263 | 0 | 22515 | 17325 | 2366 | 2219 | 605 | 0 | 14671 | 11235 | 1622 | 1350 | 464 | 0 | 49550 | 9641 | 7202 | 968 | 1222 | 249 | 0 | 8050 | 5608 | 909 | 1411 | 122 |  | 11038 | 7802 | 927 | 2017 | 292 |  | 7121 | 5235 | 573 | 1251 | 62 |  | 7754 | 6031 | 1134 | 543 | 46 |  | 43604 | 85038 | 12193 | 14764 | 2546 | 0 | 114541
|  | IOM Vacc | 38 | 27 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 644 | 506 | 3 | 126 | 9 | 0 | 340 | 241 | 2 | 97 | 0 | 0 | 1022 | 128 | 96 | 4 | 26 | 2 | 0 | 912 | 684 | 6 | 208 | 14 | 0 | 748 | 615 | 0 | 130 | 3 | 0 | 1413 | 1189 | 2 | 220 | 2 | 0 | 3201 | 405 | 279 | 0 | 126 | 0 | 0 | 733 | 485 | 2 | 246 |  |  | 1042 | 835 | 0 | 207 | 0 |  | 1177 | 937 | 0 | 240 | 0 |  | 0 | [5 empty] | 3357 | 5894 | 19 | 1637 | 30 | 0 | 7580
|  | DRC paramedic | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174 | 145 | 1 | 26 | 2 | 0 | 174 | 94 | 73 | 1 | 19 | 1 | 0 | 127 | 111 | 1 | 14 | 1 |  | 118 | 106 | 3 | 9 | 0 |  | 277 | 227 | 11 | 34 | 5 |  | 0 | [5 empty] | 616 | 662 | 17 | 102 | 9 | 0 | 790
Output Indicator 1.4
| # of migrants benefiting from mental health and psychosocial support | Planned | 998 | [5 empty] | 1996 | [5 empty] | 2994 | [5 empty] | 3992 | [5 empty] | 3992 | 998 | [5 empty] | 1996 | [5 empty] | 2994 | [5 empty] | 3992 | [5 empty] | 3992 | 4002 | [5 empty] | 8004 | [5 empty] | 12006 | [5 empty] | 16008 | [11 empty] | 16008
|  | Achieved | 870 | 396 | 286 | 131 | 57 | 0 | 4176 | 1525 | 457 | 1837 | 357 | 0 | 6902 | 3334 | 519 | 2631 | 418 | 0 | 11061 | 5775 | 628 | 4063 | 595 | 0 | 11061 | 3012 | 2191 | 135 | 659 | 27 | 0 | 9207 | 6648 | 388 | 1977 | 194 | 0 | 17041 | 12121 | 929 | 3593 | 398 | 0 | 26705 | 19178 | 1528 | 5455 | 544 | 0 | 26705 | 2864 | 2074 | 138 | 621 | 31 | 0 | 4994 | 1483 | 87 | 541 | 19 | 0 | 9833 | 3210 | 249 | 1259 | 121 | 0 | 11236 | 968 | 76 | 262 | 97 | 0 | 11757 | 375 | 64 | 51 | 31 | 0 | 11757 | 33063 | 2770 | 12252 | 1438 | 0 | 49523 | 1980 | 23992 | 206.4%
Source
|  | IOM MHPSS | 870 | 396 | 286 | 131 | 57 | 0 | 3149 | 972 | 171 | 1706 | 300 | 0 | 1716 | 1098 | 46 | 518 | 54 | 0 | 1534 | 824 | 73 | 532 | 105 | 0 | 7269 | 1048 | 639 | 112 | 287 | 10 | 0 | 1964 | 1552 | 23 | 372 | 17 | 0 | 1751 | 1127 | 135 | 425 | 64 | 0 | 2260 | 1560 | 42 | 644 | 14 | 0 | 7023 | 1884 | 1312 | 102 | 458 | 12 | 0 | 1299 | 887 | 65 | 332 | 15 |  | 1212 | 835 | 43 | 293 | 41 |  | 442 | 323 | 13 | 61 | 45 |  | 521 | 375 | 64 | 51 | 31 |  | 5358 | 11900 | 1175 | 5810 | 765 | 0 | 19650
|  | Intersos PSS | 0 | 0 | 0 | 0 | 0 | 0 | 157 | 157 | 0 | 0 | 0 | 0 | 1010 | 711 | 16 | 276 | 7 | 0 | 2625 | 1617 | 36 | 900 | 72 | 0 | 3792 | 1964 | 1552 | 23 | 372 | 17 | 0 | 4231 | 2905 | 230 | 946 | 150 | 0 | 6083 | 4346 | 406 | 1191 | 140 | 0 | 7404 | 5497 | 557 | 1218 | 132 | 0 | 19682 | 980 | 762 | 36 | 163 | 19 | 0 | 831 | 596 | 22 | 209 | 4 | 0 | 3627 | 2375 | 206 | 966 | 80 |  | 961 | 645 | 63 | 201 | 52 |  | 0 | [5 empty] | 6399 | 21163 | 1595 | 6442 | 673 | 0 | 29873
Output Indicator 1.5
| # of migrants referred for specialised services, including victims of trafficking and GBV | Planned | 543 | [5 empty] | 1086 | [5 empty] | 1629 | [5 empty] | 2172 | [5 empty] | 2172 | 543 | [5 empty] | 1086 | [5 empty] | 1629 | [5 empty] | 2172 | [5 empty] | 2172 | 125 | [5 empty] | 750 | [5 empty] | 1376 | [5 empty] | 2002 | [11 empty] | 2002
|  | Achieved | 95 | 57 | 32 | 5 | 1 | 0 | 358 | 242 | 71 | 41 | 4 | 0 | 1192 | 521 | 174 | 326 | 171 | 0 | 1457 | 737 | 196 | 348 | 176 | 0 | 1457 | 214 | 145 | 15 | 52 | 2 | 0 | 214 | 145 | 15 | 52 | 2 | 0 | 658 | 433 | 41 | 174 | 10 | 0 | 1147 | 821 | 93 | 217 | 16 | 0 | 1147 | 372 | 315 | 27 | 24 | 6 | 0 | 586 | 145 | 39 | 26 | 4 | 0 | 978 | 305 | 41 | 35 | 11 | 0 | 1277 | 213 | 35 | 47 | 4 | 0 | 1600 | 232 | 56 | 34 | 1 | 0 | 1600 | 2768 | 487 | 731 | 218 | 0 | 4204 | 2700 | 6346 | 66.25%
Source
|  | IOM to hospital | 95 | 57 | 32 | 5 | 1 | 0 | 263 | 185 | 39 | 36 | 3 | 0 | 806 | 266 | 88 | 285 | 167 | 0 | 249 | 204 | 19 | 22 | 4 | 0 | 1413 | 136 | 105 | 13 | 17 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384 | 302 | 49 | 27 | 6 | 0 | 520 | 333 | 294 | 22 | 14 | 3 | 0 | 0 | [5 empty] | 350 | 274 | 37 | 30 | 9 |  | 293 | 209 | 34 | 46 | 4 |  | 323 | 232 | 56 | 34 | 1 |  | 1299 | 2128 | 389 | 516 | 199 | 0 | 3232
|  | IOM to services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 134 | 33 | 14 | 4 |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 185 | 134 | 33 | 14 | 4 | 0 | 185
|  | DRC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6 | 3 | 0 | 1 | 0 | 10 | 68 | 31 | 2 | 34 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 444 | 288 | 26 | 122 | 8 | 0 | 105 | 86 | 3 | 16 | 0 | 0 | 617 | 34 | 18 | 3 | 10 | 3 | 0 | 23 | 11 | 3 | 9 | 0 |  | 42 | 31 | 4 | 5 | 2 | 0 | 6 | 4 | 1 | 1 | 0 |  | 0 | [5 empty] | 105 | 475 | 45 | 197 | 15 | 0 | 732
|  | NRC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 13 | 15 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 34 | 10 | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 3 | 2 | 0 | 0 | 0 | 6 | 0 | 3 | 3 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 11 | 31 | 20 | 4 | 0 | 0 | 55
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output Indicator 1.6
| # of migrants who receive legal counselling to address critical humanitarian and protection needs. | Planned | 1210 | [5 empty] | 2420 | [5 empty] | 3630 | [5 empty] | 4840 | [5 empty] | 4840 | 1210 | [5 empty] | 2420 | [5 empty] | 3630 | [5 empty] | 4840 | [5 empty] | 4840 | 3375 | [5 empty] | 6750 | [5 empty] | 10125 | [5 empty] | 13502 | [11 empty] | 13502
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 376 | 19 | 42 | 3 | 0 | 3357 | 2645 | 345 | 358 | 9 | 0 | 6858 | 5381 | 614 | 825 | 38 | 0 | 6858 | 3809 | 2993 | 257 | 520 | 39 | 0 | 8121 | 3210 | 549 | 1227 | 142 | 0 | 12861 | 6612 | 763 | 2291 | 202 | 0 | 15925 | 9028 | 878 | 2797 | 229 | 0 | 15925 | 4076 | 3310 | 183 | 538 | 45 | 0 | 9811 | 4532 | 292 | 869 | 42 | 0 | 14042 | 3526 | 163 | 475 | 67 | 4 | 16580 | 2135 | 60 | 328 | 15 | 0 | 16580 | 0 | 0 | 0 | 0 | 0 | 16580 | 30905 | 2190 | 5832 | 436 | 4 | 39363 | 2525 | 23182 | 169.8%
Source
|  | NRC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 13 | 15 | 0 | 0 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 63 | 25 | 19 | 6 | 0 | 0 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 79 | 5 | 3 | 2 | 0 | 0 | 0 | 6 |  | 3 | 3 |  |  | 1 | 0 | 1 | 0 | 0 |  | 182 | 158 | 1 | 20 | 3 |  | 0 | [5 empty] | 194 | 267 | 43 | 23 | 3 | 0 | 336
|  | DRC | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 376 | 19 | 42 | 3 | 0 | 2889 | 2256 | 311 | 316 | 6 | 0 | 3466 | 2701 | 269 | 467 | 29 | 0 | 6795 | 3784 | 2974 | 251 | 520 | 39 | 0 | 4277 | 3175 | 292 | 707 | 103 | 0 | 4725 | 3402 | 199 | 1064 | 60 | 0 | 3060 | 2412 | 115 | 506 | 27 | 0 | 15846 | 4071 | 3307 | 181 | 538 | 45 | 0 | 5729 | 4532 | 289 | 866 | 42 |  | 4230 | 3526 | 162 | 475 | 67 | 4 | 2356 | 1977 | 59 | 308 | 12 |  | 0 | [5 empty] | 16386 | 30638 | 2147 | 5809 | 433 | 4 | 39027
Output Indicator 1.7
| # of attendees of awareness sessions on migrants' rights and humanitarian assistance | Planned | 8317 | [5 empty] | 16634 | [5 empty] | 24951 | [5 empty] | 33268 | [5 empty] | 33268 | 8317 | [5 empty] | 16634 | [5 empty] | 24951 | [5 empty] | 33268 | [5 empty] | 33268 | 2937 | [5 empty] | 6474 | [5 empty] | 10011 | [5 empty] | 13548 | [11 empty] | 13548
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 167 | 167 | 0 | 0 | 0 | 0 | 1186 | 789 | 47 | 343 | 7 | 0 | 7538 | 4671 | 394 | 2284 | 189 | 0 | 7538 | 4462 | 3123 | 209 | 1006 | 124 | 0 | 27545 | 19342 | 1955 | 5588 | 660 | 0 | 57720 | 42789 | 4089 | 9557 | 1285 | 0 | 68521 | 50567 | 4837 | 11651 | 1466 | 0 | 68521 | 3364 | 2439 | 86 | 820 | 19 | 0 | 11524 | 6168 | 176 | 1772 | 44 | 0 | 20579 | 6169 | 404 | 2400 | 82 | 0 | 26417 | 4302 | 223 | 1234 | 79 | 0 | 32456 | 5111 | 233 | 668 | 27 | 0 | 32456 | 79427 | 6353 | 20829 | 1906 | 0 | 108515 | 10000 | 80084 | 135.5%
Source
|  | Community members | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 77 | 0 | 0 | 0 | 0 | 411 | 202 | 23 | 107 | 79 | 0 | 488 | 323 | 234 | 41 | 18 | 30 | 0 | 944 | 713 | 16 | 199 | 16 | 0 | 731 | 446 | 18 | 180 | 87 | 0 | 586 | 292 | 87 | 159 | 48 | 0 | 2584 | 282 | 226 | 0 | 56 | 0 | 0 | 380 | 301 | 47 | 19 | 13 | 0 | 374 | 336 | 0 | 38 | 0 |  | 220 | 160 | 3 | 57 | 0 |  | 0 | [5 empty] | 1256 | 2987 | 235 | 833 | 273 | 0 | 4328 | 2463
|  | Migrants | 0 | 0 | 0 | 0 | 0 | 0 | 167 | 167 | 0 | 0 | 0 | 0 | 942 | 545 | 47 | 343 | 7 | 0 | 5941 | 3680 | 324 | 1834 | 103 | 0 | 7050 | 4139 | 2889 | 168 | 988 | 94 | 0 | 22139 | 15506 | 1730 | 4383 | 520 | 0 | 29444 | 23001 | 2116 | 3789 | 538 | 0 | 10215 | 7486 | 661 | 1935 | 133 | 0 | 65937 | 3082 | 2213 | 86 | 764 | 19 | 0 | 7780 | 5867 | 129 | 1753 | 31 | 0 | 8681 | 5833 | 404 | 2362 | 82 |  | 5618 | 4142 | 220 | 1177 | 79 |  | 6039 | 5111 | 233 | 668 | 27 |  | 31200 | 76440 | 6118 | 19996 | 1633 | 0 | 104187 | 1896
Output Indicator 1.8
| # of individuals receiving training in mainstreaming cross-cutting issues such as inclusion, protection, LCD, CDR PSS and MRE. | Planned | 73 | [5 empty] | 146 | [5 empty] | 219 | [5 empty] | 292 | [5 empty] | 292 | 73 | [5 empty] | 146 | [5 empty] | 219 | [5 empty] | 292 | [5 empty] | 292 | 90 | [5 empty] | 232 | [5 empty] | 444 | [5 empty] | 464 | [11 empty] | 464
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 66 | 34 | 0 | 0 | 0 | 191 | 122 | 69 | 0 | 0 | 0 | 191 | 25 | 19 | 6 | 0 | 0 | 0 | 53 | 36 | 17 | 0 | 0 | 0 | 267 | 159 | 108 | 0 | 0 | 0 | 407 | 252 | 155 | 0 | 0 | 0 | 407 | 17 | 4 | 13 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 31 | 13 | 1 | 0 | 0 | 0 | 65 | 23 | 11 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 65 | 414 | 249 | 0 | 0 | 0 | 663 | 1940 | 1048 | 63.26%
Source
|  | NRC Protection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 66 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 25 | 19 | 6 | 0 | 0 | 0 | 28 | 17 | 11 | 0 | 0 | 0 | 60 | 55 | 5 | 0 | 0 | 0 | 66 | 44 | 22 | 0 | 0 | 0 | 179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 18 | 7 | 0 | 0 | 0 | 0 | [5 empty] | 25 | 219 | 85 | 0 | 0 | 0 | 304
|  | HI Inclusion | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 56 | 35 | 0 | 0 | 0 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 12 | 8 | 0 | 0 | 0 | 20 | 17 | 4 | 13 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 5 | 4 | 0 | 0 | 0 | 0 | [5 empty] | 26 | 77 | 60 | 0 | 0 | 0 | 137
|  | HI PSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154 | 68 | 86 | 0 | 0 | 0 | 54 | 37 | 17 | 0 | 0 | 0 | 208 | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | 105 | 103 | 0 | 0 | 0 | 208
|  | HI Safety | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | [5 empty] | 14 | 13 | 1 | 0 | 0 | 0 | 0 | [5 empty] | 0 | [5 empty] | 14 | 13 | 1 | 0 | 0 | 0 | 14
Output Indicator 1.9
| % of training participants in mainstreaming cross-cutting issues demonstrating increased knowledge in these topics | Planned | 70% | [5 empty] | 70% | [5 empty] | 70% | [5 empty] | 70% | [5 empty] | 70% | 70% | [5 empty] | 70% | [5 empty] | 70% | [5 empty] | 70% | [5 empty] | 70% | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80%
|  | Achieved | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 72% | 0 | 0 | 0 | 0 | 0 | 72% | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 58.25% | 2.34 | 2.32 | 0 | 0 | 0 | 58.25% | 80% | [5 empty] | 0% | [5 empty] | 86% | [5 empty] | 89.5% | [17 empty] | 84% | 80% |  | 84%
Source
|  | NRC Protection | 0 | [5 empty] | 0% | [5 empty] | 0% | [5 empty] | 0% | [6 empty] | 0% | [5 empty] | 0% | [5 empty] | 0% | [5 empty] | 45% | 45% | 45% |  |  |  | 0.45 | 0% | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 90% | [12 empty] | 0.45 | 0.45 | 0 | 0 | 0 | 68%
|  | HI Inclusion | 0% | [5 empty] | 0% | [5 empty] | 0% | [5 empty] | 72% | [6 empty] | 0% | [5 empty] | 0% | [5 empty] | 0% | [5 empty] | 89.5% | 92% | 87% |  |  |  | 0.895 | 80% | 0.85 | 0.5 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 89% | [12 empty] | 1.77 | 1.37 | 0 | 0 | 0 | 83%
|  | HI PSS | [43 empty] | 98.5% | 97% | 100% |  |  |  | 0.985 | 0% | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0.97 | 1 | 0 | 0 | 0 | 99%
|  | HI Safety | [43 empty] | 0% | 0% | 0% |  |  |  | 0 | 0% | [11 empty] | 86% | 0.84615 | 1 | 0 | 0 | 0 | [13 empty] | 0.84615 | 1 | 0 | 0 | 0 | 86%
Output Indicator 1.10
| # of government health consultants trained by IOM on healthcare | Planned | 22.5 | [5 empty] | 45 | [5 empty] | 67.5 | [5 empty] | 90 | [5 empty] | 90 | 22.5 | [5 empty] | 45 | [5 empty] | 67.5 | [5 empty] | 90 | [5 empty] | 90 | 25 | [5 empty] | 25 | [5 empty] | 50 | [5 empty] | 50 | [11 empty] | 50
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 48 | 38 | 10 |  |  |  | 180 | 120 | 60 |  |  |  | 228 | 158 | 70 |  |  |  | 228 | - | 230 | 99.13%
Source
Output Indicator 1.11
| % of surveyed migrants reporting satisfaction with services received | Planned | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80%
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90% | 60% | 30% | 0% | 0% | 0% | 0% | 60% | 30% | 0% | 0% | 0% | 95% | 60% | 30% | 0% | 0% | 0% | 87% | 134% | 90% | 0% | 0% | 0% | 87% | 97% | [5 empty] | 97% | [5 empty] | 0.79333 | [5 empty] | 99% | [5 empty] | 32.67% | [11 empty] | 70% | 80% | 80% | 70%
Source
|  | IOM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 95% | - | - | - | - | - | 81% | 64% | 17% | 0% | 0% | 0% | [7 empty] | 95% | 1279 | 19 | 456 | 6 |  | 41% | [5 empty] | 100% | [5 empty] | 98% | [11 empty] | 85%
|  | NRC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90% | 60% | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [6 empty] | 93% | 50% | 43% | 0% | 0% |  |  | 94% | [5 empty] | 96% | [5 empty] | 97% | [5 empty] | 97% | 236 | 1 | 58 | 3 | [13 empty] | 95%
|  | DRC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | 0% | 0% | 0% | [37 empty] | 0%
|  | INTERSOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [6 empty] | 0% | 0% | 0% | 0% | 0% | 0% |  | 100% | 303 | 13 | 60 | 3 | 0 | 100% | 266 | 19 | 41 | 3 | 0 | 100% | 368 | 44 | 103 | 25 |  | 100% | 36 | 1 | 5 | 0 | [13 empty] | 100%
Output Indicator 1.12
| % of surveyed migrants aware of the availability of a feedback mechanism | Planned | 4 | [5 empty] | 8 | [5 empty] | 12 | [5 empty] | 16 | [5 empty] | 16 | 4 | [5 empty] | 8 | [5 empty] | 12 | [5 empty] | 16 | [5 empty] | 16 | 64% | [5 empty] | 64% | [5 empty] | 64% | [5 empty] | 64% | [5 empty] | 64% | [5 empty] | 64%
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 21 | 0 | 0 | 0 | 0 | 42 | 42 | 0 | 0 | 0 | 0 |  | 36 | 36 | 0 | 0 | 0 | 0 | 58 | 58 | 0 | 0 | 0 | 0 | 1999 | 1033 | 966 | 0 | 0 | 0 | 100% | 1033.81 | 966 | 0.19 | 0 | 0 | 100% | 88.39% | [5 empty] | 82.67% | [5 empty] | 100% | [5 empty] | 100% | [5 empty] | 4% | [11 empty] | 83% | 80% | 80% | 83%
Source
|  | IOM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | [6 empty] | 48% | 1044 | 21 | 450 | 6 | [7 empty] | 100% | 17 | 1 |  |  |  | 4% | [11 empty] | 51%
|  | NRC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 21 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 36 | 36 | 36 | 0 | 0 | 0 | 0 | 22 | 22 | 0 | 0 | 0 | 0 | 1941 | 975 | 966 | 0 | 0 | 0 | 100% | 81% | 0% | 19% | 0% | 0% | 2000 | [5 empty] | 0 | 100% | [5 empty] | 100% | [5 empty] | 100% | [17 empty] | 100%
|  | DRC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0
|  | INTERSOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0 | 88.39% | 322 | 0 | 13 | 0 | 0 | 100% | 266 | 19 | 41 | 3 | 0 | 100% | 368 | 44 | 103 | 25 |  | 100% | 36 | 1 | 5 | 0 | [13 empty] | 97%
Output 2: Refugees and asylum-seekers have improved access to protection services (UNHCR) | Output Indicator 2.1
| # of individuals supported with SGBV prevention and response | Planned | 137 | [5 empty] | 275 | [5 empty] | 413 | [5 empty] | 550 | [5 empty] | 550 | 1456 | [5 empty] | 1650 | [5 empty] | 1926 | [5 empty] | 2000 | [5 empty] | 2000 | 3156 | [5 empty] | 3156 | [5 empty] | 3156 | [5 empty] | 3156 | [5 empty] | NA | [5 empty] | 3156
|  | Achieved | 346 | 104 | 242 |  |  |  | 467 | 107 | 360 |  |  |  | 521 | 121 | 400 |  |  |  | 1047 | 196 | 851 |  |  |  | 1047 | 1789 | 351 | 1438 |  |  |  | 2201 | 446 | 1755 |  |  |  | 2565 | 665 | 1900 |  |  |  | 2697 | 677 | 2020 |  |  |  | 2697 | 2786 | 699 | 2087 |  |  |  | 2937 | 737 | 2200 |  |  |  | 2986 | 705 | 2281 |  |  |  | 3157 | 745 | 2412 |  |  |  | NA | [5 empty] | 3157 | [5 empty] | 3157 | 1650 | 3156 | 100%
Source
Output Indicator 2.2
| % of assisted refugees reporting that some of their immediate protection needs were fulfilled | Planned | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | NA | [5 empty] | 80%
|  | Achieved | - | [5 empty] | - | [5 empty] | - | [5 empty] | - | [5 empty] | - | - | [5 empty] | - | [5 empty] | - | [5 empty] | - | [5 empty] | - | - | [5 empty] | - | [5 empty] | - | [5 empty] | - | [5 empty] | NA | [5 empty] | - | [5 empty] | - | 90% | 80% | -
Source
Output Indicator 2.3
| # of gender-specific community-based committees working on SGBV prevention and response | Planned | 12 | [5 empty] | 12 | [5 empty] | 12 | [5 empty] | 12 | [5 empty] | 12 | 12 | [5 empty] | 12 | [5 empty] | 12 | [5 empty] | 12 | [5 empty] | 12 | 15 | [5 empty] | 15 | [5 empty] | 15 | [5 empty] | 15 | [5 empty] | NA | [5 empty] | 15
|  | Achieved | 12 | [5 empty] | 12 | 7 | 5 |  |  |  | 12 | 7 | 5 |  |  |  | 12 | 7 | 5 |  |  |  | 12 | 12 | 7 | 5 |  |  |  | 12 | 7 | 5 |  |  |  | 12 | 7 | 5 |  |  |  | 12 | 7 | 5 |  |  |  | 12 | 14 | 8 | 6 |  |  |  | 14 | 8 | 6 |  |  |  | 15 | 9 | 6 |  |  |  | 15 | 9 | 6 |  |  |  | NA | [5 empty] | 15 | [5 empty] | 15 | 48 | 15 | 100%
Source
Output Indicator 2.4
| # of children supported with child protection activities | Planned | 81 | [5 empty] | 162 | [5 empty] | 244 | [5 empty] | 325 | [5 empty] | 325 | 2000 | [5 empty] | 2200 | [5 empty] | 2400 | [5 empty] | 2600 | [5 empty] | 2600 | 5352 | [5 empty] | 5352 | [5 empty] | 5352 | [5 empty] | 5352 | [5 empty] | NA | [5 empty] | 5352
|  | Achieved | 85 |  |  | 42 | 43 |  | 438 |  |  | 227 | 211 |  | 891 |  |  | 502 | 389 |  | 1712 |  |  | 955 | 757 |  | 1712 | 2476 |  |  | 1376 | 1100 |  | 3539 |  |  | 2058 | 1481 |  | 4358 |  |  | 2551 | 1807 |  | 4848 |  |  | 2840 | 2008 |  | 4848 | 4875 |  |  | 2855 | 2019 |  | 4901 |  |  | 2871 | 2030 |  | 5072 |  |  | 3875 | 1197 |  | 5355 |  |  | 4091 | 1264 |  | NA | [5 empty] | 5355 | [5 empty] | 5355 | 975 | 5352 | 100.1%
Source
Output Indicator 2.5
| # of Best Interest Determination assessments conducted | Planned | 64 | [5 empty] | 128 | [5 empty] | 191 | [5 empty] | 255 | [5 empty] | 255 | 110 | [5 empty] | 120 | [5 empty] | 130 | [5 empty] | 140 | [5 empty] | 140 | 324 | [5 empty] | 324 | [5 empty] | 324 | [5 empty] | 324 | [5 empty] | NA | [5 empty] | 324
|  | Achieved | 55 |  |  | 26 | 29 |  | 82 |  |  | 37 | 45 |  | 87 |  |  | 41 | 46 |  | 97 |  |  | 57 | 40 |  | 97 | 110 |  |  | 62 | 48 |  | 178 |  |  | 107 | 71 |  | 219 | [5 empty] | 233 | [5 empty] | 233 | 255 |  |  | 195 | 60 |  | 299 |  |  | 229 | 70 |  | 321 |  |  | 245 | 76 |  | 325 |  |  | 249 | 77 |  | NA | [5 empty] | 325 | [5 empty] | 325 | 765 | 324 | 100.3%
Source
Output 3: Internally Displaced People (IDPs) have improved access to humanitarian and protection services (IOM & UNHCR) | Output Indicator 3.1
| # of IDPs receving unconditional cash grants (UNHCR) | Planned | 400 | [5 empty] | 800 | [5 empty] | 1200 | [5 empty] | 1600 | [5 empty] | 1600 | 4000 | [5 empty] | 4800 | [5 empty] | 5600 | [5 empty] | 6400 | [5 empty] | 6400 | 11205 | [5 empty] | 11205 | [5 empty] | 11205 | [5 empty] | 11943 | [5 empty] | NA | [5 empty] | 11205
|  | Achieved | 558 | 231 | 327 |  |  |  | 110 | 554 | 556 |  |  |  | 2865 | 1424 | 1440 |  |  |  | 3237 | 1607 | 1630 |  |  |  | 3237 | 5193 | 2591 | 2602 |  |  |  | 6714 | 3382 | 3332 |  |  |  | 7931 | 4219 | 3712 |  |  |  | 9825 | 5940 | 3884 |  |  |  | 9825 | 11641 | 7038 | 4602 |  |  |  | 11943 | 7221 | 4722 |  |  |  | 11943 | 7221 | 4722 |  |  |  | 7221 | 4722 |  |  |  |  | NA | [5 empty] | 11943 | [5 empty] | 11943 | 4800 | 11205 | 106.6%
Source
Output Indicator 3.2
| # ofIDPs receiving legal assistance (UNHCR) | Planned | 750 | [5 empty] | 1500 | [5 empty] | 2250 | [5 empty] | 3000 | [5 empty] | 3000 | 3750 | [5 empty] | 4500 | [5 empty] | 5250 | [5 empty] | 6000 | [5 empty] | 6000 | 12443 | [5 empty] | 12443 | [5 empty] | 12443 | [5 empty] | 12443 | [5 empty] | NA | [5 empty] | 12443
|  | Achieved | 831 | 526 | 305 |  |  |  | 1718 | 1020 | 698 |  |  |  | 2549 | 1545 | 1004 |  |  |  | 3020 | 1781 | 1240 |  |  |  | 3020 | 5415 | 2817 | 2599 |  |  |  | 7202 | 3646 | 3557 |  |  |  | 8606 | 4448 | 4159 |  |  |  | 8963 | 4596 | 4367 |  |  |  | 8963 | 9883 | 5068 | 4815 |  |  |  | 10803 | 5540 | 5263 |  |  |  | 11862 | 6083 | 5779 |  |  |  | 12445 | 6382 | 6063 |  |  |  | NA | [5 empty] | 12445 | [5 empty] | 12445 | 9000 | 12433 | 100.1%
Source
Output Indicator 3.3
| # of IDPs receiving PSS (UNHCR) | Planned | 4250 | [5 empty] | 8500 | [5 empty] | 12750 | [5 empty] | 17000 | [5 empty] | 17000 | 21250 | [5 empty] | 25500 | [5 empty] | 29750 | [5 empty] | 34000 | [5 empty] | 34000 | 43540 | [5 empty] | 43540 | [5 empty] | 43540 | [5 empty] | 43540 | [5 empty] | NA | [5 empty] | 43540
|  | Achieved | 3616 | 1756 | 1860 |  |  |  | 8492 | 4494 | 3998 |  |  |  | 17125 | 9066 | 8059 |  |  |  | 18467 | 9775 | 8692 |  |  |  | 18467 | 28245 | 14833 | 13412 |  |  |  | 30077 | 15923 | 14154 |  |  |  | 32587 | 17179 | 15408 |  |  |  | 34068 | 17873 | 16194 |  |  |  | 34068 | 34554 | 18128 | 16425 |  |  |  | 34554 | 18128 | 16656 |  |  |  | 39074 | 20498 | 18576 |  |  |  | 44472 | 23330 | 21242 |  |  |  | NA | [5 empty] | 44472 | [5 empty] | 44472 | 51000 | 43540 | 102.1%
Source
Output Indicator 3.4
| % of assisted IDPs reporting that some of their immediate protection needs were met (UNHCR) | Planned | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | NA | [5 empty] | 80%
|  | Achieved | - | [5 empty] | 99% | [5 empty] | - | [5 empty] | 90% | [5 empty] | 95% | - | [5 empty] | 93% | [5 empty] | - | [5 empty] | - | [5 empty] | - | - | [5 empty] | - | [5 empty] | - | [5 empty] | - | [5 empty] | NA | [5 empty] | - | [5 empty] | - | 75% | 80% | -
Source
Output Indicator 3.5
| # of IDPs and host community members benefiting from life-saving health care (IOM) | Planned | 4875 | [5 empty] | 9750 | [5 empty] | 14625 | [5 empty] | 19500 | [5 empty] | 19500 | 4875 | [5 empty] | 9750 | [5 empty] | 14625 | [5 empty] | 19500 | [5 empty] | 19500 | 4000 | [5 empty] | 8000 | [5 empty] | 12000 | [5 empty] | 16000 | [11 empty] | 16000
|  | Achieved | 5176 | 1078 | 2095 | 889 | 1114 | 0 | 8260 | 2220 | 3155 | 1319 | 1566 | 0 | 11159 | 3019 | 4098 | 1862 | 2180 | 0 | 15553 | 4055 | 5616 | 2741 | 3141 | 0 | 15553 | 5086 | 657 | 2317 | 1032 | 1080 | 0 | 9378 | 1704 | 3747 | 1899 | 2028 | 0 | 13877 | 2363 | 5380 | 2970 | 3164 | 0 | 15812 | 2836 | 6100 | 3326 | 3550 | 0 | 15812 | 4516 | 1222 | 1316 | 1016 | 962 | 0 | 16789 | 5666 | 4504 | 3409 | 3210 | 0 | 21890 | 6886 | 5907 | 4684 | 4413 | 0 | 25686 | 7624 | 7106 | 5532 | 5424 | 0 | 32381 | 8987 | 9673 | 6863 | 6858 | 0 | 32381 | 15878 | 21389 | 12930 | 13549 | 0 | 63746 | 53100 | 55000 | 115.9%
|  | Source | 0
|  | IOM MC (IDP) | 5176 | 1078 | 2095 | 889 | 1114 | 0 | 3084 | 1142 | 1060 | 430 | 452 | 0 | 2899 | 799 | 943 | 543 | 614 | 0 | 4394 | 1036 | 1518 | 879 | 961 | 0 | 15553 | 5086 | 657 | 2317 | 1032 | 1080 | 0 | 4292 | 1047 | 1430 | 867 | 948 | 0 | 4499 | 659 | 1633 | 1071 | 1136 | 0 | 1935 | 473 | 720 | 356 | 386 | 0 | 15812 | 4516 | 1222 | 1316 | 1016 | 962 |  | 12273 | 4444 | 3188 | 2393 | 2248 |  | 5101 | 1220 | 1403 | 1275 | 1203 |  | 3796 | 738 | 1199 | 848 | 1011 |  | 6695 | 1363 | 2567 | 1331 | 1434 |  | 32381 | 15878 | 21389 | 12930 | 13549 | 0 | 63746
|  | IOM RH (IDP) | 489 | 0 | 489 | 0 | 0 | 0 | 99 | 0 | 99 | 0 | 0 | 0 | 182 | 0 | 182 | 0 | 0 | 0 | 236 | 0 | 236 | 0 | 0 | 0 | 1006 | 106 | 0 | 106 | 0 | 0 | 0 | 108 | 0 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | 0 | 720 | 0 | 0 | 0 | 934 | 0 | [5 empty] | 202 |  | 202 |  |  |  | 60 |  | 60 |  |  |  | 212 |  | 212 |  |  |  | 593 | 277 | 207 | 89 | 20 |  | 1067 | 277 | 2621 | 89 | 20 | 0 | 3007
|  | IOM HA (IDP) | 987 | 340 | 504 | 68 | 75 | 0 | 854 | 324 | 430 | 59 | 41 | 0 | 221 | 52 | 137 | 17 | 15 | 0 | 1041 | 2 | 623 | 211 | 205 | 0 | 3103 | 655 | 88 | 404 | 76 | 87 | 0 | 1147 | 181 | 646 | 176 | 144 | 0 | 1523 | 250 | 787 | 259 | 227 | 0 | 734 | 189 | 364 | 95 | 86 | 0 | 4059 | 635 | 236 | 358 | 20 | 21 |  | 400 | 228 | 161 | 5 | 6 |  | 2594 | 604 | 756 | 633 | 601 |  | 2541 | 505 | 851 | 548 | 637 |  | 4350 | 896 | 1686 | 797 | 971 |  | 10520 | 3895 | 7707 | 2964 | 3116 | 0 | 17682
|  | IOM Vacc (IDP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | IOM MC (HC) | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | IOM RH (HC) | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | IOM HA (HC) | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | IOM Vacc (HC) | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Output Indicator 3.6
| # of IDPs and host community members benefiting from MHPSS and PSS (IOM) | Planned | 1000 | [5 empty] | 2000 | [5 empty] | 3000 | [5 empty] | 4000 | [5 empty] | 4000 | 1000 | [5 empty] | 2000 | [5 empty] | 3000 | [5 empty] | 4000 | [5 empty] | 4000 | 2000 | [5 empty] | 4000 | [5 empty] | 6000 | [5 empty] | 8000 | [11 empty] | 8000
|  | Achieved | 7113 | 327 | 856 | 3770 | 2160 | 0 | 11881 | 361 | 1067 | 6397 | 4056 | 0 | 15961 | 410 | 1498 | 7173 | 6880 | 0 | 16049 | 410 | 1498 | 7207 | 6934 | 0 | 16049 | 1374 | 44 | 226 | 813 | 291 | 0 | 6051 | 155 | 695 | 3062 | 2139 | 0 | 12629 | 195 | 767 | 7055 | 4612 | 0 | 15220 | 195 | 767 | 8095 | 5185 | 0 | 15220 | 12657 | 599 | 1453 | 6660 | 3945 | 0 | 32035 | 1310 | 3381 | 9309 | 5378 | 0 | 43048 | 463 | 1415 | 5567 | 3568 | 0 | 43140 | 0 | 86 | 1 | 5 | 0 | 43140 | 0 | 0 | 0 | 0 | 0 | 43140 | 2986 | 8622 | 37440 | 25361 | 0 | 74409 | 38400 | 16000 | 465.1%
Source
|  | IOM MHPSS (IDP) | 7113 | 327 | 856 | 3770 | 2160 | 0 | 4768 | 34 | 211 | 2627 | 1896 | 0 | 4080 | 49 | 431 | 776 | 2824 | 0 | 88 | 0 | 0 | 34 | 54 | 0 | 16049 | 1374 | 44 | 226 | 813 | 291 | 0 | 4677 | 111 | 469 | 2249 | 1848 | 0 | 6578 | 40 | 72 | 3993 | 2473 | 0 | 1613 | 0 | 0 | 1040 | 573 | 0 | 14242 | 12657 | 599 | 1453 | 6660 | 3945 | 0 | 0 | [5 empty] | 1086 | 57 | 111 | 566 | 352 |  | 92 | 0 | 86 | 1 | 5 |  | 0 | [5 empty] | 13835 | 1261 | 3915 | 22529 | 16421 | 0 | 44126
|  | IOM CRP (IDP) | [43 empty] | 978 | 9 | 22 | 601 | 346 | 0 | 978 | 0 | 0 | 0 | 0 | 0 | 0 | 19185 | 1259 | 3289 | 9304 | 5333 |  | 9518 | 319 | 1195 | 4872 | 3132 |  | 0 | [5 empty] | 0 | [5 empty] | 28703 | 1587 | 4506 | 14777 | 8811 | 0 | 29681
|  | IOM MHPSS (HC) | [43 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 193 | 51 | 92 | 5 | 45 |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 193 | 51 | 92 | 5 | 45 | 0 | 193
|  | IOM CRP (HC) | [43 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | [5 empty] | 409 | 87 | 109 | 129 | 84 |  | 0 | [5 empty] | 0 | [5 empty] | 409 | 87 | 109 | 129 | 84 | 0 | 409
| Output Indicator 3.7 | [38 empty] | 28678
| # of health facilities provided with operational support (IOM) | Planned | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 1 | [5 empty] | 1 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 1 | [5 empty] | 1 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 1 | [11 empty] | 1
|  | Achieved | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | [5 empty] | 4 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 9 | 7 | 7 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 7 | [5 empty] | 7 | 3 | 3 | 233.3%
Source
|  | IOM | 0 | [17 empty] | 0 | [5 empty] | 0 | [18 empty] | 1 | [5 empty] | 1 | 7 | 7 |  |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 | [5 empty] | 7 | [5 empty] | 8
Output Indicator 3.8
| # of child protection cases identified and assisted with reintegration support (IOM) | Planned | [18 empty] | 75 | [5 empty] | 75 | [18 empty] | 75 | [5 empty] | 75 | 87 | [5 empty] | 87 | [5 empty] | 87 | [5 empty] | 87 | [5 empty] | 87 | [5 empty] | 87
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 30 | 0 | 30 | 9 | 0 | 0 | 0 | 9 | 0 | 15 | 0 | 0 | 0 | 6 | 0 | 48 | 0 | 0 | 19 | 14 | 0 | 87 | 0 | 0 | 28 | 11 | 0 | 87 | 11 | 0 | 0 | 2 | 9 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 0 | 20 | 55 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 0 | 69 | 134 | 0 | 203 | 225 | 237 | 85.65%
Source
|  | IOM | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 30 |  |  |  | 30 |  | 30 | 9 | 0 | 0 | 0 | 9 | 0 | 6 | 0 | 0 | 0 | 6 | 0 | 33 | 0 | 0 | 19 | 14 | 0 | 39 | 0 | 0 | 28 | 11 | 0 | 87 | 11 |  |  | 2 | 9 |  | 0 |  |  | 0 | 0 |  | 75 | 0 | 0 | 20 | 55 |  | 0 | [5 empty] | 0 | [5 empty] | 86 | 0 | 0 | 69 | 134 | 0 | 203
Output Indicator 3.9
| # of IDPs and host community members referred for specialized services (IOM) | Planned | 318.75 | [5 empty] | 637.5 | [5 empty] | 956.25 | [5 empty] | 1275 | [5 empty] | 1275 | 318.75 | [5 empty] | 637.5 | [5 empty] | 956.25 | [5 empty] | 1275 | [5 empty] | 1275 | 99 | [5 empty] | 198 | [5 empty] | 296 | [5 empty] | 366 | [5 empty] | 436 | [5 empty] | 366
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 7 | 4 | 0 | 0 | 0 | 92 | 22 | 12 | 34 | 24 | 58 | 92 | 67 | 0 | 8 | 37 | 22 | 59 | 161 | 29 | 45 | 55 | 32 | 87 | 223 | 40 | 67 | 72 | 44 | 87 | 379 | 108 | 140 | 82 | 49 | 87 | 379 | 113 | 10 | 10 | 51 | 42 | 0 | 187 | 10 | 1 | 41 | 22 | 0 | 272 | 24 | 49 | 0 | 12 | 0 | 359 | 30 | 16 | 33 | 8 | 0 | 530 | 0 | 0 | 96 | 75 | 171 | 530 | 204 | 228 | 337 | 232 | 316 | 1001 | - | 2916 | 34.33%
Source
|  | IOM CRP (IDP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | [5 empty] | 58 | 0 | 0 | 34 | 24 | 58 | 58 | 59 | 0 | 0 | 37 | 22 | 59 | 28 | 0 | 0 | 18 | 10 | 28 | 29 | 0 | 0 | 17 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116 | 93 | 0 | 0 | 51 | 42 | 0 | 60 |  |  | 40 | 20 |  | 12 | 0 | 0 | 0 | 12 |  | 41 | 0 | 0 | 33 | 8 |  | 171 | 0 | 0 | 96 | 75 | 171 | 377 | 0 | 0 | 326 | 225 | 316 | 551
|  | IOM CRP (HC) | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NRC (IDP) | 0 | [5 empty] | 0 | [5 empty] | 11 | 7 | 4 | 0 | 0 | 0 | 23 | 15 | 8 | 0 | 0 | 0 | 34 | 8 | 0 | 8 | 0 | 0 | 0 | 66 | 29 | 37 | 0 | 0 | 0 | 33 | 11 | 22 | 0 | 0 | 0 | 156 | 68 | 73 | 10 | 5 | 0 | 263 | 20 | 10 | 10 | 0 | 0 | 0 | 11 | 10 | 1 |  |  |  | 73 | 24 | 49 |  |  |  | 46 | 30 | 16 | 0 | 0 |  | 0 | [5 empty] | 150 | 204 | 228 | 10 | 5 | 0 | 447
|  | NRC Children (IDP) | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 1 |  |  |  | 1 |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 1 | 0 | 0 | 0 | 1 | 0 | 1
|  | NRC (HC) | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NRC Children (HC) | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2 |  |  | 1 | 1 |  | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 2 | 0 | 0 | 1 | 1 | 0 | 2
Output Indicator 3.10
| # of beneficiaries of legal assistance (CDR) for Yemeni displacement affected populations (IOM) | Planned | 108 | [5 empty] | 217 | [5 empty] | 325 | [5 empty] | 433 | [5 empty] | 1275 | 108 | [5 empty] | 217 | [5 empty] | 325 | [5 empty] | 433 | [5 empty] | 1275 | 375 | [5 empty] | 750 | [5 empty] | 1125 | [5 empty] | 1500 | [11 empty] | 1500
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371 | 186 | 185 | 0 | 0 | 0 | 875 | 342 | 533 | 0 | 0 | 0 | 875 | 1171 | 419 | 518 | 140 | 94 | 0 | 3434 | 1538 | 1662 | 140 | 94 | 0 | 4681 | 2156 | 2291 | 140 | 94 | 0 | 6252 | 2702 | 2968 | 297 | 285 | 25 | 6252 | 695 | 391 | 304 | 0 | 0 | 0 | 1035 | 507 | 528 | 0 | 0 | 0 | 1356 | 670 | 686 | 0 | 0 | 0 | 2931 | 1513 | 1418 | 0 | 0 | 0 | 2931 | 1513 | 1418 | 0 | 0 | 0 | 2931 | 4557 | 4919 | 297 | 285 | 25 | 10058 | 8975 | 4050 | 248.3%
Source
|  | NRC legal counselling (IDP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 371 | 186 | 185 | 0 | 0 | 0 | 504 | 156 | 348 | 0 | 0 | 0 | 875 | 1171 | 419 | 518 | 140 | 94 | 0 | 2263 | 1119 | 1144 | 0 | 0 | 0 | 1247 | 618 | 629 | 0 | 0 | 0 | 1287 | 477 | 493 | 157 | 160 | 25 | 5968 | 557 | 315 | 242 | 0 | 0 | 0 | 340 | 116 | 224 |  |  |  | 321 | 163 | 158 |  |  |  | 1575 | 843 | 732 | 0 | 0 |  | 0 | [5 empty] | 2793 | 4412 | 4673 | 297 | 254 | 25 | 9636
|  | NRC legal assistance (IDP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283 | 0 | 0 | 141 | 142 | 0 | 385 | 0 | 0 | 183 | 202 | 0 | 668 | 464 | 89 | 45 | 158 | 172 | 0 | 1966 | 673 | 603 | 384 | 306 | 0 | 1073 | 591 | 482 | 0 | 0 | 0 | 1287 | 477 | 493 | 157 | 160 | 0 | 4790 | 186 | 33 | 68 | 39 | 46 | 0 | 395 | 5 | 66 | 184 | 140 |  | 34 | 13 | 21 |  |  |  | 1017 | 7 | 10 | 498 | 502 |  | 0 | [5 empty] | 1632 | 1888 | 1788 | 1744 | 1670 | 0 | 7090
|  | NRC legal counselling (HC) | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 284 | 69 | 184 | 0 | 31 | 0 | 284 | 138 | 76 | 62 | 0 | 0 | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 138 | 145 | 246 | 0 | 31 | 0 | 422
|  | NRC legal assistance (HC) | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 1073 | 153 | 192 | 373 | 355 | 0 | 1073 | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 153 | 192 | 373 | 355 | 0 | 1073
Output Indicator 3.11
| # of IDPs receiving awareness sessions on civil documentation rights and humanitarian assistance (IOM) | Planned | 417 | [5 empty] | 834 | [5 empty] | 1251 | [5 empty] | 1668 | [5 empty] | 1668 | 417 | [5 empty] | 834 | [5 empty] | 1251 | [5 empty] | 1668 | [5 empty] | 1668 | 250 | [5 empty] | 500 | [5 empty] | 750 | [5 empty] | 1000 | [11 empty] | 1000
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451 | 253 | 177 | 17 | 4 | 0 | 4864 | 377 | 757 | 1249 | 2030 | 0 | 4864 | 749 | 0 | 656 | 37 | 56 | 0 | 4148 | 1761 | 1638 | 0 | 0 | 0 | 6089 | 975 | 966 | 0 | 0 | 0 | 9117 | 817 | 1811 | 152 | 248 | 74 | 9117 | 336 | 151 | 185 | 0 | 0 | 0 | 1252 | 354 | 513 | 16 | 33 | 0 | 1531 | 108 | 171 | 0 | 0 | 0 | 2441 | 560 | 350 | 0 | 0 | 0 | 2441 | [5 empty] | 2441 | 5356 | 7224 | 1471 | 2371 | 74 | 16422 | 4336 | 4336 | 378.7%
Source
|  | NRC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451 | 253 | 177 | 17 | 4 | 0 | 4413 | 377 | 757 | 1249 | 2030 | 0 | 4864 | 749 | 0 | 656 | 37 | 56 | 0 | 3399 | 1761 | 1638 | 0 | 0 | 0 | 1941 | 975 | 966 | 0 | 0 | 0 | 3028 | 817 | 1811 | 152 | 248 | 74 | 9117 | 336 | 151 | 185 | 0 | 0 | 0 | 916 | 354 | 513 | 16 | 33 |  | 279 | 108 | 171 |  |  |  | 910 | 560 | 350 | 0 | 0 |  | 0 | [5 empty] | 2441 | 5356 | 7224 | 1471 | 2371 | 74 | 16422
Output Indicator 3.12
| % of surveyed IDPs and host community members reporting satisfaction with services received (IOM) | Planned | [50 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80%
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.5% | 50% | 43% | 0% | 0% | 0% | 0.465 | 88.5% | [5 empty] | 94% | [5 empty] | 96% | [5 empty] | 48.5% | [5 empty] | 0% | [11 empty] | 87% | 80% | 80% | 87%
Source
|  | IOM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | [5 empty] | 0 | 83% | 28 | 32 | 0 | 0 |  | 92% | 2 | 10 | [27 empty] | 88%
|  | NRC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.5% | 50% | 43% | 0% | 0% |  | 0.465 | 94% | 50 | 44 | 0 | 0 | 0 | 96% | [5 empty] | 96% | [5 empty] | 97% | 560 | 350 | [15 empty] | 86%
Output Indicator 3.13
| % of surveyed IDPs and host community members aware of the availability of a feedback mechanism (IOM) | Planned | [50 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80% | [5 empty] | 80%
|  | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90% | 50% | 40% | 0% | 0% | 0% | 90% | 0% | [5 empty] | 50% | [5 empty] | 100% | [5 empty] | 100% | [5 empty] | 0% | [5 empty] | 100% | [5 empty] | 95% | 80% | 80% | 95%
Source
|  | IOM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [6 empty] | 0% | 28 | 32 |  |  |  | 0% | 16 | 45 | 25 | 15 | [25 empty] | 0%
|  | NRC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90% | 50% | 40% | 0% | 0% |  |  | 0% | [5 empty] | 100% | [5 empty] | 100% | [5 empty] | 100% | [17 empty] | 98%
Output 4: Strengthened protection monitoring and support to Community Based Protection Networks (UNHCR) | Output Indicator 4.1
| # of active Community Based Protection Network members trained/engaged | Planned | 73 | [5 empty] | 85 | [5 empty] | 90 | [5 empty] | 99 | [5 empty] | 99 | 140 | [5 empty] | 140 | [5 empty] | 140 | [5 empty] | 140 | [5 empty] | 140 | 187 | [5 empty] | 187 | [5 empty] | 187 | [5 empty] | 187 | [5 empty] | NA | [5 empty] | 187
|  | Achieved | 73 | 22 | 51 |  |  |  | 73 | 22 | 51 |  |  |  | 116 | 85 | 31 |  |  |  | 139 | 98 | 41 |  |  |  | 139 | 142 | 102 | 40 |  |  |  | 141 | 85 | 56 |  |  |  | 153 | 86 | 67 |  |  |  | 174 | 106 | 68 |  |  |  | 174 | 174 | 106 | 68 |  |  |  | 174 | 106 | 68 |  |  |  | 183 | 111 | 72 |  |  |  | 188 | 114 | 45 |  |  |  | NA | [5 empty] | 188 | [5 empty] | 188 | 99 | 187 | 100.5%
Source
Output Indicator 4.2
| # of people in need identified through protection monitoring | Planned | 20000 | [5 empty] | 40000 | [5 empty] | 60000 | [5 empty] | 80000 | [5 empty] | 80000 | 130000 | [5 empty] | 145000 | [5 empty] | 160000 | [5 empty] | 175000 | [5 empty] | 175000 | 241295 | [5 empty] | 241295 | [5 empty] | 241295 | [5 empty] | 241295 | [5 empty] | NA | [5 empty] | 241295
|  | Achieved | 34054 | 17508 | 16546 |  |  |  | 64876 | 31154 | 33722 |  |  |  | 98930 | 48662 | 50268 |  |  |  | 107930 | 53045 | 54886 |  |  |  | 107930 | 137314 | 67203 | 70112 |  |  |  | 189728 | 93052 | 96678 |  |  |  | 227160 | 116011 | 111149 |  |  |  | 230495 | 118077 | 112418 |  |  |  | 230495 | 231472 | 118577 | 112894 |  |  |  | 232449 | 119078 | 113371 |  |  |  | 236561 | 121190 | 115371 |  |  |  | 241415 | 123677 | 117738 |  |  |  | NA | [5 empty] | 241415 | [5 empty] | 241415 | 240000 | 241295 | 100%
Source
Output 5: Strengthened coordinatino through Protection Cluster support (UNHCR) | Output Indicator 5.1
| # of staff members and government authorities trained | Planned | 125 | [5 empty] | 188 | [5 empty] | 250 | [5 empty] | 250 | [5 empty] | 250 | 375 | [5 empty] | 438 | [5 empty] | 500 | [5 empty] | 500 | [5 empty] | 500 | 1896 | [5 empty] | 1896 | [5 empty] | 1896 | [5 empty] | 1896 | [5 empty] | NA | [5 empty] | 1896
|  | Achieved | 25 | 10 | 15 |  |  |  | 55 | 22 | 33 |  |  |  | 549 | 342 | 207 |  |  |  | 880 | 542 | 338 |  |  |  | 880 | 941 | 571 | 370 |  |  |  | 1252 | 709 | 543 |  |  |  | 1665 | 873 | 792 |  |  |  | 1665 | 873 | 792 |  |  |  | 1665 | 1729 | 906 | 822 |  |  |  | 1793 | 940 | 853 |  |  |  | 1837 | 963 | 874 |  |  |  | 1896 | 994 | 902 |  |  |  | NA | [5 empty] | 1896 | [5 empty] | 1896 | 750 | 1896 | 100%
Source
Output Indicator 5.2
| # of information products produced and disseminated | Planned | 8 | [5 empty] | 15 | [5 empty] | 23 | [5 empty] | 30 | [5 empty] | 30 | 76 | [5 empty] | 90 | [5 empty] | 105 | [5 empty] | 120 | [5 empty] | 120 | 250 | [5 empty] | 250 | [5 empty] | 250 | [5 empty] | 250 | [5 empty] | NA | [5 empty] | 250
|  | Achieved | 5 | [5 empty] | 16 | [5 empty] | 21 | [5 empty] | 66 | [5 empty] | 66 | 106 | [5 empty] | 106 | [5 empty] | 106 | [5 empty] | 211 | [5 empty] | 211 | 220 | [5 empty] | 220 | [5 empty] | 235 | [5 empty] | 250 | [5 empty] | NA | [5 empty] | 250 | [5 empty] | 250 | 90 | 250 | 100%
Source
Output Indicator 5.3
| # of protection cluster meetings held each quarter | Planned | 3 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3 | 3 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3 | 3 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3
|  | Achieved | 3 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3 | 3 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3 | 3 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3 | 3 | 3 | 100%
Source
Output 6: Yemeni population displacement and migrant monitoring (IOM) | Output Indicator 6.1
| # of reports made available to humanitarian actors in Yemen | Planned | 17 | [5 empty] | 24 | [5 empty] | 30 | [5 empty] | 31 | [5 empty] | 102 | 17 | [5 empty] | 24 | [5 empty] | 30 | [5 empty] | 31 | [5 empty] | 102 | 19 | [5 empty] | 42 | [5 empty] | 63 | [5 empty] | 85 | [11 empty] | 85
|  | Achieved | 6 | [5 empty] | 12 | [5 empty] | 17 | [5 empty] | 23 | [5 empty] | 23 | 4 | [5 empty] | 12 | [5 empty] | 20 | [5 empty] | 26 | [5 empty] | 26 | 15 | [5 empty] | 31 | [5 empty] | 46 | [5 empty] | 68 | [5 empty] | 90 | [5 empty] | 90 | [5 empty] | 139 | - | 289 | 48.1%
Source
|  | DTM Area Assessment | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 1 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 1 | 0 | [11 empty] | 0 | [11 empty] | 0 | [5 empty] | 0 | [5 empty] | 1
|  | Governorate monitoring | 2 | [5 empty] | 2 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 9 | 2 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 10 | 12 | [5 empty] | 13 | [5 empty] | 11 | [5 empty] | 16 | [5 empty] | 16 | [5 empty] | 68 | [5 empty] | 87
|  | TFPM/Displacement Dashboard | 1 | [5 empty] | 1 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 2 | 0 | [5 empty] | 3 | [5 empty] | 0 | [11 empty] | 3 | 0 | [11 empty] | 0 | [11 empty] | 0 | [5 empty] | 0 | [5 empty] | 5
|  | MCLA | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0 | 1 | [5 empty] | 0 | [5 empty] | 0 | [11 empty] | 1 | 0 | [11 empty] | 0 | [11 empty] | 0 | [5 empty] | 0 | [5 empty] | 1
|  | Migrant flow monitoring | 3 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 3 | [5 empty] | 12 | 0 | [5 empty] | 3 | [5 empty] | 5 | [5 empty] | 3 | [5 empty] | 11 | 3 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 6 | [5 empty] | 6 | [5 empty] | 22 | [5 empty] | 45
Output Indicator 6.2
| # of trainees receiving training on the new/enhanced DTM tools, methodologies, and quality control procedures to ensure the accurate and comprehensive data collection. | Planned (Previousely as # of trainings) | 0.75 | [5 empty] | 1.5 | [5 empty] | 2.25 | [5 empty] | 3 | [5 empty] | 3 | 0.75 | [5 empty] | 1.5 | [5 empty] | 2.25 | [5 empty] | 3 | [5 empty] | 3 | 0 | [5 empty] | 1500 | [5 empty] | 1500 | [5 empty] | 2300 | [11 empty] | 2300
|  | Achieved | 104 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 33 | 27 | 6 | 0 | 0 | 0 | 1966 | 1574 | 392 | 0 | 0 | 0 | 1981 | 1586 | 395 | 0 | 0 | 0 | 2162 | 1729 | 433 | 0 | 0 | 0 | 2162 | 104 | 79 | 25 | 0 | 0 | 0 | 277 | 161 | 12 | 0 | 0 | 0 | 701 | 341 | 83 | 0 | 0 | 0 | 701 | 0 | 0 | 0 | 0 | 0 | 701 | 0 | 0 | 0 | 0 | 0 | 701 | 2414 | 553 | 0 | 0 | 0 | 2967 | - | 2306 | 128.7%
Source
|  | IOM | 104 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 33 | 27 | 6 | 0 | 0 | 0 | 1933 | 1547 | 386 | 0 | 0 | 0 | 15 | 12 | 3 | 0 | 0 | 0 | 181 | 143 | 38 | 0 | 0 | 0 | 2162 | 104 | 79 | 25 |  |  |  | 173 | 161 | 12 |  |  |  | 424 | 341 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | [5 empty] | 701 | 2414 | 553 | 0 | 0 | 0 | 2967
Output 7: Cholera Response (IOM) This activity took place exclusively between 1st September 2017 and 31st August 2018. | Output Indicator 7.1 | [70 empty] | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | #REF!
| # of cholera cases treated at supported facilities | Planned | [49 empty] | 20000
|  | Achieved | [49 empty] | 22472 | [36 empty] | 22472 |  | 20000 | 112.4%
Source
Output Indicator 7.2
| # of people reached through health awareness activities | Planned | [49 empty] | 65600
|  | Achieved | [49 empty] | 60600 | [36 empty] | 60600 |  | 65600 | 92.38%
Source
Output Indicator 7.3
| # of people benefiting from water chlorination activities | Planned | [49 empty] | 80000
|  | Achieved | [49 empty] | 400000 | [36 empty] | 400000 |  | 80000 | 500%
Source
Output Indicator 7.4
| # individuals benefiting from water trucking | Planned | [49 empty] | 30000
|  | Achieved | [49 empty] | 14658 | [36 empty] | 14658 |  | 30000 | 48.86%
Source
Output Indicator 7.5
| # of people benefiting from rehabilitation of water networks | Planned | [49 empty] | 30000
|  | Achieved | [49 empty] | 56987 | [36 empty] | 56987 |  | 30000 | 190%
Source
Output Indicator 7.6
| # of people receiving cholera hygiene kits | Planned | [49 empty] | 70000
|  | Achieved | [49 empty] | 56000 | [36 empty] | 56000 |  | 70000 | 80%
Source
Output Indicator 7.7
| # of people benefiting from solid and liquid waste management activities | Planned | [49 empty] | 80000
|  | Achieved | [49 empty] | 111102 | [36 empty] | 111102 |  | 80000 | 138.9%
Source