 Programme Completion Review

Title: Building Disaster Resilience in Pakistan (BDRP)
Final Programme Spend £ (full life): £ 30.8 million approx.	Review Date:	September - November 2020
Programme Code: 203264	Start Date: July 2014	End Date: September 2020

Summary of Programme Performance

Year	2015	2016	2017	2018	2019	2020 (PCR)
Programme Score	B	B	A	A	A	A
Residual Risk Exposure Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	https://devtracker.fcdo.gov.uk/projects/GB-1-203264/documents
DevTracker Links to all logical frameworks used during programme lifetime:	https://devtracker.fcdo.gov.uk/projects/GB-1-203264/documents

A. Summary and Overview

Overall Description and Achievement:

The Building Disaster Resilience in Pakistan (BDRP) programme aimed to increase Pakistan’s capability to reduce disaster risk through better planning, preparedness and response at government and community levels. The programme was divided into: Phase I (September 2016 – September 2018); and Phase II (October 2018 – September 2020), with three main components:

Component I: Building community resilience through Community-Based Disaster Risk Management (CBDRM) by introducing practical measures to mitigate the risk from disasters and increase resilience to shocks. Selected villages and communities were involved in the development of hazard and resource maps and risk management plans. This component was delivered through a consortium, led by Concern Worldwide in partnership with ACTED, Welthungerhilfe (WHH) and the International Rescue Committee (IRC), together with their respective downstream partners in some districts.

Component II: Strengthening the Government’s District, Provincial and National disaster management architecture through: increased provincial and district technical capacity in hazard mapping; preparedness and contingency planning; as well as response. This element was delivered by the Food and Agriculture Organization (FAO), United Nations Development Programme (UNDP) and World Food Programme (WFP), with FAO being the lead agency.

Component III: Third Party Monitoring (TPM) to complement internal consortium monitoring and increase accountability, oversight and evidence-based learning on the programme, and to inform the design of future humanitarian and resilience programming in Pakistan. Phase II of this component was contracted to Integrity and its local partner VTT Global.

The programme worked in two districts each in Punjab (Rajanpur and Muzaffargarh) and Sindh (Ghotki and Kashmore) during Phase I. In Phase II, the programme scaled up work in Punjab and Sindh and expanded into Khyber Pakhtunkhwa (KP), based on district vulnerability profiles. The nine districts covered during the programme’s lifetime were:
- Punjab - Rajanpur, Muzaffargarh, Jhang;
- Sindh - Ghotki, Kashmore, Tharpakar, Dadu;
- KP - Chitral and DI Khan.

BDRP performance has been mixed over the life of the programme and has underperformed at the impact level despite achieving its agreed outcome and output targets. The original targets set out in the Business Case were modified to reflect on the ground realities and an evolving context. At the output level, the programme broadly met expectations and has been particularly instrumental during the last year in responding quickly and at par to the Covid-19 pandemic and the locust emergency. This required changes to the Theory of Change (ToC) and shifted the focus to short term response rather than planned longer term impact.

Due to the onset of Covid-19 in March 2020, regular programme activities were paused and the livelihoods of most BDRP communities were affected, mainly due to business closures, limited access to markets and government lockdown restrictions. Overall, the CBDRM structures played a role in awareness raising in the community and in bringing about behaviour change in terms of minimising the impact of the disease. The programme pivoted to include 24 new activities (18 by the Institutional Strengthening consortium in 3 districts – Jhang, Ghotki and Dera Ismail Khan – and 6 by the CBDRM consortium in all BDRP districts) supporting Covid-19-affected communities.

Prior to BDRP, there was a limited evidence base for large scale CBDRM work in Pakistan. The BDRP programme has generated useful learning on how CBDRM, alongside institutional strengthening, can promote better disaster risk management while building the resilience of vulnerable communities to natural disasters. BDRP was a key part of FCDO Pakistan’s International Climate Fund (ICF) offer and contributed significantly to the ICF targets which were part of the programme’s logical framework.

The key highlights of the programme include:
- The programme supported more than 1.5 million poor individuals: (48% women, 52% men, 2.5% people with disabilities (PWDs) and 5.7% elderly) to cope with disasters through a range of approaches including: the establishment of district level disaster coordination structures for improved response; training of farmers and demonstration of agriculture techniques, relevant in a changing climate, with provision for enhanced household income; and disaster resilient infrastructure schemes, such as bridges and culverts which enhanced the mobility, market access and evacuation routes in times of disaster.
  [note] Small channel that allows water to flow under an obstruction, e.g. a road, railroad, or trail.
- Agro-ecological zoning for Punjab and Sindh: which provides a sound foundation for implementation of agricultural interventions based on updated data and analysis.
- Application of an agriculture stress index system: to detect geographical areas with a higher likelihood of water stress and implications for food security. The system developed under BDRP is now hosted and managed by government to generate timely drought alerts.
- Increased resilience and inclusion of communities. One of the BDRP intervention districts in Sindh was hit by floods this year. The partners have reported no deaths in the targeted project areas because of timely activation of the early warning system and subsequent evacuation at community level. The programme design emphasised an inclusive approach with due focus on the needs of women, men, PWDs and the elderly. Disaggregated data is available for all the activities.

Lessons Learned
BDRP has contributed well to disaster resilience across the three provinces, but despite some successes, experience and evidence suggest a conceptual shift is needed, for the next phase of integrated resilience and humanitarian programming through BRAVE (Building Resilience and Averting Vulnerability to Emergencies), which is currently under design, including:
- Greater emphasis on problem analysis rather than needs as an entry point to action. Proximity, relationship-building and understanding of communities will lead to more appropriate activities, helps delivery partners to navigate the political/power relations and greater involvement of communities in project design with greater focus on women and girls. The most significant determinant of a person’s life chances is whether they were born male or female. BRAVE must move beyond participation of the most vulnerable towards addressing the root causes of exclusion by actively mainstreaming gender equality;
- Greater and integrated investment in household, community resilience and institutional strengthening to reduce vulnerability and improve capacity to anticipate, absorb and adapt, ensuring strategies are based on problem analysis and baselines that identify gaps, improving FCDO’s ability to quantify attributable change;
- Strengthen GoP policy and institutions and their capacity to plan/coordinate resilience and response activities, given Pakistan is a middle-income country with a functioning DRM system. Implementation plans should include processes for GoP to consult/work with local communities to ensure plans are adapted to the local context;
- Coordination and communication amongst the two main delivery components (CBDRM and Institutional Strengthening) remained a challenge throughout the programme’s life, and considerable effort and time of the programme team from FCDO went into aligning the work of the two components/consortia.

Recommendations
The programme learning and evidence has been generated through a number of different means. TPM provided systematic evidence and learning at both output and outcome levels, while consortium partners undertook a range of evaluation and research activities to investigate different aspects of the programme and used findings to adapt interventions accordingly. The following are some of the key recommendations for future programming:
- Process and impact evaluation throughout the programme would have helped to test assumptions and improve the quality of programming. The programme’s own independent evaluation component was dropped, due to reductions to the budget, whereas the Pakistan Evidence and Learning Platform (PELP) designed for FCDO Pakistan humanitarian and resilience programming under MYHP was closed prematurely due to supplier registration issues. An independent evaluation is strongly recommended for any successor programme with specific provision for process evaluation at different intervals to improve progress towards outcomes and impact. Third-party monitoring should be aligned with programme implementation timelines;
  [note] United Nations Institute for Training and Research (UNITAR) responsible for the PELP couldn’t get the required permission to work in Pakistan.
- FCDO teams should undertake a comprehensive political economy/conflict sensitivity analysis as part of future portfolio design (in early 2021) to understand the ground realities, devise a stakeholder engagement strategy and devise strategies to tackle power dynamics and ensure women are included in programme design and implementation in an appropriate way;
- Due to BDRP interventions, resilience infrastructure and knowledge have improved at the community level. However, the sustainability of these gains remains unclear with more than 60 multi-sectoral activities implemented within a span of two years under each phase. This proved to be quite ambitious and resulted in implementing partners focusing on delivery of outputs rather than strategizing impact level change. Wide-ranging early market engagement sessions should be conducted to finalise the management and delivery partners and modalities for any successor programme. Future programme interventions would be more sustainable and impactful with a longer time frame through a community driven, inclusive, and outcome-led approach through selection of delivery partners who can involve relevant government departments in planning and implementation. There needs to be a greater focus on outcomes and sustainability with the inclusion of outcome based milestone payments.
- The future portfolio should build on the approaches tested by BDRP with greater focus on a smaller number of high-impact activities. Any successor programme could also pilot new activities to respond to multiple disasters over wider geographical areas. The activities should be aligned with the 10 priority areas of Pakistan’s National Disaster Management Plan.
- The assumption in the ToC that training individuals and developing strategies would lead to sustained capacity of communities and respective government departments did not hold. Participatory, locally appropriate approaches strengthened short-term sustainability, but longer-term capacity building of institutions will require a more systemic and deep rooted approach within government systems.
- Better synergies with other FCDO programmes, implemented at district and provincial levels, e.g. Sub National Governance (SNG II) programme would have supported greater appetite and policy engagement on resilience in Punjab and KP. The coordination within and between all programme stakeholders, including programme components, and other FCDO and donor programmes should be strengthened in BRAVE by making it a formal performance criterion for improved programme delivery, ownership, and sustainability.

How this report was conducted:
The PCR was led by the BDRP lead technical advisor and BDRP programme manager together with inputs from two independent team members from FCDO. The process included interviews with government stakeholders, partners and a desk-based review of partner reports. Due to the Covid-19 pandemic, the team was not able to visit the field, however third party monitors and partners were able to feed into this report and provided valuable insights. The review was quality assured by the Senior Responsible Owner for BDRP, the Team Leader (Climate, Humanitarian and Resilience Team), FCDO Pakistan programme effectiveness team and reviewed by Head of Governance Group DFID Pakistan.

Compliance actions following approval of this report
- Ensure that the annual audited accounts and financial statements linked to the final year of the programme’s expenditure are received from all partners by February 2022, i.e. within 18 months of programme closure. Action: Senior Responsible Owner (SRO); and
- Ensure that any unspent funds remaining under each component, after paying all outstanding liabilities for activities, are settled as soon as possible and remaining funds are transferred to FCDO’s central contingency fund at latest by February 2022. Action: SRO.

Acronyms

AR	Annual Review
AEZ	Agro-Ecological Zoning
ARBIs	Agriculture Resilience Building Initiatives
ADRMOPs	Agricultural Disaster Risk Management Operational Plan
BC	Business Case
BDRP	Building Disaster Resilience in Pakistan
BRAVE	Building Resilience and Averting Vulnerability to Emergencies
CDMC	Community Disaster Management Committee
CBDRM	Community Based Disaster Risk Management
COVID	Corona Virus Disease
CSA	Climate Smart Agriculture
DDMAs	District Disaster Management Authorities
DFID	Department for International Development
DRM	Disaster Risk Management
DRR	Disaster Risk Reduction
FAO	Food and Agriculture Organisation of the United Nations
FFS	Farmer Field School
FCDO	Foreign Commonwealth and Development Office
GoP	Government of Pakistan
GLOFs	Glacier Lake Outburst Floods
GPS	Global Positioning System
IEC	Information, education and communication
(I)NGO	(International) Non-Governmental Organisation
KP	Khyber Pakhtunkhwa
LFA	Logical Framework Agreement or Log Frame
LFFS	Livestock Farmer Field Schools
MYHP	Multi Year Humanitarian Programme
M&E	Monitoring and Evaluation
NDMA	National Disaster Management Authority
O&M	Operation and Management
PCD	Procurement and Commercial Department
PCR	Programme Completion Review
PELP	Pakistan Evidence and Learning Platform
PDMAs	Provincial Disaster Management Authorities (Punjab and Sindh)
PMD	Pakistan Meteorological Department
PPE	Personal protective equipment
PWDs	People with disabilities
SIMEX	Emergency response simulation trainings and exercises
SOPs	Standard Operating Procedures
ToC	Theory of Change
TPM	Third party monitor
UC	Union Council
UERT	Union Council Emergency Response Teams
UCRF	Union council response forums
UCDRF	Union Council Disaster Resilience Fund
UN	United Nations
UNDP	United Nations Development Programme
VfM	Value for Money
VERT	Village Emergency Response Team
WASH	Water, Sanitation and Hygiene
WFP	World Food Programme
WHH	Welthungerhilfe
WOS	Women Open Schools

## B: Theory of Change and Outcome Assessment

The BDRP budget and timeframe was reduced significantly following its approval in 2014. The original design in the BC was first revised during the inception phase of the programme, in April 2017, to improve targeting. It was revised again in 2019, to incorporate learning which led to changes in the types of activities delivered.
[note] The Business Case was approved in July 2014. However, procurement was delayed because of staffing gaps and the need for further design work. In addition, the programme budget was reviewed through the Bilateral Aid Review (BAR) and Spending Review of DFID programmes, which resulted in a reduction in the overall programme budget from £76.3 million to £40.8 million.

It has been challenging to test the impact statement ‘Poor people in Pakistan (especially women) are more resilient to natural disasters’ as a large-scale disaster has not hit the communities targeted across all the districts of BDRP. However, monsoon floods in Sindh in 2020 did provide some evidence against impact indicators as explained below.

The programme’s Theory of Change is provided below.

Floods in Sindh: The 2020 floods in Sindh affected District Dadu the most as all the seven Union Councils (UCs) under BDRP were flooded. No loss of life was reported in these seven UCs as communities evacuated the villages in a timely manner. The communities had taken the following measures to limit the scale of the damage: / The Union Council Disaster Management Committees (UDMC) and Village Disaster Management Committees (VDMC) used WhatsApp groups in riverine flood areas to share information with the public at large and with other villages at the potential risk sites to take precautionary measures. / The UDMC reinforced the flood protection wall around the UC. / The communities have effectively used the emergency response equipment to help the affected population. / No loss of life was reported which implies that the resilience of communities has been strengthened. In comparison, the floods of 2011 reported 19 deaths in District Dadu.
[note] http://reliefweb.int/sites/reliefweb.int/files/resources/1511sitrep.pdf

The logical framework was periodically reviewed and updated during the life of the programme. Changes in the logical framework for Phase II included:
- Outcome 1 and 2 were slightly revised ensuring their relevance with the agreed interventions of BDRP Phase II;
- The timing of milestones was changed to bring it in line with Annual Review timing;
- Subsequent output-level targets were added in 2020 to reflect the additional Covid-19 activities and locust response;
- Disaggregated numbers were provided on sex and disability for Phase-II targets.
BDRP helped many communities to better understand disaster risk and vulnerability and adopt appropriate coping strategies. However, at the institutional level, progress was been mixed. An assessment of outcome achievements against targets is given in the table below:

OUTCOME: Increased capacity of communities and the Government to reduce disaster risk, though better planning, preparedness, response, and resource allocation at the governmental and community levels.
Outcome Indicators	PCR Target	Outcome Assessment	Outcome Rating
Number of people whose resilience has improved as a result of project support	Low resilient Households (HHs): 60% / Medium resilient HHs: 30% / High resilient HHs: 10%	Partner developed Household Resilience Indicator (HRI) indicated that at the time of baseline survey conducted in 2017, 78% households (1468 out of 1870) were in the category of Low Resilient HRI, 18% in Medium Resilient HRI and only 4% were in High Resilient category. At the end line survey – 2020: / Low resilient HHs: 38% / Medium resilient HHs: 33% / High resilient HHs: 29% / HRI provided good quantitative data but it didn’t capture resource allocation at community level as stated in the overall outcome statement. See Annex I for description of the methodology used.	A (Outcome met expectations)
DRR sectoral strategies, policies and plans adopted by stakeholders	- 15 (13 Ph-I & 2 Ph-II) strategies, policies and plans are endorsed by the Governments (KP, Sindh and Punjab) / - Climate smart agriculture is integrated in Agriculture Policy for at least one province / - 9 District emergency operation centres (DEOCs) operational and are reflected in DRM plans. / - 30% of the developed plans/ policies/ strategies are being implemented by the government in DRR/ DRM actions	- 15 (13 Ph-I & 2 Ph-II) strategies, policies and plans are endorsed by the Governments (KP, Sindh and Punjab) but no proper consideration was given to ensure adoption of these strategies by Government. / - Climate smart agriculture is integrated in Agriculture Policy for Punjab province as chapter. / Overall, no evaluation of this indicator has been done by partner resulting in less confidence on results achieved under this indicator.	B (Outcome moderately did not meet expectations)

The evidence and learning generated, particularly through TPM did encourage iterative reflection. In terms of translating outputs into the programme outcome, the following points were observed:
- Anecdotal evidence indicates that BDRP helped many communities to better understand disaster risk and vulnerability (documented in Concern’s independent evaluation and TPM reports);
- Community capacity to reduce disaster risk across a range of activity areas was enhanced and improvements in the overall resilience of men and women were recorded over the two phases (assessed on the basis of the Household Resilience Index above);
- In terms of inclusion, detailed inclusion guidelines were developed for each sector by partners and rolled out in the field. Overall, 48% women, 52% men, 2.5% PWDs and 5.7% elderly were reached under the programme. Capacity building and orientation sessions on inclusion of PWDs and the elderly were organised in each targeted district for field staff and relevant district level government departments. The programme was instrumental in registering PWDs with the districts social welfare departments. For example, around 75 PWDs from each targeted district have since become entitled to benefits from government schemes such as health care, cash grants, and exemption from some taxes;
- More emphasis was given to developing policies and strategies rather than adoption, which resulted in a weak connection with development planning by government and eventually allocation of resources.

Value for Money (VfM)
- The VfM argument made in the Business Case stage still holds; i.e. a CBDRM treated village hit by a disaster will require reduced emergency assistance compared to a non-treated village. All three BDRP outputs generally performed well against the criteria of relevance, efficiency, and equity. It is more challenging to assess the effectiveness and sustainability of the BDRP programme at this stage, mainly due to the lack of independent evaluation.
- The HRI data and evaluation study (in targeted districts) indicates that there are now 38% of households in the Low Resilient Category (compared to 78% in the baseline survey), 33% households in the Medium Resilient Category (compared to 18% in the baseline survey), and 29% in the High Resilient Category (compared to only 4% in baseline survey).
  [note] HRI explained in detail under Annex 1
- Partners evaluation reports cite many examples where individual households were able to increase their income significantly under Output 3. The communities reported more than a 50% increase in crop production (wheat, potato) due to the provision of high quality seeds. The households (approx. 75% targeted farmer families) multiplied the high quality seed and sold it to neighbouring farmers, and thus fetched a better return than selling in the market. The provision of vegetable seeds to women has promoted kitchen gardening, and improved household nutrition. Women beneficiaries reported an improvement in household nutrition as well as earning approx. Rs. 3000 on a monthly basis by selling their vegetables to neighbouring communities.
- The infrastructure provided under Output 1 at the household level (hand pumps, shelter rooms, etc.) and community level (roads, bridges, culverts, irrigation channels, drinking water supply schemes, etc.) improved community access to markets and service providers and is likely to help them cope with future disasters. For example, an iron bridge (with an input cost of £21,000) was re-constructed in Chitral to enhance the mobility of communities and consequently the livelihood opportunities. The community was able to save the labour cost of more than £140,000, (this was just the savings on account of the labour used for loading/ unloading goods on trucks during the past 6 months). The other co-benefits like access to main city markets, availability of gasoline, etc., were in addition to this.
- The CBDRM consortium across the whole programme indicated that female beneficiaries’ employment status improved from 2% to 22%, while unemployed status decreased from 41% to 4%.
- Moreover, case study examples suggest a range of costs from £2,200-2,500 to benefits of £10,000-50,000, depending on the intervention considered. This suggests benefit-cost ratios of 4.5-20, which is a return of £4.5 - £20 for every £1 spent. As these are only case study examples and not representative, the overall results could vary significantly. However, this still suggests strong VfM for this stand of work, and the programme overall.

For a programme input cost of approximately £2,500 per Union Council Disaster Management Committee (UCDMC), the programme has managed to increase economic opportunities which is an important indicator for building resilience of communities to disasters in terms of savings available. A preliminary financial analysis of one of the UCDMCs in district Rajanpur when estimated for potential economic benefits provides a figure of approximately £50,000* thus significantly improving community resilience. / (*Based on financial analysis, ratios, cost calculations mechanism and referred methods for calculating financial benefits/ returns of some of development interventions as listed in the BDRP- End of project evaluation, BDRP II Mid-term evaluation, and the BDRP Business Case documents).
[note] Includes set-up and operations, and training costs, but not exposure visits costs.
[note] For select variable such as investment cost of 2 KM of road; investment cost of 300 meter of pavement connecting two UC villages; investment cost of 1 KM long flood protection to the entire UC; estimates of avoided agriculture productivity loss because of flood protection; estimated savings on costs potential loss of life cost as avoided by flood embankment; avoided health related expenses because of improved communications etc.

## C: Detailed Output Assessment

Output Number #1 and Title		Target communities have resilience building measures in place (disaggregated by community structures, households)
Output Score		A
Impact weighting (%)		40%	Impact weighting revised since last AR?	No

Output Indicator	Final Logical framework Target		Final Result Achieved	Indicator Score
1.1 Number of community-based disaster risk management structures established and functioning effectively	630 Village Disaster Management Committees established (VDMCs) / 63 Union Council Disaster Management Committees (UCDMC) established / 28 Union Council Emergency Response Teams (UCERTs) established		645 Village Disaster Management Committees established - A / 93 Union Council Disaster Management Committees established – A+ / 28 Union Council Emergency Response Teams (UCERTs) established - A	A (met expectation) / Based on the Group Maturity Index (GMI) done by the partner, 41.3% of the UCs and 20% of the village level social structures achieved highest maturity level, i.e. institutional independence stage based on the GMI ranking - indicating these structures are more likely to continue functioning after the BDRP’s support is over. / Most of the structures under highest maturity levels are from Phase I which shows that community group development processes take time and need sustainability plans.
1.2 Number of people who have benefitted from improved Water, Sanitation and Hygiene (WASH)	Safe defecation (beneficiaries of triggering exercises): 903,000 (male 460,530; female 442,470; disabled 45,150) / Safe drinking water through water supply schemes: 374, 818 (male 191,157, female 183,661, disabled 7,500) / Communities received prevention messages on Covid-19 through mass awareness campaigns / 4,896,031 (male 2,506,768; female 2,389,263; disabled 97,921) / Beneficiaries trained in skills for fighting Covid-19 (sanitizers, masks, soaps) / 4,410 (male 2,258, female 2,152, disabled 88) / UNDP to sterilise 6 public buildings and sanitise in 1 Federal and 3 Provincial areas		Safe defecation (beneficiaries of triggering exercises): 975,864 (male 499,642; female 476,222; disabled 19,517) – A / Safe drinking water through water supply schemes: 615,138 (male 315,102; female 300,036, disabled 16,290) – A++ / Communities received prevention messages on Covid-19 through mass awareness campaigns / 7,403,968 (male 3,790, 832; / female 3,613,136, disabled 148,079) – A++ / Beneficiaries trained in skills for fighting Covid-19 (sanitizers, masks, soaps) / 6,474 (male 699, female 5,775, disabled 30) – A++ / Procurement has been completed while a disinfection exercise will be completed by 30th Dec under a new arrangement between UNDP and FCDO - C	A (met expectation) / This indicator was flexed following approval on BDRP’s Covid-19 response activities. The major changes include inclusion of provision/installation of 27 water supply schemes in the targeted health units which approximately doubled the total number of beneficiaries reached. / However, UNDP planned activity under institutional strengthening component was agreed as part of Covid-19 pivot; however, remained incomplete and will be undertaken under MYHP to ensure sustainability of BDRP work.
1.3 Number of people who have benefitted from improved DRR infrastructure	273,000 (male 139,230, female 133,770; disabled 13,650) through 378 schemes		332,110 (male 170,040, female 162,070, disabled 9,908) through 382 schemes	A+ (moderately exceeded expectation) / All the targeted plus additional schemes have been completed.
1.4 Number of people who have benefitted from disaster resilient shelters	5,600 persons (male 2,856 female 2,744) benefitted from 800 disaster resilient shelters		5,656 persons (male 2,885 female 2,771, disabled 131) benefitted from 808 disaster resilient shelters	A (met expectation)

Supporting narrative for the score:
This output has met or exceeded all milestones and has scored an ‘A’ overall. The output was able to swiftly respond to Covid-19 related needs on the ground from March 2020 and demonstrated a sufficient level of effort by the partners to complete all the activities on time. Marginalised groups like women, children, PWDs and the elderly were a primary focus of all interventions under Component I.

Indicator # 1.1: The range of CBDRM activities generally responded to the priorities of beneficiaries and stakeholders. Learning from Phase 1, combined with stakeholder consultation, ensured trainings were generally relevant to local needs and context. A number of local incidents, as well as drought in some locations, tested different V/UDMCs. This enabled the stronger ones to put skills and training into practice, in the process building their profile and legitimacy in the wider community and at district levels. However, many committees and their skills have not been fully tested yet. Lately, the Covid-19 pandemic saw many groups play an important role in awareness campaigns. As per the TPM assessment, in 68% (231 out of 338 beneficiaries) of instances it was reported that V/UDMC members were involved in awareness raising, promoted precautionary measures, and conducted sessions regarding Covid-19 spread, where they sensitised the community to wear face masks and wash hands with soap. However, the short programme time frame meant there was little time for committees to systematically address wider risk reduction priorities in their plans while supported by the CBDRM consortium.

Indicator # 1.2: The range of WASH-related activities was seen as relevant, given recurring issues and concerns around water contamination and access to clean drinking water for vulnerable groups. Water contamination of pumps and wells during flooding, and in normal times, was regularly highlighted as a concern, while water pump design responded to a need to improve access for PWDs and the elderly. Hygiene promotion training validated through TPM were found to be relevant in all locations. There were indications that hygiene awareness training was contributing to improved sanitation practice; for example, there was a reduction in open defection and an increase in hand washing and cleaning.

Indicator # 1.3 and 1.4: The DRR infrastructure projects remained on course to provide a valuable contribution to community resilience. Beneficiaries assessed through TPM confirmed the relevance of disaster-resilient shelters, and BDRP interventions were seen as relevant to the needs and climatic conditions of the disaster-prone communities. The value in emergencies of medium to large-scale livelihood and DRR infrastructure schemes (like evacuation routes and bridges) was highlighted by most beneficiaries. As with the new hand pumps, PWD considerations were clearly factored into community infrastructure projects, improving day-to-day or emergency access to safe place or designated assembly points, and sending clear messages about inclusion. While replication of designs among the wider community was challenging, there were positive examples of good practice spreading to non-beneficiary households which introduced partial improvements, often with raised foundations, light roof structures and other essential features. Challenges included low community awareness to enable scaling up; limited household resources to pay for improvements/additional work; and the absence of supporting information, education and communication materials in some locations.

VfM Assessment:
It is evident through different programme reports and case studies that Output 1 performed well and delivered good VfM. Building on one district’s preliminary results (detailed in the next bullet) on overall VfM for bringing DRM to communities, suggests a cost-benefit ratio of 4.5:1. That is a return of £4.5 for every £1 spent. However, given this is only one district example, and does not include all costs.

Provision and replication of shelter, which is flood resilient and safe, reduced losses and disaster vulnerabilities of local communities. For a programme input cost of approximately £2,200 per village the programme has provided approximately £10,000 in terms of avoided disaster housing damage costs; rebuilding cost savings; increased disposable income of vulnerable village households; increased skilled mason earning (reported 20% increase in baseline construction income post training); and avoided assets loss per year. Though the average unit cost for shelters has been slightly higher as compared to similar interventions - findings from an outcome assessment, on replication of shelters in five programme districts, show that 84% of the community members partially replicated the BDRP model shelter; while 16% constructed their homes in the same vicinity with full replication of the shelter.
[note] Includes shelter related costs, masons training costs, and tools costs etc.
[note] Based on financial analysis, ratios, cost calculations mechanism and referred methods for calculating financial benefits/returns of some of development interventions as listed in the BDRP I End of project evaluation, BDRP II Mid-term evaluation, and the BDRP Business Case documents

All the community based disaster risk management structures were established and functioning effectively as assessed by partners independent evaluation and TPM reports. These structures have offered distribution of roles and responsibilities within community members in times of disasters. According to VfM assessments done by Concern and TPM reports, 30% of vulnerable group participation was mandatory in VDMC formation with women taking 45% of the total membership and while 2% membership went to PWDs. 58% of total beneficiaries utilising water facilities provided by the programme were women and 6% were PWDs. Of the total beneficiaries of household resilient shelters, 48% were women.

The costs incurred against the Output 1 indicators were within a range of +/- 20% but often varied significantly over the last year due to the Covid-19 context. Where baseline data was available, it was observed that actual costs incurred by the consortium during the year demonstrated savings except for the efficiency measure for CBDRM trainings, which was marginally higher than the baseline due to Covid-19 SOPs requirement. See table below:

Type	Indicator	Baseline	Q5	Q6	Q7
Economy	Cost per community structured formed including trainings	£294	£106	£115	£240
Economy	Cost per beneficiary of establishing a VDMC	£0.18	N/A	N/A	£0.15
Economy	Cost per disaster management plan produced	£1,496	N/A	N/A	£1,222
Efficiency	Unit cost per participant for CBDRM trainings delivered	£125	£81	£69	£139
Equity	Percentage of women members represented in VDMC		37%	37%	45%
Equity	Percentage of PWDs members represented in VDMC/UDMC	N/A	2%	2%	2%

Lessons learned through this output, and recommendations for future programming:
If the established community structures continue to exist and perform, they will need at least two to three more years to be fully mature and independent. Any successor programme should allow longer periods of social mobilisation before and after formation, with external support phasing out once committees are registered and functioning effectively and accountably for better sustainability of programme interventions.

The Community Based Disaster Risk Management Committees were generally created using existing social structures. Buying into existing power dynamics can serve to further reinforce exclusion of certain groups and decrease the likelihood of women’s involvement. Currently the structures are gaining community acceptance as well as building skills in understanding needs, developing plans and articulating demands. If the successor programme plans to revive the existing structures, FCDO should continue to have at least one follow-up visit over the coming year to further understand implementation challenges and ensuring co-ordination with government as well as other FCDO and donor programmes.

Overall, the programme strived to put mechanisms in place for sustainability, mainly through the design of the programme and exit strategy, which included operation and maintenance of constructed infrastructure, linkages between V/UDMCs and social welfare departments. Any future intervention should particularly emphasise registration of committees at UC level and/or reconsider whether the current V/UDMC structure is the most effective means of building resilience at these levels by taking into consideration the National Disaster Management Plan guidelines which suggest formation of structures primarily at the UC level. Relevant government departments should be involved in the construction of medium to large livelihood infrastructure, from planning to handover, for sustainability and required follow-up support. The Union Council Disaster Management Plans (UCDMPs) prepared should feed into district-level planning such as DRR plans, agriculture resilience plans and other plans developed by government.

Output Number #2 and Title		Target stakeholders have improved skills and systems to develop, plan and apply DRM and DRR strategies and SOPs
Output Score		B
Impact weighting (%)		20%	Impact weighting revised since last AR?	No

Output Indicator	Final Logical framework Target		Final Result Achieved	Indicator Score
2.1 Number of strategic and policy documents developed	FAO: / 2 Provincial Agro Ecological Zoning (AEZ) document for Punjab and Sindh developed / 5 AEZ bi-product document / 3 Provincial Agriculture Stress Index System (Punjab, KP and Sindh) / 2 Provincial drought operational plans (Sindh and Punjab) / Resilient value chain strategies adopted/implemented in 9 targeted districts / 2 Agriculture Resilient Building Initiatives (ARBI) documents / WFP / 1 module on E-school safety / UNDP: / 03 provincial working groups formed on public private partnership / 03 provincial hackathons on disaster preparedness and response organized / 1 Monsoon Contingency Plan for 2020 developed with PDMA KP		FAO: / 2 Provincial AEZ document (Punjab, Sindh) / 5 AEZ bi-product document / 3 Provincial Agriculture Stress Index System (Punjab, KP and Sindh) / 1 Provincial drought operational plan for Sindh developed. Not completed for Punjab. / Resilient value chain strategies adopted/implemented in 9 targeted districts / 2 ARBI documents - A / WFP: / 1 module on E-school safety - A / UNDP: / 03 provincial working groups formed on public private partnership / 03 provincial hackathons on disaster preparedness and response organize / 1 Monsoon Contingency Plan for 2020 developed with PDMA KP (UNDP has planned this intervention, however during execution, focus shifted from provincial to national as WFP supported PDMA KP, and UNDP utilized its resources to support NDMA) - A	A (met expectation)
2.2 Number of DRM/DRR plans, strategies and structures developed and adopted by target stakeholders	FAO: / 4 District ADCRMOPs (Muzaffargarh, Rajanpur, Kashmore and Ghotki) / 2 Provincial ADRMOPs (Punjab, Sindh) / 9 target district level Climate smart profiles / UNDP: / 9 District DRR plans developed / 4 annual reviews of DRR plans / 09 District emergency operation centres (DEOCs) established		FAO: / 4 District ADCRMOPs (Muzaffargarh, Rajanpur, Kashmore and Ghotki) / 2 Provincial ADRMOPs (Punjab, Sindh) / 9 target district level Climate smart profiles in in the process of being developed (final deliverable delayed) - A / UNDP: / 9 District DRR plans developed / 4 annual reviews of DRR plans / 05 DEOCs completed, (04 are in process (will be handed over by end Oct) - B	B (moderately did not meet expectation)
2.3 Number of people trained with new DRR/DRM Skills	FAO: / 4,640 persons trained through 44 capacity building events / UNDP: / 330 persons trained through 05 Provincial Disaster Risk Reduction (DRR) & Climate Change Adaptation (CCA) training / 09 training sessions organized for district officials on DRR, CCA and Early Rapid Needs Assessment (ERNA) guidelines / WFP: / 125 persons trained through 3 emergency response Simulation Exercises (SIMEX) trainings / 2 capacity development and augmentation sessions / 1 of E-School Safety Modules launched / Concern: / 124,500 people trained with new DRR/DRM skills		FAO: / 4,640 persons trained through 44 capacity building events – B (Data taken from FAO’s preliminary report- final report delayed) / UNDP: / 330 persons trained through 05 Provincial DRR & CCA training / For DRR, CCA and ERNA guidelines trainings, 04 training sessions are completed - B / WFP: / 80 persons trained through 2 SIMEX training sessions. / 2 capacity development and augmentation sessions have been conducted / 1 E-School Safety Module was developed but not launched due to Covid-19. - B / (WFP’s activities were delayed due to Covid-19; hence another arrangement has been agreed between WFP and FCDO and they will continue these activities under MYHP now) / Concern: / 167,524 (male 85772, female 81,752, disabled 3350 – A+	B (moderately did not meet expectation)
2.4 Number of advisory structures established and functional at district, provincial and federal level	FAO: / 19 Provincial Management Committee meetings done / 7 Technical Support Group meetings / 6 Programme Steering Committee meetings		FAO: / 19 Provincial Management Committee meetings done / 7 Technical Support Group meetings / 5 Programme Steering Committee meetings	B (moderately did not meet expectation)

Supporting narrative for the score:
This output aimed to improve the level of knowledge among government and disaster management practitioners, strengthening the skill base and ensuring adequate resources were in place to plan, prepare and respond to a disaster and to implement stronger DDR and DRM strategies. The output struggled to embed and sustain long term improvements in government capacity and moderately missed most milestones and therefore scored a ‘B’ overall.

Indicator # 2.1: The Agro Ecological Zoning (AEZ) documents introduced the identification of revised agro-ecological zones in Punjab and Sindh. New zones have been established based on climate, soil characteristics, crop norms, and economic variables. The AEZs are supporting the formulation of policies and strategies for sustainable and diversified use of natural resources and investments to harness production potential. In the longer run, the government and associated stakeholder will be able to adapt to the unique zonal requirements and will amend cropping systems according to water availability, soil and climatic conditions and market demands. Furthermore, the provincial governments have prepared 6 PC-1s linked to beneficial crops highlighted by the AEZ. UNDP formed working groups on public private partnership (PPP) involving key private sector actors in KP, Sindh, and Punjab. Frameworks for PPP already exist in all the provinces in the form of PPP Cells; however, they were not adequately involved in DRR. This work was slightly affected by the restrictions on movement due to Covid-19 during the last year.
[note] Planning Commission Proforma 1 (PC-1) – is a planning tool for the development and execution of any projects in Pakistan Government Departments.

Indicator # 2.2. & 2.3: Over 4,600, government officials, programme partners and others received training in DRR/DRM through this output. However, the majority of officials interviewed in depth by the TPM did not feel BDRP capacity building had significantly changed behaviour and competence of trained government personnel. Adoption of knowledge products at the district and provincial level also showed mixed results. There were numerous reasons why government involvement in document development was weak and ranged from a lack of clear strategy for some activities to limited or no involvement by relevant government decision makers and technical experts for others. Beneficiaries (officials) stated that some of the documents were useful in the wake of rapid climatic changes, such as the agro-ecological zoning document developed by FAO in Punjab and under development in Sindh. PDMA Punjab also appreciated WFP establishing District Emergency Operation Centres (DEOCs) and requested similar centres at the Provincial level which they felt would be very helpful in preparing and responding to any disasters especially during the Covid-19 response. PDMA KP recommended a closer coordination with the KP Government under any humanitarian and resilience future programme and was not satisfied with work done under Output 2.

Indicator # 2.4: The main coordination mechanism was the high-level quarterly Steering and Programme Management Committee Meetings, hosted by the National and Provincial Disaster Management Authorities (NDMA and PDMA) respectively, and facilitated by FAO. Delays in Technical Support Group formation and their subsequent meeting affected progress at the field level. The coordination mechanism established through the formation of Technical Support Groups varied across districts and in most districts did not work effectively. This was, in part, due to inconsistent interest and direction from government officials and provincial departments. This resulted in lower operational involvement, of the relevant departments, during the programme cycle and limits its sustainability beyond the programme’s life.

VfM Assessment:
Unit costs for strategy and policy development under Output 2 showed a mixed trend over the programme life. As the programme evolved and activities were scaled up, unit cost variance both increased and decreased for different output interventions. For example, a) Unit costs for updating/defining AEZ at provincial levels doubled over 3 years; b) Unit costs for establishing EOC’s tripled, and c) Unit cost per agriculture disaster management operational plan (ADMOP) halved. Unit costs per provincial level policy/strategy development showed a favourable trend from £4,058 to £3,266 during Phase I and II respectively.

All consortium partners for Output 2 employed district administration and government premises to establish and execute programme workplans resulting in maximum possible economy. However, the inflation rate over the years resulted in higher costs of execution. This increase was offset and managed within the agreed budget.

The adoption of BDRP led good practices in cotton, wheat and vegetable cultivation (laser levelling, ridge sowing and compost application etc.), ensured the project beneficiaries achieved a cumulative increase of 14%, 25% and 20% respectively in Gross Value of their Production. Similarly, introduction of the use of ridges for watering, reduced the total area to which surface irrigation was to be applied, reducing water consumption by 20-30%. This is proving to be of immense help for drought hit areas specifically in Sindh.

Although this output did not include direct interventions aimed at challenging discrimination and harmful social norms, all interventions were screened through a gender lens to ensure no harm, and inclusivity beyond the scope of the project. FCDO and the FAO consortium ensured that marginalised and disaster-prone areas were included in the government endorsed villages selected for programme implementation.

Lessons learned through this output, and recommendations for future programming:
Complementarity and strong coordination, amongst various programme components, are essential to achieve clear common and sustainable objectives with strong government buy-in (e.g. embedding programme deliverables and learning within relevant government forums). The coordination within and between all programme stakeholders, including programme components and other FCDO and donor programmes, should be strengthened by making it a formal performance criterion for improved programme delivery, ownership, and sustainability.

A TPM deep dive in November 2019 found that officials’ awareness and use of the knowledge products, being produced under the programme, appears to be relatively low. Capacity building activities do not seem to have significantly contributed to improved performance and competence of trained officials. There were multiple challenges faced when engaging with the Government, including constraints such as: frequent government staff turnover, capacity issues, and the lack of policy/legislation and resources to operationalise knowledge products. The ToC assumption that training individuals and developing strategies would lead to sustained capacity being built and adoption of practices/policies did not hold in Pakistan’s context. For training in particular to be more effective, future programmes should consider measures such as departmental need and buy-in; evidence based training need assessment, documentation of training records and post training impact assessment studies.

The coordination mechanism established through the formation of Technical Support Groups varied across districts and in most districts did not work effectively. This was in part due to inconsistent interest and direction from government officials and provincial departments. This resulted in lower operational involvement of the relevant departments during the programme life. A government engagement strategy should be devised at the beginning of the programme to map out different government stakeholders, their roles and responsibilities, capacity needs and support required. More systematic involvement of Planning and Development (P&D) department should be looked into under the successor programme. Successful implementation of plans depended largely on availability of financial resources. The programme teams will have to make sure that plans are translated into action by being reflected in annual development plans or through approval of PC1s before rolling out.

Output Number # 3 and Title		Target communities are introduced to sustainable livelihoods and environmental management practices for resilience building
Output Score		A
Impact weighting (%)		40%	Impact weighting revised since last AR?	No

Output Indicator	Final Logical framework Target		Final Results Achieved	Indicator Score
3.1 Number of community level on-farm agricultural resilience building initiatives and new improved environmental management practices demonstrated which support resilience and sustainable livelihoods	FAO: / 26 Agricultural Resilience Building Initiatives (ARBI) practices demonstrated / 108 Climate Smart Agriculture (CSA) demo plots established / 27 Climate Smart Villages (CSVs) formed / 343 of FFS/WOS/LFFS / Food security assistance (Agri inputs etc.) provided to 1000 households (HH) as part of CoviD-19 emergency response / 50 Ultra Low Volume (ULV) Sprayers & and 1300 personal protective equipment (PPEs) handed over to government / Concern: / 3845 Plots established		FAO: / 26 ARBI practices demonstrated / 154 CSA demo plots established (additional plots established and demonstrated - target's overachieved) / 27 CSV formed / 343 of FFS/WOS/LFFS - A / Food security assistance (Agri inputs etc.) provided to 1000 HHs (distribution will be completed by 10th Oct) / 44 Ultra Low Volume (ULV) Sprayers & and 1300 PPEs handed over to government – (Remaining 6 will be handed over in October) - B / Concern / 4468 Plots established – A+	A (met expectation)
3.2 Number of households in targeted areas (most vulnerable 20%) that have benefitted from diversified livelihood options	107,414 Households		126,701 Households.	A+ (moderately exceeded expectation)
3.3 No of beneficiaries who have received Covid-19 cash grants (disaggregated by gender)	Concern: / 21,150 (male 10,830, female 10,320, disabled 423) / FAO: / 450 (male 400, female 50)		Concern: / 21,727 male 10,034, female 10,034, disabled 192) - A+ / FAO: It was not possible for FAO to complete activities as planned. Budget allocated to these activities was moved to provide 400 additional HH with Agri inputs. - B	A (met expectation) / Cumulative target for Concern and FAO was 21,600 of which more than 98% was to be delivered by Concern. The cumulative target was achieved.
[note] ARBI lists climate smart agriculture interventions along with their production technology which can be adopted under various climatic conductions

Supporting narrative for the score:
Output 3 aimed to introduce communities to sustainable livelihoods and environmental management practices for resilience building. The programme did this by implementing ARBIs, establishing climate smart agricultural (CSA) demonstration sites/ plots, establishing farmer field schools (FFS)/ women open schools (WOS) and livestock farmer field schools (LFFS). With most milestones being met, and strong performance and flexibility in the last 6 months of the programme, as part of the FCDO’s response to Covid-19 and the desert locust outbreak, the Output has scored an ‘A’ overall.

Indicator # 3.1 & 3.2: The FFS approach, alongside its livestock variant (LFFS) and Women Open School, responded to a clear need to address outdated practices, improve productivity, build system capacities, and strengthen the resilience of farmer’s livelihoods. Together with on-farm demonstrations (ARBIs), these training schools offered a practical capacity building approach. There were clear signs that livelihood activities have influenced practice beyond the direct beneficiary group. There is documented evidence through both partner and TPM assessments that farmers have changed their behaviours and agricultural methods, farmers have seen increased yields and have better access to services and information offered by the Agriculture Department. TPM reports indicated that BDRP helped to improve access to livelihood opportunities for women, although there is still more to be done to involve women and PWD in activities. Monitoring teams found that kitchen gardens, under Output 3.2, helped vulnerable families meet their food needs during Covid-19, in particular, and allowed some women to save up to 3,000 PKR per month. During lockdowns, some families were also able to sell excess vegetables to their neighbours or relatives at low rates as markets were closed. At the implementation level, TPM identified some issues which may have affected results slightly. These included the need to better link the timing of some training to cropping seasons; providing tool kits along with (or immediately following) training; and ensuring training was consistently detailed enough and delivered at a pace suitable for participants.

FAO worked with the Government of Pakistan’s (GoPs) agricultural line agencies to provide 44 Ultra Low Volume pesticide micron sprayers for vehicles, 1,303 items of Personal Protection Equipment (PPE) and 100 Global Positioning System (GPS) devices to support locust control operations through FCDO support. This strengthened the GoPs response capacity which ensured strong implementation of the locust response across the country with minimal to no support required during the later phases.

Indicator # 3.3: Cash Grants Assistance (CGA) of PKR 7,500 (per household) was provided to the most vulnerable households whose income sources were disrupted due to Covid-19 lock downs. The CGA were distributed through e-transfer with the support of Mobile telecoms. The assistance enabled the beneficiaries to meet their basic needs, at least for one month. An assessment was conducted by the partners to assess the proportion of funds spent on food and other household needs. 92% of the respondents spent the cash grant within the month received, the majority covered food and medical expenses. It was not possible for FAO to complete cash grant activities as planned. Budget allocated to these activities was moved to provide 400 additional HH with agricultural inputs with FCDO agreement.

VfM Assessment:
Within the total FSL budget, 40% was spent on vocational skills training, followed by crop seeds distribution at 24% and CSA trainings at 12% (Concern). The unit cost per beneficiary on CSA and vocational training showed a reduction over the course of the programme, indicating savings, although unit costs for training livestock workers and on crop seed packages increased. Case study assessments suggested that most of the training beneficiaries’ income has now doubled. The TPM team conducted a review of vocational skills training in Jhang district which confirmed that they had been effective; female participants (41-45% of the total participants) recorded an increase in employment attributable to the training. In terms of women focused investments in training, 96% of the participants in farmer training on livestock management feed and fodder preservation technologies and practice were women, while this percentage was 40% in training sessions on improved community capacity in livestock management. Vocational skill training in Phase 2 districts had 55% women participants and 41% of the small to medium entrepreneurs were women.
[note] This refers to average unit cost across all BDRP districts. Unit cost in few districts (mainly Punjab) was less than the estimated baseline value, it was very high for the remaining districts (mainly for Chitral and remote areas of Sindh) that impacted the overall average cost.

Climate Smart Agriculture (CSA) practiced and demonstrated based on the local context and farmer’s interest, under this output, primarily targeted water conservation and hazard resilience without compromising the economic benefits. 154 demonstration plots were established to test, validate and document community-level and on-farm 26 ARBIs for agro-ecological and hazard zones of project districts with a unit cost of USD 165. Establishment of demonstration plots has inculcated a multiplier effect. Under each of 154 demo plots, 25 beneficiaries were trained, i.e. 3,850 farmers in total were supported. Assuming that one demo plot was replicated per person trained, the total positive socio-economic impact is estimated at around USD 635,250.

On vocational skill training, around 61% of participants had zero income prior to training, which went down to only 6% of people reporting no income generation after receiving training. 41% of women and 15% of men were unemployed before training and results showed that only 4% remained unemployed (male and female both) after receiving vocational training.

The timely provision of micron sprayers and PPE addressed the imminent threat from the desert locust outbreak, ensuring food security, nutrition and sustainable agriculture. The provided support has treated 100,000 hectares of land and benefitted approx. 16,666 households in one month delivering at par with the anticipated delivery targets and timeframe. The control operations will be continued in the coming months and through these sprayers more famers/ households will get the benefits. Moreover, these sprayers are assets which will remain with agriculture departments for pest control measures going forward.

Lessons learned through this output, and recommendations for future programming:
Phase I and II showed that demonstration plots were an effective way of introducing new ideas to farmers, highlighting the need to strengthen linkages with markets to ensure seeds are available for farmers in future. The household nutrition/kitchen gardening package should consider beneficiaries’ preferences, local climatic conditions to align with respective cropping seasons and adapt based on feedback received from existing beneficiaries. In-addition the scale of interventions was limited considering the targeted number of beneficiaries and the benefits, beyond improved nutrition levels of households, has been documented/verified.

It was found that Women Open Schools received less support from government departments. This should be strengthened by taking into consideration cultural sensitivities around women's participation and involvement of female staff in the agriculture department.

Farmers Business Schools should have been formed at beginning of the programme to make them fully operational by the end of the programme and should have also focused on medium to large scale farmers. TPM highlighted the need for a stronger focus on quality, rather than quantity, in field schools with only a few crops/topics selected to allow more intensive sessions for greater effectiveness and impact. Vocational training courses, and activities should complement similar government and other donor training programmes to further strengthen beneficiaries FSL through better employability.

Not all interventions were successful. For example, those that required greater longer-term support from government departments or technical institutes, such as hydroponics and community-based quality seed production, were not taken up as readily by communities and were assessed as less sustainable. The involvement of relevant agriculture and livestock departments should be strengthened by aligning with similar initiatives, being led by the government, to promote sustainability and the replication of learned skills.

The programme did not conduct an evaluation, which has made it hard to assess how programme activities, for Output 3, have collectively contributed to the resilience of targeted households. Whilst the TPM and implementing team completion reports have identified some evidence of resilience being built though programme activities, it has been difficult to judge attribution and sustainability as there were no significant large scale humanitarian emergency during the programme. Any future resilience programme should consider going back to BDRP households as part of the design/ inception phase and assessing which activities were critical to building resilience to identified shocks.

D: Risk

Risk remained “moderate” throughout the life of programme, although the Covid-19 pandemic significantly affected risk levels in the final months of implementation and during programme exit. The programme also faced challenges in terms of constant changes to the budget and scope of interventions, as well as access issues for some downstream partners. However, both lead partners have managed risks and disruption well during programme implementation by including robust contingency plans in their proposals and proactive communication with the programme team at FCDO. The programme team managed a comprehensive risk register for the programme as part of its delivery plan. The register categorised risks along all six categories under FCDO’s risk framework. For each risk identified, a series of mitigation measures were in place, along with an indication of responsibility for these measures. In addition, a comprehensive Strategic Relationship Management (SRM) process was followed with Concern Worldwide and a thorough due diligence assessment was conducted for FAO with all recommendations regularly tracked and implemented.

A detailed overview of programme risks is annexed with this report.

Update on Partnership Principles
This programme includes provision of technical assistance to the Government of Pakistan through both the institutional strengthening and the CBDRM component. It did not include financial aid to government. However, the team carefully considered the Partnership Principles Assessment (PPA) throughout the life of the programme.

The PPA sets out FCDO’s assessment of commitments made by the Government to the four partnership principles (poverty reduction, financial management and accountability, domestic accountability and human rights), as demonstrated through its policies and action for reducing poverty and achieving the Sustainable Development Goals (SDGs).  The PPA is agreed with the Economic Affairs Division (EAD) in the Government of Pakistan at the federal level.  FCDO senior leadership in country reviewed the PPA with EAD in March 2019.  A further review has been delayed due to Covid-19, but we continue to discuss these important issues regularly.

Our overall judgement is that the Federal Government of Pakistan is demonstrating a reasonably credible commitment to two of the four partnership principles namely: poverty reduction and financial management.   However, there are causes for concern in certain areas of human rights where the trajectory of progress has been downward.  Domestic accountability to citizens in the areas of civic space and media freedom has also been constrained with no sign of improvements in the last year. Progress towards attainment of the SDGs and poverty reduction is proceeding at a slow pace and the rapid population growth creates more pressure. Progress on the protection of human rights is mixed. On public financial management and anti-corruption, the direction of travel is broadly neutral, although some evidence indicates improvements. There has been mixed progress towards strengthening domestic accountability with a reduction in civic space and media freedom. Substantial reform is needed in all partnership principles areas (especially on the implementation of commitments where these are in place).

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Performance of partners and FCDO, notably on commercial, and financial issues
The six year BDRP (2014 – Sept 2020) was approved by the Secretary of State in 2014. After approval, the original budget of £76.3 million was reduced as part of the UK Spending Review (2015), with some reduction in scope from the original Business Case. This resulted in activities starting in September 2016. The overall budget for BDRP was reduced to £33.89 million of which £25 million (74% of the overall budget) was allocated for a commercial contract for CBDRM work, led by Concern Worldwide. Whereas, the institutional strengthening component was implemented through a framework agreement between FCDO and FAO. Both these components were implemented through a consortia approach. Concern Worldwide led its consortium in partnership with ACTED, WHH and IRC. Whereas, FAO led its component in partnership with UNDP and WFP.

The lead partners Concern Worldwide and FAO carried the entire administrative burden of managing and co-ordinating activities under each output and consortium partners oversight. The management costs were included in the agreements with FCDO. This delivery approach also created a simplified approach for FCDO to oversee that both the work plan and logical framework reflected FCDO’s objectives. However, considering the number of actors involved in programme implementation through a consortia approach, the likelihood of risk related to fraud and corruption remained high. Strong internal controls and transparent fund flow mechanisms were therefore significant to the programming. For BDRP, standalone aid diversion agreements, independent audits, field monitoring visits and TPM reports provided assurance that funds were being used as intended. FCDO enforced strong beneficiary feedback mechanisms for all partners and had in place updated delivery chains that helped in mapping out flow of funds. The team also scrutinised partners’ financial reports and invoices; and, triangulated information through multiple reports (quarterly progress reports, TPM reports, financial reports etc.). Additionally, 90% of the CBDRM targets were linked with PBR. Disbursements from FCDO were made after retention of 10% of the quarterly fee. The retained 10% was then released by FCDO after the achievement and verification of quarterly PBR targets. This also ensured achievement of key milestones under the programme. The TPM approach was also rolled out through a phased approach which led to some gaps between the two phases due to procurement delays. However, both partners managed the assessments diligently without any major challenges.

Though the performance of FAO, under BDRP has been mixed, the Agency has a comparative advantage in terms of strong partnerships and technical know-how to work alongside government on climate and resilience building. Concern’s performance specifically remained satisfactory throughout the programme lifecycle due to its flexible and adaptive approach. However, the frequent changes in the context and programme implementation plans at times made it difficult to manage programme resources through certain delivery modalities, e.g. Concern Worldwide’s contract has been amended seven times during the four-year programme, and all these amendments were led by PCD and took several months to finalise. This is one of the key learning points for future programmes, to seek out flexibility with PCD to adjust sub-budget lines without the need for a formal amendment.

BDRP has utilised 91% of the total available budget, with an underspent of approx. £3 million of the overall approved budget. Of this £3 million, £1 million was kept as reserve in the TPM component in case the programme needed to expand the scope of TPM work and required additional funds for that. The table below summarises budget utilisation, against the various programme components.

Component	Delivery Partners	Budget (£)	Spend	%age Utilisation
Design Work for Building Resilience to Disaster in Pakistan	--	90,072	90,072	100%
Community Based Disaster Risk Management	Concern Worldwide	25,611,906	24,000,777	94%
Institutional Capacity Building of Government Agencies	FAO	6,131,258	5,500,000	93%
Monitoring, Reviews, Assessments and Management Cost	GLOW (Phase I) Integrity (Phase II)	2,058,495	905,589	44%
Grand Total		33,891,731	30,796,438	91%
[note] To be finalised based on final report due by 31 January 2021.
[note] Due to multiple iteration during the earlier years first phase was covered through a local supplier and contract under OJEU thresholds covering limited TPM scope.

The final seven months (March – September 2020) of the programme have been impacted by the Covid-19 pandemic. The nationwide lockdown and changing government priorities affected the overall implementation and completion of a few activities in time. Concern Worldwide has achieved all the targets (even surpassed targets for a few interventions), whereas, FAO has missed a few agreed milestones (approx. 15%) towards the end of the programme.

The third party monitoring supplier – Integrity - was engaged in May-19 under an output-based contract to monitor all programme activities and give an independent assessment of how the programme was being delivered including validation of key programme milestones. Integrity submitted monthly, quarterly and six-monthly monitoring reports that significantly enhanced programme oversight and evidence-based learning.

Value for Money - Economy and Efficiency:
The final approved budget of BDRP was almost half of what was originally planned. The reduced budget directly impacted the scale of the programme; however, key cost drivers identified in the Business Case remained unchanged.

In terms of the split between personnel costs and project expenses, the actual programme stands at 48% (fee) and 52% (expenses) against the original budget of 44% and 56% respectively. There were programme efficiency savings as well as accrued foreign exchange/currency gains (owing the depreciation trend of the Pakistani currency against the British Pound Sterling). These savings were later adjusted in £1.8 million that was reprogrammed for the Covid-19 response.

A saving of £425,657 from Phase I was also adjusted in Phase II to fund new technical staff positions deemed necessary for programme implementation, strengthening M&E systems, more monitoring at field level and technical training for partner staff and beneficiaries to ensure better sustainability of programme interventions. In addition, the FCDO team ensured programme delivery costs were in line with the costs of delivering similar interventions through the FCDO’s humanitarian programme and justified if delivering at a higher cost. Wherever possible, FAO field teams were placed in the government provided space in district and tehsil level departments. This helped in reducing operational costs and enabled partner teams to channel local level government resources for project beneficiaries in an effective way. All capacity and resources risks were being carefully handled through a well-informed exit strategy; however, its full implementation was slightly affected by Covid-19.

The VfM argument made in the Business Case stage still holds; i.e. a CBDRM treated village hit by a disaster will require reduced emergency assistance compared to a non-treated village. This assumption has not yet been fully tested and the Covid-19 situation made it more complicated - however, there’s good evidence (numbers and stories) suggesting that the interventions of the BDRP programme represents good VfM. Benefits consisted of avoided costs of repairing hand pumps; the reduced loss of household possessions, tools, and livestock; the reduction in loss of life and injury. However, there are additionally many softer benefits that are more difficult to value, such as community confidence, gender-related impacts, and reduced stress.

Strategic Relationship Management (SRM) and Due Diligence:
Concern Worldwide was formally reviewed for the first time under the Strategic Relationship Management (SRM) process for then DFID commercial partners in Feb 2019. It’s performance over the period under SRM analysis was generally satisfactory, with some recommendations to further improve on their co-ordination and financial management challenges including VfM monitoring and assessment.

FAO’s capacity and capability, systems, policies and processes were assessed and monitored through a comprehensive due diligence assessment. A refresh of BDRP programme specific due diligence was conducted again in July 2019. Further improvements on financial management and reporting were one of the key recommendations of the report which remained open and under discussion despite regular follow ups due to central administrative agreements.

Asset monitoring and control
In line with FCDO asset management compliance standards, comprehensive asset registers were managed and reported to FCDO quarterly. The asset spot check over the life of the programme confirmed that asset registers managed by partners were accurate. In addition to FCDO spot checks, the TPM firm was also mandated to carry out spot checks in partners’ field offices (including downstream partners).

The BDRP programme team is currently finalising their approach for asset disposal in line with programme completion requirements. This will be finalised by 31st December 2020. Key assets include vehicles, laptops, IT equipment and office furniture.

Programme-level approach to monitoring and evaluation
Monitoring and evaluation processes for the BDRP programme evolved between Phase I and II, playing an increasingly clear role in decision making at the consortium level. However, the late start of TPM and the lack of independent evaluation constrained the overall development of a robust evidence base and is a major shortcoming of the programme and a hindrance to design of the next phase of resilience interventions.

In Phase I, GLOW consultants provided third party monitoring for the CBDRM activities – the reports from these field visits provided FCDO with the assurance that activities were delivered and whether all agreed milestones achieved. The reports also enabled FCDO to collect evidence of suppliers’ performance. These reports were shared with partners and lessons incorporated into Phase II. The programme was also informed by monthly field visits, regular interviews with beneficiaries and with key stakeholders through the PMC and PSC meetings attended by programme partners, and government officials. FCDO colleagues met with implementing partners on a regular basis to discuss progress and made field visits to targeted districts. Lessons from the mid-term review by Concern Worldwide (September 2018) for Phase I were taken forward in Phase II. In Phase II, Integrity Consultants provided third party monitoring, and a four-pillar approach to M&E was developed:

FCDO level
- Annual reviews and field visits were led by programme managers and the Senior Responsible Officer (SRO) with technical support from specific FCDO Pakistan advisors. This was supported by field visits, beneficiary interviews and regular meetings with consortium members.
- Ensuring Consortia developed robust systems to track progress against the logical framework and its milestones, as well as developing a monitoring and evaluation strategy.
- Ensuring individual logical frameworks for Concern and the UN fed into an overarching programme logical framework.
- Working with partners to ensure their individual logical frameworks captured disaggregated data on disability, age and sex.

Third Party Monitoring
- TPM complemented internal consortium monitoring and increased accountability, oversight and evidence-based learning on the programme and suggested recommendations for future programming which have been discussed in this report. In Phase I, TPM was done by GLOW, and from May 2019 to September 2020 of Phase II, Integrity were contracted to do this work along with its local partner VTT Global.
- TPM reports helped FCDO to collect evidence on suppliers’ performance and to take necessary measures for course correction through the duration of the programme.
- TPM reports drew upon more than 2,000 beneficiary feedback surveys, 200 key informant interviews and 200 focus group discussions.
- In addition to monthly updates, quarterly, biannual and final reporting, TPM also undertook a number of ‘deep dive’ studies to investigate programme effectiveness and generated discussion which helped in building coordination across both the components of the programme.

Partner internal monitoring and evaluation
- Partners report to FCDO on progress on a quarterly basis and both consortia produced final reports at end of both phases to evaluate progress and to reflect on lessons.
- As the programme progressed the consortia used monitoring to adapt and learn by doing, e.g. improving the ways of delivering training to better suit the needs of beneficiaries.
- Embedded in the programme was continuous analysis, e.g. hazard, livelihood and vulnerability assessments as well as gathering learning and evidence from the piloting of new activities.
- Both delivery partners have undertaken a number of reviews of their own work to support learning and the evidence-base. This work, mainly taken forward by the Concern-led Consortium included:
  - Mid-term review and survey to measure resilience in the targeted population (September 2018);
  - VfM study by Concern (August 2020);
  - Final evaluation by Concern (August 2020); and
  - Final evaluation by FAO (to be confirmed).

Date of last narrative financial report	Concern Worldwide Oct 2020 / FAO Sept 2020 (FAO’s final financial report will be available by 31 January 2021)	Date of last audited annual statement	Concern Worldwide – June 2020 for FY 2019 / FAO – July 2020 for FY 2018