 Programme Completion Review – September 2020

Title: Support to Displaced People and Migrants 2017 - 2020
Final Programme Spend (full life): £31,727,899	Review Date:	30th November 2020
Programme Code: 300404	Start Date: / 1st June 2017	End Date: / 31st August 2020

Summary of Programme Performance

Year	2018	2019	2020
Programme Score	B	A	A
Residual Risk Exposure Rating	Major	Major	Severe

DevTracker Link to Business Case (and any addendum):	Business Case and Summary 300404
DevTracker Links to all logframes used during programme lifetime:	Logframes

Description	Score
Outputs substantially exceeded expectation	A++
Outputs moderately exceeded expectation	A+
Outputs met expectation	A
Outputs moderately did not meet expectation	B
Outputs substantially did not meet expectation	C

A. Summary and Overview

Description of the programme and what it has achieved

Yemen is the world’s worst humanitarian crisis, with over 80% of the population (an estimated 24.3 million persons) in need of some form of humanitarian assistance and protection in 2020, of which an estimated 0.3 million are refugees and migrants. Improving the humanitarian situation in Yemen is also one of the pillars of the UK’s National Security Council strategy for Yemen. There is significant public and parliamentary scrutiny of Her Majesty’s Government’s (HMG) wider policy towards Yemen, strong public support for aid being used for humanitarian purposes, and strong cross-party support for a significant UK contribution to the humanitarian response whilst needs persist at the current scale and severity.
[note] Humanitarian Response Plan Extension (May 2020), https://reliefweb.int/sites/reliefweb.int/files/resources/Extension%20Yemen%20HRP%202020_Final%20%281%29.pdf

The programme ‘Support to Displaced People and Migrants 2017-2020’ was designed to strengthen protection in the Yemen response, particularly for migrants, refugees and internally displaced people (IDPs). The expected impact of the programme was to identify and reduce the vulnerabilities of people affected by the conflict in Yemen; the expected outcome of the programme was that urgent protection and humanitarian needs of migrants, refugees and IDPs were adequately identified and met.

This programme was delivered through three components:
1. £15,509,549.67 to the International Organisation for Migration (IOM) to lead a consortium delivering protection and humanitarian assistance to migrants and IDPs in Yemen. The consortium partners were the Norwegian Refugee Council (NRC), the Danish Refugee Council (DRC), Intersos, and Humanity and Inclusion (HI). The consortium provided medical services, food vouchers, non-food items, psychosocial support, legal counselling and assistance and referrals for vulnerable migrants and IDPs. This programme also supported IOM’s population displacement tracking mechanism in Yemen. In 2018 an additional output was added to reflect the provision of additional funding (£2m) to support IOM’s response to the cholera outbreak in Yemen;
2. £12,490,486.01 to the United Nations High Commissioner for Refugees (UNHCR) to provide protection support for vulnerable refugees and IDPs, including sexual and gender-based violence (SGBV) prevention and response activities, cash transfers, non-food items and referrals. UNHCR also works to strengthen protection monitoring and support to community-based protection networks (CBPNs) and provides coordination support to the Protection Cluster;
3. £3,727,863.32 through an in-kind donation of emergency supplies to IOM to be distributed in response to the escalating situation of displacement in Hodeidah in mid-2018.

This programme was due to end on 31st May 2020 but was granted a 3 month no-cost extension due to the outbreak of COVID-19 and therefore ended on 31st August 2020.

The overall score for this programme is an A. The vast majority of output targets have been reached or exceeded (only Output 6 scored a B) and there is sufficient evidence that outcomes were satisfactorily met.

Significant achievements:
- UNHCR met all quantifiable targets, providing 5,355 children with protection support, 12,445 IDPs with legal assistance, 44,472 IDPs with psychosocial support, and 3,157 people with SGBV prevention and response activities.
- IOM met the majority of their targets and significantly exceeded several, reaching 291,607 migrants with humanitarian and protection assistance, 105,467 with healthcare and 49,523 with mental health and psychosocial support.
- Partners continued to deliver over the duration of the programme despite the increasingly restrictive operating environment in Yemen during the lifetime of the programme.
- The Civilian Impact Monitoring Project (CIMP) has been described as one of the most impactful components of this programme and was characterised as “an essential protection monitoring tool” by a range of partners and external stakeholders.

Targets not achieved:
- Partners failed to consistently report against beneficiary feedback indicators across all outputs.
- IOM underachieved against their targets for referrals for specialised services.
- HI only delivered 63% of their target for training in inclusion, psychosocial support and mine risk education.
- IOM only reached 86% of their intended target of child IDPs provided with reintegration support.

Major lessons learned and recommendations:

1. Protection interventions in Yemen are critical but referrals are limited. Specialised NGO services and the UNHCR cash assistance programme were described as ‘lifelines’ and UNHCR’s protection coordination was described as ‘vital and leading’ throughout interviews conducted as part of this review. However, there continues to be a huge gap in resources for the protection sector in Yemen, meaning a limited number of referrals were possible, particularly for specialised services such as SGBV, child protection, services for persons with disabilities, complex psychosocial support and mental health cases. In many areas of displacement, particularly remote areas, services are simply missing; elsewhere, the availability of services offered by other operational partners has decreased due to the termination of humanitarian programmes linked to the lack of overall funding for the response. For instance, the number of Community Centres run by Protection Cluster partners decreased from 37 in July 2019 to 17 in July 2020. It is recommended that future programmes:
  [note] Humanitarian Response Plan Extension (May 2020), https://reliefweb.int/sites/reliefweb.int/files/resources/Extension%20Yemen%20HRP%202020_Final%20%281%29.pdf
  1. Continue to support humanitarian protection interventions in Yemen, with a focus on specialised services for the most vulnerable;
  2. Fully assess the barriers to referrals to scope out solutions for improving referral mechanisms;
  3. Consider funding an NGO Protection Cluster co-lead to improve coordination;
  4. Consider conducting a specialised assessment of the protection situation in Yemen to support a stronger intervention for all actors.

1. Elements of this programme have been essential in supporting HMG political efforts. The Civilian Impact Monitoring Project (CIMP), funded through this programme, provides real-time reporting on conflict incidents which directly impact civilians (e.g. civilian casualties, damage to civilian infrastructure). Humanitarian agencies use these reports to respond to immediate protection needs, including providing medical care for injured civilians. CIMP also produces quarterly, annual and thematic reports which analyse trends in the conflict and how it impacts civilians. Both analytical reports and real-time incident reporting feed into HMG’s assessment of International Humanitarian Law (IHL) risks in Yemen, including relating to arms export licensing criteria, and help to inform UK advocacy with parties to the conflict on the importance of IHL. Reports are also used by the Special Envoy’s Office for peacebuilding and political track discussions and efforts. It is recommended that:
  1. The UK continues to prioritise protection of civilians in Yemen inclduing developing a coordinated cross-Government approach to strengthening protection of civillians in Yemen.
  2. The UK continues funding for CIMP through future programmes.

Monitoring, Evaluation and Learning systems should be strengthened. The number of outputs and indicators being managed by the programme are too high. This was recognised as a challenge by the FCDO team in the 2019 Annual Review (AR) and Independent Monitoring Report (IMR) commissioned through the FCDO Independent Monitoring, Evaluation and Data Analysis (IMEDA) programme, but was not actioned due to the programme closing. The IMR also found substantial issues with IOM’s information management systems, which they continued addressing until the end of this programme. For example, they could not differentiate which beneficiaries had received one off assistance versus multiple assistance. Furthermore, upon interview, partners were able to produce several anecdotal examples of positive impacts from the programme, but these were not captured in reporting to FCDO. It is recommended that future programmes:
[note] https://www.nrc.no/perspectives/2020/how-afrah-received-an-identity/ (NRC film documenting the impact of their civil registration programme, supported by FCDO). https://www.nrc.no/resources/reports/repairing-fractured-landscapes/ (NRC report on UK funded research that contributed to dispute resolution over housing, land and property issues).
  - Reduce the number of outputs and indicators being tracked;
  - Better analyse initial logframe targets and scrutinise partner data quality assurance systems in the planning phase;
  - Strengthen FCDO’s approach to remote management by having more regular but simplified partner reporting, informal liaison with downstream partners and national Civil Society Organisations, and more innovation in mitigating risks associated with remote management of partners;
  - Fully utilise the support made available by the FCDO IMEDA programme;

Accountability to Affected Populations (AAP) systems should be improved. Despite both the FCDO and partners recognising the many challenges with applying AAP in the Yemen context, this review, both ARs and the IMR found limited evidence across all outputs and outcomes of sufficient consultation with communities in the design and implementation of this programme, exacerbating safeguarding and inclusion risks. It is recommended that future programmes:
- Thoroughly consider the limitations faced with collecting beneficiary feedback of particular population groups and work with partners to scope out solutions to this in the planning phase;
- Ensure data requied for any indicators can realistically be collected;
- Improve safeguarding mechanisms at the activity level, including improving knowledge of complaints mechanisms, especially in relation to programming for migrants and refugees;
- Strengthen AAP across the FCDO Yemen portfolio by dedicating focus on improving AAP within a single programme with responsibility for mainstreaming across the rest of the portfolio.

Longer-term solutions should be sought for refugees and migrants in Yemen. Whilst the initial business case was a humanitarian intervention, a durable solutions strategy (looking at long term solutions of return, reintegration, resettlement and safe migration) with a potential focus on supporting IOM’s voluntary repatriation programme (if the conditions for voluntary return are met) and strengthening safe migration pathways could reduce the need for humanitarian support in the future. Coordination with UK Home Office initiatives in countries of origin could also be explored to complement humanitarian support in future interventions.

There were challenges with implementing a streamlined approach to supporting different population groups. The Business Case for this programme intended to support a ‘one caseload’ approach, whereby protection responses for migrants, refugees and IDPs would be harmonised into a single structure, thereby reducing staffing costs, delivering a more coordinated response, and strengthening the VfM of the programme. Although UNHCR has consolidated their protection staff into a single structure, meaning protection expertise will benefit both refugee and IDP programmes, notably on child protection, SGBV and persons with specific needs, this has not been evident across the programme as a whole. FCDO should continue to follow developments of this initiative and take this into consideration when planning future programmes.

Report methodology:

This review was conducted by a Humanitarian Adviser currently deployed to the FCDO Myanmar programme, with support from the Senior Responsible Officer (SRO) and the Programme Manager for this programme. It included a desk review of relevant programme documentation including; the Business Case, quarterly partner reports (and annexes), partner strategy documents, Independent Monitoring Reports, due diligence reports, the FCDO Annual Reviews for 2018 and 2019, lessons learnt exercises, workshop reports, and FCDO strategy documents. This review also conducted Key Informant Interviews with the six agencies implementing this programme, the Protection Cluster and Humanitarian, Access and Cash Working Group leads, and four members of staff on the FCDO Yemen team. Due to security conditions in Yemen there were no field visits conducted for this review, and due to COVID19 restrictions no in-person meetings with partners were possible. In addition, interviews with national CSO partners or Yemeni and/or migrant and refugee beneficiaries were unable to be conducted. This review tried to mitigate these limitations through a focused look at beneficiary case studies provided by partners during the desk review.

Actions following approval of this report:

One final payment remains to be transfered to IOM upon receipt of their final finance report, due 30th November. However, IOM have confirmed in writing that all funds were spent within the allocated timeframe. Asset registers for both IOM and UNHCR are being finalised and disposal of assets will be decided accordingly.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£36,000,000	£31,727,899
Timeframe	1st June 2017 – 31st May 2020	1st June 2017 – 31st August 2020
Outcomes	The expected outcome of the programme is that the urgent protection and humanitarian needs of migrants, refugees and IDPs are adequately identified and met.	This outcome has been met.

Overall assessment of programme outcomes, sustainability and VfM

The expected outcome of this programme was that the urgent humanitarian and protection needs of migrants, refugees, asylum seekers and IDPs in Yemen were identified and met. Overall, a total of 9,014 refugees and asylum seekers (compared to a target of 8,832), 291,607 migrants (target of 96,275) and 396,794 IDPs and host community members (target of 308,482) were reached with humanitarian and protection assistance over the lifetime of the programme.

The expected impact of this programme was that the vulnerabilities of people affected by the conflict in Yemen were identified and reduced, prioritising the most vulnerable. This has been largely achieved, and is particularly demonstrated through Output 1.1 whereby 181,164 migrants in Lahj, Taizz, Sana’a, Dhamar, Hadramut, Shabwah, Al Hudaydah, Aden and Sa’ada were screened and registered by DRC, Intersos and IOM, and Output 6 whereby IOM tracked 400,747 migrants from other countries (263,809) and Yemeni returnees (136,938) primarily from Saudi Arabia over the project period. In addition, UNHCR was able to identify 241,415 persons of concern (123,677 males, 117,738 females) through their protection monitoring activities under Output 4. Data collected was shared with the Protection Cluster and fed into the analysis of refugee, migrant and IDP trends, needs and prioritisation of activities in the HRP. There was also some evidence – through individual case studies - to show reduction in vulnerabilities in the immediate term.
However, evidence as to whether there was a reduction in vulnerability in the longer term was not collected. Specific indicators relating to sustainability and national systems building were not incorporated into the log frame. However, during interviews, partners were able to provide examples of sustainability and national systems strengthening. For example, INTERSOS’s partnership with Basma Association (a Yemeni Civil Society Organisation (CSO)), enabled them to conduct ad hoc mixed migration monitoring missions in North Hadramout, reaching and assessing migrants’ conditions of vulnerability. INTERSOS had a capacity strengthening plan with Basma and gave examples of how the Basma’s team’s technical capacity to provide legal advice, protection referrals and pyscosocial support to beneficiaries was as a direct or partial result of their capacity building efforts.
Value for Money evaluation

Overall this programme has achieved Value for Money (VfM) as outputs have met expectations despite a constrictive operating environment and enabled FCDO to support the most vulnerable population groups in Yemen.

Economy: Both IOM and UNHCR procured goods such as non-food items and food in large quantities at a global level through long-term agreements with suppliers to negate price and foreign currency fluctuation. When local procurement was necessary, contracts were agreed in US dollars to mitigate the impact of exchange rate fluctuations. In the 2018 Annual Review for this programme, cost-per-beneficiary was determined to be an unreliable measure of VfM, particularly for protection activities which have a wider immeasurable impact. However, as recommended in the 2019 Annual Review, FCDO should aim to agree a quantifiable measurement of VfM with future protection partners to allow for a better assessment of VfM at cost level.

Efficiency: The IOM consortium continued to strive for the most efficient approach to delivery throughout the lifetime of the programme by streamlining working groups, strengthening referrals within the consortium and improving common data collection and analysis to strengthen advocacy efforts. However, standardisation of tools across the consortium only became apparent in year three of the programme. Whilst the consortium approach did encourage cooperation between partners, IOM did not take as strong a leadership role as initially intended in the Business Case, impacting the overall efficiency of the consortium approach.

UNHCR has achieved 100% implementation against all activity targets. This can largely be attributed to the periodic revision of logframe targets throughout the implementation of the programme to reflect capacity and context, with the majority of targets being increased. This was done without any increase in financial support, showing that UNHCR were able to efficiently implement programming and reach more beneficiaries with the same budget. However, this may also be indicative of underambitious targets in the inception phase.

Effectiveness: Due to a lack of beneficiary feedback and impact reporting, it has been difficult to fully assess the overall effectiveness of this programme. However, case studies provided by partners and observations noted by third party monitoring have shown an overall positive impact of programming, particularly from the IOM consortium. It has been recommended above that future programmes establish better mechanisms to capture qualitative feedback of protection interventions and allow for a more thorough analysis of the effectiveness of programming.

Equity: Through this programme, FCDO supports four of the five most vulnerable groups identified in the 2019 Humanitarin Needs Overview: 1) IDPs and returnees, 2) children, 3) women and girls and 4) refugees, migrants and asylum-seekers. A large proportion of IDPs are also women and children, and all groups include people with specific needs. IOM’s Independent Monitoring report found that assistance was being delivered to the targeted communities, providing assurance that the most vulnerable are benefitting from this programme as intended. Both UNHCR and IOM disaggregate their data by gender, with IOM also reporting number of child beneficiaries.
[note] Humanitarian Needs Overview, (December 2018), https://yemen.un.org/sites/default/files/2019-08/2019_Yemen_HNO_FINAL.pdf

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The overall Theory of Change (ToC) underpinning this and other DFID humanitarian interventions in Yemen is shown below, with the inputs, processes and outputs relevant to this programme highlighted in red. This has been updated to reflect current assumptions and the addition of in-kind support in Year 2 of the programme.

Results were collected through narrative and logframe reports, provided by both IOM and UNHCR on a quarterly basis. However, as outlined in Section A, the monitoring, evaluation and learning systems for this programme could have been strengthened to better assess the effectiveness of programming and provide stronger assurance to FCDO of partner’s data quality assurance mechanisms.

Logframe indicator revisions were conducted in 2018 and 2019 following the submission of evidence from both IOM and UNHCR showing the need for change in results milestones. Output 7 was also added in 2018 to capture IOM’s additional cholera response. There were no revisions to indicators or targets in 2020.

## C: Detailed Output Assessment

Output Number and Title		1. Conflict affected migrants have improved access to humanitarian and protection services (IOM)
Output Score		A
Impact weighting (%)		23%		Impact weighting revised since last AR?	Yes (see footnote for explanation)

Output Indicator			Starting Target	Final Target	Final Result Achieved
1.1	Number of encountered migrants registered, identifying vulnerabilities and human rights abuses suffered.		96,275 (70% men, 3% women, 25% boys, 2% girls)	85,494	181,164 212% achieved (138,372 men, 10,157 women, 30,124 boys and 2,511 girls)
1.2	Number of migrants receiving WASH, food, non-food items, temporary shelter or transportation services.		96,275 and 70% (70% men, 3% women, 25% boys, 2% girls)	90,774	291,607 321% achieved
1.3	Number of migrants benefiting from life-saving health care.		19,800 (70% men, 3% women, 25% boys, 2% girls)	95,875	105,467 110% achieved
1.4	Number of migrants benefiting from mental health and psychosocial support		1,980	23,992	49,523 206% achieved
1.5	Number of migrants referred for specialised services, including victims of trafficking and GBV.		2,700	6,346	4,204 66% achieved
1.6	Number of migrants receiving legal counselling.		2,525	23,182	39,363 170% achieved
1.7	Number of attendees of awareness sessions on migrants rights and humanitarian asssitance		10,000	80,084	108,515 136% achieved
1.8	Number of individuals receiving training in mainstreaming cross-cutting issues such as inclusion, psychosocial support and mine risk education..		1,940	1,048	663 63% achieved
1.9	% of training participants demonstrating increased knowledge		80%	80%	84%
1.10	Number of government health consultants trained by IOM on healthcare.		Unknown	230	228 99% achieved
1.11	% of surveyed migrants reporting satisfaction with services received		80%	80%	70%
1.12	% of surveyed migrants aware of the availability of a feedback mechanism		80%	80%	83%
[note] The 2019 Annual Review did not include Output 7 ‘Cholera Response’, as this activity took place exclusively in 2018. Impact weightings for all outputs have been proportionatly altered to account for this additional activity in Year 2 of the programme.
[note] Prioritising the most vulnerable including women, children, persons with disability and the elderly.
[note] Including medical consultations, reproductive health care, health awareness, vaccinations and paramedic assistance.
[note] These sessions were provided for both migrants and community members.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

IOM has significantly overachieved against six of the above indicators, achieved the target of three and underachieved against three. Overall, this output has met expectations and therefore scores an A.

This output provides migrants with protection services including health care, psychosocial support, legal support, basic services and awareness sessions. These services are provided through IOM and consortium partners Norwegian Refugee Council (NRC), Danish Refugee Council (DRC) and Intersos. Humanity and Inclusion is also a member of the consortium, providing training to partners on cross-cutting issues such as inclusion and mine risk education.

IOM has most significantly overachieved against Indicator 1.2: ‘Number of migrants receiving WASH, food, non-food items, temporary shelter or transportation services’, reaching 321% of the intended beneficiary target. This can be largely accredited to the fact that partners encountered more migrants than initially expected as arrival numbers continued to rise throughout the lifetime of the programme. The majority of these people will have received immediate assistance upon their arrival into Yemen from Mobile Response Teams stationed across the Southern coast.

The consortium demonstrated several instances of innovative, flexible programming across the three years, which should be commended. For example, DRC added a paramedic to the response team to provide emergency first-aid, NRC recruited volunteers to notify them of new waves of arrivals, and IOM adapted their awareness raising sessions to include information about COVID-19 and safety measures to take following the outbreak of the virus.

However, the following indicators underachieved against their targets:

Indicator 1.5: ‘Number of migrants referred for specialised services, including victims of trafficking and GBV’
When consortium partners were not able to provide an appropriate service directly, they would refer migrants to other partners within the consortium and then occasionally beyond. However, sub-grants for protection activities were slow and difficult to be approved by authorities and in general there is a large gap in available protection services, particularly for victims of trafficking and GBV, due to underfunding of the response. There were also wider coordination challenges reported such as the protection services directory not being accurate, and coordination being under-resourced and inconsistent.
[note] UNHCR requested further funding support for coordination roles during this review.

Indicator 1.8: ‘Number of individuals receiving training in mainstreaming cross-cutting issues such as inclusion, pyscosocial support and mine risk education.
Technical support from HI and NRC helped the consortium ensure the inclusion of most at-risk individuals during the beneficiary identification processes and that the needs of persons with disabilities were met. However, HI faced challenges in implementing activities due to lack of approval from authorities. This was reported by IOM in 2018 and 2019 to FCDO Yemen, yet it was decided to maintain targets as HI had expected government approvals. Unfortunately, these have still yet to come through, limiting some of the support that HI was able to provide to other consortium partners.

Indicator 1.10: % of surveyed migrants reporting satisfaction with services received
This inidicator was added in Year 3 following a recommendation to in the last Annual Review to replace various beneficiary satisfaction indicators with a single one. Although the final figure for this indicator was 70% satisfaction overall, data was inconsistely reported throughout the lifetime of the programme. DRC was unable to conduct satisfaction surveys as most beneficiaries received one-time assistance and were then on the move without reliable communication channels; Intersos was unable to conduct any satisfaction surveys in Y1 and a limited number in Y2 (1.6% of beneficiaries) and Y3 (26% of beneficiaries); IOM periodically administered surveys; and NRC reported 90% satisfaction based on asking beneficiaries immediately after having been given legal assistance. The NGO consortium did develop a standardised survey tool but this was difficult to utilise in practice and partners relied on their own mechanisms which were difficult to implement with the target beneficiary group.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Overall this output delivered VfM by reaching a significant number of particularly vulnerable migrants with vital and life-saving humanitarian and protection assistance.

IOM and partners demonstrated that they provided assistance to all migrants they encountered and there were strong examples of gender and age inclusion across the consortium, contributing to FCDO’s Leave No One Behind approach. For example, while providing awareness on the legal framework and protection risks in Yemen, DRC provided specific and tailored information to female migrants, minors, and families with children regarding specific protection risks, in particular risks associated with trafficking and other forms of exploitation. Additionally, all partners reported female staff integrated into first point of contact migrant response teams and, as per the recommendation of Handicap International, DRC included the Washington Group’s questions in their screening form, enabling their migrant response teams to better identify persons with disabilities among encountered migrants. However, due to limited feedback from beneficiaries, it is probable that assumptions were not consistently checked or informed by the communities this program was serving, impacting on appropriateness and effectiveness of response.

IOM significantly overachieved against the majority of their targets for this Output but it is unclear if this is due to enhanced capacity, efficiency or low targeting and therefore does not necessarily contribute to good VfM. However, they have adapted well to challenges faced with the delivery of this output, particularly in relation to COVID19 and restictions imposed by authorities, which presented significant challenges to delivery in particular for NGO partners and they should be commended for being able to continue exceeding targets in these circumstances.

Lessons learned through this output, and recommendations for future programming

1. There were inconsistencies in the rationale for logframe targets and revisions and a lack of clarity on actual beneficiary reach under Indicators 1.1 and 1.2 of this output. Issues with data collection were also highlighted as an area of concern through third party monitoring. Therefore, monitoring systems should be more closely scrutinised throughout the lifetime of the programme, adapting as appropriate to reflect the contextual circumstances. In particular, targets should accurately reflect partners ability to operate.
2. There is a huge gap in resources for the protection sector in Yemen, meaning referrals are extremely limited. This could be addressed with increased funding and resources to the Refugee and Migrant, and Protection sub-sector coordination mechanisms, improved humanitarian access advocacy support and improved training of national CSOs. A specialised assessment of the protection situation in Yemen and suitable responses would support a stronger intervention for all actors.
3. HI’s lack of approval from authorities means they are in effect unable to operate in Yemen at present. Their operational capacity should be closely evaluated before any future support is granted; FCDO Yemen should also take into consideration how the status of government approvals can impact on the ability of actors to implement in future partnerships.
4. High turnover in programme management staff across all stakeholders of the consortium, in addition to turnover in monitoring and evaluation staff, meant there were consistent gaps in staff delivering and appropriately managing indicators. Staff turnover in a high stress environment such as Yemen should be taken into consideration in the design of any future programming and staffing models adapted accordingly.
5. There was a lack of consultations with beneficiaries and affected communities and limited feedback from beneficiaries was received. Whilst bearing in mind the particular difficulties with contacting beneficiaries from the migrant population, future FCDO programming should aim for stronger AAP systems and approaches to remote management. Partners should explore innovative ways of engaging with communities through social media or specialised and regular outreach to national CSOs.

Output Number and Title		2. Refugees and asylum-seekers have improved access to protection services (UNHCR)
Output Score		A
Impact weighting (%)		23%		Impact weighting revised since last AR?	Yes (see output 1 for explanation)

Output Indicator			Starting Target	Final Target	Final Result Achieved
2.1	Number of individuals supported with SGBV prevention and response activities		1,650	3,156	3,157 (745 male, 2,412 female) 100% achieved
2.2	Percentage of assisted refugees (disaggregated by age, gender and nationality), reporting that some of their immediate protection needs were fulfilled		90%	80%	No results reported
2.3	Number of gender specific community-based committees/ groups working on SGBV prevention and response		48	15	15 (8 male, 6 female) 100% achieved
2.4	Number of children supported with child protection activities		975	5,352	5,355 (4,091 male, 1,264 female) 100% achieved
2.5	Number of Best Interest Determination (BID) assessments conducted		765	324	325 (249 male, 77 female) / 100% achieved
[note] SGBV survivors receive medical support, legal services and psychosocial counselling.
[note] These activities are specifically implemented in Sana'a, Aden, Kharaz, camp and Lahj.
[note] A BID assessment is the formal process designed to determine a child’s best interest for particularly important decisions affecting the child, the require stricter procedural safeguards. https://www.unhcr.org/uk/protection/children/4566b16b2/unhcr-guidelines-determining-best-interests-child.html

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

UNHCR met all targets under this Output therefore scoring an A. However, they were unable to report against the beneficiary feedback indicator.

This output provides refugees and asylum seekers with sexual and gender-based violence (SGBV) prevention and response and child protection activities. As part of the child protection component, case management was conducted, and referrals were made for education, health and refugee status determination services. Based on needs, alternative care arrangements were arranged, including placement in foster families and social government centres for older male children. Children with disabilities as well as unaccompanied and separated children continued to receive support at family centres where recreational, non-formal education and psychosocial support activities were offered. Foster parents for separated children or children with disabilities were provided with cash assistance.

However, UNHCR were not able to implement the appropriate mechanisms to collect data for Indicator 2.2 across the lifetime of the programme. They were due to conduct a satisfaction survey with beneficiaries in mid-2020, but at the time of writing have not shared the results of this with FCDO. However, UNHCR did provide a list of communication materials and publicly available case studies on general programming as samples of beneficiary feedback and satisfaction. This indicator was kept in the logframe as it was expected to be reported against in the final year of programming.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

This output delivered VfM, achieving 100% against the outputs UNHCR was able to measure. This output also reaches particularly vulnerable women and children, supporting FCDO’s operational aims on gender and inclusion and the ‘Leave No One Behind’ agenda. All UNHCR programmes follow the principles of Age, Gender and Diversity Mainstreaming, rights-based approach, community-based approaches, and community-based protection as well as gender equality. However, the overall level of VfM has been difficult to assess due to a lack of beneficiary feedback and limited FCDO interaction with affected communities in Yemen. Therefore, it is probable that assumptions were not consistently checked or informed by the communities this program was serving, impacting the appropriateness and effectiveness of response.
[note] HMG policy paper, ‘Leaving no one behind: Our promise’ (March 2019) https://www.gov.uk/government/publications/leaving-no-one-behind-our-promise/leaving-no-one-behind-our-promise

Lessons learned through this output, and recommendations for future programming

Due to a lack of reporting against the beneficiary feedback indicator and lack of detail in quarterly reports, it has been difficult to measure the quality UNHCR’s activities. Future interventions need to include a beneficiary feedback mechanism that can be captured in reporting to ensure the programme is appropriately meeting the needs of target communities. This will also support a more adaptive approach to programming based on changing needs in a highly complex access and security environment.

Output Number and Title		3. Internally Displaced People (IDPs) have improved access to humanitarian and protection services (IOM and UNHCR)
Output Score		A
Impact weighting (%)		23%		Impact weighting revised since last AR?	Yes (see output 1 for explanation)

Output Indicator			Starting Target	Final Target	Final Result Achieved
3.1	Number of IDPs receiving unconditional cash grants (UNHCR)		4,800	11,205	11,943 (7,221 male, 4,722 female) / 107% achieved
3.2	Number of IDPs receiving legal assistance (UNHCR)		9,000	12,443	12,445 (6,382 male, 6,063 female) 100% achieved
3.3	Number of IDPs receiving psychosocial support (UNHCR)		51,000	43,540	44,472 (23,330 male, 21,142 female) / 102% achieved
3.4	Percentage of assisted IDPs (disaggregated by age, gender, geography, disability), reporting that some of their immediate protection needs were fulfilled (UNHCR)		75%	80%	No results reported
3.5	Number of IDPs and host community members benefiting from life-saving health care (IOM)		53,100	55,000	63,746 116% achieved
3.6	Number of IDPs benefiting from mental health and psychosocial support (IOM)		38,400	16,000	74,409 465% achieved
3.7	Number of health facilities provided with operational support. (IOM)		3	3	7 233% achieved
3.8	Number of child protection cases identified and assisted with reintegration support. (IOM)		225 (50% boys, 50% girls)	237	203 86% achieved
3.9	Number of cases referred for specialised services (IOM)		N/A	2,916	1,001 34% achieved
3.10	Number of beneficiaries of legal asssitance (IOM)		8,975	4,050	10,058 248% achieved
3.11	Number of IDPs receiving awareness sessions on rights and humanitarian assistance (IOM)		4,336	4,336	16,422 379% achieved
3.12	% of surveyed beneficiaries reporting satisfaction with services received		80%	80%	87%
3.13	% of surveyed beneficiaries aware of the availability of a feedback mechansism		80%	80%	95%
[note] Including victims of trafficking and GBV.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

UNHCR achieved three targets for this output, but failed to report against indicator 3.4. IOM overachieved against seven targets, underachieved against two and met one. Overall, this output has met expectations and therefore scores an A.
Through this output, UNHCR, IOM and consortium partners provided protection services to Internally Displaced People (IDPs) in Yemen, including legal assistance (such as counselling, accompaniments, representation and access to documentation), health care, mental health and psychosocial support, cash grants and awareness sessions. In particular, IOM’s support to seven health facilities helped sustain vital medical services to vulnerable populations amidst the collapsing health infrastructure in the country. The relevance and community acceptance of providing specialised protection services in Yemen was found to be significant through a review of case studies provided by IOM and UNHCR and should be taken into consideration in future intervention (Output 3.9).

IOM overachieved against the majority of their targets. This can be attributed to a consistent increase in need across the three years, an initial underestimation of the proportion of conflict affected IDPs who would seek out or require support through this project, and increased awareness and therefore clientbase of services throughout the lifetime of the programme.

IOM and consortium partners also attempted to prevent any exacerbation of conflict by ensuring that host communities also received assistance through this output; notably health care, legal assistance and awareness sessions. However, data was not consistently disaggregated to show the proportion of host community members receiving assistance.

The following indicators underachieved against targets:

3.4: ‘Percentage of assisted IDPs (disaggregated by age, gender, geography, disability), reporting that some of their immediate protection needs were fulfilled’
Please see output 2 for an explanation of UNHCR’s failure to report against beneficiary satisfaction indicators.

3.7: ‘Number of cases referred for specialised services (including victims of trafficking and gender-based violence)’
During the project period IOM and NRC identified 1,001 IDPs and host community members in need of specialised services and referred them to consortium partners to address their medical, protection, and livelihood needs. As detailed in output 1, referrals for specialised services are challenging in Yemen due to a lack of services available to refer to and authorities blocking or delaying approval of protection programming.

3.10: ‘Number of child protection cases identified and assisted with reintegration support’
IOM provided 203 children with reintegration support such as psychosocial support and reintegration grants. This slight underachievement was due to there being fewer numbers of child trafficking cases identified within IDP populations than expected.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Overall this output delivered VfM, overachieving against the majority of outputs, many by a significant margin. As with above outputs, this output contributes to the UK’s Leave No One Behind agenda by supporting the most vulnerable and marginalised people in Yemen.

Despite concerns from authorities in northern Yemen regarding awareness raising activities (since December 2019), following discussions with partners and local authorities, UNHCR was able to continue to deliver legal awareness raising on civil status documentation, psychosocial first aid, child protection (early marriage, birth certificates), COVID-19 and related preventive measures. Therefore, UNHCR’s status places it in a unique position to provide continuity of activities under humanitarian access constraints smaller organizations have been unable to overcome.

However, as with above outputs, the overall effectiveness of activities has been difficult to measure due to a lack of beneficiary feedback and interaction from FCDO with targeted communities.

Lessons learned through this output, and recommendations for future programming

1. As per output 1 & 2 recommendations, partners require better beneficiary feedback mechanisms, AAP systems and referral mechanisms.
2. Male IDPs disproportionately received assistance across nearly all output indictors (where disaggregated data was available). However, women and children account for roughly 75% of those displaced by the war. A closer review of the barriers to reaching women and girls and how to address this in balance should be part of the planning stage of future interventions.

Output Number and Title		4. Strengthened protection monitoring and support to Community Based Protection Networks (UNHCR)
Output Score		A
Impact weighting (%)		9%		Impact weighting revised since last AR?	Yes (see output 1 for explanation)

Output Indicator			Starting Target (All from first iteration of logframe in 2017)	Final Logframe Target	Final Result Achieved
4.1	Number of active Community Based Protection Network members trained/engaged		99	187	188 (114 male, 45 female) 101% achieved
4.2	Number of PoC identified through protection monitoring		240,000	241,295	241,415 (123,677 male, 117,738 female) 100% achieved

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score

Overall, this output has met expectations and therefore scores an A.

UNHCR partners with Intersos, ADRA, Yemen Development Foundation, Yemen Red Crescent Society, Yemen Women’s Union, Hodeidah Girls’ Foundation and Yemen Alkair for Relief and Development to support their Community Based Protection Networks (CBPNs). The core activity of the CBPNs is to conduct protection monitoring to identify persons of concern who require specialist protection support and refer them to UNHCR’s Community Centres who are then responsible for referral tracking and case management. CBPNs are also crucial in increasing the awareness, knowledge and understanding of refugees and IDPs’ rights and remedies for overcoming challenges such as lack of documentation, arbitrary detentions, risk of SGBV and harassment. Over the course of the programme UNHCR trained 188 CBPN members in legal counselling, identification of people with disabilities and psycosocial needs, and appropriate referral pathways for those in need of SGBV response, psychosocial support, healthcare and legal assistance. UNHCR reported that the expansion of the CBPNs has enhanced community participation and engagement and increased the capacity of IDPs to address these risks as well as helped to develop the common protection service directory to facilitate referrals.

UNHCR also worked to standardise the protection monitoring tool used by cluster members to ensure a consistent approach to identifying protection risks through household assessments and focus group discussions. Through this UNHCR has reached 241,415 individuals (Indicator 4.2). UNHCR feeds this information into the Protection Cluster, which helps provide an overview of the protection needs and priorities of the affected communities in Yemen and is fed into the HRP and other funding appeals to donors. However, it was noted that UNHCR has experienced an increased level of scrutiny from authorities on its protection monitoring activities since late 2019, leading to a simplification of monitoring tools that may affect their level of protection analysis. UNHCR is determined to continue engaging with authorities to reaffirm the importance of some of the protection elements in its monitoring tools, including for the determination of assistance eligibility.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Overall this Output delivered VfM, achieving both indicator targets. Community Based Protection Networks are able to support a much larger number of people than those counted through the indicators with training, outreach and awareness sessions, which were particularly helpful during the COVID19 outbreak of early 2020.

Lessons learned through this output, and recommendations for future programming

Gender balance in CBPN networks still needs to be improved, with 114 male versus 45 female CBPNs set up during the lifetime of this programme. Considering the substantial and increasing protection risks faced by women in Yemen, as reported under output 3, a clearer strategy and focus on the set up of women’s networks would benefit the protection response.

Output Number and Title		5. Strengthened coordination through Protection Cluster support (UNHCR)
Output Score		A
Impact weighting (%)		5%		Impact weighting revised since last AR?	Yes (see output 1 for explanation)

Output Indicator			Starting Target (All from first iteration of logframe in 2017)	Final Logframe Target	Final Result Achieved
5.1	Number of partner staff members and government authorities trained		750	1,896	1,896 (994 male, 902 female) 100% achieved
5.2	Number of information products produced and disseminated		90	250	250 100% achieved
5.3	Number of protection cluster meetings held each quarter		3	3	3 100% achieved

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

With all indicators reaching 100% of their targets, this output has met expectations and therefore scores an A.

During the lifetime of the programme, 1,896 government officials and partner staff have receiving training on topics such as preventing Sexual Exploitation and Abuse, case management, Initial Needs Assessment tools, protection monitoring and complaints and feedback mechanisms. Furthermore, a cumulative total of 250 dissemination products were produced throughout the length of this programme, including those released through the Civilian Impact Monitoring Project (CIMP). The CIMP is a monitoring mechanism for real-time collection, analysis and dissemination of open source data on the civilian impact from armed violence in Yemen. Daily, weekly, monthly and flash reports are used by a range of stakeholders including operational partners, the Humanitarian Access Wokring Group, the Humanitarian Country Team and the Humanitarian Coordinator’s office (through the UNHCR seconded Protection Adviser). Partners described it as ‘an essential protection monitoring tool’ and one of the most impactful humanitarian protection components of this project. Reports are also used by the Special Envoy’s Office for peacebuilding and political track discussions and efforts.

To ensure a coordinated response, three national cluster meetings have been held by the Protection Cluster every quarter to discuss operational gaps, challenges, achievements and general coordination issues. Cluster members also conducted regular meetings with CBPNs, local authorities, and other humanitarian actors.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Overall this Output delivered VfM, achieving all indicator targets. UNHCR achieved the initial targets and was able to revise up targets and meet the additional requirements under these output indicators by the end of the programme in 2020, showing strong efficiency and economy. UNHCR shows strong equity in an even number of both men and women reached with training. In addition, the wide array of stakeholders that have access to and use the CIMP products and their centrality to protection prioritisation in the Yemen response exceeds the expectations of the initial VfM rationale for this activity in the original business case.

Lessons learned through this output, and recommendations for future programming

1. CIMP has been an essential part of the nation-wide protection response. FCDO should consider ways of further strategically engaging with CIMP products to strengthen the FCDO’s own approach to Protection of Civilians in the Yemen Response.
2. FCDO could use CIMP’s analytical reporting to develop a cross-Government approach to Protection of Civilians in Yemen, addressing the drivers of civilian harm. An impact measurement framework applied to the use of this service could also support HMG protection interventions in conflicts beyond Yemen – supporting further VFM efforts and cross-HMG cooperation.
3. Due to staffing and funding gaps, quality of coordination could be improved and was recognised by both UNHCR and other protection actors through this review. In future, FCDO support to UNHCR coordination should place an emphasis on continuity and avoiding staffing gaps of critical roles which support the wider response. FCDO should also explore the addition of an NGO Protection Cluster co-lead.
Output Number and Title		6. Yemeni population displacement and migrant monitoring (IOM)
Output Score		B
Impact weighting (%)		9%		Impact weighting revised since last AR?	Yes (see output 1 for explanation)

Output Indicator			Starting Target	Final Logframe Target	Final Result Achieved
6.1	Number of reports made available to humanitarian actors in Yemen		NA	289	139 48% achieved
6.2	Number of training sessions conducted on new/enhanced DTM tools, methodologies, and quality control procedures to ensure the accurate and comprehensive data collection		NA	2,306	2,967 129% achieved
[note] Including Displacement Tracking Matrix (DTM), governorate monitoring, displacement dashboard, Multi-Cluster Location Assessment (MCLA) and migrant flow monitoring.

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

IOM has both exceeded and underachieved against targets for this output. Overall, this output has not met expectations and therefore scores a B.

During the project life cycle, IOM’s Displacement Tracking Mechanism (DTM) team collected data and published 139 reports and datasets: 1 DTM Area Assessment, 87 Governorate monitoring, 5 Displacement Dashboards, 1 Multi-Cluster Location Assessment and 45 migrant flow monitoring reports. DTM records the flow of IDPs within Yemen and migrant flow monitoring tracks the movement of migrants into Yemen as well as returns from Saudi Arabia. These reports are vital to the planning and implementation of the humanitarian response in Yemen. However, the DTM system was slow to start up and encountered bureaucratic access issues in its implementation, leading to the release of fewer reports than intended. However, the DTM reinitiated its area assessment in November 2018 and has continued to publish rapid displacement tracking reports since. Furthermore, DTM began using its field presence and performing additional data collection and reporting related to COVID-19 as well as identifying vulnerable migrants whose plans have changed as a result of border closures or entry requirements.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Overall this Output did not fully meet expectations in providing VfM.

IOM expertise and management of the DTM system did not meet expectations set out in the original Business Case for the implementation of this programme. DTM was not fully implemented until November 2018 (nearly 18 months into the programme cycle) and humanitarian partners have restarted an inter-agency IDP tracking taskforce to complement DTM data on IDP flows due to concerns with DTM’s methodology.

Additionally, nearly 5 times as many men were trained to collect DTM data than women (2,414 men, 553 women), reducing the equity value of this output. It has been suggested that the quick restart of the DTM system in 2018 meant insufficient focus was placed on gender equality in recruitment.

Lessons learned through this output, and recommendations for future programming

If supported with appropriate expertise and operational lead in and set up time, DTM can be an invaluable tool to support both IOM and the wider humanitarian programming for IDPs, refugee and migrants in Yemen. However, any future support of DTM should be in consultation with the newly established interagency IDP taskforce, and FCDO should work with IOM on realistic targets given the operational context and environment for implementing monitoring activities.

Output Number and Title		7. Cholera response (IOM)
Output Score		A
Impact weighting (%)		8%		Impact weighting revised since last AR?	Yes (see output 1 for explanation)

Output Indicator			Starting Target	Final Logframe Target	Final Result Achieved
7.1	Number of cholera cases receiving health care at supported facilities		20,000	20,000	22,472 112% achieved
7.2	Number of individuals reached through the health awareness activities (HH and awareness sessions)		65,600	65,600	60,600 92% achieved
7.3	Number of people benefiting from water chlorination activities		80,000	80,000	400,000 500% achieved
7.4	Number of individuals benefiting from water trucking		30,000	30,000	14,658 48% achieved
7.5	Number of individuals benefitting from the rehabilitation of water networks		30,000	30,000	56,987 190% achieved
7.6	Number of individuals benefiting from cholera hygiene kit provision		70,000	70,000	56,000 80% achieved
7.7	Number of individuals benefiting from solid and liquid waste management activities		80,000	80,000	111,102 138% achieved

Briefly describe the output’s activities and achievements during its lifetime and provide supporting narrative for the score.

This output has met expectations and scores an A.

In 2018, DFID extended its support to IOM’s cholera response, funding £2 million for cholera-related activities between 1st September 2017 and 31st August 2018. During this period, IOM targeted 14 districts in Hajjah, Hodeidah, Taizz, Ibb and Amran, working mostly through the Yemen Family Care Association and Yemen Red Crescent Society. Although some activities have underachieved against planned targets, overall IOM were able to treat 2,472 additional cases of cholera than planned and reach almost double the intended beneficiaries with water and sanitation hygiene (WASH) activities. Movement restrictions, access issues caused by security developments, and limited administrative capacity of implementing partners contributed to IOM’s failure to reach the Indicator 7.4 and 7.6 targets.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

This output shows good VfM as IOM were able to quickly and effectively absorb additional funds to cover an emergency need.

Lessons identified this year, and recommendations for the year ahead linked to this output

1. This project was originally intended to last from 1st September 2017 to 1st March 2018. However, IOM faced delays in rolling out some project activities due to bureaucratic hurdles presented by local authorities and security concerns and so was granted a no-cost extension to 31st August 2018. If FCDO is to fund a similar surge project in the future, these obstacles should be taken into consideration and factored into timelines.
2. These delays also meant IOM was required to initially implement most activities through its downstream partners, which required continual support to guide them through financial and reporting procedures. Working through implementing partners facilitated access and enabled IOM to begin the response sooner. IOM should ensure lessons learnt through this process are captured and used to enhance future activities and partner relationships.
D: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The overall risk rating of the programme has increased from Major to Severe over the past year following the outbreak of the Covid-19 pandemic in early 2020 and increased hostility towards humanitarian actors in the country, particularly in the North. The mitigation measures for the highest risk categories (external context/ delivery and safeguarding) are identified below. The programme continued to operate within FCDO Yemen’s risk appetite across the three years. A copy of the full risk register for this programme has been included in Annex A.

Risk / category	Risks	Mitigation measures	Residual risk
External context/ Delivery	1. Conflict situation deteriorates, reducing the ability of partners to deliver / 2. Threats to staff and operations from state or non-state actors / 3. Bureaucratic impediments (particularly in the North), such as procurement and distribution delays, visa refusals, restricted movement and data collection, or air space regulations, prevent programme delivery and access. / 4. Lack of humanitarian access due to the conflict / 5. Restraints on commercial imports prevent programme delivery / 6. Exchange rate fluctuation negatively impacts programming / 7. Covid-19 and subsequent border closures, travel bans and restrictions / 8. Risk of aid diversion meaning goods do not reach those in need	- FCDO works advocates with all parties to the conflict on humanitarian access; and HMG supports the work of Special Envoy to work towards a political solution. / - FCDO work with all major donors to lobby on the importance of keeping ports open to help tackle humanitarian crisis and maintains high level of communication with all partners to monitor the situation and proactively escalate issues. / - UNHCR and IOM have operational hubs throughout Yemen to strengthen the capacity of the humanitarian response system to operate. / - UNHCR and IOM work closely with local partners who have better access and networks across the country. / - UNHCR and IOM are in regular contact with government and defacto authorities to establish their mandate and activities and regularly meet with local authorities to improve access. / - OCHA’s Access Monitoring Working Group works to lobby on access constraints and support negotiation processes. / - UNHCR and IOM regularly monitor the security situation and use the EHOC deconfliction notification system to deconflict field missions. / - UK engagement with authorities in North and South to advocate for humanitarian access. / - Partners employ local staff and NGOs as appropriate and hold regular meetings with local and religious authorities to improve local access and acceptance. / - Partners coordinate closely with UN security departments and have completed contingency planning and relocated and diverted operations in response to extreme situations. / - Most procurement for the programme is done on the international market in USD to avoid exchange rate fluctuations. / - Ongoing engagement, contact, dialogue and communication with partners at the country level to monitor the situation. / - Both partners submit deconfliction requests and keep on top of security updates to minimise risk. / - Appropriate precautions and controls such as security guards, bars, CCTV, stock logs etc. are in place in facilities. / - Both have beneficiary feedback mechanisms through which beneficiaries can report instances of fraud or aid diversion and are working to strengthen these systems.	Severe
Safe / guarding	1. Programming is not conflict-sensitive and causes unintended negative impact / 2. Risk of sexual exploitation, abuse or trafficking by partner staff to colleagues or beneficiaries (increased as a result of covid-19 and reduced oversight from international staff) / 3. Negative perception of refugees and migrants puts them at increased risk of harm	- Both IOM and UNHCR strive for a conflict sensitive approach to implementation, for example by also supporting host communities / - High level of flexibility is factored into the programme. / - Beneficiary feedback is collected and utilised. / - Partners will increase the capacity of neighbourhood watch teams as well as community/local conflict resolution mechanisms to promote peaceful coexistence. / - FCDO Yemen has established a conflict sensitivity platform to provide technical assistance to partners. / - IOM is proactively doing conflict mapping and analysis in 8 governorates. / - Enhanced due diligence assessments have been completed for both partners with limited risks identified and recommendations will be regularly updated. / - Safeguarding reporting requirements are set out in the MoU and risks are discussed at quarterly meetings.	Severe

Risks and challenges to delivery were continually discussed at quarterly meetings and through narrative reports with both IOM and UNHCR. Neither IOM nor UNHCR formally reported any instances of fraud, loss or aid diversion to FCDO over the lifetime of the programme.

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

The IOM consortium struggled with underspend throughout the lifetime of the programme, spending 64% of their forecast in Year 1, 75% in Year 2 and 68% in Year 3. This can largely be attributed to obstacles and restrictions imposed by authorities in Yemen that can be unpredictable and difficult for partners to solve. For example, in order to abide by humanitarian principles and ensure they were reaching the most vulnerable, DRC had to pause some activities in late-2019 when SCMCHA refused to verify beneficiary lists. They were able to resume in January 2020.

Managing finances across the consortium has been challenging for IOM and has led to instances of confusion and inconsistency between IOM and FCDO financial tracking mechanisms. IOM was also not always proactive in warning FCDO of anticipated underspend which could have had serious consequences for the Yemen portfolio. The FCDO programme team remained flexible, allowing rollover between years and extending the programme end date from 31st May 2020 to 31st August 2020 to accommodate delays caused by the COVID19 pandemic.Despite these issues, IOM has been able to spend their full allocated budget within the extended time frame.

UNHCR spent according to forecasts and within the allocated timeframe of the programme. They were also able to quickly absorb additional funds for the procurement of non-food and emergency shelter kits in response to increased displacement in mid-2019.

Both IOM and UNHCR have supplied asset registers and FCDO is finalising the arrangements for these accordingly.

The IOM consortium approach was chosen to encourage joint planning, information sharing, exchange of ideas, experiences and lessons learned and reduce the risk of duplication. However, in practice, management of the consortium has proven to be a challenge for IOM across the years. Partners interviewed for this review did not indicate any substantial differences in management from this model versus IOM management through bilateral agreement with downstream partners. A closer examination of what worked and what did not, would be useful for future partner selection processes.
It is recommended that future programmes:
- Set budgets according to the FCDO financial year (April – March) and align partner reporting accordingly.
- Take into serious consideration the likelihood of implementation delays given the challenging operating environment in Yemen.
- Introduce FCDO and partner finance teams early on and ensure all requirements, timeframes and reporting preferences are clearly understood.
- Fully analyse the benefits and VfM of a consortium approach, consulting members of the IOM consortium in doing so.

Programme-level approach to monitoring and evaluation

Both IOM and UNHCR provided narrative reports and logframe updates each quarter. The quality and timeliness of narrative reports has improved over time and they have been valuable resources for the FCDO team. However, logframe submissions from IOM were often incorrect or missing data, indicating a lack of internal quality assurance.

Quartely meetings were consistently held throughout the programme, often in Amman, where teams had the opportunity to meet face-to-face. However, due to the security situation in Yemen, FCDO staff were not able to visit Yemen. As an alternative solution, FCDO commissioned Independent Monitoring Studies of both UNHCR and IOM’s activities funded through this programme.

IOM’s first study in 2018 consisted of a desk-based review and field visits to IOM, DRC, NRC and INTERSOS programming in Sana’a, Aden and Lahj. This study assessed their performance as moderate, with the most significant finding being that there were inconsistencies in the data reported on beneficiary numbers. IOM has since amended their data collection methods to address these areas of concern. Other significant findings related to poor beneficiary satisfaction, lack of knowledge of feedback mechanisms, insufficient operating hours of hospitals and lack of equipment and staff. Positive findings included staff speaking to beneficiaries in their own language, no evidence of informal payments, and that all beneficiaries were from the intended target populations.

The second study in 2020 visitied three IDP camps in Taizz where residents were supported with Information, Counselling and Legal Assistance from NRC. It was noted that activities met the criteria, with few or no improvements to be made. Beneficiaries held the project team in high regard and reported high satisfaction with counselling sessions.

UNHCR did not take part in any studies throughout the duration of this programme but had participated in one in late 2016 which assessed their cash transfers for refugees and IDPs. The study found that the vast majority of beneficiaries were in legitimate need of assistance, beneficiary data was accurate and people verified having received payments. Cost, geographic and cultural access were generally good, beneficiary satisfaction was generally high and other measures of quality of the payment process were high. Areas for improvement included verifiability of selection criteria, beneficiary complaints mechanisms, database accuracy and estimates of beneficiaries per household.

Date of last narrative financial report	Submitted to FCDO July 2020	Date of last audited annual statement	UNHCR: 31st March 2020 / IOM: 1st July 2020

Annex A: Risk Register November 2020

Risk / category	Risks	Mitigation measures	Residual risk
Delivery	1. FCDO has a reduced monitoring capacity without staff present in country. / 2. Hostile environment creates high staff turnover and risks low capacity of staff to deliver / 3. Reliance on downstream partners for delivery / 4. Poor financial management leading to significant underspend (IOM) / 5. Weak consortium management and cooperation (IOM) / 6. Value for Money (VfM) is not achieved	- IOM and UNHCR have both participated in FCDO’s Independent Monitoring programme. / - IOM have several members of staff covering finances in country and regularly meet with consortium partners to monitor financial reporting. / - IOM has a dedicated Consortium Coordinator and facilitates regular meetings with all consortium members to discuss common issues and challenges. FCDO holds quarterly meetings with the consortium which has increased over the reporting period to monthly meetings with all consortium members to more closely monitor implementation and financial management. / - FCDO has increased the percentage of time the Programme Manager spends on financial monitoring of IOM reports, including conducting thorough reviews of financial reports and forecasts and setting out expectations clearly at monthly meetings and in written communication. The Programme Manager and SRO have also worked closely with the Senior Programme Manager and Humanitarian Team Leader to ensure they are aware of any financial challenges and can provide appropriate support. / - VfM is continually assessed through reviews and independent monitoring.	Major
Fiduciary	1. Aid diversion through loss or damage / 2. Risk of fraud and corruption taking place. / 3. FCDO funds are diverted to de-facto government institutions or terrorist organisations.	- Due diligence assessments have found that IOM and UNHCR have fraud and corruption policies sufficient to investigate and tackle fraud. / - We practice and encourage clear, consistent and open communication on fraud and corruption with partners. / - Both partners have participated in independent monitoring which found no reports of fraud or aid diversion. / - Annual audited statements provide assurance funds all accounted for. / - Partners ensure they are not working with any FCDO blacklisted organisations. / - Delivery chain mapping has been completed for the programme. / - There is minimal procurement through this programme. / - Both submit deconfliction requests and keep on top of security updates to minimise risk. / - Appropriate precautions and controls such as security guards, bars, CCTV, stock logs etc. are in place in facilities. / - Both have beneficiary feedback mechanisms through which beneficiaries can report instances of fraud or aid diversion and are working to strengthen these systems. / - MoUs conon-food itemrm partners obligation to comply with UK counter-terrorism legislation. / - Mitigation measure for Delivery risks also apply.	Major
External context	1. Conflict situation deteriorates, reducing the ability of partners to deliver / 2. Threats to staff and operations from state or non-state actors / 3. Bureaucratic impediments (particularly in the North), such as procurement and distribution delays, visa refusals, restricted movement and data collection, or air space regulations, prevent programme delivery and access. / 4. Lack of humanitarian access due to the conflict / 5. Restraints on commercial imports prevent programme delivery / 6. Exchange rate fluctuation negatively impacts programming / 7. Covid-19 and subsequent border closures, travel bans and restrictions	- FCDO works advocates with all parties to the conflict on humanitarian access; and HMG supports the work of Special Envoy to work towards a political solution. / - FCDO work with all major donors to lobby on the importance of keeping ports open to help tackle humanitarian crisis and maintains high level of communication with all partners to monitor the situation and proactively escalate issues. / - UNHCR and IOM have operational hubs throughout Yemen to strengthen the capacity of the humanitarian response system to operate. / - UNHCR and IOM work closely with local partners who have better access and networks across the country. / - UNHCR and IOM are in regular contact with government and defacto authorities to establish their mandate and activities and regularly meet with local authorities to improve access. / - OCHA’s Access Monitoring Working Group works to lobby on access constraints and support negotiation processes. / - UNHCR and IOM regularly monitor the security situation and use the EHOC deconfliction notification system to deconflict field missions. / - UK engagement with authorities in North and South to advocate for humanitarian access. / - Partners employ local staff and NGOs as appropriate and hold regular meetings with local and religious authorities to improve local access and acceptance. / - Partners coordinate closely with UN security departments and have completed contingency planning and relocated and diverted operations in response to extreme situations. / - Most procurement for the programme is done on the international market in USD to avoid exchange rate fluctuations. / - Ongoing engagement, contact, dialogue and communication with partners at the country level to monitor the situation.	Severe
Safe / guarding	1. Programming is not conflict-sensitive and causes unintended negative impact / 2. Risk of sexual exploitation, abuse or trafficking by partner staff to colleagues or beneficiaries.	- Both IOM and UNHCR strive for a conflict sensitive approach to implementation, for example by also supporting host communities / - High level of flexibility is factored into the programme. / - Beneficiary feedback is collected and utilised. / - Partners will increase the capacity of neighbourhood watch teams as well as community/local conflict resolution mechanisms to promote peaceful coexistence. / - FCDO Yemen has established a conflict sensitivity platform to provide technical assistance to partners. / - IOM is proactively doing conflict mapping and analysis in 8 governorates. / - Enhanced due diligence assessments have been completed for both partners with limited risks identified and recommendations will be regularly updated. / - Safeguarding reporting requirements are set out in the MoU and risks are discussed at quarterly meetings.	Severe
Operational	1. FCDO is unable to fulfil its duty of care towards staff. / 2. Low internal staff capacity due to heavy workloads, lack of monitoring capability and risk of PM/Adviser gap.	- FCDO staff are not currently able to travel to Yemen. FCDO instead prioritises travel to the region to enable regular monitoring of programming and establish strong relationships with partners. / - Programme Manager ensures all programme documents (delivery plan, delivery chain, programme summary) and Vault folders are kept up to date so key information can be easily accessed and passed on. / - FCDO has appropriate recruitment processes in place for timely recruitment.	Moderate
Reputational	1. Largescale aid diversion or fraud case / 2. Mass casualty or damage incident affecting FCDO programmes / 3. Safeguarding risks are realised	- FCDO encourages clear, open, honest conversations about these risks with partners, aiming to identify and mitigate against them early. / - Safeguarding and fiduciary mitigation measures cover reputations risk mitigation.	Major