## Annual Review
Title: SPRING Accelerator (Assets for Adolescent Girls Programme)
Programme Value £ (full life): £14,587,110 FCDO - 65%; £3,568,205 USAID - 16% ; £2,417,554 DFAT - 11%; £1,734,532 Nike Foundation - 8% Total = £22,307,401		Review date: 17/12/2020
Programme Code: / GB-1-203375	AMP start date: / 17/12/2013	AMP end date: / 31/03/2022

Summary of Programme Performance
Year	2014	2015	2016	2017	2018	2019	2020
Overall Output Score	A	A	A+	A	A+	A+	A+
Risk Rating	Moderate	Severe	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	http://iati.fcdo.gov.uk/iati_documents/4787590.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/56133092.xlsx

A. SUMMARY AND OVERVIEW

Description of programme
SPRING was implemented from July 2014 to September 2019. It supported two cohorts across East Africa (Ethiopia, Tanzania, Kenya, Uganda and Rwanda) and two cohorts across South Asia (Bangladesh, Pakistan, Nepal and Myanmar). SPRING worked with businesses to develop products and services which would help girls stay safe, learn, earn and save, and improve their wellbeing. The programme supported 74 enterprises operating across nine countries to develop innovative solutions that had, as of September 2019, reached over 2.5 million girls and attracted £13.8m in investment.
[note] 2,156,880 through one business in Tanzania and 377,334 through other SPRING businesses
[note] This is comprised of equity (42%), grants (36%) and debt (16%)

Implementation was completed in September 2019, and the programme is now in an evaluation phase which runs to 2022. The evaluation looks at programme performance (PPE- the design of SPRING); business performance (BPE - how businesses adapted as a result of SPRING) and is undertaking 8 impact evaluations (IE - whether businesses improved girls economic and social outcomes). Over the summer of 2020, USAID identified surplus funds of £567,228 available for the evaluation partner, as the GBP value of their 2015 USD$5m commitment had increased. A revised set of deliverables, due from December 2020, was agreed and a contract amendment signed in October 2020. The uplift will allow the evaluation partner to: i) widely disseminate SPRING lessons; ii) provide focused support for SPRING businesses; and iii) determine business and prototype sustainability in current Covid-19 context.

In March 2020, FCDO signed an accountable grant agreement to fund the GenderSmart Investing Summit (GSIS) with up to £90,000 through the SPRING programme. This built on SPRING’s pioneering work to “attract large scale investment [that benefits girls] through effective communications that demonstrate the opportunities to others”. The Summit will bring together stakeholders to advance gender-lens investing; enable outcomes-orientated conversations on gaps, challenges and opportunities; and unlock gender-smart capital at scale. It has a proven record of success: commitments made on site at the 2018 GSIS (which did not receive FCDO funding) exceeded £6.8 billion ($9 billion).

Summary supporting narrative for the overall score in this review
This report covers the period November 2019 to October 2020 and measures the performance of the ongoing work by the evaluation partners and GSIS, except for Section B reviews the performance of the programme as a whole. The programme has scored A+ overall because, despite Covid-19 related delays, the evaluation partner, whose work has a higher weighting, has exceeded its targets in terms of both timeliness and quality standard. The evaluation partner has also made efforts to share knowledge of the SPRING programme with a wider audience. The GSIS held a well-attended series of virtual sessions, and plans are well-developed for the virtual event in February.

Major lessons and recommendations for the year ahead

Major lessons from the programme
The evaluation partner captured lessons to inform the design and implementation of future programmes that aim at working with adolescent girls in developing countries. A selection of these is shared here:
1. Weighted targets could be used in innovative but high-risk programmes to increase flexibility. SPRING had to achieve scale targets, which meant it had to be relatively confident in the viability of the businesses it selected. Accelerators usually operate with a much higher acceptable failure rate, which allows them to invest in high-risk and less tested business models. Programme designers need to take this into account in future accelerator-style programmes. Flexible or weighted targets might have a role to play when different aspects of a programme have different levels of impact - e.g. for SPRING, a girl targeted as a consumer might have attracted a lesser weighting.

2. FCDO programmes that work with early-stage businesses need to realistically assess what the business can achieve within the timeframe of the programme. Businesses with concepts but which have not yet attempted to implement them (“idea stage”) will be unlikely be ready to deliver in a shorter timeline (SPRING’s was 9 months per cohort); but mature businesses may have insufficient focus to be able to engage with a programme like SPRING (it may be difficult for the CEO to take extended periods out of the office to attend bootcamps). Accelerators seeking innovative partners need to identify businesses which have substance beyond an idea and the ability to commit, innovate and make decisions quickly. Ideally the businesses will be at growth stage – making a profit and seeking to expand.

3. The private sector can develop solutions which benefit adolescent girls, but to make these solutions commercially viable businesses need to embed them as part of a broad approach, or make their social benefits clear so they can unlock impact investments or grants. To ensure businesses can sustainably reach girls at scale, they should include adolescent girls as part of a broader consumer base group, rather than develop girl-specific products. They should ensure girls can make use of the products, for example, providing training with a digital product when girls are expected to have lower digital literacy. Where girl-specific products or services are developed, businesses can increase prototype sustainability by working through NGO, donor or government partners to make products with social benefits commercially viable, or by subsidising prototype activities through more profitable business streams.

4. Integrating girls as actors in value chains (distributors, advertisers, etc) is difficult for businesses to do successfully, but it has the potential for in-depth impact among girls when sufficient support and mentoring is provided. Businesses which aim to provide income-generating and employment opportunities to adolescent girls should only do so if they have the necessary resources and capacity in place to provide on-going support to girls. Girls can face increased social barriers related to their mobility, confidence and/or care burdens which limit their productivity. Businesses including girls in their value chain should provide opportunity for mentoring, on-the-job training, and emotional support and sense of belonging, as well as flexible work opportunities which are compatible with girls’ family and school commitments.
5. Businesses wanting to reach adolescent girls with products and services that benefit them should not think about this group in a vacuum but carry out careful stakeholder mapping of important decision-makers and influencers in girls’ lives. Research with girls’ “gatekeepers” (adults with significant control over girls’ lives) and other influential individuals in their lives (such as teachers) is key to reaching adolescents of all ages and backgrounds. Human-centred design (HCD) research with key gatekeepers in girls’ lives throughout development, design, launch and marketing process can also facilitate girl reach by generating an in-depth understanding of concerns held by gatekeepers.

Recommendations for the year ahead

These are the summary recommendations which should be prioritised. Limited further recommendations are found for each output in Section C:

1. FCDO SRO should agree refreshed logframe targets with the implementing partners by January 2021 for the Summit and March 2021 for the evaluation. The logframe should be refreshed to better reflect the remaining work strands, and SRO should judge the best way to capture the ongoing work at outcome level, as well as agreeing output indicators that track the engagement with SPRING businesses and development stakeholders.

2. FCDO SRO and evaluation partner should ensure both contribute contacts, events and ideas to the planned dissemination and lessons strategy due in December 2020, to ensure key partners are reached with the lessons from SPRING.

3. FCDO SRO should ensure FCDO colleagues attend and engage with the GenderSmart Investing Summit, take notes to facilitate the learning of others, and explore possibility of UK announcement at the Summit relating to impact investment programmes, by end December 2020.

4. The AMP end date should be immediately amended by the SRO to reflect the length of the M&E contract – using a very light touch business case amendment submission. While examining the contract to proceed with the SPRING uplift, FCDO discovered that the AMP end date for the SPRING programme is 31 March 2022, while the M&E contract runs to 30 June 2022. The contract existed before AMP, so it is assumed this was an inputting error by previous programme manager.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

This section considers changes over the programme’s lifetime. The SPRING theory of change (ToC) is presented in Annex A. There were no changes to the ToC from last year as implementation ended in September 2019. The evaluation partner’s work will contribute to understanding of the impact level contribution of the SPRING programme. SPRING was designed with an innovative and iterative implementation model, responding to a refined understanding of its operational context. This approach resulted in different iterations of its programme level theory over time. The ToC’s original focus on getting “direct economic assets to girls” was broadened to include a wider range of products, services, and business opportunities.

The evaluation partner found that return on direct SPRING investment was greater than 1 in terms of external investment leveraged, meaning that businesses generally leveraged more monetarily than the funds SPRING invested. However, in terms of prototype revenue, the return on investment of SPRING financial support was on average less than 1, based on data collected during the life of the programme. While prototype and overall sales performance improved over time, several SPRING businesses still struggled to ensure prototype profitability and prototype revenue in most cases remained small. This links to Major Lesson 3 in Section A - businesses need to approach girls as part of a broad commercial strategy, or make the social benefits of girl-focused products clear so they can unlock impact investments or grants. Businesses that did this successfully were able to get a positive return on investment. Cost per girl reached was £6.82 (£45.81 excluding outlier business Ubongo). Stay Healthy interventions were the most cost-effective per girl reached. Earn and Save prototypes were the least cost-effective.

Overall, the effectiveness of the programme is likely to increase as a result of changes this year, which have been achieved within the original budget envelope of the programme:
1. The increase in dissemination activities undertaken by the evaluation partner means that the lessons from the programme’s innovative design and approach are more likely to be taken up by a wider set of stakeholders.
2. The new partnership with the GenderSmart Investing Summit will contribute to the ecosystem level by increasing awareness and targeting of girls, and opportunities to invest in products and services that benefit women and girls.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

This section considers whether the programme as a whole is on track to reach its outcomes and impact. SPRING exceeded all the original outcome targets in September 2019. The impact can only be fully assessed once all eight Impact Evaluations (IE) are completed. To date, three of five impact evaluations have reported improved outcomes for girls in line with the target of 60%. Implementation has ended so no action can be taken to alter the impact.

The outcome is: Enterprises provide market-based solutions (i.e. products and services) that can benefit girls and contribute to their economic empowerment. There are three outcome indicators:

	Target (Sept 2019)	Achieved (Sept 2019)
Outcome indicator 1: Cumulative number of SPRING-supported businesses securing external investment, aided by participation in SPRING	20	31
Outcome indicator 2: Cumulative number of adolescent girls reached with SPRING-supported businesses’ products, services or employment opportunities	200,000	2,534,214
Outcome indicator 3: Cumulative number of SPRING-supported businesses who have increased sales from products, services, or business models benefitting girls by 20% or more.	50	55

The programme’s impact statement is: Enterprises, investors and markets contribute to economic empowerment of adolescent girls. An indicator for this was agreed as ‘% of girl beneficiaries reporting improved outcomes linked to economic empowerment, disaggregated by SPRING-supported business’, with a target of 60%.

As part of the Impact Evaluations (IE), the evaluation partner measured and reported on a number of dimensions related to improved outcomes, which reflected the four impact areas of the programme: learning, earning, staying healthy and staying safe. Each of these dimensions was reported on separately within the IE report, and in some cases the improved outcomes related to these dimensions varied considerably. Information from the six IEs completed to date is shared in Annex B.
[note] There are to be eight impact evaluation reports, in terms of the evaluation design. Six endline evaluations have been completed at the time of writing.

Of the five IEs with qualitative figures, three (360Ed, Ubongo and Paritran) have over 60% of respondents reporting improved outcomes for at least one dimension. One IE (iSocial) reported improved outcomes at a rate above 60%, but the endline results were lower than the baseline result; the last IE (Shekinah) reported positive outcomes at only a rate of 18%. It is notable that more successful businesses were from the later cohorts, which indicates that SPRING improved its selection process and programme delivery. The remaining two IEs due in 2021 will show if this trend continues.

There are currently no outcome level targets relating to the GenderSmart Investing Summit, or the evaluation partner’s work. FCDO SRO should agree refreshed logframe targets with the implementing partners by January 2021 for the Summit, and March 2021 for the evaluation. The logframe should be refreshed to better reflect the remaining work strands, and SRO should judge the best way to capture the ongoing work at outcome level, as well as agreeing output indicators that track the engagement with SPRING businesses and development stakeholders. (Summary recommendation 1).

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

This section considers whether the ongoing activities should continue. The programme continues to deliver good value for money for FCDO, which has been able to make use of the programme’s strong performance to get the buy-in of other donors. The ongoing evaluation work is producing and synthesising detailed lessons for FCDO and other development actors on how to reach girls through the private sector, and how to run accelerator programmes. The creation of this knowledge enhances the value of SPRING, and the uplift in the budget from USAID will ensure that more effort is spent on embedding these lessons in relevant organisations.

The GenderSmart Investing Summit represents good value to the UK, which is one of many sponsors. The Summit contributes to the ecosystem level outcomes of the SPRING Theory of Change (see annex A) that businesses and investors recognise girls as a market segment, and that SPRING generates awareness and demonstration effects around products that benefit girls. It also contributes to the ecosystem impact of SPRING – that following increased awareness, new impact investors will crowd into the gender-targeted market.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	SPRING participants launch prototypes designed to reach and benefit adolescent girls
Output number:		1	Output Score:	-
Impact weighting (%)		0	Weighting revised since last AR?	Yes ↓

Output Title	SPRING-supported businesses improve their investment readiness
Output number:		2	Output Score:	-
Impact weighting (%)		0	Weighting revised since last AR?	Yes ↓

Output Title	SPRING-supported businesses benefit from human centred design and other forms of SPRING TA to improve business viability and develop products and services benefitting girls
Output number:		3	Output Score:	-
Impact weighting (%)		0	Weighting revised since last AR?	Yes ↓

Output Title	Ecosystem stimulation for products and services benefitting adolescent girls
Output number:		4	Output Score:	-
Impact weighting (%)		0	Weighting revised since last AR?	Yes ↓

Briefly describe the output’s activities, and provide supporting narrative for the score.

Outputs 1-4 related to the implementation phase of the programme. Detailed assessment of their performance can be found in the 2019 annual review.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

A note on how to treat VFM over the remaining life of the SPRING programme was completed this year. It concluded that the M&E reports provide a separate, deep measure of the true effectiveness of the SPRING programme, something many programmes lack. This will allow FCDO to get a true sense of the VFM, beyond what it was possible to monitor during the life of the programme. In the programme completion report (expected in 2022), once all of the impact evaluations are completed, a more in-depth judgement of the effectiveness of the programme can be undertaken, using the evaluations to assess the implementation period with more detail than is currently possible.

Describe any changes to this output during the past year, and any planned changes as a result of this review
The impact rating of these outputs was reduced to 0%, to reflect that no further work is being undertaken towards these targets. No further changes are planned.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Three of the 5 summary recommendations in the 2019 AR fell to the SRO and programme manager:
- To record the extensive network of contacts linked to SPRING – this was done.
- To consider the best way to record VFM – this was completed via a note in June 2020 that assessed the best options for each indicator under each remaining output. This has formed the basis of the VFM assessments in this report.
- To draw up a dissemination plan for sharing lessons across FCDO – a comms plan was produced but this has been superseded by the evaluation partner’s work to increase dissemination activities. Ad-hoc meetings to share SPRING’s lessons were held with colleagues in PSD, EPIC and colleagues in external secondment to the Shell Foundation.
Output Title	High quality delivery of independent evaluation
Output number:		5	Output Score:	A+
Impact weighting (%)		90	Weighting revised since last AR?	Yes ↑ (new output)

Indicator(s)	Milestone(s) for this review	Progress
5.1 % of agreed milestones delivered on an annual basis as per the agreed timetable/work plan, reflecting agreed changes	80%	Met expectations / 11 of 13 reports (84%) delivered as per agreed workplan.
5.2 % of milestones delivered that are of a good quality, comments are addressed and reports are approved	80%	Moderately exceeded expectations / 100%

Briefly describe the output’s activities, and provide supporting narrative for the score.

Overall, this output has scored an A+ because indicator 5.2 which measures the quality of the reports is weighted more than 5.1 which measures the timeliness of reports. All submitted reports were completed to a high standard, as judged by USAID’s evaluation experts, exceeding the target of 80% of reports. The higher score also reflects that the evaluation partner made further efforts to embed the learning from the SPRING programme in FCDO:
- In January 2020, the evaluation partner made a presentation during Evaluation Unit’s ‘Evaluation Week 2020’, drawing on SPRING as an example. The presentation focused on adaptive evaluation to support adaptive programmes and was delivered to FCDO’s evaluation cadre.
- The evaluation partner worked with FCDO Evaluation Unit to feed into the methodological design of an internal policy paper on procuring and managing adaptive programmes. The evaluation partner was able to co-develop a case study on SPRING to be used as one of the three cases studies in the paper. Evaluation Unit confirmed work continues to finalise this.
- The evaluation partner, the implementing partner and FCDO SRO jointly developed an abstract on ‘Adaptive Evaluation for Adaptive Programming’ for the 2020 European Evaluation Society Conference. The abstract was accepted and rolled over to the 2021 conference, as it was postponed due to Covid-19.
Indicator 5.1 – Met expectations – Of the 13 milestones planned this reporting year, 11 have been delivered as per the agreed timetable (84%). This is the minimum number of reports that could be delivered in order to meet the target, so it is judged as meeting expectations despite slightly exceeding the numerical target. Of the delivered reports, two had extensions agreed by FCDO. Two further impact evaluations have not been submitted this year due to delays in accessing schools, where the interviews with girls take place. The work will be resumed in early 2021, depending on in-country conditions.

Indicator 5.2 – Moderately exceeded expectations – All 11 submitted milestone reports responded promptly to extensive donor comments from DFAT, FCDO and USAID in a clear and well-reasoned manner. The final products were judged by the donor group to be frank, coherent, logical and well formatted in that they identify useful findings upfront. FCDO SRO approves the products once other donors indicate they are satisfied with the drafts. Major lessons have been presented in Section A above; see Annex B for a full list of impact evaluations to date, and Annex C for full list of products produced this year and selected key findings.
[note] Milestone	Component	Cohort	Timeliness	Selected Key Findings 1	Thematic Learning Area Reports	BPE	N/A	5 reports delivered on time	The evaluation partner carried out in-depth primary research with 28 of the 75 businesses to gather insights and learn lessons on how they reached girls and improved their lives. The reports focused on: / a) reaching girls through the value chain; / b) reaching girls through technology; / c) reaching girls through stakeholders; / d) targeting different age groups; / e) narrow and broad targeting of girls. / The reports produced useful insights on what works (and what does not) to reach adolescent girls through business solutions. 2	Endline research finalised Business 4 (iSocial)	IE	Cohort 2	Fieldwork report and impact evaluation of iSocial business, delivered on time.	See Annex B for more detail. iSocial’s product impacted how girls benefitted from access to information, products and mentorship. Overall, there is limited evidence of depth of girl impact. 3	Baseline research finalised Business 6 (JBS)	IE	Cohort 2 (replacement AcceleratED – Cohort 3)	Fieldwork report shared with donors in January 2020 after agreeing extension due to late-stage change with businesses.	Confirmed robustness of evaluation methodology and provided baseline sample to compare with endline. 4	Annual Report 2019	General	N/A	Delivered on time.	N/A 5	Cohort 4 Dissemination Activities	Dissemination	Cohort 4	Development of 14 Infographics. Delivered on time.	Infographics which captured the stories of 14 case studies of cohort 4 businesses and how the used the SPRING programme, and the outcomes they achieved. 6	Baseline research finalised Business 7(360ed)	IE	Cohort 4	Delivered on time	Confirmed robustness of evaluation methodology and provided baseline sample to compare with endline. 7	Baseline research finalised Business 8 (LearnObots)	IE	Cohort 4	Delivered on time	Confirmed robustness of evaluation methodology and provided baseline sample to compare with endline. 8	PPE Summative Report	PPE	N/A	Delivered after extension agreed with donors.	Highlighted several lessons for implementers (including summary lesson 1 in Section A). Assessed that part of SPRING’s underlying hypothesis (that private sector players could profitably play a role in providing products and services to girls) was proved by the evaluation. 9	Bi-Annual Report 2020	General	N/A	Delivered on time	N/A 10	BPE Summative Report	BPE	N/A	Delivered on time	Summarised several findings for using businesses to benefit adolescent girls (including lessons 2-4 in Section A). It also notes the 4 common characteristics that the businesses with the highest girl reach had: i) continuing to use HCD to better understand and respond to the needs of adolescent girls; ii) using technology as a key targeting mechanism; iii) engaging stakeholders external to the target group; and iv) reaching girls as part of a broader target group. 11	Endline research finalised Business 7 (360ed)	IE	Cohort 4	Delivered on time	See Annex B for detailed breakdown. Reading Bay Kin booklets increased knowledge and understanding related to body privacy, self-defence, puberty, sexual and reproductive health, HIV protection and laws and rights and improved girls’ perceptions of inappropriate actions by an adult. These changes better equip girls to identify and respond appropriately to risks and threats, improving their safety and wellbeing. 12	Endline research finalised Business 6 (JBS)	IE	Cohort 2 (replacement AcceleratED – Cohort 3)	Data collection impacted by COVID-19, evaluation partner has contingency plan in place if access to schools is further delayed.	Not yet known. 13	Endline research finalised Business 8 (LearnOBots)	IE	Cohort 4	Data collection impacted by COVID-19, evaluation partner has contingency plan in place if access to schools is further delayed.	Not yet known.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The SPRING M&E is supplied by TetraTech under a fixed output payment-by-results contract. The determining factor of whether the M&E is cost-effective is if the reports are used well. During the implementation period, the evaluation work provided valuable data spot-checks and a feedback mechanism that helped the implementer to refine the bootcamp design. In the current phase, the evaluation’s findings must be used by donors and key stakeholders beyond the implementation team. Knowledge sharing has been ad-hoc to date, but the increased focus on dissemination in the future period will increase the reach and understanding of SPRING’s findings.

Reviewing each area individually confirms the evaluation work remains good value for money:
- Economy: the inputs (money from FCDO, DFAT and USAID) are fixed and were negotiated at procurement stage. Through exchange rate gains, the programme was able to increase its total value, at no cost to FCDO. The contract is £4,044,946, with USAID covering most of the cost, with contributions from DFAT, and FCDO covering the majority of the VAT. FCDO contribution is approx. £700,000, reflecting a saving versus funding it alone.
- Efficiency: because it is a payment by results contract, the inputs (data collection, M&E expertise and travel) are turned into the outputs at a fixed conversion agreed at procurement stage, which was negotiated to ensure good value, and locked in at a fixed cost over 8 years of the contract.
- Effectiveness: Effectiveness can be measured in two ways, i) how effectively do the reports assess the SPRING programme, and ii) how effectively are the reports used to guide and inform decisions by other parts of FCDO, and other stakeholders. The former will be assessed as the reports are approved (and performance to date is high – see previous section), while the latter is FCDO’s role and harder to measure (but will be improved with the new dissemination activities).
- Equity: SPRING’s evaluation has a high equity performance given that all the product-users involved in the evaluation are girls, and where appropriate analysis considers the difference in age groups and between rural and peri-urban girls. The beneficiaries of the research will be colleagues across FCDO and other development and impact-investing stakeholders. Effort is taken to reach a wide audience through maintaining a website and associated mailing list.
Additionally, the M&E provides a separate, deep measure of the true effectiveness of the SPRING programme, something many programmes lack. This will allow FCDO to get a true sense of the VFM, beyond what it was possible to monitor during implementation. The judgement of the programme’s cost-effectiveness as at September 2019, therefore, may change as more impact evaluations (IE) and other M&E reports are produced. Findings from the IEs to date are covered in Annex B.

Describe any changes to this output during the past year, and any planned changes as a result of this review
Due to currency exchange rate fluctuations over the years, USAID’s contribution – committed in dollars - has increased in value. As a result, the donors have jointly agreed to slightly expand the number of milestones for the evaluation partner by reinvesting the increased value of USAID’s contribution in a budget uplift of the value of £567,228. The contract amendment was approved in October 2020 and all activities can take place within the existing contractual timeframe. FCDO, USAID and the evaluation partner have agreed to a package of three additional stands of deliverables to support knowledge generation and lesson sharing by the evaluation partner:

1. Widely disseminate SPRING lessons on both project design and impact, targeting:
  1. Other donors
  2. Programme designers and evaluators
  3. Programme implementers

Building on existing ‘Dissemination Activities’ milestones, the evaluation partner will be able to ensure the many lessons for the SPRING profile are widely shared and built upon by many interested parties. Activities under this strand include:
- An ‘indirect’ approach - maintaining the SPRING website with its large reach and audience, adding additional content on evaluations, which includes infographics, interactive datasets and short videos based on the Summative Reports, and amplifying this through social media channels and the SPRING mailing list;
- A ‘direct’ approach – attending multiple evaluation seminars and conferences, developing thematic strands for dissemination to relevant parties (i.e. consolidating all health and/or education evaluations to share with health / education funders or businesses); and
- A ‘focused’ approach – directly contacting interested organisations (Master Card Foundation, UNFPA, Gates Foundation, etc) to deliver workshops or seminars that are particularly relevant to ensure the lessons from SPRING are used by a wide audience beyond the involved donors.

Provide focused business support, e.g. KPI data collection and use for SPRING businesses, and safeguarding support, etc.
The 75 SPRING businesses were the core of the original programme, and SPRING provided them with a range of technical assistance and support, primarily human-centred design training in order to improve their products and services for use by adolescent girls. This strand builds on selected businesses’ existing relationships with the M&E supplier and will provide them with further support and training, to ensure they can reach and benefit adolescent girls, through virtual training sessions.

The below strand will determine what exactly will be most useful to the businesses, but it is expected KPI collection (for use when seeking investment), safeguarding training (for continued engagement with girls), market research, and business development tools and skills will featured prominently.

Determine business and prototype sustainability in current Covid-19 context
Building on the evaluation partner's work to judge the sustainability of SPRING prototypes, this research piece will look at the extent to which businesses are continuing to target girls; whether their SPRING prototypes are still part of their offering; how their businesses operations and sales have been impacted by Covid-19, and how Covid-19 has affected their ability to reach girls.

This research will provide a valuable insight into how Covid-19 has impacted the ability of businesses to reach girls. This will give another angle to help understand the full picture of the impact of Covid-19 on girls, as it is already clear they are likely to face higher care burdens, decreased access to education, long-term impact on their employment potential and increased risk of gender-based violence. This research piece will also highlight the needs of businesses that can be met by the business-focused support included in point (2).

A revised milestone payment-by-results schedule has been agreed, which incorporates these new activities.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Progress on recommendations from the previous AR
This was a new output this year, but summary recommendations 1 and 2 from 2019 were taken forward by the evaluation partner.
SPRING’s M&E partner should consider investigating the investor environment in their Programme Performance Evaluation (PPE) report, due in February 2020, which looks at how successful the SPRING programme was. The ‘investor environment’ in this instance, refers to the make-up of the investor landscape in a given context.

After consideration, the evaluation partner did not report on this in the PPE report because the SPRING implementing partner and donors decided before Cohort 1 that the role of contextual constraints – such as social norms, investor ecosystem, market regulations and regulatory frameworks – was beyond the accelerator’s scope and not feasible to achieve within five years. This area was therefore not identified as a key evaluation question within the Evaluation Framework that was approved by FCDO, USAID and DFAT, so limited data had been collected on this. The PPE annex on the evolution of the ToC reports on this shift. The BPE, however, does explore the impact of SPRING on the businesses being better equipped to attract investment. It found that almost half (35) of the businesses had succeeded in attracting further investment.

Human centred design has been a core feature of the SPRING accelerator. As part of the Business Performance Evaluation Summative report, due in June 2020, the M&E partner should, as agreed, conduct research into which aspects of this approach were crucial to SPRING businesses, which were less relevant, and if certain aspects have been dropped or replaced in future prototypes, why this is the case.

Business feedback on Human Centred Design (HCD) was gathered through the End of Cohort surveys and sustainability interviews. Findings were used to assess the relevance of HCD to business needs, its effectiveness of as a programme input and recommend potential improvement to its delivery within the PPE Summative report. The extent to which HCD has been applied by the businesses, and the sustainability of the implementation of all the phases of this methodology was assessed as part of the BPE Summative Report.

Lessons learned
The key lessons uncovered by the evaluation reports to date have been shared in Section A.

Offline finance monitoring should be done for all FCDO programmes with funding from multiple donors. The finances for SPRING are complex. The USAID exchange rate gain was only acted upon this year as until now all non-FCDO funds had been held in a shared account without independent tracking of donor balances. A spreadsheet that allows closer financial monitoring of other donors’ funds has been set up and will be used for the rest of the programme, alongside regular Crown Agents bank statements.
Recommendations for the year ahead
FCDO SRO and evaluation partner should ensure both contribute contacts, events and ideas to the planned dissemination and lessons strategy due in December 2020, to ensure key partners are reached with the lessons from SPRING (Summary recommendation 2).

FCDO SRO and the evaluation partner should agree the best way to adequately capture and reflect the ongoing evaluation work as part of the update to the logframe by March 2021. (Part of Summary recommendation 1).

The AMP end date should be amended immediately to reflect the length of the M&E contract – using a very light touch business case amendment submission. While examining the contract to proceed with the SPRING uplift, FCDO discovered that the AMP end date for the SPRING programme is 31 March 2022, while the M&E contract runs to 30 June 2022. The contract existed before AMP, so it is assumed this was an inputting error by previous programme manager. (Summary recommendation 4).

Output Title	GenderSmart Investing Summit contributes to the sphere of gender-smart investing
Output number:		6	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	Yes ↑ (new output)

Indicator(s)	Milestone(s) for this review	Progress
6.1 GenderSmart team demonstrate effective delivery of GenderSmart Investing Summit(s)	Strong delivery of virtual Summit over 2020 and plans in place for first summit	Met Expectations / 14 interactive sessions held over May-July 2020. / Dates and themes confirmed for full virtual summit in February 2021.

Briefly describe the output’s activities, and provide supporting narrative for the score.

The GenderSmart investing summit was originally planned for April 2020. This was postponed due to Covid-19 and instead a series of virtual events took place over the summer, with a full in-person summit planned for December 2020, but then postponed again to February 2021 and made virtual.

Indicator 6.1 – Met expectations – There were 14 interactive sessions between May and July 2020 on topics including Covid-19-responsive and gender-smart finance, Investable Opportunities, Climate & Gender Finance, Data, the Gender-Smart Narrative, and Pathways from Education to Employment. There were 389 people registered for events, of which 357 people attended (91%). There were 191 repeat participants and 25% of attendees attended more than 4 sessions. Attendees were from 37 countries and over 40 different organisations. See pie chart below for audience breakdown.

Beyond the virtual sessions, working groups and a commitment tracker have been set up. As of November 2020, the commitment tracker shows a total of £11.1bn ($14.6bn) committed by summit participants (since 2018).

Plans for the main summit progressed, with the GenderSmart team using learning from the virtual sessions to ensure the February event is as successful as possible. They identified 15 lessons including the need to improve the gender diversity of their audience. In response to this lesson, a roundtable with 40 men in the gender-investing community was held, including an FCDO private sector development adviser.

A final agenda for the February summit is expected in December – a draft agenda has been shared with sponsors in October 2020.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

The VFM note produced this year considered how to measure VFM for this output:
- Economy: FCDO has contributed $50,000 to date and is one of many donors. The 2018 summit cost around $1.2m, but the costs for the virtual 2021 summit are expected to be lower.
- Efficiency: The summit has responded extremely flexibly to the pandemic, ensuring that the virtual summit can go ahead, as well as holding additional summer sessions for attendees, so its efficiency is higher than expected initially.
- Effectiveness: the 2018 summit had pledges worth around £6.9bn ($9bn). Pledges to date have increased to £11.1bn, as mentioned above. The summit continues to effectively drive commitments and pledges of gender-smart financing.
- Equity: The decision to plan a virtual summit was taken in part to ensure there could be global participation while international travel remains limited. 73% of participants of the summer sessions were from Western Europe or the United States: GenderSmart is making efforts to increase attendees from the global south, including through running a scholarship programme (which allocates free tickets). The Summit team are taking steps to ensure their audience is more gender-diverse, as mentioned above.
The simplest judge of success is whether pledges and new funding made at the Summit exceed significantly the cost of the Summit. Pledges made in the interim since the 2018 summit have already exceeded the original expected cost substantially. Additional but difficult to quantify benefits on top of pledges are that the Summit continues to move the policy agenda forward and the increased awareness of previously gender-blind funders. For these reasons, the relatively small investment in the Summit remains good value for money for FCDO.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
This was a new output this year, as the accountable grant agreement was signed in February 2020. In-year, the date of the summit shifted, and the logframe targets drafted in June for this output reflect this delay.

Given the ecosystem impact that the Summit has the potential to have, FCDO SRO should consider a outcome level indicator for this output, which contributes to the original outcomes of the SPRING programme, in line with its Theory of Change (see annex A) (summary recommendation 1).

Delays to the 2020/21 Summit have had a knock-on effect for the date of the 2022 Summit and are expected to push this beyond the current life of the SPRING programme. In the next reporting year, FCDO SRO should agree a way forward to address this (output recommendation 3).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
This was a new output for the programme this year so there are no previous recommendations.
Lessons learned this year
1. The climate and gender working group developed a briefing note which highlighted a number of tools and datasets available to those wanting to make the case for gender-smart climate investments. For investors, it recommended bringing a climate/gender lens to due diligence, funding the development of tools, case studies, reports that look at this nexus, and provide technical assistance on the climate/gender nexus for funds and companies to increase capacity in the sector. This note is being drawn on by FCDO, as part of plans for how to integrate gender-themes into the COP26 Summit.
2. The GenderSmart team recognised from feedback they should provide more precise articulation of how sessions help delegates achieve specific sectoral, thematic, regional or institutional goals. This will ensure the right attendance and improve participant satisfaction.
Recommendations for the year ahead
FCDO SRO to include an outcome-level indicator linked to the commitments made at the summit as part of the annual logframe refresh by January 2021. (Part of Summary recommendation 1).

FCDO SRO should ensure FCDO colleagues attend and engage with the GenderSmart investing summit, take notes to facilitate the learning of others, and explore possibility of UK announcement at the Summit relating to impact investment programmes, by end December 2020. (Summary recommendation 3).

If the February 2021 Summit is successful, FCDO should consider the case for seeking a no-cost time-extension to the SPRING programme to ensure the second Summit can be done in partnership with FCDO, or explore the option for an alternative programme to house the funding relationship.
D: RISK

Overview of risk management

Although the programme has achieved its reach targets, the risk rating remains high as the evaluation reports will be used to conclude whether this programme was successful in terms of impact. The overall programme risk rating is major. Using a private sector development approach to improve girls’ ownership of assets, access to education, health and wellbeing and deliver impact is a novel approach. The ongoing Impact Evaluations are crucial to understanding whether the depth of impact was achieved – therefore the risk remains that the programme’s ToC may be disproved.

As the programme moved into its evaluation phase, the risk register has been revised accordingly. In addition, further revisions have been carried out in response to the outbreak of the Covid-19 pandemic which has had a direct effect on the viability of SPRING businesses, and the travel and face to face interaction needed for the data collection activities of the evaluation partner.

FCDO review risks on at least a quarterly basis – this has dropped from bi-monthly as the programme no longer has a dedicated programme manager. As of November 2020, the top three risks, listed in order of residual impact, for the programme are:

Risk	Gross likelihood	Gross impact	Mitigating Action	Residual likelihood	Residual impact	Residual Risk
Poor safeguarding of girls – evaluation activities that directly engage adolescent girls in the programme are not implemented in a safe and appropriate way, either by the supplier or downstream partners	Possible	Severe	TetraTech International is bound by a strict code of conduct in addition to a set of minimum standards, and does training for all downstream partners on safeguarding. FCDO has sought assurances on their policies and will check compliance with ongoing monitoring visits.	Unlikely	Moderate	Moderate
COVID 19 prevents or otherwise impacts in-country M&E data collection, meaning that the supplier is unable to produce deliverables as planned	Possible	Moderate	Evaluation partner worked up contingency plan and programme management remains flexible in response to Covid-19. Tetratech is closely monitoring the situation and is working with local research partners to identify local researchers who can conduct data collection. They are also discussing remote options for enumerator training and data collection, in case there are continued delays to access Nepal and Pakistan. New workplan is mostly virtual to overcome Covid restrictions.	Possible	Minor	Moderate
Covid-19 related delays to the first GenderSmart Summit means the second summit to be supported by FCDO is pushed beyond the current SPRING programme end date	Almost certain	Minor	Consider a short extension to SPRING to cover the dates of the second summit based on the success of the first summit	Possible	Minor	Moderate

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency. [max 1 page]

TetraTech
The evaluation partner has taken over the completion of the annual risk assessment for the programme, which covers financial and operational risks and processes. FCDO and the supplier meet monthly to discuss progress, finances and ad-hoc issues. The partner is responsive to FCDO requests and incorporates large amounts of feedback from FCDO and other donors in the evaluation products. The supplier delivers in line with the milestone contract, but it became apparent this year that the contract end date and the AMP end date were mismatched. Summary recommendation 4 states that immediate action should be taken to ensure the AMP end date reflects the length of the M&E contract.

The evaluation partner is on a Payment by Results contract, so forecasting is accurate based on when deliverables are due. VFM has been discussed under each live output. The evaluation partner always delivers the milestones within the agreed budgets and has sought to use local partners and virtual training where Covid-19 has prevented travel to ensure work is not stopped.

The evaluation partner has put in place safeguarding policies in response to security concerns and because of the work with vulnerable populations. FCDO has reviewed these policies and issues related to girl safety are discussed regularly. For example, a letter that sought parental permission for girls to join the evaluation was shared with FCDO for review. In addition, the evaluation partner has produced guidelines and protocols in response to Covid-19 which currently prevent the deployment of any data collection activity if this can pose health risks to the team, businesses and beneficiaries.

DFAT and USAID
The donor group for SPRING meets approximately every 6 months. Two meetings were held in the reporting period, facilitated by the evaluation partner. USAID attended virtually; DFAT received an update by email due to the large time-differences. Ad-hoc conversations were also held during the period to gather views from USAID and discuss finances. Virtual bi-annual meetings will continue to monitor the performance of the supplier and findings of the reports.

Donor budgets
Due to currency exchange rate fluctuations over the years, USAID’s contribution of $5m in 2015, has increased in value. An uplift to the existing contract was agreed, with corresponding VAT payments funded by DFAT, interest the shared account has accrued 5 years, and a small amount by USAID with their express permission. This has increased the contract by £567,228. The budget uplift was approved in October 2020 – FCDO’s contribution has remained the same. A donor breakdown is below.
	Contribution to M&E	Spend to 12-10-2020	Remaining
DFAT	£477,729	£130,237	£347,492
USAID	£3,567,217	£2,964,827	£602,390
Total	£4,044,946	£3,095,065	£949,881
VAT costs	£808,990	£619,013	£196,912
Of which	FCDO: £695,565	£619,013	£76,532
	DFAT: £61,854	-
	USAID: £989	-
	Interest: £50,582	-

GenderSmart Investing Summit
FCDO signed a low value accountable grant agreement with ImpactAssets, a non-profit US-based company who lead production of the summit. The GenderSmart team are incredibly responsive and collaborative in their approach to designing the summit. They discussed emerging issues relating to Covid-19 with FCDO as they were happening. Given the low value of this grant, and that FCDO is one of many donors, programme management of this aspect is proportionally light touch. As part of the Due Diligence process ahead of signing the accountable grant, the FCDO programme manager reviewed their financial controls and reporting. They were found to be strong and GenderSmart shared relevant information and documents to satisfy FCDO enquiries. FCDO will review financial performance of the Summit in the next AR, comparing costs year on year.

Date of last narrative financial report	November 2020	Date of last audited annual statement	September 2019 (from implementing partner)

## Annex A. Theory of Change

## Annex B – Findings from Impact Evaluations to date

Business, Country, / Cohort	Main Finding	Specific IE findings
ToTohealth, / Tanzania / Cohort 1	The business had a positive impact on health-seeking behaviour, though the magnitude was still low given prevailing contextual barriers. The greatest change was in improved MCH knowledge and awareness, though corresponding changes in attitudes and behaviour were more tenuous.	As a prototype evaluation, data was not collected in a quantitively, so no percentage findings are available for ToTohealth.
Shekinah, / Rwanda / Cohort 1	By endline, there was a significant reduction in the activity of the cooperatives. All cooperatives were inactive outside of the harvest season (July-October). Girls had not improved their earnings. Most girls were paid informally in cash rather than through secure banking channels. Girls’ savings doubled from baseline to endline, and there was a greater understanding of, interest and participation in savings.	82% of endline respondents felt they had worked and earned more before they joined their Shekina cooperative / 18% more girls were involved in income generation activities at endline. / Girls reported generally that they earned more before joining the cooperative. / Girls reported feeling more confident as a result of the intervention.
iSocial, / Bangladesh / Cohort 2	This impacted how girls benefitted from access to information, products and mentorship. Overall, there is limited evidence of depth of girl impact.	74% of endline respondents report changing their behaviour as a result of the intervention, but this dropped from 84% at baseline. / Respondents reported buying fewer products from the intervention agents at endline.
Paritran (Fightback) / Nepal / Cohort 2	Girls improved their knowledge of safety and self-defence techniques. Girls reported improved psychological and physical health and self-confidence in their ability to stay safe and defend themselves	A significant percentage of girls reported feeling more secure in public areas as a result of the intervention. (In extra-curricular activities (+16%); where they spent time by themselves (+13%), at school (+12%) or on public transport (+11%)) / 74% of girls were able to more readily handle stress and fear when under threat and 72% reported to be more able to identify a dangerous situation. / At endline, nearly all trained girls felt their confidence (88%), ability to defend themselves (96%), feel safe (92%), and able to stay away from danger (92%) had improved.
Ubongo / Kenya / Cohort 3	Specific audience sub-groups (e.g. younger or urban girls) increased their knowledge and understanding of earning, saving and budgeting concepts and in some instances, changed their financial behaviour. However, these effects were often not sustained to endline given the short exposure to a singular, 20-minute episode.	43% of treatment girls understood that a budget is a plan for how you want to spend money on things / In assessing wants v needs, 70% of girls correctly identified the four individual needs of food, water, somewhere to live and clothes. / 46% of treatment girls (an increase of 16%) understood that earning money means exchanging skills or products for money. / 78% of treatment girls understood that saving means ‘putting money to one side towards a future goal’. / 64% of treatment girls reported preparing a budget to spend money on things that they needed for a project they were working on.
360Ed / Myanmar / Cohort 3	Reading Bay Kin booklets increased knowledge and understanding related to body privacy, self-defence, puberty, sexual and reproductive health, HIV protection and laws and rights and improved girls’ perceptions of inappropriate actions by an adult. / These changes better equip girls to identify and respond appropriately to risks and threats, improving their safety and wellbeing.	69% of treatment girls reported that they would seek adult assistance regarding a friend’s pregnancy / 62% of treatment girls reported that condoms were the best way to prevent pregnancy and sexually transmitted diseases during sexual intercourse / 73% of treatment girls increased their understanding of emergency contraception / 82% of girls reported an awareness of ART as a treatment for HIV.

## Annex C - Full list of reports planned for this reporting year and key findings