Project Completion Review - post April 2018

Title: Ghana Oil and Gas for Inclusive Growth (GOGIG)
Final Programme Value £ / (full life): 15,415,590	Review Date:	25 November 2020
Programme Code: 204330	Start Date: / 12 March 2014	Final End Date: / 30 September 2020
[note] A full list of abbreviations are provided at the end of the document

Summary of Programme Performance

Year	2014	2015	2016	2017	2018	2019	2020
Programme Score	B	A	A	A+	A+	A	A+
Risk Rating	Medium	Medium	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4269520.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5584543.xlsx

A. Summary and Overview (1-2 pages)

Summary
GOGIG has been a successful and influential programme, securing six times its programme cost in additional government revenue, and facilitating improved governance of the oil and gas sector. GOGIG’s theory of change was validated by events and by the verifiable achievement of outcomes, while the project partners were able to deliver each of the 18 indicators spread across the 6 outputs. Most of the interventions have been sustained; there are some though which will require continued government commitment to be fully sustainable. This was a timely programme, providing relevant improvements to the management of the oil and gas sector shortly after it became operational, and not long before it is likely to reduce in significance as the world transitions towards low carbon energy. The main lesson of the project is that delivering change in a complex sector like oil and gas requires a range of instruments, partnerships and high-quality technical expertise. The initial failure of the programme to go beyond revenue mobilisation and allocation to explore non-revenue pathways (such as through policy work relating to Gas, Local Content, Gender Equity and Local Impacts) to inclusive growth was corrected midway and a new output area was designed. Its successful approach, as well as the partnerships it has generated will be important in future FCDO programming, especially the proposed new revenue management programme.

This PCR was researched and drafted by an expert independent reviewer. The final document has been edited by the SRO for clarity, brevity and to provide further information where needed. However, the assessments of external reviewer are retained, and additional assessments by the FCDO team are labelled.
## Background: Objectives, Approach and Key Partners

The Ghana Oil and Gas for Inclusive Growth programme was primarily aimed at transforming oil and gas resources into accelerated inclusive growth for Ghanaian citizens through complex policy, regulatory and institutional reform interventions. It aimed to support the legal framework and key state institutions involved in the management of the oil and gas sector to ensure they were able to carry out their functions effectively. In parallel, the intervention would promote accountability by building the capacity of civil society and Parliament to monitor and challenge sector performance. The assumption was that this would enable improved revenue, sector efficiency and accountability, and thereby contribute towards increased growth and stability and reduced poverty.

GOGIG was designed to work with State actors (Bank of Ghana (BoG), Ghana Revenue Authority (GRA), Ministry of Energy (MoE), Ministry of Finance and Economic Planning (MoFEP), and the Petroleum Commission (PC)) and non-State actors including the Africa Centre for Energy Policy (ACEP), Natural Resource Governance Institute (NRGI) and Public Interest and Accountability Committee (PIAC)). This group of partners was subsequently broadened to include others such as: Environmental Protection Agency (EPA), Ghana National Petroleum Companyn (GNPC), Ministry of Environment, Science and Technology (MESTI), Parliament of Ghana (notably, the Parliamentary Committee on Mines and Energy), Ministry of Planning, National Development Planning Commission (NDPC), the Ghana Extractive Industries Transparency Initiative (GHEITI), and the Civil Society Platform on Oil and Gas (CVPOG). The programme complemented other DFID programmes, such as the STAR-Ghana governance programme and the Western Region Coastal Foundation (WRCF) initiative, which was a community impact initiative, affecting communities in the offshore enclave of Western Region of Ghana.

A variety of operational support tools were used during GOGIG (technical assistance, grants, capacity building, research, multi-stakeholder dialogue and facilitation). A Steering Committee consisting of the State institutions benefitting from the GOGIG support and the World Bank served as a flexible platform to test ideas and obtain peer insights. This was especially important since GOGIG was implemented during a period of significant political and economic change. GOGIG met this challenge well, underpinned by regular political economy analysis and adaptive programming.

Operating Context
GOGIG commenced in December 2014 with a total budget of £15,415,590 and was due to complete in December 2019. Two No-Cost Extensions were applied to the programme; to 30 June 2020, and then to 30 September 2020 to enable a responsible close-out post-covid, with the completion of some ongoing projects, and the conclusion of the Learning and Dissemination Plan.

The project was implemented in a period of significant political and economic change. These conditions demanded flexibility of response – through timely strategic analysis and adaptive programming. The change of Government in 2016 created challenges. GOGIG not only had to adapt to changes in personnel and personalities that headed key institutions, but to influence and align with the priorities of the new administration to ensure that progress on work initiated under the previous administration could be sustained. An unexpected ministerial change in 2018 also threatened the progress being made by the programme in supporting strategic decisions at the Ministry of Energy, but the programme adapted well to ensure that the momentum was not lost.

Four issues are notable over the operating period:

1. Oil production quadrupled from less than 50,000 barrels per day in 2016 to over 200,000 per day within three years.
2. GDP growth which was below zero when the project began in 2015, peaked at over 10% in 2017, and has averaged above 5% since 2018.
3. The outlook of Ghana’s crude production and contribution of the oil and gas sector to the economy received a major boost with the successful appraisal of the Pecan oil field by Aker Energy with more oil discovered in March 2019.
4. Oil prices which reached a high of $107 during 2014, the year the programme began, had plummeted to $53 by the close of that year. They dropped even further to $34 in 2015 and to $26 in 2016 before beginning to see modest levels of recovery from 2017 – 2019, averaging $50 - $65 during the period. In 2020 they plummeted to a low of just above $11 primarily due to the impact of the COVID pandemic on demand but have now recovered to around $45.
Notwithstanding the relatively low contribution of oil and gas revenues to the GDP (<5%), data suggests that the growth of the petroleum sector had a direct bearing on economic growth generally. Together these economic indicators validated the premises on which GOGIG was established: the need to devise interventions to support institutional reforms that would lead to effective management of oil and gas resources in Ghana if the benefits of this growth were to be shared equitably.
[note] Source: GOGIG Revenue Model (middle case scenario). See Table 5 in L&DP Synthesis Report, ‘Table 5 Historical and Projected Net Public Petroleum Revenues developed by Dr Theo Acheampong and Dr Carole Nakhle. See also Study 7 Understanding the channels through which growth in an extractive sector like Oil and Gas can lead to inclusive development, by Rajan Soni and Prof. Felix Ankomah Asante.
## Theory of Change and Logframe

The Theory of Change was informed by a political economy analysis undertaken during the Inception Phase. It was challenging to articulate a single theory that captured all the detail necessary to explain how the initiatives would support sector governance. As a result, in addition to developing an overall theory for the programme, an ‘outcome mapping’ approach was adopted that de-constructed the theory into individual outputs, using the political economy analysis to focus on the specific pathways to potential change within each area.

Following the discovery of oil and gas offshore in 2007 and subsequent production in late 2010, the Government of Ghana (GoG) passed various pieces of legislation to align the sector with international best practice in terms of industry governance and revenue management. The co-existence of old legislation such as the Petroleum (Exploration and Production (E&P)) Law 1984 alongside new laws created a regulatory regime with institutional overlaps and potential conflicts. The operating context assessed by the DFID Business Case identified three broad issues affecting oil and gas sector governance. These were incoherent sector policy, weaknesses in the legislative and institutional framework and constraints on effective sector regulation and oversight. Despite the potential for significant revenue inflows expected from the sector, the institutional systems and arrangements for revenue capture and oversight were largely ineffective and would not ensure effective revenue capture.

These challenges were expected to be addressed through the provision of:
- Technical assistance to relevant institutions;
- Technical inputs through submission of policy briefs, analyses and opinions on policy instruments such as legislation, policy plans, and implementation strategies to anchor sector operations;
- Targetted capacity building to strengthen technical and operational regulatory functionality;
- Provision of technical tools and operational systems to enhance delivery of regulatory functions;
- Accountable grants to accountability actors to strengthen their oversight of the sector.

Following the Mid Term Review (2017) the theory of change was revised to articulate the “non-revenue pathways by which the oil and gas sector contributes to inclusive growth”. This informed the introduction of an Output (5) in the logframe which emphasised four areas of focus: Gas, Local Content, Gender Equity and Local Impacts.

The expected Outcome of GOGIG was "Effective management of oil and gas resources in Ghana", with the Impact of "Inclusive economic growth and poverty reduction through a well-managed oil and gas sector". The Outcome and the Impact remained unchanged during the programme.

The logframe constantly evolved throughout the programme, especially after each annual review. The programme had adopted an adaptive approach to delivery, and therefore it was expected that activities and the indicators for monitoring progress would change from year to year, while the overall objective remained the same.

Each of Outputs 1-3 had an indicator that measured progress in developing the capability of the supported State institutions and since the targets had been accomplished by end 2018, the emphasis on capacity building was reduced. Late in the programme (2019) a new indicator was introduced into Output 1 to track how the allocation of concession blocks was being handled and the monitoring of the same by civil society. Also, in 2019, an indicator was introduced into Output 3 to assess progress on the overall management of the Annual Budget Funding Amount (ABFA) component of petroleum revenue.

An overview of logframe changes is provided in Annex 1.

An overview of all results accomplished for each Output is provided in Annex 2.

Key Achievements

Overall, GOGIG has been a successful programme. It achieved the desired outcomes of improved governance, higher revenue capture and strengthened institutional capacity. It consistently achieved its outputs in each project year. Some of the headline results include the following:

- The quality of governance in the oil and gas industry in Ghana has improved overall as reflected in improved scores in the Resource Governance Index;
  [note] The published score by NRGI in 20 was and assessments of baseline in 2014 and 2019 carried out with the same methodology and consultants by GOGIG
- The Petroleum Unit and Transfer Pricing Unit of GRA has contributed to an increase in revenue capture of over £230 million (GHc 1749.9 million) - out of which £90m could be attributed to GOGIG - this is six times higher than the programme cost; and which has been channelled to priority sectors for enabling inclusive growth.
  [note] ‘Revenue capture’ is defined as estimated revenue identified for Government or losses prevented through a range of GOGIG initiatives. This is a term used by GRA itself to describe revenue confirmed as being due. It stops short of collection as that is impacted by factors beyond the control of both GRA and GOGIG.
- A clearly articulated Government vision for the sector and how it contributes to national development;
Strengthened legal and policy framework for the sector with the passage of the Exploration & Production (E&P) Act; development of the Energy Policy; the Oil and Gas Environmental Management Policy; and the Health, Safety, Security and Environment (HSSE) policy;
- Strengthened capacity of key institutions working in the upstream oil and gas sector – Ministry of Energy, Petroleum Commission, GRA Petroleum Unit;
- Improved management of the Annual Budget Funding Amount (ABFA) that funds projects in priority sectors including Education, Healthcare, Roads, Agriculture;
- Creation of the Ghana National Infrastructure and Investment Database for the National Development Planning Commission (NDPC);
- Strengthening the Public Interest and Accountability Committee’s (PIAC’s) institutional capacity to play an effective oversight role;
- Civil society is better equipped to enhance accountability and transparency in the sector.

1.4	Summary of performance

GOGIG aimed to achieve three key outcomes: improving regulation and oil and gas governance; ensuring additional oil and gas revenue capture and management; and enhancing the capacity of a number of state and non-State actors in the management of the oil and gas industry. All the three outcome targets were achieved.
At the Output level the programme worked towards achieving a total of eighteen different output indicators, of which ten exceeded their target and eight achieved target. Out of the twelve output indicators in the logframe for the final year, the end of programme targets was exceeded for seven indicators and achieved for remaining five.

Overall, three out of the six target output were rated as A+, while the remaining three attained an A rating, despite delays in starting the implementation of the programme.

Outcome Level Performance
	Baseline	End of Programme target	Performance against target
Quality of regulation and governance as evidenced by Resource Governance Index (RGI) Score for the oil and gas Sector	64 / (2014)	5% improvement over baseline score of 64	Score of 83 in 2019, representing 29% improvement over the baseline
Value of additional oil revenues captured and losses averted	N/A	5% of additional revenue captured (this in 2019 stood at £37,783,378.83 (US$48,854,664.5)	6.2% of additional revenue captured, equivalent to / £90,631,708.47 (US$117,188,611.69)
Number of state institutions' actions positively influenced pertaining to management of oil and gas resources.	N/A	17	21

Summary of performance against total output indicators over the programme period
Output Description	Indicator / Weighting	Performance	Average Score
Regulatory mandate and policy coherence in the oil and gas sector enhanced: 5 indicators	20%	2 exceeded / 3 achieved	A+
Oil and gas revenue capture and oversight improved: 3 indicators	20%	All 3 exceeded	A+
Oil and gas revenue management and oversight improved: / 3 indicators	20%	1 exceeded / 2 achieved	A
Enhanced public engagement through, but not limited to, increased accountability actors' capability for oversight of the oil and gas sector: 3 indicators	15%	2 exceeded / 1 achieved	A+
Non-revenue pathways by which the oil and gas sector can contribute to inclusive growth identified and enhanced: / 2 indicators	15%	Both targets exceeded (marginally)	A
Documentation and dissemination of programme learning / 2 indicators	10%	Both targets achieved	A

Source: GOGIG project team, validated through external review

Way Forward
The recent decision by the UK to end support to fossil fuels overseas will certainly limit UK assistance to the extractives sector in general. GOGIG, however, was designed not to support the Oil & Gas industry; its primary objective was to improve governance in the sector and improve revenue mobilisation which could then facilitate inclusive growth. FCDO is not considering a successor programme to GOGIG; however, it will be prudent to use GOGIG’s engagement as a springboard to support GoG to plan for a transition towards a low carbon pathway. And as we enter a new business planning phase, HMG will decide on the extent of our engagement to ensure that Ghana’s revenue, including from oil & gas, are managed effectively. This is critical for helping Ghana to move beyond aid.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

The narrative below has been summarised from the GOGIG PMT PCR (reviewed and validated)

Output Title	Regulatory mandate and policy coherence in the oil and gas sector enhanced
Output number per L.F.		1	Average Output Score	A+
Average Impact weighting (%)?		20%	Impact weighting % revised since last A.R.?	↑(2017); ↓(2018 & 2019)

Indicator(s)	Target	Achievement
Number of actions taken to tackle policy, regulatory gaps, conflicts and overlaps in mandates	2	3 / Achieved
Improving capability of the Petroleum Commission Geoscience Unit	3.0	3.9 / Achieved
Steps taken to advance implementation of Health, Safety, Security and Environmental Policy	HSSE policy and implementation strategy developed	Achieved in 2018
Number of initiatives to advance delivery of institutional mandates / (Initial target was 23 but this was adjusted to 26 in 2018)	26	26 / Achieved
Progress towards strengthening the Government petroleum block allocation process and civil society monitoring of the process / (This was a new indicator added in 2019)	2 actions	3 actions / Achieved
[note] The capability rating is a quantitative measure of changes in key capacity building priority areas with government partners. The actual scores reflect self-assessment ratings provided by the respective government institutions using a simple rating scale of 1-7, with 1 being the lowest and 7 being the highest.

Tackling policy, regulatory gaps, conflicts and overlaps in mandates achieved

With GOGIG support, gaps and overlaps in oil and gas sector governance were identified and validated by the Ministry of Petroleum. GOGIG assisted the Ministry of Energy to complete the Energy Sector policy. The new policy harmonises all previous policy documents and critically defines the petroleum sector as comprising an ‘upstream’ and ‘downstream’ segment. This distinction resolves the outstanding question regarding the overlapping mandates between the Petroleum Commission, National Petroleum Authority and the Energy Commission relating to the previously supposed ‘midstream’ segment of the gas sector. It also supported the Petroleum Commission (PC) to complete a strategy paper on addressing overlapping regulatory functions. It analysed the Exploration and Production (E&P) law to identify consistency with other legislation and existing petroleum agreements.

Improving capability of the Petroleum Commission Geoscience Unit

GOGIG provided on-site training and a mentoring programme via a expert consultant embedded in the Geoscience Unit for a period of one year. This was to improve the Commission’s capacity to perform the core function of efficiently managing petroleum resources. This capacity building was complemented by the provision of industry reference software by GOGIG (the ‘Petrel and Landmark suite’).

Health, Safety, Security and Environmental (HSSE) Policy

GOGIG provided technical and logistic assistance for the development of a HSSE policy framework, and its translation into an HSSE Manual for operators in the sector. It also supported its practical implementation through the rolling out of initiatives on incident management, standards and procedures, and leadership and management competency development to enhance HSSE in the sector.

Initiatives to advance delivery of institutional mandates

GOGIG supported a range of initiatives for strengthening the mandate of key institutions in the sector. Some of the key initiatives included the following:
- It worked with state and non-state actors to help shape the overarching oil and gas sector law, the Petroleum Exploration and Production Act 919 and its subsidiary Regulations, through technical inputs to Parliament and subsequent advocacy for their timely passage.
- GOGIG provided technical assistance to lead discussions and draft the text of subsidiary regulations including: Petroleum (Exploration and Production) (Data Management) Regulations 2017; the Petroleum (Exploration and Production) (Health, Safety and Environment) Regulations 2017; and the Petroleum (Exploration and Production) (General) Regulations 2018 introduced by the Ministry.
- It provided technical assistance to formulate a document setting out the principles on disclosure and procedures for obtaining information that GNPC would make available to the public routinely or upon request.
- It gave technical input on the strategy “blueprint” for Accelerating Oil and Gas Exploration and Development, which is the medium-term plan for attracting investment into the sector.
- It collaborated with the Norad Oil for Development Programme to provide the framework for managing both the environmental and social implications flowing from oil and gas extraction activities.
- It provided advice and support to MoE on implementing the ruling from the International Tribunal of the Law of the Sea (ITLOS) on the border dispute between Ghana and Cote D’Ivoire. TA further advised on dealing with concerns raised by Togo on the maritime border with Ghana.
- It provided targeted policy briefs such as hub-based development of marginal fields as part of the overarching strategy for oil and gas resource extraction and rationalising the institutional framework to operationalise the Gas Master Plan.
- GOGIG provided technical assistance to support the Ministry with drafting the Gas Act.
- The programme supported the drafting of regulations on mandatory fisheries impact assessment to be considered by the Fisheries Commission in revising the Fisheries Act; and a Manual of Operator Costs has been developed as reference material for the Ministry and PC to enable benchmarking against other petroleum producer countries.
- The programme supported the design of the Ghana Upstream Students Internship Programme (GUSIP) to train graduates and technicians to acquire practical skills and competence required for the oil and gas sector.

Strengthening the Government petroleum block allocation process

The programme helped the Ministry of Energy access expert analysis and inputs on the bid assessment framework and on the invitation to tender documentation and bid evaluation criteria. This support also enabled MoE to establish new fiscal thresholds as part of the bidding round. It also provided support to CSOs to review the bidding process, compare with international best practice and provide recommendations to government.

Evidence, output quality and sustainability

Output quality is assessed by FCDO as good, based on the evidence of tangible changes in policy and regulations and by strengthening key policy and regulatory institutions. Of the thirteen substantive policy submissions made to the Government between 2017 and 2019, the Government adopted and implemented recommendations from eleven, representing an 85% adoption rate. Impacts are assessed as generally sustainable because these have resulted in changes in the legal framework for the sector and made institutions stronger. However, the government needs to continue to maintain its commitment on policy coherence and institutional support. Out of 15 projects under this output, 8 are already sustainable, 4 projects require continued government support – 3 projects may not be sustained.

Key Lessons Learned

Flexible and adaptive programming can enable programmes like GOGIG to adapt to institutional changes. GOGIG made relevant programme-wide changes to ensure that its objective of working with state partners was met;

Reducing the trust deficit between state actors and civil society organisations and the creation of platforms for engagement between them went a long way in helping shape a progressive legal and regulatory framework; and

GOGIG programme served as important platform to remove a silos approach to working and provided the platform for institutions to collaborate.

Recommendations for future programmes (or other engagements in this sector)

Whilst the original DFID Business Case assumption underpinning Output 1 objectives, that improved policy coherence and mandate clarity would lead to better sector management, remains valid, future enforcement, which often requires political interest and motivation, will require oversight by strong non-state actors;

The approach adopted by GOGIG was more comprehensive than many other reform programmes because it combined policy, legal, regulatory and institutional reforms. This approach, although more resource and time intensive, is considered value for money as without it, it is unlikely that the outputs would have been as effective;

Any future programming should be more aware of how oil and gas sectors typically work and plan into business case development more realistic expectations about how vested interests may threaten institutional reform. A Political Economy Analysis is essential in conceptualisation and effective execution; and

GOGIG was designed by UK officials, in consultation with Ghanaian partners. However, consultations leading up to the development of future programme should be broader, and engage Government partners earlier to ensure ownership amongst stakeholders and a more accurate assessment of issues and opportunites from an early stage.

Output Title	Oil and gas revenue capture and oversight improved
Output number per L.F.		2	Average Output Score	A+
Average Impact weighting (%)?		20%	Impact weighting % revised since last A.R.?	Y↓ (2019)

Indicator(s)	Target	Achievement
Number of initiatives delivered to identify and improve revenue capture	19	23 / Achieved
Number of initiatives implemented to support inter/intra agency coordination to avert and retrieve potential revenue losses	5	6 / Achieved
Improving the capability of the Petroleum Unit, Ghana Revenue Authority	3.7	4.38 / Achieved
[note] Methodology mentioned under output 1

Identifying and improving revenue capture

This indicator was fully met. Some of the key initiatives undertaken include the following:

- GOGIG provided initial support to address legislative gaps, specifically developing the regulations for the new Income Tax Law (2015) which replaced the Petroleum Income Tax Law and addressed issues such as ring fencing of costs and inappropriate capitalisation.
- A comprehensive diagnostic study of potential revenue losses along the oil and gas value chain was undertaken in 2017. It identified potential revenue losses of up to £473m (US$612m), £99m (US$128m) in corporate income tax, £373m (US$483m) in Additional Oil Entitlement, and £773,000 (US$1m) in surface rentals fees. These findings were summarised in policy briefs and presented to Deputy Commissioner of Large Tax Payers Office and Heads of Petroleum, Transfer Pricing and Customs Unit and ministers.
- The programme supported the development of petroleum audit practice notes to provide guidance on calculations of licence fees and surface rental, deduction of income from disposable petroleum rights, appropriate capitalisation, and additional oil entitlement, and capital allowance, chargeable income of a unitised field, parent company cost, hedging, and various other provisions in other legislation.
- GOGIG commissioned a modelling of projected revenue from the Jubilee and Sankofa fields based on production levels/plans and the terms of the relevant petroleum agreements to provide a reference for the Petroleum Unit in estimating potential tax revenue from the operators. The team was trained on how to use the model to revise revenue projections as the assumptions and relevant variables changed.
- GOGIG procured the IDEA electronic audit tool from KPMG for the Petroleum Unit and arranged for additional hands-on training and support to enhance the use of the software for auditing. The software and the training provided together led to a progressive improvement in audit performance. According to GRA, the training helped to reduce the length of time spent on auditing international oil companies from six to two months as well as helped detect several outstanding tax revenues in 2018 and 2019 audits.
- GOGIG supported PIAC as an accountability actor to produce its semi-annual and annual reports from 2015 to 2019, which regularly highlighted the issue of unpaid petroleum revenues (including surface rents, corporate income tax and royalty payments) by defaulting companies. The programme further supported PIAC to do media advocacy on these unpaid revenues. In 2018, the Ministry of Finance acknowledged PIAC’s role for using these mechanisms to reinforce the commitment of upstream operators to pay outstanding surface rental fees owed. GOGIG also supported GHEITI and PIAC to use media channels to raise public awareness and demand further investigation to explain why the sale of the Ghana share of crude oil from the TEN field has been at a lower price than the share sold by the operator. Estimates from the MoF had put the value lost from the crude oil sales to be around £6.9m (US$9m).

Support inter/intra agency coordination to avert and retrieve potential revenue losses

This indicator was also fully met. The programme engineered a coordinated institutional approach to tackle some of the critical issues identified in revenue administration by enabling the establishment of the Multi-Agency Petroleum Revenue Committee to coordinate Government efforts to pursue revenues identified. The main issue the Committee pursued was assessing the windfall Additional Oil Entitlement (AOE) tax. Subsequent GOGIG-supported regular technical meetings of the Committee culminated in the issuance of tax assessments to oil companies for £77.3m (US$100m) as the AOE amount due.

This inter-agency technical collaboration on cost audits between the Petroleum Commission, the Ghana National Petroleum Corporation and the Ghana Revenue Authority enabled a coordinated State approach in addressing outstanding and problematic issues arising from regular audits of upstream companies to ensure speedy resolution and revenue collection.

Improving the capacity of the Petroleum Unit and GRA

GOGIG rolled out a range of generic and specific technical training to enhance the knowledge and competence of the Petroleum Unit team. This considerably increased the GRA audit abilities to review larger number of financial statements and financial transactions to ascertain whether the correct amounts of tax liabilities had been declared by the companies. It supported development of an audit manual of standard operational procedures for conducting routine and specialised audits by the Petroleum Unit. It has also enhanced capacity to handle a range of risk identification criteria including; effective tax rates; organisational structure of multinationals; related party transactions; debt financing and intra-group loans; use of low-tax jurisdictions and treaty shopping; management and service fees; hedging and derivatives; transfer pricing issues; and history of tax losses and tax paid. About 10 staff at the Petroleum Unit benefited from this training and enabled GRA to make an early recovery of an additional £17m (US$22m) in unpaid corporate income tax and interest payments in 2017.

Evidence, output quality and sustainability

Output quality is assessed by FCDO as good, based on the evidence of the various initiatives undertaken to enhance revenue capture as well as the institutional strengthening of the GRA petroleum unit. Impacts are assessed as generally sustainable because the government has adopted processes and systems to ensure that future revenue streams are also realised; however, it needs to continue to ensure inter-agency collaboration so that all relevant agencies coordinate effectively. Out of 12 projects under this output, 9 are already sustainable or purpose has been achieved, 2 projects require continued government support – 1 project may not be sustained.

Key Lessons Learned

A specific lessons learned study commissioned by GOGIG on Output 2 produced the following lessons:

Governments can be slow in taking critical actions for the benefits of their citizens. The role and involvement of accountability actors given their public mandate is critical in this regard to get the public to put pressure for action. This was evident in the way the government was forced to demand recovery of additional oil entitlement revenue from companies;

Evidence suggests that long term nature of GOGIG’s institutional capacity building is beneficial. The impact of capacity building in improving revenue capture has been the result of cumulative capacity-building initiatives implemented over the life cycle of the programme. This underscores the need for continual training and mentoring to increase the chances of the gains being sustained;

Inter-agency collaboration has been a challenging but vital part of resolving issues and enhancing government effectiveness. For instance, during the computation of additional oil entitlement, Petroleum Commission, GRA and GNPC came together and managed to resolve the methodological difference in the computation of otherwise important source of revenue to Government; and

The mode of delivery of training is critical in delivering the necessary outcome. In the view of some of the beneficiary institutions the training programme was successful because they used Ghanaian expertise and ensured that the expert was embedded in their institution for a reasonable length of time. This provided learners the opportunity to learn by doing while getting continuous guidance.

Recommendations for future programmes

The reliance on indigenous Ghanaian expertise for capacity building programmes and the adoption of mass-training programme approach under this output proved to be effective and should be adopted in similar programmes;

The inter-agency platform established by GOGIG under this output that allowed revenue capture institutions, the national oil company and the regulatory institutions to pull resources and expertise together should be given due consideration under future similar programmes; and

Continual training and mentoring should be central to future support in this area since this proved to be effective in ensuring that the gains recorded were sustained.

Output Title	Oil and gas revenue management and oversight improved
Output number per L.F.		3	Average Output Score	A
Average Impact weighting (%)?		20%	Impact weighting % revised since last A.R.?	Y↓(2017 only)

Indicator(s)	Target	Achievement
Number of initiatives that identify and improve planning, allocation, utilisation, investment and reporting of petroleum revenue	23	27 / Achieved
Number of initiatives that improve monitoring and learning on projects funded with Annual Budget Funding Amount (ABFA)	7	7 / Achieved
Capability of the Energy, Oil and Gas Unit at Ministry of Finance in revenue management and Petroleum Secretariat at Bank of Ghana enhanced	5.6	5.6 / Achieved
[note] Methodology mentioned under output 1

Improve planning, allocation, utilisation, investment and reporting of petroleum revenue

The target was fully met, with 27 initiatives being undertaken. Some of the most important initiatives include the following:

- GOGIG supported the MoFEP to complete revisions to the Petroleum Revenue Management Act (PMRA) in 2015 and the drafting of regulations for this Act. In 2019, another review of the Act was also supported by GOGIG;
- The programme supported improvements in petroleum forecasting through training using the IMF Fiscal Analysis of Resources Industries model to improve precision of petroleum revenue projections for budget preparation;
- With funding and technical inputs from GOGIG, an ABFA investment guide was developed by the Ministry of Planning for MoF and other government ministries, departments and agencies to streamline budgeting and implementation of ABFA-funded projects;
- GOGIG provided support to complement efforts to revive the Investment Advisory Committee to function as set out in the PMRA, through the provision of technical experts. This enabled a review the existing management arrangement for fund investment and assessment of the investment portfolio. The experts also helped develop proposals on alternative models for managing the Sovereign Wealth Fund and building a website to enhance transparency around the performance of the funds;
- GOGIG also enhanced the systems being used by BoG and MoFEP to facilitate fiscal oversight and investment decisions. For BoG, GOGIG procured and installed Bloomberg software to localise real-time investment of petroleum revenues, which until then was being done on their behalf by Bloomberg in New York;
- The programme facilitated the inclusion of civil society in the deliberation processes for the review of PRMA in 2015 and 2019. The programme consistently supported PIAC to produce its reports on petroleum revenue management. These reports revealed shortfalls in petroleum revenue management and increasingly served as a resource to create awareness on and inform public discourse on the accountable use of petroleum revenues. For example, it highlighted the need for Government to account for GHc400m of unspent ABFA revenue that was not accounted for in the Government’s 2017 Reconciliation Report;
- Similarly, the programme provided emergency support to produce the GHEITI 2015 and 2016 audit reports to enable Ghana to fulfil this global transparency requirement and avoid suspension from the global Extractives Industry Transparency Initiative;
- GOGIG provided financial and technical support to the National Development Planning Commission to develop a one-stop database of all infrastructure projects. GOGIG support focused on uploading information on ABFA-funded projects on the database to allow for an analysis of key trends and performance.

Monitoring of ABFA-funded projects

The target was fully met. The programme supported the monitoring of ABFA funded projects in irrigation, free senior high school, rural electrification and roads with the objective to identify measures to improve future investment. In 2019, out of the total ABFA amount, 46% were spent on roads, 45% on education, 6% on agriculture and 4% on health. Both PIAC and MoF embarked on separate monitoring exercises, with the GOGIG team aiding both partners to improve monitoring methodologies, tools and learning. These led to compilation and submission of policy recommendations to Government for an ABFA Investment Guide, Public Investment Plan and mainstream ABFA projects in district plans. The programme also supported ACEP to undertake a Value For Money (VFM) analysis of a sample of ABFA projects and to share the findings and lessons at the 2019 budget hearing. With GOGIG support, for the first time, the MoF prepared and published the list of ABFA projects as part of the 2019 budget. A resource application framework was also developed with the MoF Budget team for rational allocation of ABFA funds. The fact that now PIAC is being supported through budgetary funds and its remit might be extended to the entire extractives sector through the proposed Natural Resource Governance (NRG) Bill augurs well for transparency and accountability in the sector.
[note] PIAC 2019 Annual Report

Technical Capacity Building for Ministry of Finance and the Bank of Ghana

An initial needs assessment jointly conducted with MoF and BoG revealed the need for improved technical knowledge and competencies relating to their core functions in petroleum revenue investment and management respectively. GOGIG supported the team at the Petroleum Funds Secretariat to undertake training focused on enhancing the capabilities of the staff in Sovereign Wealth Funds investment, risk management and financial market analysis. Capacity building for MoF focused on enhancing the capability of the staff of the Energy, Oil and Gas Unit on financial analysis and modelling, petroleum economics and fiscal regimes, oil and gas sector industry knowledge, liquefied natural gas and oil and gas risk management. In addition, practical training on contract negotiations, which involved both the MoF and BoG as well as other key institutions was offered to improve contract negotiations and value realisation.

Evidence, output quality and sustainability

Output quality is assessed by FCDO as good, based on the evidence of improved forecasting, allocation of petroleum revenue, monitoring and reporting of ABFA funds and improved institutional capacity. Impacts are assessed as generally sustainable because of the improved processes and systems to manage petroleum revenue. PIAC has been allocated direct budgetary funds to continue its work and under the new Natural Resource Governance Bill, its mandate will expand to cover the entire extractive sector. However, government commitment to adhere to improved transparency and accountability standards will be critical. Out of 10 projects under this output, 4 are already sustainable and 6 projects require continued government support to be sustainable.

Key Lessons Learned

A learning study commissioned by GOGIG on Output 3 highlighted the following lessons and innovations:

The use of two-prong approach of working with both Government and non-state accountability actors worked well. When there was resistance to reforms from the Government, the programme activated accountability actors to create demand for reforms or generate empirical evidence in favour of reforms;

Creating a platform to bring accountability actors together to work with Government on key oil and gas policy and regulatory reforms has eased the tension which had previously characterised the dialogue between government and civil society. However, there is some risk that the accountability actors could become too comfortable if care is not taken, and may not be effective in carrying out their mandate are required;

By keeping its engagement with state institutions and accountability actors distinct and separate, GOGIG was able to take forward its work at both ends effectively. It also helped the programme to avoid any unnecessary problems that could have resulted in possible confrontation between the two sides; and

The continual use of political economy analysis to adapt the programme to changes in the political and economic context was very critical. This included a specific PEA to understand the political dynamics which drive decisions on resource allocations to inform strategizing how to make further progress in addressing challenges in petroleum revenue management.

Recommendations for future programmes

The neutral convening platform created by GOGIG to bring accountability actors together to work with Government on key oil and gas policy and regulatory reforms could also be an effective tool for future programmes as it eased the tension which had otherwise characterised the dialogue;

For the sustainability of different interventions, future programmes should choose the institutional home carefully. For instance, problems could have been avoided if NDPC had hosted the infrastructure database from the beginning instead of Ministry of Planning which could have a sustainability problem in the advent of change in administration or reshuffling of Cabinet; and

The pursuit of strategic engagement at the highest level, and the continual use of PEA to adapt to changes in the political and economic context, the shifting needs of partners and learning from implementation, should be given the most attention in similar, future programmes.

Output Title	Enhanced public engagement and oversight of the oil and gas sector
Output number per L.F.		4	Average Output Score	A+
Average Impact weighting (%)?		15%	Impact weighting % revised since last A.R.?	Y↓(2019)

Indicator(s)	Target	Achievement
Number of initiatives that promote inclusion of citizens' inputs in sector policies and demand for transparency and accountability in oil and gas issues	28	29 / Achieved
Number of joint government-accountability actors' engagement facilitated by GOGIG on key sector issues	16	16 / Achieved
Number of changes that demonstrate increased technical and leadership competencies, and organizational development of selected accountability actors	25	27 / Achieved

Inclusion of citizens' inputs in sector policies and demand for transparency and accountability

The output has been fully met. The programme supported a range of initiatives to promote inclusion of citizens inputs in sector policies. Some of key initiatives undertaken include the following:

- Public forums were held during the 2016 election period by ACEP to consolidate a citizens’ energy manifesto in 2016;
- Live radio discussion sessions were organized by ACEP to rally citizens support and inputs for beneficiary ownership, open contracting and competitive bidding provisions in E&P Act;
- ouroilmoney.com – an online platform was created by ACEP’s to promote citizen-led accountability on petroleum revenue utilization and management;
- From 2016 to 2019, PIAC has held regional and district level forums to educate and elicit citizens’ inputs on petroleum revenue management;
- The programme supported MoE to host four forums (in Accra, Kumasi, Takoradi and Tamale) on engagement with citizens and civil society on future energy sector policy;
- GOGIG supported Ghana EITI to host local radio discussions in three regions to improve public understanding of the importance of Beneficial Ownership Disclosure in extractives sectors;
- The programme worked with PenPlusBytes (a civil society partner) and selected media houses and journalists to raise public awareness on issues like the ExxonMobil Contract, natural gas production, and the 2018 Budget provisions for petroleum sector;
- It supported Ghana EITI to improve citizens’ awareness on Ghana’s crude oil sales and associated risks through citizen’s engagement on its commodity trading transparency report;
- Consultations were organised with frontline oil communities on the PC’s draft social performance guidelines;
- Public presentation and workshop were organised on the analysis of GNPC expenditure and ACEP was supported to engage with Parliament on scrutiny of GNPC’s budget;
- Worked with IMANI Foundation to share research findings on the impact of upstream contracts on end-user electricity tariffs;
- Events were organised for dissemination of Ghana EITI report on oil and gas and mining in Tamale, Kumasi, Sunyani, New Abirem and Tarkwa; and
- Community level training in Western Region to enable ABFA beneficiary communities to access information on projects in their area.

Enabling engagement between government and accountability actors

GOGIG created platforms to enhance Government and accountability actors’ engagements where critical inputs from the latter were appreciated and considered by Government partners. The approach to delivery of this indicator was unique in the sense that it built preparatory activities which led to effective contributions from accountability partners. For instance, accountability actors’ engagements with the Ministry of Energy on the General Petroleum Regulations was highly appreciated by the Government as key inputs from accountability actors positively influenced Government decisions. Similarly, the requirement of Beneficial Ownership Disclosure at the beginning of the competitive bidding process was accepted and codified in the General Petroleum Regulations.

In addition, the programme supported ACEP to establish the Oil Governance Summit as an annual platform for civil society, Government and industry stakeholders from Ghana and other parts of Africa to converge and deliberate on topical industry issues. This initiative has also promoted constructive discourse and reduced scope for adversarial interaction between Government and civil society. Other examples of GOGIG facilitation include convening the first policy engagement forum between the MoE and CSOs and the maiden dialogue between civil society and the Petroleum Commission to discuss the need for circumspection by CSOs in their bid to empower communities to demand their rights to avoid inadvertently promoting conflict.

The programme facilitated CSOs engagement with the Budget Office of the MoF on the proposed Fiscal Responsibility Law (FRL). It also promoted CSOs discussions with the Registrar General to advocate for a provision on an open BOD register in the new Companies Bill. It supported PIAC’s engagement with government agencies including PC, GRA, GNPC, BoG and MoF to interrogate findings and recommendations from its Annual Reports. A positive outcome of this engagement was the Minister of Finance writing to GNPC to query its crude oil pricing.

Strengthening technical and institutional capabilities of Accountability Actors

This output was also fully met. GOGIG provided institutional strengthening interventions to PIAC and ACEP to enhance their technical capacity, institutional capabilities, and networks to constructively engage with government and citizens. ACEP, with support from other CSO actors, made critical inputs to Petroleum (Exploration and Production Act, 2016, (Act 919)), General Petroleum Regulations, National Energy Policy, and other policies that improved upstream regulation and how the Government conducted business in the upstream sector. GOGIG support enabled PIAC to develop its Strategic Plan and human resource and finance manuals, along with the establishment of a fully staffed and functioning secretariat. GOGIG’s capacity-building interventions and CSO engagements has increased the number of CSOs engaging in oil and gas issues. CSOs, including IMANI Africa and the Institute for Fiscal Studies (IFS), have now created oil and gas desks.

GOGIG designed a targeted technical, leadership capacity building programme for mid-level staff and organisational development training for senior staff of GOGIG accountability partners. Although this was aimed at improving the overall capabilities of partners, GOGIG ensured the next cohort of CSOs/oversight leaders were better prepared to lead and sustain oversight on the oil and gas sector.

Evidence, output quality and sustainability

Output quality is assessed by FCDO as good, based on the evidence of tangible improvement in the technical and institutional capacity of civil society organisations to sustain oversight on the sector and hold the government to account. There is stronger and better engagement between CSOs and the government in policy areas through newly developed institutional mechanisms. These impacts are likely to be sustained; however, going forward the government should continue to engage with CSOs in a constructive manner. Out of 12 projects under this output, 8 are already sustainable, 3 projects require continued government support – 1 project may not be sustained.

Key Lessons Learned

Activities and results under this output confirm the important assumptions around the theory of change pertaining to the role of accountability actors in the oil and gas sector. The programme support to CSOs made them credible partners and encouraged Government to see their relevance and the need to expand the frontier of consultation. This led to an evolving new culture of stakeholder consultation between civil society and Government;

Creating a platform to bring accountability actors together to work with Government on key oil and gas policy and regulatory reforms eased the tension which has otherwise characterised the dialogue among these two parties. The approach to delivery of this key output in the programme was unique as the contribution from the accountability actors positively influenced Government decisions;

Building the capacity of PIAC has enhanced their public image and credibility as key public institution to act to ensure effective management of petroleum revenues. Now consideration is being given to PIAC to expand its mandate to cover the entire extractive industry through the new Natural Resource Governance Bill; and

The strong advocacy and dialogue, including the use of the media, were key in bringing about the amendment of the PRMA (Act 815) to guarantee secure funding for the activities of PIAC.

Recommendations for future programmes

Given that Ghana is moving towards onshore exploration and production, future programmes may consider working with a wider set of accountability actors and community groups in order to mitigate risks related to land use and environmental issues.

To further enhance transparency and accountability of oil and gas regulatory and policy frameworks, the capacity of the accountability actors, including PIAC, ACEP and CSO platforms should be further enhanced

The Programme Steering Committee arrangement did not create space for representation of the CSOs groups and accountability actors. A separate arrangement was instituted to allow for information sharing between the SC and the CSO groups. Future programmes may explore ways to minimise the transaction costs involved in engaging CSOs within the programme framework.

Output Title	Non-revenue pathways of the oil and gas sector to inclusive growth enhanced
Output number per LF		5	Average Output Score	A
Average Impact weighting (%)?		15%	Impact weighting % revised since last AR?	Y↓ (2019)

Indicator(s)	Target	Achievement
Number of initiatives that promote government and public understanding and delivery of non-revenue pathways of the oil and gas sector to inclusive growth.	7	8 / Achieved
Progress towards improving local impact management	5 actions	6 actions / Achieved

Initiatives that promote government and public understanding of non-revenue pathways to inclusive growth

This output was fully met. Some of the key initiatives undertaken in this regard were:

- In the absence of publicly available data, GOGIG commissioned two gender-focused analyses and one research study to generate evidence that would facilitate better understanding of the gender gaps relating to women’s participation in the sector. They were a “Mapping of gender representation in leadership roles in the oil and gas industry of Ghana” and “Gender Review of the Local Content Regulations” to assess gender gaps in implementation for consideration in the revision of the regulations, and a study on “Gender diversity of the upstream oil and gas sector of Ghana” to generate baseline data on women’s representation in the workforce. A gender review of the local content law by GOGIG was also finalised and submitted to the Petroleum Commission;
- GOGIG supported partners ACEP and Ghana Oil and Gas Service Provider Association (GOGSPA) to assess the implementation of the local content law from both an operational and policy standpoint to ensure that proposals offered to amend the law were grounded in a balanced perspective of local content challenges. The reviews highlighted among others, the low levels of women-owned business’ participation in oil and gas value chain. Key recommendations proposed to the Petroleum Commission were to define more clearly the distinction between a ‘Ghanaian registered’ entity and a fully ‘indigenous” Ghanaian company; and to promote the inclusion of women-owned business in decision-making processes and their access to local content opportunities;
- GOGIG set up a `Women in Energy’ platform consisting of women professionals in the sector to advance the leadership of women and participation in the energy sector in Ghana. After a period of planning and preparatory activities, the platform was successfully launched in February 2020 with a strong show of support from high profile stakeholders. The platform is legally registered and has a high-powered and motivated board comprising six prominent leaders from the sector; and
- The programme promoted awareness of the linkages between oil and gas revenues and economic growth to frame deliberations at the 2017 Energy Summit and to emphasise the strategic potential of gas within the industrialisation agenda of the new administration.

Improving local impact management

This output was fully met.

- GOGIG supported the Petroleum Commission with technical support to develop guidelines for stakeholders in the design, implementation, monitoring, evaluation and reporting of social performance for the upstream petroleum industry. The principles and operating procedures covered in the guidelines included the need for prior stakeholder engagement with host communities of oil and gas operations, community and social development and grievance management.
- A local impact management framework was produced by GOGIG for the Ministry of Energy and the Ghana National Petroleum Corporation. It categorised necessary preparations at different phases of onshore petroleum operations, guidelines for how risks and impacts to communities onshore should be proactively managed, and roles and responsibilities of different state institutions.
- GOGIG supported the Environmental Protection Agency (EPA) to adapt the existing offshore Strategic Environmental Assessment (SEA) and for the Ministry of Energy to take a greater role in the coordination of the SEA process. This was complemented by a `sensitivity atlas’ within portions of the Voltaian basin to guide policy makers in the oil block allocation process.

Evidence, output quality and sustainability

Output quality is assessed by FCDO as good, based on the evidence of progress made to mainstream non-revenue aspects in the sector such as local content, gender, local impacts. The impacts are however less likely to be sustained given that these initiatives are relatively recent in the programme lifecycle and key insitutions may lack capacity to take them forward. FCDO will collaborate with NORAD to institutionalise some of the initiatives, particularly on the local impact assessment and SEA. Out of 4 projects under this output, 2 are already sustainable and 2 projects require continued government support to be sustainable.

Key Lessons Learned

The main theme of the programme, which is inclusive growth, was not defined with sufficient clarity or agreement at the start of the programme and the pathways for achieving that agreement were not clearly identified. A series of adaptive learning studies eventually helped the Steering Committee to clearly define it and the associated indicator for tracking progress. A more holistic approach should have been considered at the outset; and

Through adaptive learning studies, understanding and addressing the likely impacts of onshore exploration on local populations was identified as one of the weakest areas for Ghana, and this provided appropriate feedback for GOGIG to leverage resources to ensure that this was put firmly on the Government agenda.

Recommendations for future programmes

Future programmes should, at the outset, define important concepts such as inclusive growth during inception phase and its pathways identified and articulated in the Business Case and theory of change; and

Notwithstanding the adaptive programming approach, there is a need to resist the temptation of introducing new interventions especially during the closing stage of the programme. These can be hard to complete and much harder to sustain even if funding allows for their initial delivery.

Output Title	Documentation and dissemination of programme learning
Output number per LF		6	Average Output Score	A
Average Impact weighting (%)?		10%	Impact weighting % revised since last AR?	Y (↑) (2019)

Indicator(s)	Target	Achievement
Number of knowledge products and events to share learning from the programme	8 knowledge products and 4 events.	8 knowledge products and 4 events. / Achieved
Categories of stakeholders reached with knowledge products and learning events	All GOGIG partners and at least five non-GOGIG partner categories	All categories reached / Achieved

Knowledge products and events to share learning

The output was fully met. The programme undertook seven learning studies, as agreed with GOGIG's Steering Committee, key partners and FCDO.

Study 1: Improvements in Clarifying Regulatory Mandates and Policy Coherence across Government- Aligned to Output 1;
Study 2: Improvements in the capture and oversight of oil and gas (O&G) revenues, including a case study on the Multi-Agency Petroleum Revenue Committee (MAPERC) - Aligned to Output 2;
Study 3: Improving Petroleum Revenue management for inclusive growth - Aligned to Outputs 3 and 5;
Study 4: Enhanced public engagement and oversight of the O&G sector, including a case study on the Public Interest Accountability Committee (PIAC) Aligned to Outputs 1 to 5;
Study 5: Preparing Civil Society and for new challenges and opportunities - Considers international best practice, history of civil society in Ghana, and work in Outputs 1 to 5;
Study 6: Unanticipated consequences of GOGIG's work - Considers all outputs to identify consequences beyond those reported in the logframe to inform VfM and produce a fuller account of GOGIG; and
Study 7: Understanding the channels through which growth in an extractive sector like Oil and Gas can lead to inclusive development - Literature Review, comparative approaches to Inclusive Growth and potential application to Ghana, to inform public discourse.

A video documentary on key programme achievements, innovations and lessons learnt was also produced.
Studies 1, 2 and 3, confirm that three principles making up the GOGIG approach were essential in structuring partnerships that led incrementally to the achievement of significant results. These were:
- Politically adaptive programming: programming based on regular political-economy analyses;
- Partner-responsiveness: flexibility to respond to changing context and partners’ priorities; and
- Pragmatic opportunism: dynamically identifying opportunities with greater potential for success, rather than persisting linearly with a predetermined course of action based on a set work plan.

The studies noted the emphasis on fostering constructive convergence between the government and civil society. Studies 1-5 came to the view that this approach had been effective and was preferable to the alternative pathway often proposed to instigate change: encouraging civil society to adopt an adversarial advocacy voice in dealing with the government. The programme accent on constructive convergence was also visible within Government through GOGIG interventions which facilitated intra-governmental forums.

Some of the key factors that enabled the programme to work effectively were:

- Validation of the programme direction by a Steering Committee composed of representatives from the leading State institutions involved in the sector and chaired by an esteemed academic and former vice-chancellor of the University of Ghana. The composition of this committee and the fact that DFID agreed not to be represented on it gave legitimacy to the programme;
- An entirely national in-country team of professionals with the soft and hard skills to read the local context and establish positive, collaborative relations with counterparts in the Government and civil society. These are essential pre-conditions for adaptive programming; and
- Deployment of the majority of consultants with extensive local knowledge and experience and technically respected by the State partners. These consultants were also able to appropriately leverage international best practice in offering solutions that were realistic and practical for Ghana.

Stakeholders reached with knowledge products

The knowledge products were shared with the following stakeholders.
- Government ministries and agencies that GOGIG supported
- Civil society partners that worked on the programme and other CSOs
- Donor agencies such as GIZ
- Other FCDO-funded programme - STAR GHANA
- Organisations working on disability - Ghana Association of the Deaf and Ghana Blind Union
- Academia - University of Exeter programme on environmental justice

A learning event was also organised to discuss the findings from the learning studies and to discuss the road ahead for the sector. The Deputy Minister, MoE, was the keynote speaker at the event, alongside the Development Director of FCDO.

Evidence, output quality

Output quality is assessed by FCDO as good, based on the learning papers, which have helped distil learnings from the programme. The learning papers have been shared with all key stakeholders. FCDO did not formally assess the quality of the learning papers, but they have proved useful in shaping future work.

Key Lessons Learned
Identifying strategies for distilling, capturing and disseminating learning from the programme’s working approaches, successes and challenges, should have been integral from inception. However, the learning plan to help disseminate the programme’s outcome was developed only in 2018, which was a lost opportunity; and

The engagement with media in the programme was not integral right from inception. Except for the Inception Report, which gave some attention to communication under the programme, the Business Case did not highlight the issue of strategic communication. The programme should have addressed this need right from the inception stage.

Recommendations for future programmes
In future, development of similar programmes should articulate upfront the pathway for disseminating learning from the programme’s working approaches, successes and challenges; and

A communication strategy should be conceptualised into the programme development to serve as effective tool in not only disseminating learning from the programme’s working approaches, successes and challenges, but also to contribute towards achieving the objectives.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and major changes to it (1/2 page)
The intervention was based on the Natural Resource Charter with three key outputs forming the basis of the intervention design:
[note] Natural Resources Governance Institute, 2nd Edition (2014)
- Strengthening oversight and enhancing regulation of the sector;
- Improving revenue capture; and
- Improving revenue management.

Strengthening oversight and enhancing regulation of the sector depended considerably on the Ministry of Energy being able to provide strong leadership and a clear policy direction to steer all the Government stakeholders in the sector. It was assumed that this could be achieved through building the technical capability of Petroleum Commission, through increased demand for accountability from the President, and through supporting civil accountability actors and monitoring bodies to sustain their demands on the ministry.

Improving revenue capture would be achieved through focusing on the entry points where there is Government support for change. Both the MoFEP and the Ghana Revenue Authority were change champions. Support was provided to the Authority to build the revenue administration capacity of the Petroleum Unit in order to accurately assess and collect oil sector revenues. Advisory support to Ministry of Energy would aim to encourage more attention to tax policy issues so that this aspect could be addressed as well.

Improving revenue management would be achieved through enhancing the technical capacity of MOFEP and the Bank of Ghana to ensure that the institutional requirements, systems and procedures for sound revenue management were in place.

The Theory of Change was informed by a political economy analysis undertaken during the Inception Phase. It was found to be challenging to articulate a single theory that captured all the detail necessary to explain how the initiatives would support sector governance. As a result, in addition to developing an overall theory for the programme, an ‘outcome mapping’ approach was adopted that de-constructed the theory into individual outputs, using the political economy analysis to focus on the specific pathways to potential change within each area.

The expected Outcome of GOGIG was "Effective management of oil and gas resources in Ghana", with the Impact of "Inclusive economic growth and poverty reduction through a well-managed oil and gas sector". The Outcome and the Impact remained unchanged during the programme.

The TOC was premised upon the assumption that the interventions to support institutional reforms would lead to effective management of oil and gas resources in Ghana if the benefits of this growth were to be shared equitably. A closer assessment of the prevailing governance and institutional conditions suggested that reforms needed to be systemic, and undertaken across the value-chain of the oil and gas sector, if the expected outcome was to be achieved, and if the benefits of the new and increasing stream of revenues were to benefit the wider population. A flexible and adaptive approach was identified as being prudent, given the political and economic uncertainties in the sector.

The Business Case did not provide a detailed definition of ‘inclusive growth’ and it was for the programme to fully rationalise it in terms of activities linked to Outputs and Outcomes. As a result, a new output was added in 2017 - `Non-revenue pathways by which the oil and gas sector can contribute to inclusive growth identified and enhanced’. In 2018, to ensure that the programme captured key learnings as a result of the intervention, a sixth output - `Documentation and dissemination of programme learning’ - was also added.

Explain major changes to the logframe (1/2 page)

The logframe constantly evolved throughout the programme, especially after each annual review. The revisions reflected changes in Government policy direction, recommendations from DFID (SROs); changing landscape of expectation; and feedback from annual reviews. As mentioned earlier, two new output areas were added. These were done without losing end-of-programme targets and benchmarks in the Business Case.

At the outcome level, a third indicator was introduced in 2017 as 'number of government actions positively influenced pertaining to management of oil and gas resources'. This was changed in 2018 to 'number of state institutions actions positively influenced pertaining to management of oil and gas resources’, acknowledging the programme’s reach beyond a narrow focus on Government core institutions to sectoral state institutions such as PIAC and GHEITI.

Each of Outputs 1-3 had an indicator that measured progress in developing the capability of the supported State institutions and since the targets had been accomplished by end 2018, the emphasis on capacity building was reduced. Late in the programme (2019) a new indicator was introduced into Output 1 to track how the allocation of concession blocks was being handled and the monitoring of the same by civil society. Also, in 2019, an indicator was introduced into Output 3 to assess progress on the overall management of the Annual Budget Funding Amount (ABFA) component of petroleum revenue.

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved

The Theory of Change asserted that by taking actions as targeted across the five output levels, the three outcome areas – improved governance, higher revenue capture, institutional capacity - will be achieved. The assumptions underlying the TOC held true and the targets were achieved both at the Output level and at the Outcome level.

Outcome 1: Improvements in the quality of governance and effectiveness of sector management as assessed by the Resource Governance Index (RGI)
Programme End Target: 5% improvement on baseline score of 64
Programme End Achievement: Score of 83 representing 29% improvement on baseline

Highlights of programme achievements under the three (3) main RGI components which contributed to areas of improvement on the RGI in the 2019 assessment are as follows;

COMPONENT 1: VALUE REALIZATION
GOGIG contributed to all four (4) sub-components making up this component

Licencing - Contributed to 5 out of 6 areas that experienced improvements
Taxation - Contributed to 2 out of 3 areas that experienced improvements
Local Impact - Contributed to 2 out of 3 areas of improvement
State owned enterprises - Contributed to 3 out of 4 areas of improvements.

COMPONENT 2: REVENUE MANAGEMENT
GOGIG contributed to one (1) of the sub-components making up this component
National Budget - Contributed to all three areas of improvements

COMPONENT 3: ENABLING ENVIRONMENT
GOGIG contributed to Government Effectiveness and Regulatory Quality – two (2) of the sub-components making up this component

Outcome 2: Additional Revenue Captured through GOGIG support and contributions
Programme End Target: Additional revenue captured annually progressively increases to 5% of total petroleum revenue
Programme End Achievement: 6.2% of total annual petroleum revenue

Cumulatively, GOGIG support to the Petroleum Unit and Transfer Pricing Unit of GRA has contributed to an increase of over USD 300 million (GHc 1749.9 million) equivalent to 0.5 per cent of GDP in 2019. Out of this amount, USD 117 million, equal to 0.2 per cent of GDP is the revenue attributed to GOGIG interventions. This exceeds the business case target of 1:5 and translates to a rate of return of 1:7.42
[note] 2019 Article IV Consultation, Dec 18, 2019 for Ghana (Table 2a). Nominal GDP at GHc 349,193 million.
[note] GHc 667.98 million
The annual breakdown is as follows.
Additional Revenue Captured	Source of revenue	Gross Amount Realized by Government in USD	Percentage Attributed to GOGIG	GOGIG Share of Attribution in USD	GOGIG Share of Attribution in GBP
2016	GRA Transfer pricing audits findings and surcharges	$3,571,428.57	100%	$ 3,571,428.57	£ 2,678,571.43
2017	Deferred Tax & Interest payment detected through audits by GRA and supported by GOGIG	$22,073,745.00	75%	$ 16,555,308.75	£12,582,034.65
2018	Additional oil entitlement windfall tax identified through / GOGIG diagnosis of revenue losses	$100,000,000.00	30%	$ 30,000,000.00	£21,000,000.00
	Bank of Ghana improved earnings from the investment of Heritage & Stabilization funds through the application of technical skills and Bloomberg software provided to them by GOGIG.	$3,500,000.00	80%	$ 2,800,000.00	£1,960,000.00
	Outstanding Surface rentals fees paid by upstream through PIAC advocacy.	$824,949.74	50%	$ 412,474.87	£ 288,732.41
2019	GRA Transfer pricing audits findings and surcharges	$18,910,000.00	45%	$ 8,509,500.00	£ 6,977,790.00
	Additional tax revenue identified by GRA through the application of IDEA software and other technical provided to them by GOGIG	$158,113,998.58	35%	$ 55,339,899.50	£45,378,717.59
Total		$306,994,121.89		$ 117,188,611.69	£90,865,846.08

Outcome 3: Number of state institutions’ actions positively influenced around the management of oil and gas resources
Programme End Target: 17
Programme End Achievement: 21

Some of the key actions undertaken state institutions that positively influenced the sector include the following:
- Passage of E&P Act and regulations incorporating open contract provisions presented to government and advocated for by ACEP to government for inclusion in the act.
- Ministry of Energy (MoE) adopted GOGIG recommendations in shaping the content of a blueprint for accelerated oil and gas exploration and development. (2018)
- First ever comprehensive energy policy drafted by the government to guide reforms and attract investment to the sector (2018)
- Petroleum Commission savings of US$450 million cost on Aker Energy plan of development through the application of the Landmark and Petrel software and technical knowledge provided by GOGIG to the Geoscience and Engineering units of the PC (2019)
- Online petroleum register created by government to grant public access to all petroleum agreements signed and permits issued.
- Inclusion by Registrar General’s Department’s (RGD) of Beneficial Ownership Disclosure (BOD) requirements in the new companies’ bill.
- Parliament’s directive to GNPC to stop spending on non-core areas and the subsequent cancellation of the Corporation’s sponsorship deal with the national football team, the Black Stars, based on recommendation by PIAC.
- Funding of PIAC for the first time through the national budget following amendment to PRMA to allow allocation of petroleum revenue directly to PIAC as advocated for by ACEP.
- MoF publication of ABFA funded project list for the very first time in the annual budget following persistent advocacy of PIAC and ACEP through GOGIG support and direct engagement of GOGIG TA with MoF on preparation of list

Outcome Quality, Evidence and Sustainability

The quality of evidence of the outcomes is good: improvements in the governance of the oil and gas sector in Ghana between 2015 and 2020 were captured by the global Resource Governance Index. This is further corroborated by the fact that the policy and regulatory framework in Ghana has been significantly improved with GOGIG support. A stronger institutional framework and a stronger accountability space provides further evidence of the positive results achieved. While most of the gains may be sustainable as they are enscrined by law, many other gains may be dependent on the future commitment of the government to the reform agenda.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme (1 page)

The programme was designed to achieve VfM by ensuring that the sector worked effectively to reduce revenue leakages, disincentivise corruption, and reduce mismanagement and business losses. Though the Business Case recognised the difficulty of quantifying many of the programme benefits, it estimated that the programme would represent value for money if the value of revenue losses or additional revenue captured translated to £5 per every £1 spent on the programme. The end of programme assessment by PMT indicated that the programme has outperformed the VfM proposition in the Business Case. Overall, GOGIG has achieved £7.42 per every £1 spent on the programme.
[note] as at June 2020

Economy
The total cost savings made on expected project expenses through adherence to financial safeguards and other cost-cutting strategies amounted to £256,938.34. This means that at a total programme spent of £12,238,339.39 by June 2020, the programme had saved an average £0.02 for every £1 spend. The continued use of in-country experts for the programme management and delivery of key interventions significantly drove down the cost, as it allowed the programme to cut down on flight, accommodation and other expenses usually associated with international consultants.

Efficiency
GOGIG assessed its performance on efficiency through the total spend on direct programme implementation as a percentage of total programme spend as well as the quantity and quality of programme output deliverables achieved against targets.

From the total programme spend of £12,238,339.39 GOGIG ensured that 59%, amounting to £7,181,790.25 spent, constituted direct implementation. This performance was 1% under the FRF benchmark threshold of 60% target set for programme spend. All twelve Output level performance indicator targets were achieved with seven exceeding targets: input to output efficiency was achieved at greater than the expected rate. Quality was high: of the thirteen substantive policy submissions made to the Government between 2017 and 2019, the Government adopted and implemented recommendations from eleven, representing an 85% adoption rate.

For the Flexible Response Fund spend on programme implementation, the programme leveraged a total partner contribution of £312,006.05. When compared to total amount of £7,181,790.25 spent on approved FRF projects, it shows that for every £1 spent by GOGIG, partners contributed an estimated value of £0.04. Securing partner contributions to FRF projects was not a requirement in the Business Case; however, partner contributions towards project implementation incentivised efficient spending on the programme and was also evidence of the commitment and ownership particularly of the Government partners.

Effectiveness
This was assessed by looking at evidence that supports how well programme Outputs were contributing to the expected Outcomes of the programme. Two main indicators were used to support this assessment, additional oil revenue leveraged from every pound spent on the programme, and the significant changes achieved by GOGIG as a contribution to effective management of oil and gas resources.

The GOGIG programme was principally designed to achieve effectiveness by supporting the Government to seal revenue leakages along the oil and gas value chain. The target of 5% of the total earnings of the Government from the sector was exceeded and the total attribution value translated to 7.2% of total petroleum revenue in 2018.

The Business Case financial scenario also projected a benefit cost ratio of 1:5, expecting £5 for every £1 invested. The programme’s cumulative performance on additional revenue captured and losses prevented shows an improved performance when compared with programme spending to date. Overall, £7.42 had been realised from every £1 invested in the programme.

GOGIG also achieved non-revenue benefits from the programme. These benefits also contributed to the achievement of outcomes by helping enable a stronger regulatory framework for the sector and higher accountability standards. These include:
- A framework of guidelines on social performance developed for the Petroleum Commission to regulate upstream operators’ community level operations;
- Improved PIAC capacity to hold the Government accountable and elicit responsiveness on lapses in petroleum revenue management;
- Government commitment to set up an online Petroleum Register;
- Ministry of Finance publication of list of projects to be funded with ABFA as part of annual national budget reading.

Equity
For GOGIG, “equity” was central to the programme focus on inclusiveness. The space for this has been limited, yet the programme took reasonable steps to impact positively on equity when the opportunity was presented. GOGIG assessed its performance on equity through:
- Percentage of policy-making projects including voice of marginalised groups;
- Percentage of programme participants at policy-making events drawn from frontline communities; and
- Percentage of programme resource persons on FRF project implementation who were women.

Cumulatively, the programme ensured that 68% of all policy-making projects implemented included the voice of marginalised groups. The opportunity was leveraged on policy-related projects that have clear spaces for stakeholder engagement. Where opportunities arose, the programme made a deliberate effort to ensure that partners created pathways for marginalised groups to voice their aspirations on the policies being formulated.

Between 2017 and 2018, the programme supported five policy-making events with issues that were relevant to the interest of frontline oil communities. Of this, the programme ensured that 23% of the participants were drawn from frontline oil communities.
[note] As shown by the attendance sheets of these events

Given the low participation of women in sector policy development and other notable initiatives, GOGIG also targeted and facilitated the involvement of women as resource persons in sector policy development and other key initiatives. A resource person in this respect refers to an expert engaged to make presentations and other inputs to shape sector issues at forums, seminars, workshops and other technical dialogues and committees.

Between 2017 and 2019, the programme ensured that 25 of the total 108 resource persons were women. To sustain these gains beyond GOGIG, the programme has created the Women in Energy Platform to advance visible women leadership and participation in the oil and gas sector.
[note] When GOGIG compiled results

E: RISK (½ page)

Overview of programme risk (noting the rating from page 1) during the past year and over the life of the programme

The trajectory of risk remained relatively stable throughout the programme with an overall risk rating of Moderate. Overall, the programme was successful in identifying and managing the risks arising primarily from the complexity of the programme, its range of partners and the political economy analysis of the evolving context.

The PMT put in place a risk management system to roll out mitigation measures that responded to risks identified. The programme also maintained a risk register which was revised in 2017 to comply with the latest guidance which ensured a comprehensive risk assessment across the various categories. Risks were mainly identified through insights gained from regular PEAs and weekly updates on developments with partners/projects and were mostly mitigated by incorporating learning into projects to respond to changing needs and leveraging partner relationships and the right incentives to deliver objectives.

Some of the significant risks that materialised and were mitigated include:

Slowdown of government business and paralysis in major policy and decision making in the lead up to the 2016 elections
Mitigation measures included ramping up accountability interventions to take advantage of the opportunities that the electioneering season presented. On the government side, the focus was on operational functioning rather than policy work which carried the risk of being abrogated if a new administration came into power. Once the newly elected Government assumed office, GOGIG was well prepared and positioned to respond to by quickly establishing key relationships with new appointees such as the Minister of Energy.

Reputational risks from the election support project were well managed
The design of the election support project interventions enabled GOGIG to maintain neutrality and avoid the risk of being perceived as being partisan.

The risk from the loss of key leadership supporters at the MoE and the Petroleum Commission, and the presence of new government appointees
The GOGIG team had anticipated this risk and leveraged relationships with the SC members to secure early meetings with new appointees for briefings on the GOGIG programme and to get a sense of the new Government’s direction. Mitigation measures initiated the previous year ensured that handing over processes at the MoE for the incoming Ministerial team included documentation of GOGIG’s support which allowed GOGIG to be recognised as a credible partner for continued support with the new Government.

The change of the Minister of Energy in 2018 with whom the programme had an established engagement
The programme’s credibility, strengthened relationships at both the technical and Deputy Ministerial levels enabled the team to minimise this impact and the programme’s cooperation with the Ministry continued with a request for renewal of TA services;

Loss of trained professionals: A major risk to the programme was loss of key technical personnel in relevant positions. For instance, at the Ministry of Finance two senior persons moved which was a big setback to the programme given the knowledge and skill they possessed. Similarly, the Head of the Transfer Pricing Unit of GRA and the CEO of the Petroleum Commission, who were key programme partners moved on in 2017. However, the programme approach to mitigating such potential setbacks was to adopt an institution-wide approach for engagement and training. Also, the Steering Committee arranged for an “alternate” who would step in as replacement in the event of loss of any member.

Learning and Adaptation mechanism: According to some of the stakeholders, the learning and adaptation mechanism inherent in the programme had been by far the most useful factor for ensuring the success of the programme. While it has allowed for the necessary flexibility to be achieved in the implementation of the programme, it has also offered opportunity for management to learn useful lessons and take the necessary corrective action. This has helped in maintaining programme momentum in the advent of changes in political environment.

Although several external risks did not materialise, the interventions rolled out as part of mitigation measures provided a good foundation to be leveraged by future programmes. An example is the set of interventions implemented by the programme to address the negative impacts of onshore activities in the Voltaian Basin. As a result of the programme’s extensive work in this area, managing local impacts has been placed on the Government’s agenda with local and international partnerships developed with the MoE, GNPC, PC, EPA, Chatham House and Ghanaian experts.

Partnership Principles
The Partnership Principles are not used in the management and monitoring of GOGIG given that the programme does not entail financial aid and use of country systems. The last update to the Partnership Principles undertaken in August 2019 indicated no changes in trend for the Government of Ghana’s commitment to poverty reduction, respecting human rights, accountability and improving public financial management, although concerns remain on fiscal responsibility and level of corruption.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

The relationship between OPM and DFID was generally robust with strong engagement between the FCDO SRO and programme manager and the PMT in Ghana. The frequent changes in programme managers at OPM was not helpful though the strong local team on the ground helped. During programme, DFID changed the terms and conditions of engagement, and that raised some concerns for OPM and partners in terms of contracting and delayed some of the activities.

OPM’s reporting, financial management and forecasting was high quality, timely and detailed throughout the programmes, recording an average underspend variance of 3.57%. DFID made payment to OPM monthly upon submission of invoices by GOGIG for programme expenditure. All expenditures were clearly identified under a budget line and adequate descriptions of all expenditure were mostly provided. OPM provided quarterly financial progress reports as part of the quarterly reporting to DFID. In these quarterly progress reports, GOGIG continued to report on key budget lines as a percentage of monthly expenditure, and monthly actual versus forecast expenditure, as well as FRF expenditure breakdown by output area and by spend type.

There were good systems in place for undertaking programme expenditure reviews. With the support of DFID Corporate Effectiveness team, a workshop on DFID’s policy on Fraud and Corruption as well as Safeguarding was provided to the GOGIG Programme team. There was one report on fraud made within the reporting year involving a service provider used by the GOGIG team but there was no loss to DFID. However, given the risk that the programme was exposed to, the GOGIG team suspended all future engagements with the facility until such a time where there was sufficient evidence that strong and robust systems had been put in place by the facility to prevent a repeat of such fraud.

Annual audits for the implementing period were undertaken. The audits indicated that internal control systems were strong to avoid financial malpractices. Controls were in place to ensure all functional responsibilities were segregated such that no single person performed a transaction from initiation to completion.

OPM deployed a range of local and international consultants. They could access high quality subject experts and managed them well. Most long-term consultants were engaged for an extended period on the programme, enabling continuity and relationship-building.

Performance on Milestone payments
The FRF payment modality, which was agreed in 2016, allowing a 10% deduction from the cost of FRF disbursements until pre-agreed milestones are submitted and signed off by the DFID SRO was implemented and working well. In January 2018, DFID and the Programme agreed for the 10% payment modality on the FRF to be conditional on the satisfactory submission of Learn-Adapt reports, which was submitted with each quarterly report. GOGIG met 100% of milestones under this payment modality.

Grant and Delivery Chain Management
The GOGIG programme used the DFID Due Diligence Framework to carry out its due diligence. Prior to grant disbursement, the Grants Manager ensured that all necessary documentation including detailed forecast for project activities and completed request for funds were obtained and carefully reviewed. Any additional documentation required was either verified during on-site visits or via email. The GOGIG team conducted expenditure verifications of all grantee partners over the programme period, including Institute of Fiscal Studies (IFS), IMANI, ACEP, Ghana Industrial Trawlers Association (GITA), PIAC, Centre for Budget Advocacy (CBA), Centre for Environmental Impact Analysis (CEIA), Centre for Extractives and Development Africa (CEDA) and Penplusbytes.

Date of last narrative financial report	awaiting information
Date of last audited annual statement	awaiting information

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

The GOGIG programme was large and complex, involving the provision of a flexible support to a variety of stakeholders engaged in the oil and gas sector through a mixture of direct technical assistance and accountable grants.
The initial logframe was reviewed annually in response to the programme’s learning and insights on emerging priorities as identified through the regular political economy analysis. Recommendations from DFID annual reviews also occasioned some revisions to the logframe. Output level indicators which had been achieved before the end of the programme were archived whilst emerging priorities, such as the launch of the first competitive licensing round were featured in the logframe to ensure measurable performance in responding to those priorities. Quarterly reviews of progress against logframe targets were held both within the PMT and with the Steering Committee, reflecting a strong emphasis on ensuring strong programme performance. In addition, the programme developed a Value for Money framework to guide assessment, tracking, and reporting on the programme performance on VfM.

An internal quality assurance process was developed and implemented as part of the project design process. This allowed for the vetting of each proposed project idea to assess its relevance within the operational context, alignment to programme results and value for money. Project documents detailing the details for implementation included a risk assessment to ensure that all risks were monitored and appropriate mitigation strategies identified.

A PCR process was undertaken by an independent consultant in Sep-Oct 2020 assessing extensive documentation and discussing the programme with around 25 stakeholders (across all core State partners, and civil society representatives). The PMT was interviewed as was the supplier/service provider (OPM).

Evidence (1/2 page)

GOGIG invested significantly in its M&E systems, and this has proven very valuable for the purposes of accountability, learning and adaptation. The GOGIG quarterly and annual reports, the learning and adaptation studies, the political economy analysis reports and interim 2020 PCR provided useful evidence. In addition to the quantitative ratings, the reports provide considerable qualitative evidence that is used to explain, contextualise and justify changes in ratings.

With the exception of the Impact indicator and Outcome indicator 1 where data has not been available on an annual basis due to how it is captured, nearly all the outcome and output indicators have adequate data to make effective analysis of progress being made towards target. There is no reason to doubt the quality of data provided for assessment on quarterly and annual basis, which was triangulated with the SRO and programme manager’s frequent engagement with project stakeholders.
.
Learning (1/2 page)

The programme through the MEL Manager provided tailored MEL support to partners to streamline project results framework, understand the conduct of monitoring, and tracking of results. This involved providing relevant templates to facilitate quarterly reporting from programme partners and mapping of outcome results. An end of project review was also conducted on each grant project approved for a partner. These regular reviews generated important lessons, which informed continual improvement in grant management process with partners. Annual partnership review meetings provided the opportunity for meetings with all partners to share programme performance in previous year and plan for the ensuing year.

Throughout the programme, DFID held regularly weekly meeting with the GOGIG PMT leader to closely monitor activities and ensure appropriate linkages with related programmes. The programme further provided accounts of programme performance through quarterly and annual reports submitted to DFID. During the final period, the programme commissioned seven learning studies to distil lessons for broader dissemination to partners as a strategy to sustain momentum of policy reforms supported by GOGIG.
Progress on recommendations from annual reviews for this programme (1/2 page)

During the programme lifespan, a total of five reviews were commissioned by DFID to assess achievement of planned results. The logframe and the evidence base presented by the programme served as the basis for assessing and scoring progress. While the programme scored a B in its first annual review in 2014, its performance progressively improved to an A+ by the mid-term review in 2017. The programme scored an A in its last AR in 2019, prior to the conduct of the programme completion review.

Following each review, several recommendations were made which had implications for the programme’s strategic direction and delivery. Below are the notable areas where changes were made in line with the recommendations:

Programme Scope

- The programme’s theory of change was revised to fully articulate the linkages to its inclusive growth objective. This broadened the programme scope from its previous narrow emphasis on revenue capture and utilisation of oil revenues to include non-revenue pathways through which the oil and gas sector could contribute to inclusive growth.
- The 2015 Annual Review approved the programme team’s plans to use the upcoming elections as an opportunity to build sustained civil society support around key issues in the sector. This resulted in the design and successful implementation of an election support project in 2016 that was guided by strategies that ensured that the election outcome did not deplete GOGIG’s influence.
- Based on the 2016 Annual Review recommendation, the programme broadened its points of engagement for revenue capture to include approaches to minimising revenue losses. This strategic shift to complement efforts at identifying additional revenues also expanded the opportunity to improve the programme’s Value for Money.
- Making oversight and accountability a cross-cutting area of working rather than standalone as originally envisaged by the Business Case; and
- Coordination of engagement with other DFID programmes and complement similar donor efforts such as Norad to clearly delineate areas of work and points of collaboration. These informed the level and scope of interventions particularly for Government partners such as the GRA, PC and MESTI as well as accountability actors work on commodity trading and anti-corruption.

Performance Measurement

Each review had specific recommendations to strengthen the logframe which resulted in the following:
- Agreement of baseline needs and data for all indicators;
- Agreement of output weightings to accurately reflect programme efforts;
- Introduction of indicators at the outcome level to reflect revenue being used for inclusive growth areas. This was subsequently revised;
- Clarifying definitions of outputs and indicators to distinguish and better capture achievements as well as avoid overlaps;
- Introduction of new Output 5 focused on non-revenue pathways by which the oil and gas sector could contribute to inclusive growth; and
- Introduction of new Output 6 focused on capturing and disseminating learning from the programme to inform future design of technical assistance programmes.

Programme Delivery

Policy coordination: Recognising the opportunity presented by the change in government in 2018 to drive greater policy coherence in oil and gas reform led to the recommendation for GOGIG to continue playing a strong coordination role to streamline engagement on policy and regulation reform. Two inter-related areas of work were rolled out with the first focused on using the informal convening and coordination role of GOGIG to bring together State institutions to consider cross-sectoral issues such as inclusive growth and development, targeted use of ABFA funds to stimulate change within the institutions, and adoption of progressive policies. The second area of work pursued the establishment of structural mechanisms for coordination and implementation of government policies. The latter led to the establishment of task forces and inter-ministerial committees to address known overlaps and potential conflict in ongoing policy initiatives.

Review of existing partnerships: During the programme, recommendations were made to assess and strengthen the programme’s partnerships. In 2016, the Annual Review recommendation to capitalise on the upcoming elections led to work with several oversight actors apart from the two core programme partners; ACEP and NRGI. This included partnerships with CSOs and media which placed oil and gas issues in the debate in the run-up to elections. On the other hand, in line with the 2018 Annual Review recommendation to review existing partnerships in light of new opportunities and the changing context, the programme reduced its the capacity building assistance to the Bank of Ghana’s Ghana Petroleum Funds Secretariat and eventually closed its support.

Sustainability

With two years remaining on the programme, the Annual Review tasked the programme to commence planning for its exit and how the impact of the programme will be sustained. Specifically, GOGIG was to focus on further leveraging output level results to influence additional changes at the Outcome level targeted at sustaining the sector’s progress and mitigating risks of regression after programme closure by developing and rolling out a sustainability and exit plan.

To implement this recommendation, the PMT undertook:

- A sustainability mapping exercise of all programme interventions to assess the status of sustainability and develop a plan for any further interventions required;
- Sustainability considerations were then used to assess new project proposals in subsequent years with mechanisms integrated in the implementation to ensure sustained impact beyond the programme lifetime; and
- A new Output 6 on capturing and dissemination learning from the programme was added to the logframe to ensure distillation of lessons from its implementation model and experience in the sector to inform future engagement on extractives in Ghana, and the future design of technical assistance programmes.

The mapping identified that 31 out of 53 Projects (60%) were already sustainable or had fully achieved their purpose; 17 out of 53 (32%) achieved the intended results yet required further progress by partners with or without further donor support to make an outcome impact that could be considered sustainable; and five of 53 (10%) did not achieve the originally-intended result and either had to be adapted to achieve a different result or abandoned altogether.

For most of the implementing partners, changes made so far will be sustained. Most of the changes made are irreversible, internal mechanisms have been instituted to ensure that they endure. In the case of the Ministry of Finance for instance, the Government now fully funds the preparation of key revenue reports. Other institutions such as Petroleum Commission, Ministry of Energy, NDPC and GNPC have confirmed setting resources aside to sustain implementation of the initiatives commenced under GOGIG.

In the case of PIAC, the amendment of the PRMA (Act 815) will ensure that the activities of PIAC are fully funded by the Government. This was achieved through strong advocacy and dialogue including the use of the media to exert pressure when payments slowed. The only apprehension is that there could be a reversal of this progress in the event of political changes. Currently, the funding of PIAC is protected by law and is secure. The Government will need to maintain the funding of PIAC, by upholding the amendment of the PRMA (Act 815). The Women in Energy Platform is established but fragile with no long-term funding base.

Sustainability of reform is very dependent on the commitment to it by the Government of the day. It is already clear that the Government seeks to negotiate directly with oil companies, instead of using competitive bidding process for new concessions. This is despite that there is provision in the E&P Law, regarding allocation of blocks that it should be by competitive bidding. So, the beneficiary institutions will need to uphold the law, in internal discussions with the Government. It is not clear that this will be the case.

There is commitment among the accountability actors to maintain their activities in the sector; however, they will still need to have a secure funding base in order to keep the government to account. The work of PIAC, NRGI, ACEP and CVPOG is critical particularly when the Government seeks to act outside the law. Without secure long-term funding, the efforts of the accountability actors may be limited in this regard.

#### Abbreviations and Acronyms

ABFA	Annual Budget Funding Amount
ACEP	Africa Centre for Energy Policy
ACET	African Centre for Economic Transformation
AMV	African Mining Vision
AOE	Additional Oil Entitlement
AfDB	African Development Bank
BoG	Bank of Ghana
CEPIL	Centre for Public Interest Law
CHRAJ	Commission on Human Rights and Administrative Justice
CSPOG	Civil Society Platform on Oil and Gas
DFID	Department for International Development (UK Aid)
E&P	Exploration and Production
EIA	Environmental Impact assessment
EMT	Economic Management Team
EOCO	Economic and Organised Crime Office
EOGU	Energy, Oil and Gas Unit
EPA	Environmental Protection Agency
ESIA	Environmental and Social Impact Assessment
FARI	Fiscal Analysis of Resource Industries
FRL	Fiscal Responsibility Law
G8	Group of Eight (countries)
GDP	Gross Domestic Product
GHc/GHC	Ghana Cedis
GHEITI	Ghana Extractive Industries Transparency Initiative
GHF	Ghana Heritage Fund
GIZ	German International Development Agency
GLSS	Ghana Living Standards Survey
GNPC	Ghana National Petroleum Company
GNT	Government Negotiation Team
GoG	Government of Ghana
GOGIG	Ghana Oil and Gas for Inclusive Growth
GOGSPA	Ghana Oil and Gas Service Provider Association
GPFS	Ghana Petroleum Funds Secretariat
GRA	Ghana Revenue Authority
GSF	Ghana Stabilisation Fund
GSS	Ghana Statistical Service
HSSE	Health, Safety, Security and Environment
IBRD	International Bank for Reconstruction and Development
IFC	International Finance Corporation (of the World Bank)
IG	Inclusive Growth
ILO	International Labour Organisation (of the UN)
IMAT	Inter-agency Modelling and Analysis Team
Indepaz	Institute for Development and Peace (Columbia)
INGO	International Non-Governmental Organisation
IPC-IG	International Policy Centre for Inclusive Growth
ISODEC	Integrated Social Development Centre
ISSER	Institute for Statistical, Social and Economic Research, University of Ghana
KII	Key Informants Interviews
LEAP	Livelihood Empowerment against Poverty Programme
LF	Logframe
M&E	Monitoring and Evaluation
MAPERC	Multi-Agency Petroleum Revenue Committee
MDAs	Ministries, Departments and Agencies
MEL	Monitoring, Evaluation and Learning
MMDAs	Metropolitan, Municipal and District Assemblies
MoE	Ministry of Energy
MOE	Ministry of Education
MoEP	Ministry of Energy and Petroleum
MoF	Ministry of Finance
MoH	Ministry of Health
MoP	Ministry of Planning
NAO	National Audit Office
NDC	National Democratic Congress
NDPC	National Development Planning Commission
NHIS	National Health Insurance Scheme
NPP	New Patriotic Party
NRGI	Natural Resource Governance Institute
O&G	Oil and Gas
OCTP	Offshore Cape Three Points (Oil and Gas field)
OECD	Organisation for Economic Cooperation and Development
OfD	Oil for Development programme (Norway)
OGCBP	Oil and Gas Capacity Building Project (of the World Bank)
OLP	Oversight Leadership Programme
PC	Petroleum Commission
PEFA	Public Expenditure and Financial Accountability
PFM	Public Finance Management
PHC	Population and Housing Census
PIAC	Public Interest and Accountability Committee
PIP	Public Investment Projects
PNDCL	Provisional National Defence Council Law
PRIS	Petroleum Revenue Information System
PRM	Petroleum Revenue Management
PRMA	Petroleum Revenue Management Act
PU	Petroleum Unit (of GRA)
RGI	Resource Governance Index
SC	Steering Committee (of GOGIG)
SDG-F	Sustainable Development Goals Fund
SEA	Strategic Environmental Assessments
SHS	Senior High School
SRO	Senior Responsible Officer
TEN	Tweneboa Enyenra Ntomme (Oil Field)
ToC	Theory of Change
ToR	Terms of Reference
TPU	Transfer Pricing Unit (of GRA)
UN	United Nations
UNDP	United Nations Development Programme
UNIDO	United Nations Industrial Development Organisation
VfM	Value for Money
VPI	Voluntary Principles Initiative
VPSHR	Voluntary Principles on Security and Human Rights
WB	World Bank
WEF	World Economic Forum
WIE	Women in Extractives