ADDENDUM TO BUSINESS CASE INCLUDING COST EXTENSION

SUMMARY INFORMATION
Project Name	Programme for Strengthening State Capabilities
Country or region targeted	India
Type of cost extension (if applicable)	Cost extension
Original project budget	£4.5 m
Original project start and end dates	November 2018 – November 2023
Cost extension value (if applicable)	£496,000
New project end date (if applicable)	NA
Business Case Quest Document No.	HoD Approval- 39,991,341 / Business Case- 49,569,630

INFORMATION
What is the project’s purpose?
The purpose of the Programme for Strengthening State Capabilities (PSSC) is to address the significant institutional capacity constraints at India’s national sub-national and sectoral levels that is leading to sub-optimal growth and development outcomes. The programme supports interventions that systematically diagnose capacity constraints in selected national, state and sectoral institutions and provide bespoke capacity building and implementation strengthening support. It also supports Government of India (GoI) in designing and implementing flagship reforms that aims to transform the functioning of the economy and help deliver results commensurate with India’s ambitions of that of a rising power. DFID India is leveraging expertise of all major development stakeholders to achieve this goal.
What is the objective of the cost extension or other changes?
The key objective of the cost extension is to enable the UK to support GoI in its ambitious Civil Service Modernisation (CSM) Plan that aims to transform India’s archaic administration and enable faster and better economic and social development delivery and outcomes. To deliver on this agenda, though the GoI has chosen the World Bank as its primary delivery partner, it is strongly relying on learning and adapting from the UK’s experience in civil service reforms. / DFID India plans to use this demand driven opportunity and provide strong bespoke support to GoI and the PSSC is the channel to provide the support. In addition to channelling £1.25 m through a World Bank Trust Fund to support GoI on CSM, the programme intends to fund a Senior Adviser as Secondee to the World Bank. The Secondee, apart from providing high quality technical advice to the World Bank’s core team delivering on CSM, will bring in the best of UK’s institutions and expertise and the World Bank and GoI have been keen to partner with UK institutions on civil service and governance. In addition, the programme will keep a small fund to allow for adaptive programming and robust monitoring. / The programme’s chosen approach of supporting GoI’s CSM agenda primarily through the World Bank has been carefully chosen after considering multiple options: / Option 1: Do nothing / The Business as Usual or Do Nothing option will avoid requirement of any additional funds for this programme. This however will be a lost opportunity for the UK to support one of GoI’s most ambitious reform agenda including no real traction to driving civil service modernisation from a UK interest (more private sector and climate impact of CSM) and limited ability to drive the Best of British from outside. Also, being outside the World Bank does not provide the full influence and strength which the Bank’s internal platform provides. / Option 2: Provide the additional funds to another delivery partner to support GoI on CSM / Channelising programme funds through delivery partners other than the World Bank might give the UK some scope to support GoI on CSM on niche areas. But, given that the World Bank is GoI’s delivery partner of choice on CSM and by virtue of being a multilateral, no other delivery partner (private consulting firms, think tanks) will have as effective a convening power and the requisite clout to influence the government. / Option 3: Channelise additional funds through the World Bank to support GoI on CSM / This option allows the UK to leverage the multilateral system and deliver on supporting India’s key reform agenda in the most effective and economical way. This additional funding in the form of a secondment will allow the UK to use the World Bank’s internal platform, expertise pool and its convening power. This access will allow the UK to bring in the best expertise and learnings globally as well as the UK and influence positive change. / In view of the pros and cons of the above options, the programme has chosen Option 3 as the key rationale for the cost extension. / Harmonisation:
What is the additional and total support the UK will provide?
To fully support GoI on the CSM agenda, UK’s total contribution through the programme is expected to be £1.77 m. Of this, £1.274 m is available as per the programme’s current approved budget of £4.5 m. / The programme therefore requires an additional budget of £496,000 of which £376,000 is the additional fund required to support the secondment and £120,000 to deploy robust monitoring mechanisms and for bringing in additional UK expertise, as the programme progresses.
What are the expected results?
The expected results will be aligned with PSSC’s outcome and impact indicators namely: / Outcome: Improved policies and systems to strengthen government capabilities (Indicator: Level of changes made in the policies and systems in the government machinery) / Impact: Enhanced state capability for service delivery leading to better performance towards the SDGs / In addition, the additional activities funded through the cost extension will ensure stronger governance of UK funds channelised through the World Bank and lead to a multitude of high quality global and UK institutional partnerships.
What is the approach to implementation?
The implementation will have a three-pronged approach to ensure value for money and maximised development impact: / Partner with the World Bank (through a Trust Fund arrangement) to support the GoI on modernising its bureaucracy / Deploy a programme funded Senior Adviser as secondee to drive the CSM reform from within the Bank and bring in the best of UK and global as needed / Strengthen monitoring by contracting a third-party service provider. / Gender Equality / The programme complies with the Gender Equality Act of 2014. When addressing key policy issues and governance barriers to economic growth using the additional funds, the programme will have a clear focus on strengthening capacity of institutions to identify and implement gender and disability responsive policies and practices. Appropriate indicators will also be included in the logframe to capture the effect of the programme on greater gender equality in development outcomes. / Terrorism and Bribery / Given the nature of the component that the additional funding will support, there is low risk of misappropriation of funds for terrorist purposes. A key mitigating factor is that the additional funds will be channelised primarily through the World Bank – thus ensuring appropriate level of transparency and accountability. For all non-multilateral partners, due diligence will be done as a key risk mitigating factor.