## 20192020 Achievements
AFRICAN AGRICULTURAL TECHNOLOGY FOUNDATION LOGFRAME (2018-2022)
RESULT AREAS | PERFORMANCE INDICATORS |  | Performance against key indicators | [6 empty] | Risks /Asumptions and Mitigation
IMPACT | Impact Indicator 1 | Baseline | Targets and Achievements | 2017/2018 | 2018/2019 | 2019/ 2020 |  | Percentage achivement | Narrative
Transforming Livelihoods Through Innovative Agricultural Technologies to improve incomes and improve food security | Percentage increase of income of farmers using improved technologies | Annual Average (FAOSTAT 2016) Agricultural Income (crops) $100.3 Cassava Baseline Figures income per ha( Nigeria $354.9 ; Uganda $ 816.94 USD Zambia $ 461.5) | Planned |  |  | Cassava revenues per ha (USD)Nigeria - 511.9 Uganda - 1096.94 Zambia - 702.5 |  | 44% increase in Nigeria , 34% increase in Uganda and 52% decrease in Zambia | Significant impact of CAMAP was noted in the increase in yields and consequently revenues from cassava. Average yield of fresh cassava (MT/ha) and revenues (USD/ha) were higher for the treatment groups than the control groups across the three countries. At baseline (2014), the mean yield (fresh cassava) was 10 MT in Nigeria, 14 MT in Uganda and 12 MT in Zambia. In comparison, cassava productivity across the three countries had improved to 18.6 MT/ha in Nigeria, 21.3 MT/ha in Uganda and 21.4 MT/ha in Zambia. The maximum yield ranged from between 42 MT/ha in Nigeria, 46.3 MT/ha Uganda and 44.0 MT/ha in Zambia. The average contribution to revenues was 157 USD/ha in Nigeria, 280 USD/ha in Uganda and USD 241/ha in Zambia. | Risks: High levels of price and income volatility for farmers are related to the market fundamentals of supply and demand intensified by other macro-economic variables, the broad political and legislative environment for farmers, and speculation on agricultural products. Mitigation: Encouraging farmers to using the appropriate technologies (e.g. by planting drought-resilient crop varieties or investing in irrigation methods), farmers can reduce the risks of yield losses due to weather conditions. AATF can empower farmers by creating policy and legal frameworks that improve their ability to manage these risks. Apart from enhancing the training of farmers and providing reliable information on market developments, public policies can maintain safety nets to help farmers to deal with income loss as a result of catastrophic events or major disturbances of the markets.
|  |  | Achieved |  |  | Price for a Kg or a ton? More precision is needed
Impact Indicator 2
| Percentage increase in yield of farmers adopting AATF technologies | Annual Average (Africa) (FAOSTAT 2017): Cowpea 873.6kg/ha, Maize 2072.6kg/ha, Rice 2443.9 kg/ha Cassava Baseline figures 10 MT/ha in Nigeria, 14 MT/ha in Uganda and 12 MT/ha in Zambia | Planned |  |  | Mechanised Cassava yield (MT/ha : 18.6 MT/ha in Nigeria, 21.3 MT/ha in Uganda and 21.4 MT/ha in Zambia |  | 86% Increase in Nigeria ; 52% increase in Uganda and 78% increase in Zambia
Achieved
Source of data: Surveys, National Statistics
PRIMARY OUTCOME | Primary Outcome Indicator 1 | Baseline: 2016/2017 | [7 empty] | Assumptions and AATF operational standards of measurements
Increased adoption of commercialized agricultural technologies by farmers in Sub-Saharan Africa | Number of households using agricultural technologies accessed or developed through AATF projects (TAAT Maize 46,875 tonnes = 1.875Million households ; Cowpea 21,000 Households ; TELA 200 tons = 8,000 farmer households , Striga 3250 tons = 130,000) | 226,000 Farmer Households | Planned | 345000 | 575000 | 530000 |  | 302% | In total, 16003.85 tons of certified seed were supplied to the farmers in relation to the targeted supply of 5,300 tons (see performance indicators). The total seed supplied was sufficient to reach about 1,600,385 households. The seeds were distributed 100% through Seed Companies, Agro-dealers and government input programmes. Below is a summary a)TAAT Maize - A total of 15,528 tons of TAAT Maize products was sold/distributed to farmers in Kenya, Uganda,Tanzania, Zambia , Zimbabwe and Nigeria . This translates to about 1,608,800 households. The use of government imput programs and the accelerated allowed TAAT Maize Project to reach more farmrers than initially planned . b) TELA- 82tons of transgenic seed was sold in South Africa. Translating to 8200 households reached. c) WEMA - A total of 293.85 tons of TEGO seed was sold Kenya,Tanzania and Uganda . This translates to about 29, 385households. d) STRIGA -A total of 100 tons of IR seed was sold by NASECO In Uganda . This translates to 10,000 households. | 1. AATF will be able to identify and access appropriate technologies for dissemination to SSA farmers 2. AATF will be able to identify and maintain partners for production, promotion and stewardship of the technologies it disseminates 3. AATF will be able to identify and reach farmers that are willing and able to adopt the technologies it disseminates 4. AATF will be able to effectively adopt the mechanization services
| Output Indicator 2.2 |  | Achieved | 228663+300,700 | 631600 | 1600385
| Primary Outcome Indicator 2 | [8 empty] | Operational standards of measurement 2SKgs of seed produced cultivates 1 Hectare of land One household averagely cultivates I hectare of land Its assumed that each household comprises of an average of 2 smallholder farmers
| Number of mechanization operations done (CAMAP and Agridrive 78,150; TAAT Cassava 1,200) | 3500 Operations | Planned | 7500 | 11450 | 17550 |  | 78.27% | A total of 13,736 operations were done in Nigeria, Uganda, Zambia . This translates to about 4,579 farmers . The operations can be dissaggregated as follows ; a) Cassava Mechanization Project (CAMAP) contributed about 2599 Operations ( Uganda 550 and Zambia 2009) b) CAMAP /Agridrive in Nigeria performed a total of 11,177 operations which is more than 80% of the total mechanization operations.
|  |  | Achieved | 4882 | 10426 | 13736
Source of data: Production and sales records , mechanization request sheet , farmer lists
Objective 1: Diversify agricultural technologies accessed for use in SSA |  | Baseline:2016/2017 | Targets and Achievements | 2017/2018 | 2018/2019 | 2019/ 2020 |  | 19/20 Percentage achievement | Narrative | Assumptions
Intermediate Outcome 1: Increased deployment of diverse improved seed-based agricultural technologies
Immediate Outcome 1.1 Increased availability, access and release of diverse agricultural technologies | Indicator 1.1.1 | [8 empty] | 1. AATF will be able to identify and access appropriate technologies for dissemination to farmers in Sub Saharan Africa . 2. AATF will be able to identify and access products and/or varieties of suitable markets for the technologies it disseminates
| Number of new agricultural technologies accessed targeting agricultural productivity, nutrition and post harvest loss | 8 technologies | Planned | 2 | 1 |  |  | 0 | AATF continue to put mechanisms in place to access new technologies in the impact areas . Below are some of the activities around the focus areas ; a)Agricultural productivity and Stress Management :AATF is exploring discussions with ICRISAT on available drought tolerant sorghum germplasm. b) Nutrition During this period ,AATF has been having discussions with Corteva for Biofortified Sorghum and also held negotiations with IRRI on High iron and zinc rice. Discussions with Corteva and IRRI are still ongoing. Addionally ,AATF is currently working with Tanager to exploring nutrition sensitive approaches to guide on the overall strategic positioning of “nutrition” in line with its expectations for the strategy. c) Post harvest management: AATF is also on processing and value addition in cassava with CLAYUCA who have since shared a quotation of the cassava flour processing plant with AATF.
|  |  | Achieved | 1 | 0
Indicator 1.1.2
| Number of products/varieties accessed | 10 products/varieties | Planned | 20 | 109 | 150 | 279 | 113.3% | Seeds2B Project/ PASTA: Ghana 19 (2tomatoes, 7 onions); Malawi –113 (41 soybean, 31 groundnuts,8 cowpea ,7 pigeon pea ,26 tomatoes). Uganda 32 (23 soybeans, 9 tomatoes) Zimbabwe 6 (Soybean)
|  |  | Achieved | 89 | 62 | 170 | 321
Indicator 1.1.3
| Number of Products/varieties developed | 53 products/varieties | Planned | 5 | 10 | 20 | 35 | 130% | A total of 26 varieties developed TELA 13 {13 – 8BT & 5 stack); Hybrid Rice 11, Cowpea 2
|  |  | Achieved | 20 | 20 | 26 | 66
Indicator 1.1.4
| 1.3 Number of Products/varieties released | 23 products/varieties | Planned | 3 | 10 | 10 | 23 | 180% | A total of 18 varieties were released during the reporting period : WEMA/ Drought TEGO (3) varieties, Cowpea: PBR Cowpea 2 varieties released TELA 2, Hybrid 2, TAAT Maize 6, Seeds 2B 3 (Groundnuts 2, 1 soybean )
|  |  | Achieved | 5 | 13 | 18 | 36
Immediate Outcome 1.2 Increased awareness and demand of diverse seed based agricultural technologies | Indicator 1.2.1 | [8 empty] | 1. AATF will continue to maintain and attract partnerships for delivery of its goal 2. Farmers and other stakeholders are willing to learn more about AATF technologies
| Number of farmers participating in AATFs agricultural education sensitization and outreach activities (demos, field days, trainings, workshops etc.) (Hybrid Rice 32,000; NEWEST 1,000; COWPEA 20,000; Seeds2B 20,000; TELA 10,000; TAAT Maize 120,000; OFAB 200,000) | 11,300 smallholder farmers | Planned | 55000 | 62000 | 70000 | 187000 | 48.99% | TAAT Maize 10,084 , Quali Basic Seed 17,306, Seeds2B 171 , TELA 43 , Hybrid Rice 232, GATES 178, Cowpea 5,920, OFAB 300, NEWEST 60 . Recent COVID 19 restrictions on movement largely affected the implementation of this activity for all AATF projects leading to the low performance against our annual target
| Indicator 1.2.2 |  | Achieved | 14612 | 42101 | 34296 | 91009
Indicator 1.2.2
| Number of other stakeholders (excluding farmers) engaging with AATF through AATF training workshops, seminars, outreaches, advocacy meetings | 563 Stakeholders | Planned | 500 | 700 | N/A | 1200 | N/A | These indicator has been merged with indicator 3.3.1 on value chain actors .
|  |  | Achieved | 563 | 6465 |  | 7028
Source of data: Licence agreements ,activity participation lists , training records
Intermediate Outcome 2: Increased deployment of mechanization, nutrition and digital agricultural technologies |  | Baseline:2016/2017 | Targets and Achievements | 2017/2018 | 2018/2019 | 2019/ 2020 |  | Percentage achievement | Additional information and Comments | 1. AATF will be able to identify and access mechanization, nutrition and digital agricultural for dissemination to SSA farmers 2. AATF will be able to effectively adopt the use of digital platforms in delivering on its mandate
Immediate Outcome 2.1 Increased scale out of nutrition enhancing agricultural technologies. | Indicator 2.1.1
| Number of nutrition-based technologies being deployed by AATF | 1 nutrition technology | Planned | 0 | 0 | 1 | 1 | 0% | AATF is endevouring to have at least one new technology deployed on nutrition before 2022. During this period ,AATF has been having discussions with Corteva for Biofortified Sorghum and also held negotiations with IRRI on High iron and zinc rice. Discussions with Corteva and IRRI are still ongoing. Addionally ,AATF is currently working with Tanager to exploring nutrition sensitive approaches to guide on the overall strategic positioning of “nutrition” in line with its expectations for the strategy.
|  |  | Achieved | 0 | 0 | 0
Achieved
Immediate Outcome 2.2 Increased awareness and uptake of mechanization and digital solution models. | Indicator 2.2.1
| Number of farmers aware of mechanization services by AATF (engaged through training workshops, seminars, outreaches, field days etc.) | 450,000 smallholder farmers | Planned | 550000 | 650000 | 1100000 |  | 59.71% | In the reporting period, the project reached a total of 656,783 farmers with mechanization information. The farmers reached were repeat farmers and no new farmers were reached as the COVID-19 restrictions on movement largely affected the implementation of this activity by CAMAP.
Achieved
|  |  | Achieved | 450000 | 656783 | 656783 | 1763566
Indicator 2.2.2
| Increased number of digital platforms used by farmers | 1 (One) ICT platform | Planned | 0 | 1 | 2 |  | 150% | Accessed the Samawati Compliance Notebook App for AATF Projects and the Artificial Intelligence based Tractor Hiring App for Agridrive Limited. Follow ups have also been made with Kurai on the drone technology- AATF will partner with Agridrive Ltd to commercialize the use of agricultural drones in data collection, validation, and analysis for decision making.
Achieved
| Increased digital platforms used by farmers | 2 ICT platforms | Achieved | 0 | 1 | 3 | 4
Indicator 2.2.3
| Number of farmers linked to AATF technologies using digital solution platforms | 5,000 smallholder farmers | Planned | 5000 | 15000 | 25000 | 45000 | 53.33% | AATF continued to link farmers through CAMAP and TAAT Projects . The 13000 farmers were contuining farmers and no new farmers were linked during the reporting period. The activity was largely affected by budget cuts for the TAAT Maize project and the activity was pushed to phase 3 .
|  |  | Achieved | 5000 | 8000 | 13000 | 26000
Source of data: Activity lists, farmer records, Digital platforms in use, digital data
Objective 2: Accelerate commercialization of agricultural technologies for improved farmer livelihoods |  | Baseline: 2016/2017 | Targets and Achievements | 2017/2018 | 2018/2019 | 2019/ 2020 |  | Percentage achievement | Narrative | Assumptions and AATF operational standards of measurements
Intermediate Outcome 3: Improved service delivery systems for agricultural interventions.
Immediate Outcome 3.1 Increased number of viable business models and approached for commercialization | Indicator 3.1.1 | [8 empty] | That the use of extension services continues to be an effective and efficient delivery approach
| Number of business models for licencing, production, distribution to ensure quicker and faster technology adoption | 2 models | Planned | 1 | 0 | 1 | 2 | 200% | Business Licensing models for TELA and PBR Cowpea finalized. Plans are underway to license the newly registered Seeds2B varieties.
|  |  | Achieved | 1 | 1 | 2 | 4
Immediate Outcome 3.2 Strengthened technology dissemination delivery networks along the value chains | Indicator 3.2.1
| Number of extension agents trained as TOTs | 70 extension agents | Planned | 85 | 85 | 90 | 260 | 694.4% | AATF continuous to work with extension agents through the CAMAP, TELA, OFAB, Cowpea and TAAT Maize program and Seeds2B . During the reporting period , a total of 625 extesnsion agents worked witn AATF (TELA 8, CAMAP 15, PBR Cowpea 592, Seds2B 10) Target for this activity was overachieved as a result of new PBR Cowpea project. Targets will be revised accordingly. |  | 1EDR124Zf
|  |  | Achieved | 85 | 124 | 625 | 834
Immediate Outcome 3.3 Strengthened technology dissemination delivery networks along the value chains | Indicator 3.3.1
| Number of value chain actors that AATF works with to create market systems supportive of agricultural development. | 1200 value chain actors | Planned | 0 | 5000 | 8000 | 13000 | 87.69% | AATF worked with a total of about 7,015 value chain actors who include seed companies, agrodealers, seed producers, grain traders, processors, transporters etc to strengthen technology dissemination networks. The indicator was merged with indicator 1.2.2
|  |  | Achieved | 1200 | 920 | 7015 | 9135
Source of data: Commercialization reports ,training lists ,collaborative agreements | Source of data : Licence agreements ,list of released products and /or varieties
Intermediate Outcome 4: Improved service delivery systems for agricultural interventions. |  | Baseline: 2016/2017 | Targets and Achievements | 2017/2018 | 2018/2019 | 2019/ 2020 |  | Percentage achievement | Narrative | Risks Economic instability, risk and insecure conditions for investing: Frequent shifts in government policy on linking smallholders to markets in SSA on matters such as trade, storage and movement of grains, and price controls deterring investment. Institutions involved in technology adoption may not take on outputs from ATTF Policies to scale Mitigation AATF will encourage farmers to form farmer associations, groups and cooperatives when dealing with other actors in supply and value chains. This helps them to aggregate sales, input purchase, loans and technical assistance. This will not only help farmers to economize on transactions costs, but also, they should give the group greater bargaining power, especially when facing those with monopoly power. They can also be a means by which farmers make their voice heard within policymaking. Policy advocacy campaign
Immediate Outcome 4.1 Increased market linkages between farmers and off-takers | Indicator 4.1.1
| Number of farmers linked to off-takers (CAMAP 55,000; TAAT Maize 1,400) | 18,000 smallholder farmers | Planned | 22000 | 26000 | 55000 | 103000 | 166.3% | AATF’s new strategy has increased market linkages between farmers and off-takers. During the period a total of 91,470 farmers were linked to offtakers through the TAAT Maize Project
|  |  | Achieved | 18000 | 61033 | 91470 | 170503
Immediate Outcome 4.2 Increased use of harmonized frameworks for release and registration and cross-border marketing of agro-inputs and agricultural commodities. | Indicato 4.2.1
| No. of technology policies, laws, regulations and standard operating procedures harmonized across countries and regions | 0 policies | Planned | 0 | 2 | 2 | 4 | 200% | CFT permits were granted in Kenya, Nigeria, and Ethiopia. Additionally, EIA approvals were granted in Mozambique
|  |  | Achieved | 0 | 1 | 4 | 5
Source of data: Farmer lists/farmer group records ; Analysis reports on policy frameworks | Source of data : Licence agreements ,list of released products and /or varieties
Objective 3: Create an enabling environment for increased uptake and use of agricultural technologies |  | Baseline:2017/2018 | Targets and Achievements | 2017/2018 | 2018/2019 | 2019/ 2020 |  | Percentage achievement | Narrative
Intermediate Outcome 5: Improved Regional and national agricultural policy and agribusiness environment
Immediate Outcome 5.1 Improved policy and institutional frameworks for commercialization and adoption of innovative technologies | Indicator 5.1.1
| Number of countries with functional biosafety systems | 0 countries | Planned | 0 | 1 | 1 | 2 | 100% | This included the passage of the Plant Variety Protection law and Regulations in Malawi; the passage of Seed Law in Liberia, and the approval of Guidelines for Public Participation in review of applications for general release of GM crops in Ethiopia
|  |  | Achieved | 0 | 2 | 1 | 3
Indicator 5.1.2
| Number of polices/legislations passed/amended to aid testing and commercialization of improved technologies in target countries | 2 policies/legistlations | Planned | 2 | 3 | 5 | 10 | 80% | At regional level, notable milestones were witnessed regarding implementation of COMESA regionally harmonized seed regulations with Egypt becoming the 8th Country to fully domesticate the regional instrument. In other regional economic block, efforts by AATF resulted in the finalization of regional quarantine pest list and commencement of development of Executive Regulations for Seed Import/Export in ECOWAS region; and the initiation of revision of pesticide registration laws/regulations by EAC
|  | 2 | Achieved | 2 | 2 | 4 | 8 | 66.67%
Immediate Outcome 5.2 Enhanced implementation of policies and regulations to support commercialization of innovative technologies. | Indicator 5.2.1
| Number of governments engaged on policy deliberations on commercialization of agricultural biotechnology/technologies | 0 governments | Planned | 0 | 6 | 6 | 12 | 150% | 9 (Biotech – KE, UG, TZ) Other – EAC BR & RW, Agra- ET, GH, MW& MOZ
|  |  | Achieved | 0 | 9 | 9 | 18
Indicator 5.2.2
| Number of governments indicating formal commitments to implement policy, regulatory reforms for technology deployment | 0 policies | Planned | 0 | 3 | 6 | 9 | 33.33% | Ongoing discussion on legislative changes on EMCA in Kenya for TELA Project . Preliminary Discussion on possibility of ER Dossier to prop the process in Tanzania
|  |  | Achieved | 0 | 3 | 2 | 5 |  | Preliminary Discussion on possibility of ER Dossier to prop the process in Tanzania
Indicator 5.2.3
| Number of polices/legislations passed/amended to aid testing and commercialization of improved technologies in target countries | 2 policies | Planned | 2 | 3 | 2 | 7 | 100% | Triggered by earlier initiatives by the TAAT Policy, Egypt managed to move to full domestication, approval of Guidelines for Public Participation in review of applications for general release of GM crops in Ethiopia
|  | 2 | Achieved | 2 | 1 | 2 | 5
Output 5: Robust outreach awareness, education and advocacy efforts to create a more receptive regulatory and commercial environment for agricultural technology advances. | Output indicator 5.3.1
| Number of beneficiaries reached through advocacy, outreach and regulatory interventions that will bolster enhanced capacity for private sector and seed systems in general. | 500,000 beneficiaries | Planned | 800000 | 2000000 | 2000000 | 4800000 | 87.8% | Most of the numbers were reached through media. The media consultant is providing a basis for the share of reach AATF can claim. In the mean time it is estimated that AATF reaches about 2% of the total media coverage for the specific media channel.• Social media reach 509,457 (no. of people who have viewed content) Press MEDIA reach – 1,4400,000
|  |  | Achieved | 853100 | 1681905 | 1756019 | 4291024
Source of data : Memorandum of understandings , Engagement agreements actual legislation /policy documents , regulatory approvals ,media analysis | Source of data : Licence agreements ,list of released products and /or varieties
Cross cutting focus areas for the organization |  | Baseline:2017/2018 | Targets and Achievements | 2017/2018 | 2018/2019 | 2019/ 2020 |  | Percentage achievement | Narrative
Cross Cutting Output 6: AATF positions itself as a credible and responsible go to organization for transfer of agricultural technologies | Output indicator 6.1
| Number of requests for partnerships; specialist technical expertise/ experience and knowledge sharing on agricultural technology transfer among key targets. | 15 requests | Planned | 15 | 25 | 30 | 70 | 76.67% | 5 requests for partnerships/collaboration; 1 requests for specialist technical expertise/experience 4 requests for knowledge sharing; 13 request for specific technology. Details will be provided on the AATF AS A TO GO organization report .
|  |  | Achieved | 33 | 47 | 23 | 103
Output indicator 6.2
| Number of new partnerships/collaborations/strategic alliances actualized to enhance the quality of AATF interventions | N/A | Planned | 0 | 7 | 8 | 15 | 50% | AUDA-NEPAD signed off on and operationalised, Partnership with Tanager on Gender and Nutrition, EAC; NEARLS, CARD partnership confirmed as steering committee member recommendation to General Meeting
|  |  | Achieved |  | 3 | 4 | 7
Output indicator 6.3
| Increase (quality and quantity) in number of mentions in both traditional and social media and drive stakeholder engagement (retweets, likes, clicks, views and responses) to support organization goals | 15000 | Planned | 20000 | 25000 | 37500 | 82500 | 243.8% | Facebook: 77,658; Twitter: 13, 494; Press 610 The social media increase is attributed to the media buying activities that gave the brand maximum visibility and engagement. TOTAL - 91762
|  |  | Achieved | 12388 | 31575 | 91442 | 135405
Output indicator 6.3
| Knowledge products developed and disseminated (Impact stories, books and booklets, journal articles, policy briefs, conference proceedings published, book chapters | 74 | Planned | 74 | 12 | 15 | 101 | 80% | Revised AATF brochure; FAQ Ke TELA; High level BoT 2019 report; 3 leaflets – (AATF in Realignment with COVID; TAAT Policy 2 leaflets) AATF brochure; Poster - TAAT maize; AHYRA leaflet; I Blog by ED, Proceedings of High Level Policy Meeting, AATF 2019 Annual Report
|  | 14 | Achieved | 14 | 15 | 12 | 41
Cross Cutting Output 7:Appropriate agricultural technologies accessed and licenced for sustainable use by small holder farmers in target countries | Output indicator 7.1
| Number of trademarks/patents/PVP filed in project countries | 1 trademark | Planned | 2 | 2 | 4 | 8 | 100% | 4 Trademarks renewed in Tanzania (WEMA, TEGO, Drought TEGO and TELA)
|  |  | Achieved | 2 | 2 | 4 | 8
Output indicator 7.2
| Number of sub-licenses negotiated and signed with partners | 12 | Planned | 39 | 20 | 18 | 77 | 61.11% | Developed 3 commercialization Licensing Strategies for (Hybrid Rice, Seeds 2B and PBR Cowpea)​ Negotiated and drafted Commercialization License Agreements (WEMA & TELA) in 2019 .. ​6 Commercialization Sub-licenses drafted and finalized with Seed Companies in 2020
|  | 39 | Achieved | 39 | 10 | 11 | 60
Cross Cutting Output 8: AATF is a well managed, efficient and effective organization. | Output indicator 8.1
| Percentage of review/audit/evaluation recommendations implemented. | 85% | Planned | 85% | 90% | 100% |  | 100% | All the 3 (three) findings from prior year audit fully implemented
|  | 77% fully and 30% partially | Achieved | 77% fully and 23% patially | 67% | 100%
Output indicator 8.2
| Staff turn over rate (below 10%) | 5% | Planned | 5% | 5% | 5% |  | 120% | Staff turnover rate is at 6% which is an increase from the expected rate of 5%
|  | 23% | Achieved | 5% | 2% | 6%
Source of data: Memorandum of understandings, media analysis, Audit reports, HR files | Source of data : Licence agreements ,list of released products and /or varieties

## Performance Indicators 20192020
Performance Related Funding Indicators for Phase III of DFID support to the African Agricultural Technology Foundation.
Notes
Performance related funding will only be considered if Logframe indicators are achieved.
Peformance Areas | 2016/2017 |  | 2017/2018 |  | 2018/2019 | 2018/2019 | 2019/2020 | 2019/2020
Organizational Behaviors | Indicator | Achieved | Indicator | Achieved | Target Indicators | Achievements | Target indicators | Achievements
Commercial/Private Sector Focus | At least 50% which is 16 out of 31 (16 Internationally Recruited Staff (IRS) and 15 Nationally Recruited Staff (NRS) of the professional staff trained in commercial approaches in agricultural technology commercialisation. At least two business models developed and tested by end of 2017 | 28 Staff Trained in Commercial / Private Sector Focus. (7 Staff members trained in Quality Management Systems, 9 in KEPHIS Private Seed Certification and 12 in Product Stewardship and Commercial Seed Production) | Enhanced capacity of seed companies in the commercialization pathway of AATF products : Number of companies engaged ; trained and implementing the standard operating procedures. | Under the WEMA, TELA®, StrigAway, Seeds2B, Hybrid Rice, MLN, QBS and TAAT projects a total of 82 seed companies in 13 countries (5 countries in East Africa; 5 in Southern Africa and 3 in West Africa) were engaged In addition, some companies where visited in the field to monitor the implementation and compliance with the general seed stewardship requirements. | 1. Number of seed companies engaged on seed production and overall business management through licensing and contract | AATF continued strategic engagements with private seed companies and conducted capacity building in several areas. A total of 106 companies where reached for various interventions.. During the current reporting period, three seed companies (1 Kenya; 1 Tanzania and 1 Uganda), were provided with technical backstopping services under the WEMA project, Seed production technical backstopping support was provided to one seed company in Uganda on the Striga Way Technology and eight seed companies in Kenya were trained on the use of RDKs to detect MLN in seed crops. Further, 48 seed companies in Kenya, Tanzania and Ethiopia were visited and information was gathered using the Open Data Kit (ODK) tool on the status of MLN in seed production fields, application and effectiveness of MLN management practices, effectiveness of MLN rapid diagnostic kits and gaps to galvanize further action to improve MLN disease management. To ensure compliance under the TELA® maize (transgenic) project; Six Seed Systems and Stewardship Leads (SSSLs) from 5 TELA countries were taken for a learning visit in Brits, South Africa to have field experience in the production of transgenic hybrids and the seed processing. Such exposure will have the SSSLs to provide backstopping services once transgenic are approved for commercialization in respective countries. In addition, six SSSLs were trained in TELA seed production research protocols. This was to build their capacity to conduct research on seed parents once transgenic approvals are obtained and SSS TELA team in Ethiopia were trained on Excellence Through Stewardship (ETS) in Addis Ababa. This was again further preparation for sustainable deployment of transgenic hybrids when they get approved in the country. The TAAT Maize Compact led by AATF 24 companies were engaged in Kenya, Tanzania, Uganda, Zambia and Zimbabwe to license products for the TAAT Maize Compact. The TAAT maize program also deployed Fortenza Duo (FD) seed treatment chemical in Zambia and Zimbabwe to protect the maize crops against fall armyworm (FAW). 24 seed companies were engaged in Zambia and Zimbabwe to treat and distribute Fortezza Duo (FD) treated seed to farmers to protect crops against fall armyworm (FAW). The seed companies who commercialized FD were trained on dosage, mixing of the chemical, machine calibration and stewardship requirements for sustainable use of the seed treatment chemical. AATF is responsble for establishing demos for farmers through seed companies under the QBS project to stimulate demand for Foundation Seed. 20 companies were engaged to establish aorund 1,342 demos | 1. Number of seed companies engaged on seed production and overall business management through licensing and contract | Through various projects AATF managed to engage a total of 130 seed companies in East Africa (83), Southern Africa (38), West Africa (6) and Central Africa (3). Due to the COVID-19 pandemic some of the engagements from Q2 of 2020 were done virtually. Below is the type of engagement per project 1) WEMA project – licensing of DroughtTEGO hybrids in WEMA and outside WEMA countries and backstopping on seed production 2) TELA – licensing of TELA hybrids in South Africa, capacity building and technical backstopping on seed production. 3) TAAT – seed production activities, field demos and field days on climate smart maize varieties and complementary technologies to maximize productivity 4) Striga (IR maize) – seed production activities in Uganda 5 ) PASTTA – variety testing and official release for commercialization 6) Hybrid rice – technical backstopping and training on seed production 7) QBS – new maize hybrids promotion for adoption by farmers through demos and field days 8) MLN – Backstopping to ensure MLN free seed production, deployment of MLN rapid diagnostic kits and MLN tolerant varieties To ensure complience for the TELA project ,visits were made on account management to eight seed companies in Mozambique in Nov 2019. Only two out of the eight sed companies visited, produce maize seed locally. The rest produce in other countries such as Malawi, Zimbabwe, South Africa and Zambia, and import their seeds into the country. Those that produce outside the country cited limited grower base and seed quality standards as the major reasons for producing seed elsewhere. Therefore, there is need to come up with a TELA seed production strategy for Mozambique. The National Seed Authority and APROSE (Portuguese Acronym for Association for the Promotion of the Seed Sector) were also visited during the period to learn more about the seed sector to guide the development of transgenic seed system using TELA® hybrids in Mozambique
[5 empty] | 2.The number of seed companies with capacity enhanced and audited for compliance – through seed production and stewardship training and retooling, etc. |  | 2.The number of seed companies with capacity enhanced and audited for compliance – through seed production and stewardship training and retooling, etc.
|  |  | Set up and operationalize a commercial arm for AATF's sustainability (How many are set up and how many are functioning) | AATF established established Agridrive, which is a private sector driven alternative model of accelerating commercialization of agricultural technologies. | 3. Operationalization of Agridrive, tracking the folowing indicators (2019 to act as baseline) 1.Number of mechanisation operations done under Agridrive 2.Percentage increase in sales revenue under Agridrive 3.Percentage increase in profit under agridrive | Agridrive Limited performed well during the reporting period. As at the 25th of September 2019, at total of 9,077 ha (93.1%) out of the target of 9,750 ha of operations had been commited from the farmers. The target might be surpased considering we still have two new orders comimg in.The financial target for 2019 is to have net revenues of about $443,586. A total of $425,263 representing 95.8% has been committed as of the 25th of September 2019. This represent a 149% increase in revenue from last year. Agridrive Limited is expected to break even by year 2020 | 3. Operationalization of Agridrive, tracking the folowing indicators (2019 to act as baseline) 1.Number of mechanisation operations done under Agridrive 2.Percentage increase in sales revenue under Agridrive 3.Percentage increase in profit under agridrive | Agridrive Limited managed to undertake all its activities with revenues generated from its operations without any money coming from AATF. A total of 16,550 mechanisation operations were targeted for 2020. By the first week of September 2020, a total of 11,177 operations had been completed representing 60.1%. However, work is progressing well, and we expect to surpass 16,000 ha by the end of December 2020 representing 91.1% of the target. The financial target for 2020 from mechanisation was to have a net revenue of about $911,000.00. By first week of September 2020, Agridrive had successfully generated a total revenue of $1,765,580 (representing 194% of target). Of this amount, a total of $1,597,307.00 has already been paid to Agridrive representing 90.5% of the amount generated in 2020. This figure is also expected to increase as work is still underway until the end of December 2020 when Agridrive’s financial year ends.
[7 empty] | Operationalization of QBS , tracking the folowing indicators 1.Volume of seeds produced 2.Percentage increase in sales revenue 3.Percentage increase in profit | Note reuslts are tracked on a yearly basis so these resutls are Jan - Dec. Sales year to date is 19.5t Additional 85t is estimated to be sold with confirmed orders, which make the latest 2020 estimated result 104.5t compared to the target of 115t.This year QBS has expanded its business portfolio to ramp up revenues while foundation seed sales increases. This is on the condition that it does not divert its focus on the core foundation seed business. This is for example to produced certified seed on behalf of seed companies. QBS has also tried out the foundation seed production of beans. Sometimes there is also a need to clean the pre foundation seed to ensure quality in the process, which can also be seen in the table. Production has been a total of 455.4mt against a target of 402.4mt.
Gender and Inclusion | Gender Specialist hired on short term assignments to train staff on Gender Mainstreaming. All concept notes and proposals have gender disaggregated data and AATF Gender Focal persons identified and spearheading the gender mainstreaming across all AATF activities. | Grace Muinga has been appointed as the AATF contact point for Gender related issues in AATF. Training on Gender mainstreaming is being organzed for all AATF staff in October 2017. The training will be done by AWARD. | Staff/Partner Training Modules on Gender Mainstreaming in place and being implemented. Institute gender analysis as a standard part of AATFs problem analysis | A total of 36(13 female and 23 males) AATF staff were trained on Gender Mainstreaming on the 25th to 27th September 2018 . The training was meant to to equip them with a deeper and practical understanding of gender concepts as well as enhance their skills in making programs and institutions more gender responsive. Plans are underway to train pratners on gender mainstreaming based on the revised gender strategy. | Partner training on gender mainstreaming modules / Mainstreaming gender at AATF | Gender mainstreaming and inclusion continues to be an integral part of AATF. Since the approval of gender strategy (2018-2022), AATF has made significant strides in ensuring that gender is mainstreamed throughout the life project cycle. Building from the gender staff training September 2018 two major changes have been evident; 1) the collection of gender disaggregated data from projects; realization of gender inequalities by staff within the countries of operations. This awareness and collection of gender disaggregated data is a major factor in conducting further analysis for effective project implementation. AATF intends to conduct gender analyses from the data collected. This is imperative in mainstreaming gender. To ensure consistency in implementing the Gender strategy, AATF has planned to conduct gender training for its board members to sensitize them on the importance of gender mainstreaming and highlight their role in it. | Mainstreaming gender at AATF | As AATF continues to mainstream gender, a SharePoint page has been created to facilitate sharing of information on the same with staff. A gender training manual is also under development to facilitate self-paced learning for staff and partners. This is envisioned to transition into an e-module that will be available to partners for learning. AATF has also embedded gender dynamics in its Socio-Economic Studies like the recently concluded NEWEST Rice Market Study. One of the key findings from this study was on the emphasis to take on a value chain approach in implementing projects where needs of men and women rice farmers are considered based on the gender differences. AATF has also developed a concept note with an objective that centered on women empowerment. This concept note titled Strengthening Cassava Value Chain Through Public Private Partnerships (PPP) For Efficient Production and Natural Resource Management In Zambia, Nigeria, Uganda And Ghana was submitted to USAID for funding but was unsuccessful. The team is exploring other funding opportunities. AATF Board has nominated Ms Dahlia Garwe as the gender champion to support the organization on providing strategic guidance on the gender strategy and linking AATF with gender related resource mobilization opportunities.
Business Plan and strategy | AATF strategy Finalised by August 2017 and the drafting of the Business Plan underway in October 2017 | Work on the strategy is currently ongoing with first brainstorming done on the 7th and 8th of June 2017. Second brainstorming done on the 11th to the 13th of September 2017. Draft report has been shared with the Board for their comments. | Strategy Implemnation Plan and Business Plan Implementation being implemented and progress Report being shared | The Corporate Strategy with its implementation plan for the first year was approved in May 3rd, 2018 as well as a progress on its implementation was reported at that board meeting as well as in the virtual Board meeting in July. Additionally ,the the AATF Business 2018 – 2022 has been developed to outline how AATF will exploit emerging opportunities and harness its expertise in agribusiness to position agriculture in the global macro environment in SSA. | Implementation of the AATF Business Plan and Strategy, focussing on achievement of the institutional framework and key deliverables in the business plan. | The implementation of the AATF Business 2018 – 2022 is now in full swing after its approval by the board of trustees in 2019. The branding of AATF took a center stage of the transformed AATF. Implementation has also focused on how to maximize impact through the development and socialization of the results framework and the impact areas as well as the collection of data around the new results framework. The progress is shown in how project managers report internally on alignment with the strategy and the results framework. There has been brainstorming sessions on building a balanced project portfolio to ensure new projects are initiated under digital agriculture and the nutrition and post-harvest technologies impact areas. Two successful workshops were held to the discuss the above and several recommendations are now being pursued. In addition, in the digital agricultural area, AATF is pursuing the digitization of seed inspection and quality control through the Seed Assure Alliance. AATF has also intensified its effort in commercialization of agricultural technologies through the commercialization strategy, for example testing and expanding approaches under TAAT, the gazettement of AATF seed inspectors and closer alignment with Country Government for the introduction of new technologies, for example in Rwanda, Senegal and Togo. In addition the purpose of the formation of AHyRA (The Alliance for Hybrid Rice in Africa) is to accelerate the commercialisation of Hybrid Rice in the region. Further, the continued work and progress on AATF’s commercial entities (QBS and Agridrive Limited) is providing overwhelming positive reports. AATF is leveraging its company incubation experience for other opportunities. | Implementation of the AATF Business Plan and Strategy, focussing on achievement of the institutional framework and key deliverables in the business plan. | As part of continuing systems development, AATF focused on delivering appropriate technologies to farmers and deliver results by ensuring inclusive collaboration with partners. By supporting the agenda’s in AATFs strategy 2018-2022 and just two and half years into its five-year strategy, AATF has showed commitment on its interventions and has directly reached 3.2 million smallholder farmers and an indirect reach of about 4.9 million farmers through advocacy, outreach and policy interventions since 2018. During the reporting period , a total of 3,360,983 small holder farmers were reached (1,604,964 direct reach and 1,756,019 indirectly reached through advocacy efforts)
Monitoring ,Evaluation and Learning | External Recruitment Agency engaged by March 2017. Senior M&E Officer recruited by May 2017. The AATF strategic road map for M&E and impact evaluation developed. AATF staff trained on current evaluation and impact assessment approaches by CLEAR (Inhouse AATF Training Organised) by October 2017 | M&E Officer are recruited in July 2017. Two training on Impact Evaluation by CLEAR ( 25 AATF Satff) and J-Pal (4 Staff) were done in July 2017. An Impact Evaluation Seminar by Dr Speilman done on the 27th of June 2017. | AATF has commissioned at least one independent evaluation | AATF has initiated an independed evaluation for the Open Forum for Agricultural Biotechnology (OFAB) project focusing on the OFAB’s desired outcomes and impacts in enhancing understanding and acceptance of agricultural biotechnology and building of an enabling environment for decision making and generating lessons and trends with regards to biotechnology adoption. The Evaluation is projected to be completed by March 2019. | Conduct at least two impact evaluations/assessments and at least 1 indepth assessment. | 1) AATF has initiated an independed Impact evaluation for the Striga in Control Project. The impact evaluation process will include conducting a quick analysis to find out if the project has been able to reduce striga weed infestation and identify changes needed to enable fulfilment of the potential eradication of striga in maize in Kenya Uganda and Tanzania . This is done through Tegemeo Institute of Agricultural policy and Development, Egerton University. 2) An Evaluation is also being conducted by BMGF for the Open Forum for Agricultural Biotechnology (OFAB) project focusing on the OFAB’s desired outcomes and impacts in enhancing understanding and acceptance of agricultural biotechnology and building of an enabling environment for decision making and generating lessons and trends with regards to biotechnology adoption. 3) A market analysis for PASTA Project was conducted and finalized in March 2019 4) AATF planned to conduct an indepth assessment for the TAAT Policy project in about 8 countries but due to budget cuts by AfDB ,this activity was postponed to TAAT II . As soon as the reports from the the impact studies have been finalized , a lessons sharing workshop with be held to synthesize the findings from the evaluations ,institutionalize the recommendations and use them for decision making . | Conduct at least two impact evaluations/assessments | AATF initiated an independent impact evaluation for the Water Efficient Maize for Africa (WEMA) project. The process of selecting a consultant is underway. An evaluation for the Cassava Mechanization and Agro-processing project (CAMAP) project was also initiated and completed .
[5 empty] | Sharing relevant evaluative information through an appropriate use friendly mechanism for the collection and dissemination of lessons learned to generate informed programmatic decisions (At least 2 learning workshops) |  | Sharing relevant evaluative information through an appropriate use friendly mechanism for the collection and dissemination of lessons learned to generate informed programmatic decisions (At least 2 learning workshops) | AATF also conducted virtual meetings to share and analyze findings from the Striga Impact Evaluation as well as the OFAB Evaluation .
Fund raising | AATF has raised $5M from new investor(s) | There has been progress in reaching out to new donors like GIZ, SIDA, JICA, Danida, SDC and also establishing relations with strategic partners for joint fundraising like COMESA where concepts note have been submitted to EC and JICA of 40 M, the University of Cambridge where there are plans for joint proposals and Agropolis where one proposal on sorghum and millet to FFAR unfortunately was un successful. We are also considering AGRA a strategic partner for funding and we are in the last stages of getting the first phase of funding for regulatory work. TAAT funding and the IFAD proposal which were anticipated to be approved this year are delayed and discussions still ongoing. Consequently there hasn't been any grants approved for any new donors in this reporting period, however we have had income approved of 18M over the reporting period. Please see RM Score Card attached for further progress in RM. | AATF has raised $5M from new investor(s) | AATF secured a contribution from TAAT of a total of 4.5M USD for one year. Contracts are for a three-year period where the yearly disbursement are dependent on performance. In addition, after a 2-year period of discussions with AGRA on policy interventions, AATF secured a one-year pilot phase grant of 250k USD. Hence AATF has two new investors as of this period. In addition, the new TELA project of 24M USD from BMGF was granted, which eased some of the financial constraints at the beginning of the period. As a total approximately 34M USD was secured for this period with 4.7M representing new donors. | Develop and submit at least 12 conceptnotes/ proposals for consideration | A total of 15 proposals and concept notes where submitted for consideration to a number of donors. (See RM Update attached) | Develop and submit at least 12 conceptnotes/ proposals for consideration | 19 concept notes/proposal was submitted. See porposal pipeline report. Attached
[5 empty] | Number of proposals funded (at least 3) | 5 proposals were funded (See RM update attached) | Number of proposals funded (at least 3) | 4 approved: PBRcowpea/TELA (considered as one collaborative agreement), USDA - Country Codex- support, Agridrive -Feed and Fodder production ALDDN project, Digital Twin Earth (DTE) Precursors Telespazio consortium
[5 empty] | Number of new donors (at least 2) | AATF received a total of 3 new donors (See RM update attached) | Number of new donors (at least 2) | European Space Agency (ESA), Sahel
[5 empty] | Amount raised from new donors (At least USD 2.5M) | USD 0.97M was received from new donors. (See RM Update attached) | Amount raised from new donors (At least USD 2.5M) | 1.7M+
Reach or scale -AATF Products | WEMA - 837T( Kenya 452T, Mozambique 300T, South Africa 51T, Uganda 31T, Tanzania 4T:- Distributed through 95% Seed Companies and Agrodealers and 5% AATF supported demonstrations) ; STRIGA - 200T(Kenya 100T, Uganda 70T, Tanzania 30T - Distribution Channel :- 90% Seed Companies & Agrodealers, 10% NGOs, Goverments) ; CAMAP - 5,000 households (4,150 Nigeria, 350 Zambia, 300 Uganda : Delivery channel is through private service providers and AATF through full cost recovery) | WEMA - A total 1,871.67 tons of WEMA seed was sold in with 400,95 tons being sold in Kenya and 4,5 tons in Tanzania, 386 tons in Uganda, 30 tons in South Africa, 100 tons in Mozambique and 930,31 tons in Zimbabwe. A total of 187,600 households were reached. All the seeds were distributed 100% through Seed Companies and Agro-dealers. STRIGA - A total 147,6 tons of IR Maize seed was sold in with 62,0 tons in Kenya and 85,6 tons in Tanzania. All the seeds were distributed 100% through Seed Companies and Agro-dealers. A total of 36,900 households (15,000 in Kenya and 21,400 in Uganda) were reached. CAMAP - A total of 3,150 households reached from October 2016 to September 2017 (2,685 households in Nigeria, 338 in Zambia, and 127 in Uganda) The delivery channel is through private service providers and AATF through full cost recovery. | WEMA - 1250T( Kenya 625T, Mozambique 250T, South Africa 187,5T, Uganda 125T, Tanzania 62,5T:- Distributed through 95% Seed Companies and Agrodealers and 5% AATF supported demonstrations) ; STRIGA - 250 T(Kenya 150T, Uganda 100T - Distribution Channel :- 90% Seed Companies & Agrodealers, 10% NGOs, Goverments) ; CAMAP - 4100 households (.100 Nigeria, 500 Zambia, 400 Uganda : Delivery channel is through private service providers and AATF through full cost recovery) | a)WEMA - A total of 1,572 tons of TEGO hybrids seed were sold – 702t in Uganda; 688t in Kenya; 96t in Tanzania; 75t in Mozambique and 11t in South Africa. In addition, 16 tons of TELA (transgenic) seed were sold to smallholder farmers in South Africa. In total, 1,588 tons of certified seed were supplied to the farmers surpassing the targeted supply of 1,250 tons by 27%. The total seed supplied was sufficient to cultivate a total of 63,520ha, reaching about 158,800 households (157,200 households with TEGO hybrids and 1,600 households with TELA hybrids). b) STRIGA -A total of 263 tons of IR seed was sold in 2018, which was 263 tons compared to 147 tons sold in 2017. In Uganda a total of 95 tons were sold and in Kenya 168 tons. The seed quantities achieved in Uganda and Kenya managed to surpass the target for 2018 of 250 tons by 5.2%. The total seed of 263 tons supplied was sufficient to cultivate about 164,38ha of land and reaching about 65,750 farm households . All the seeds were distributed 100% through Seed Companies and Agro-dealers. c) CAMAP - A total of 4822 direct mechanisation and 6300 indirect ( through partners ) in Nigeria translating to 3,707 ha of land interpreted to 3,707 households assuming a farmer does an average of 3 operations and planting at least an hectare of land . In Uganda, a total of 558 mechanisation operations were done covering 176 households and in Zambia, a total of 690 mechanisation operations covering 230 households were done . In total 4113 households benefited from CAMAP services | TAAT Maize 3000 Tons, WEMA -250 Tons, Striga 100 Tons: Distributed through 95% Seed Companies and Agrodealers and 5% AATF supported demonstrations , 10% NGOs, Goverments. CAMAP - 11,150 Mechanization operations (9750 Nigeria (includes Agridrive) ,700 Zambia , 700 Uganda) Taat Cassava : 300 Operations. Delivery channel is through private service providers and AATF through full cost recovery | In total, 6,316 tons of certified seed were supplied to the farmers relating to the targeted supply of 5,757 tons. The total seed supplied was sufficient to reach about 631,600 households. The seeds were distributed 100% through Seed Companies, Agro-dealers and government input programmes. Below is a summary. a)TAAT Maize - A total of 5,513 tons of TAAT Maize products was sold/distributed to farmers in Kenya, Uganda,Tanzania,Zambia and Zimbabwe. This translates to about 582,000 households. b) TELA- 18 tons of transgenic seed was sold in South Africa. Translating to 1800 households reached. c) WEMA - A total of 685 tons of TEGO seed was sold Kenya and Uganda. This translates to about 68,500 households. d) STRIGA -A total of 100 tons of IR seed was sold in Tanzania by NASEKO. This translates to 10,000 households. | 5300 tonnes (TAAT Maize , Cowpea , Households ; TELA , WEMA , Striga ) | In total, 16003.85 tons of certified seed were supplied to the farmers in relation to the targeted supply of 5,300 tons (see performance indicators). The total seed supplied was sufficient to reach about 1,600,385 households. The seeds were distributed 100% through Seed Companies, Agro-dealers and government input programmes. Below is a summary a)TAAT Maize - A total of 15,528 tons of TAAT Maize products was sold/distributed to farmers in Kenya, Uganda,Tanzania, Zambia , Zimbabwe and Nigeria . This translates to about 1,608,800 households. The use of government imput programs and the accelerated allowed TAAT Maize Project to reach more farmrers than initially planned . b) TELA- 82tons of transgenic seed was sold in South Africa. Translating to 8200 households reached. c) WEMA - A total of 293.85 tons of TEGO seed was sold Kenya,Tanzania and Uganda . This translates to about 29, 385households. d) STRIGA -A total of 100 tons of IR seed was sold by NASECO In Uganda . This translates to 10,000 households.

## AATF Logframe 5 year period
AFRICAN AGRICULTURAL TECHNOLOGY FOUNDATION LOGFRAME (2018-2022)
RESULT AREAS | PERFORMANCE INDICATORS |  | Targets and Achievements | [6 empty] | Risks /Asumptions and Mitigation
IMPACT | Impact Indicator 1 | Baseline |  | 2017/2018 | 2018/2019 | 2019/2020 | 2020/2021 | 2021/2022 | Cumulative
Transforming Livelihoods Through Innovative Agricultural Technologies to improve incomes and improve food security | Percentage increase of income of farmers using improved technologies | Annual Average (FAOSTAT 2016) Agricultural Income (crops) $100.3 | Planned | [5 empty] | 20% | Risks: High levels of price and income volatility for farmers are related to the market fundamentals of supply and demand intensified by other macro-economic variables, the broad political and legislative environment for farmers, and speculation on agricultural products. Mitigation: Encouraging farmers to using the appropriate technologies (e.g. by planting drought-resilient crop varieties or investing in irrigation methods), farmers can reduce the risks of yield losses due to weather conditions. AATF can empower farmers by creating policy and legal frameworks that improve their ability to manage these risks. Apart from enhancing the training of farmers and providing reliable information on market developments, public policies can maintain safety nets to help farmers to deal with income loss as a result of catastrophic events or major disturbances of the markets.
Achieved
Impact Indicator 2
| Percentage increase in yield of farmers adopting AATF technologies | Annual Average (Africa) (FAOSTAT 2017) Cassava 8794 kg/ha Cowpea 873.6kg/ha Maize 2072.6kg/ha Rice 2443.9 kg/ha | Planned | [5 empty] | 30%
Achieved
Source of data : Surveys ,National Statistics
PRIMARY OUTCOME | Primary Outcome Indicator 1 | Baseline:2016/2017 | [7 empty] | Assumptions and AATF operational standards of measurements
Increased adoption of commercialized agricultural technologies by farmers in Sub-Saharan Africa | Number of households using agricultural technologies accessed or developed through AATF projects ( TAAT Maize 46,875 tonnes = 1.875Million households ; Cowpea 21,000 Households ; TELA 200 tons = 8,000 farmer households , Striga 3250 tons = 130,000) | 226,000 Farmer Households | Planned | 345000 | 575000 | 530000 | 300000 | 250000 | 2000000 | 1. AATF will be able to identify and access appropriate technologies for dissemination to SSA farmers 2. AATF will be able to identify and maintain partners for production, promotion and stewardship of the technologies it disseminates 3. AATF will be able to identify and reach farmers that are willing and able to adopt the technologies it disseminates 4. AATF will be able to effectively adopt the mechanization services
| Output Indicator 2.2 |  | Achieved | 228663+300,700
| Primary Outcome Indicator 2 | [8 empty] | Operational standards of measurement 2SKgs of seed produced cultivates 1 Hectare of land One household averagely cultivates I hectare of land Its assumed that each household comprises of an average of 2 smallholder farmers
| Number of mechanization operations done (CAMAP and Agridrive 78,150 ; TAAT Cassava 1200) | 3500 Operations | Planned | 7500 | 11450 | 14500 | 19400 | 26500 | 79350
|  |  | Achieved | 4882
Source of data : Production and sales records , mechanization request sheet , farmer lists
Objective 1 : Diversify agricultural technologies accessed for use in SSA |  | Baseline:2016/2017 |  | 2017/2018 | 2018/2019 | 2019/2020 | 2020/2021 | 2021/2022 | Cumulative | Assumptions
Intermediate Outcome 1 : Increased deployment of diverse improved seed-based agricultural technologies
Immediate Outcome 1.1 Increased availability, access and release of diverse agricultural technologies | Indicator 1.1.1 | [8 empty] | 1. AATF will be able to identify and access appropriate technologies for dissemination to farmers in Sub Saharan Africa . 2. AATF will be able to identify and access products and/or varieties of suitable markets for the technologies it disseminates
| Number of new agricultural technologies accessed targeting agricultural productivity ,nutrition and post harvest loss | 8 technologies | Planned | 2 | 0 | 1 | 1 | 1 | 5
|  |  | Achieved | 1
Indicator 1.1.2
| Number of products/ varieties accessed | 10 products/varieties | Planned | 20 | 109 | 96 | TBD | TBD | 225
|  |  | Achieved | 89
Indicator 1.1.3
| Number of Products/ varieties developed | 53products/varieties | Planned | 5 | 10 | 20 | 20 | 20 | 75
|  |  | Achieved | 20
Indicator 1.1.4
| 1.3 Number of Products/ varieties released | 23 products/varieties | Planned | 3 | 10 | 30 | 6 | 10 | 59
|  |  | Achieved | 5
Immediate Outcome 1.2 Increased awareness and demand of diverse seed based agricultural technologies | Indicator 1.2.1 | [8 empty] | 1. AATF will continue to maintain and attract partnerships for delivery of its goal 2. Farmers and other stakeholders are willing to learn more about AATF technologies
| Number of farmers participating in AATFs agricultural education sensitization and outreach activities (demos, field days, trainings, workshops etc.) ( Hybrid Rice 32,000; NEWEST 1,000; COWPEA 20,000 ;Seeds2B 20,000; TELA 10,000; TAAT Maize 120,000 ; OFAB 200,000) | 11,300 smallholder farmers | Planned | 55000 | 62000 | 70000 | 93000 | 123000 | 403000
| Indicator 1.2.2 |  | Achieved | 14612
Indicator 1.2.2
| Number of other stakeholders (excluding farmers) engaging with AATF through AATF training workshops, seminars, outreaches, advocacy meetings | 563 Stakeholders | Planned | 500 | 700 | 1000 | 1200 | 1500 | 4900
|  |  | Achieved | 563
Source of data: Licence agreements ,activity participation lists , training records
Intermediate Outcome 2 : Increased deployment of mechanization ,nutrition and digital agricultural technologies |  | Baseline:2016/2017 |  | 2017/2018 | 2018/2019 | 2019/2020 | 2020/2021 | 2021/2022 | Cumulative | 1. AATF will be able to identify and access mechanization, nutrition and digital agricultural for dissemination to SSA farmers 2. AATF will be able to effectively adopt the use of digital platforms in delivering on its mandate
Immediate Outcome 2.1 Increased scale out of nutrition enhancing agricultural technologies. | Indicator 2.1.1
| Number of nutrition-based technologies being deployed by AATF | 1 nutrition technology | Planned | [5 empty] | One(1) nutrition project
Achieved
Achieved
Immediate Outcome 2.2 Increased awareness and uptake of mechanization and digital solution models. | Indicator 2.2.1
| Number of farmers aware of mechanization services by AATF (engaged through training workshops, seminars, outreaches, field days etc.) | 450,000 smallholder farmers | Planned | 550000 | 650000 | 875000 | 1100000 | 1375000 | 1375000
Achieved
|  |  | Achieved | 450000
Indicator 2.2.2
| Increased number of digital platforms used by farmers | 1 (One) ICT platform | Planned | 0 | 1 | 2 | 2 | 1 | 6 ICT platforms
Achieved
| Increased digital platforms used by farmers | 2 ICT platforms | Achieved | 0
Indicator 2.2.3
| Number of farmers linked to AATF technologies using digital solution platforms | 5,000 smallholder farmers | Planned | 5000 | 15000 | 25000 | 25000 | 30000 | 100000
|  |  | Achieved | 5000
Source of data : Activity lists ,farmer records , Digital platforms in use ,digital data
Objective 2: Accelerate commercialization of agricultural technologies for improved farmer livelihoods |  | Baseline:2016/2017 |  | 2017/2018 | 2018/2019 | 2019/2020 | 2020/2021 | 2021/2022 | Cumulative | Assumptions and AATF operational standards of measurements
Intermediate Outcome 3 : Improved service delivery systems for agricultural interventions.
Immediate Outcome 3.1 Increased number of viable business models and approached for commercialization | Indicator 3.1.1 | [8 empty] | That the use of extension services continues to be an effective and efficient delivery approach
| Number of business models for licencing ,production ,distribution to ensure quicker and faster technology adoption | 2 Business models | Planned | 1 | 0 | 1 | 0 | 1 | At least 3 models
|  |  | Achieved | 1
Immediate Outcome 3.2 Strengthened technology dissemination delivery networks along the value chains | Indicator 3.2.1
| Number of extension agents trained as TOTs | 70 extension agents | Planned | 85 | 85 | 90 | 90 | 90 | 355
|  |  | Achieved | 85
Immediate Outcome 3.3 Strengthened technology dissemination delivery networks along the value chains | Indicator 3.3.1
| Number of value chain actors that AATF works with to create market systems supportive of agricultural development. | 1200 value chain actors | Planned | 0 | 5000 | 6000 | 8000 | 10000 | 29000
|  |  | Achieved | 1200
Source of data : Commercialization reports ,training lists ,collaborative agreements | Source of data : Licence agreements ,list of released products and /or varieties
Intermediate Outcome 4 : Improved service delivery systems for agricultural interventions. |  | Baseline:2016/2017 |  | 2017/2018 | 2018/2019 | 2019/2020 | 2020/2021 | 2021/2022 | Cumulative | Risks Economic instability, risk and insecure conditions for investing: Frequent shifts in government policy on linking smallholders to markets in SSA on matters such as trade, storage and movement of grains, and price controls deterring investment. Institutions involved in technology adoption may not take on outputs from ATTF Policies to scale Mitigation AATF will encourage farmers to form farmer associations, groups and cooperatives when dealing with other actors in supply and value chains. This helps them to aggregate sales, input purchase, loans and technical assistance. This will not only help farmers to economize on transactions costs, but also, they should give the group greater bargaining power, especially when facing those with monopoly power. They can also be a means by which farmers make their voice heard within policymaking. Policy advocacy campaign
Immediate Outcome 4.1 Increased market linkages between farmers and off-takers | Indicato 4.1.1
| Number of farmers linked to off takers (CAMAP 55,000; TAAT Maize 1400 ) | 18,000 smallholder farmers | Planned | 22000 | 26000 | 55000 | 55000 | 60000 | 60000
|  |  | Achieved | 18000
Immediate Outcome 4.2 Increased use of harmonized frameworks for release and registration and cross-border marketing of agro-inputs and agricultural commodities. | Indicato 4.2.1
| No. of technology policies,laws ,regulations and standard operating procedures harmonized across countries and regions | 0 policies | Planned | [5 empty] | 14 policies
Achieved
Source of data : Farmer lists/farmer group records ; Analysis reports on policy frameworks | Source of data : Licence agreements ,list of released products and /or varieties
Objective 3: Create an enabling environment for increased uptake and use of agricultural technologies |  | Baseline:2017/2018 |  | 2017/2018 | 2018/2019 | 2019/2020 | 2020/2021 | 2021/2022 | Cumulative
Intermediate Outcome 5 : Improved Regional and national agricultural policy and agribusiness environment
Immediate Outcome 5.1 Improved policy and institutional frameworks for commercialization and adoption of innovative technologies | Indicator 5.1.1
| Number of countries with functional biosafety systems | 0 countries | Planned | 0 | 1 | 1 | 1 | 1 | 4
|  |  | Achieved | 0
Indicator 5.1.2
| Number of polices/legislations passed /amended to aid testing and commercialization of improved technologies in target countries | 2 policies/legistlations | Planned | 2 | 3 | 5 | 4 | 2 | 16
|  | 2 | Achieved | 2
Immediate Outcome 5.2 Enhanced implementation of policies and regulations to support commercialization of innovative technologies. | Indicator 5.2.1
| Number of governments engaged on policy deliberations on commercialization of agricultural biotechnology / technologies | 0 governments | Planned | 0 | 6 | 6 | 5 | 3 | 20
|  |  | Achieved | 0
Indicator 5.2.2
| Number of governments indicating formal commitments to implement policy, regulatory reforms for technology deployment | 0 policies | Planned | 0 | 3 | 2 | 2 | 1 | 8
|  |  | Achieved | 0
Indicator 5.2.3
| Number of polices/legislations passed /amended to aid testing and commercialization of improved technologies in target countries | 2 policies | Planned | 2 | 3 | 5 | 4 | 2 | 16
|  | 2 | Achieved | 2
Output 5: Robust outreach awareness, education and advocacy efforts to create a more receptive regulatory and commercial environment for agricultural technology advances. | Output indicator 5.1
| Number of beneficiaries reached through advocacy, outreach and regulatory interventions that will bolster enhanced capacity for private sector and seed systems in general. | 500,000 beneficiaries | Planned | 800000 | 2000000 | 2000000 | 2500000 | 3000000 | 10300000
|  |  | Achieved | 853100
Source of data : Memorandum of understandings , Engagement agreements actual legislation /policy documents , regulatory approvals ,media analysis | Source of data : Licence agreements ,list of released products and /or varieties
Cross cutting focus areas for the organization |  | Baseline:2017/2018 |  |  | 2018/2019 | 2019/2020 | 2020/2021 | 2021/2022 | Cumulative
Cross Cutting Output 6: AATF positions itself as a credible and responsible go to organization for transfer of agricultural technologies | Output indicator 6.1
| Number of requests for partnerships; specialist technical expertise/ experience and knowledge sharing on agricultural technology transfer among key targets. | 15 requests | Planned | 15 | 25 | 30 | 35 | 35 | N/A
|  |  | Achieved | 33
Output indicator 6.2
| Number of new partnerships/collaborations/ strategic alliances actualized to enhance the quality of AATF interventions | N/A | Planned | 0 | 7 | 8 | 9 | 11 | 35
Achieved
Output indicator 6.3
| Increase (quality and quantity) in number of mentions in both traditional and social media and drive stakeholder engagement (retweets, likes, clicks, views and responses) to support organization goals | 15000 | Planned | 20000 | 25000 | 37500 | 56250 | 84500 | 238250
|  |  | Achieved | 12388
Output indicator 6.3
| Knowledge products developed and disseminated (Impact stories, books and booklets, journal articles, policy briefs, conference proceedings published, book chapters | 74 | Planned | 74 | 12 | 15 | 20 | 20 | 67
|  | 14 | Achieved | 14
Cross Cutting Output 7:Appropriate agricultural technologies accessed and licenced for sustainable use by small holder farmers in target countries | Output indicator 7.1
| Number of trademarks /patents /PVP filed in project countries | 1 trademark | Planned | 2 | 2 | 3 | 4 | 4 | 15
|  |  | Achieved | 2
Output indicator 7.2
| Number of sub licenses negotiated and signed with partners | 12 | Planned | 39 | 20 | 20 | 18 | 15 | 112
|  | 39 | Achieved | 39
Cross Cutting Output 8: AATF is a well managed, efficient and effective organization. | Output indicator 8.1
| Percentage of review/audit/evaluation recommendations implemented. | 85% | Planned |  | 90% | 90% | 90% | TBD | TBD
|  | 77% fully and 30% partially | Achieved
Output indicator 8.2
| Staff turn over rate (below 10%) | 5% | Planned |  | 5% | 5% | 5% | TBD | TBD
|  | 23% | Achieved
Source of data : Memorandum of understandings , media analysis ,Audit reports ,HR files | Source of data : Licence agreements ,list of released products and /or varieties

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.