## Annual Review Template – from April 2020

Title: Impact Evaluations on urban transport, transport corridors and road safety across multilateral development banks and bilateral programmes (ieConnect)
Programme Value £ (full life): 12.25m		Review date: November 2020
Programme Code: 204931	AMP start date: November 2016	AMP end date: November 2021

Summary of Programme Performance
Year	2016	2017	2018	2019
Overall Output Score	A	A	A+	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	http://iati.FCDO.gov.uk/iati_documents/5627325.odt
DevTracker Link to results framework:	http://iati.FCDO.gov.uk/iati_documents/5578223.xlsx

A. SUMMARY AND OVERVIEW
Description of programme
Impact Evaluations on urban transport, transport corridors and road safety across multilateral development banks and bilateral programmes (ieConnect) is a transport window within the World Bank’s (WB) Impact Evaluation to Development Impact (i2i) multi-donor trust fund (MDTF). The MDTF is managed by the WB’s Development Impact Evaluation (DIME) department. FCDO contributes to the MDTF through two programmes: 1) the Fund for Impact Evaluation (also known as i2i), managed by the Evaluation Unit in FCDO’s Research and Evidence Division (RED) and 2) the ieConnect programme under the Growth Research Team (GRT). ieConnect aims to increase the availability and use of impact evaluation (IE) evidence for the selection, design, and implementation of transport infrastructure projects, particularly in low income, lower-middle income countries or fragile and conflict affected states (FCAS). It focuses on four pillars: urban mobility, transport corridors, road safety and rural roads and has two cross-cutting themes of fragility and women’s economic empowerment (WEE). FCDO’s funding has leveraged contributions to the MDTF from the EU delegations in Mozambique and Rwanda as well as support in cash and in-kind from partner governments and other parts of the WB for the cost of delivering IEs.
[note] Impact evaluations (IE) assess whether development interventions are effective and achieve the intended targets and are essential in building an evidence base on what works best, ensuring impactful interventions at scale and returns on investment to drive Value for Money (VfM) decision making.
Sustainable transport is the second largest sector by lending volume for the eight Multilateral Development Banks (MDBs), with about $20 billion on average lent every year. It is also normally in the top three sectors for spending by FCDO partner country governments. The United Kingdom is the second largest donor to the WB and other MDBs so a significant proportion of this funding is from UK Aid. Hence getting transport investment right is crucial for the use of government resources, economic development and trade, and ultimately poverty elimination. However, only 0.4% of all impact evaluations from 2000 to 2012 were for transport projects, meaning the evidence base for decision-making in the sector is weak.
[note] https://www.adb.org/documents/progress-report-2016-2018-mdb-wg-sustainable-transport
[note] Including UK ODA resources. FCDO spends a limited amount on infrastructure investments directly, but makes significant indirect ODA investments through capital contributions and concessional fund replenishments in the MDBs.
[note] Cameron, Drew B; Mishra, Anjini; and Brown, Annette N. “The growth of impact evaluation for international development: how much have we learned?” 2015, Journal of Development Effectiveness Vol 8, No1.
Summary supporting narrative for the overall score in this review
This review mostly covers progress during 2019. The programme met or exceeded almost all of the outcome and output milestones for 2019 and is largely on track to meet the end of programme targets (subject to COVID-19 delays). Two milestones – one outcome and one output – were not met: the outcome because of earlier delays in the programme outlined in previous Annual Reviews and transport/health journals’ policies for journal publication, and the output because it was not realistic and alternate arrangements have been put in place. It should be noted the ieConnect annual report, and the results captured in this annual review, were to December 2019. The programme scores an A+ this year. IeConnect expect strong progress towards outcomes in 2020 so next year’s annual review will need to demonstrate this progress, as expected with one year remaining in the programme. For example, as of September 2020 two IEs had presented final results to WB management and COVID-19 specific surveys had been completed in two counties, with one leading to a working paper with international coverage.
[note] Evidence from Female Workers in Ethiopia’s Ready-Made Garment Industry at https://osf.io/gwy5r/
[note] After low-income women lose their jobs in the COVID-19 economy, what happens to them? at https://ww2.gatesfoundation.org/ideas/articles/coronavirus-economic-impact-women?utm_source=to&utm_medium=em&utm_campaign=wc&utm_term=lgc
To respond to COVID-19 response and recovery and building on their experience through ieConnect, the ieConnect team initiated the Mobility Data Analysis Task Force with other areas in the WB. It uses mobile phone ‘big data’ to identify potential virus hotspots and to help partner governments with planning and communication, commencing in Uganda, Mozambique and one other country, with negotiations under way for The Gambia and Ghana. In addition, there are early indications that pivoting for COVID-19 activities will have a positive outcome. The crisis has generated interest outside the transport sector to use the mobile data and baseline information already collected for mobility, pricing and market impacts and urban/rural economic impact analysis.
In Tanzania, ieConnect has been evaluating the impacts of the placement of the Dar es Salaam Bus Rapid Transit system on socio-economic outcomes, including gentrification, as well as satisfaction with the system. From its conception, the evaluation has influenced the government to ascertain whether an intervention or investment should be pursued and at what scale. In all, 58 percent of government respondents document that the IE motivated the scale-up or scale-down of the intervention evaluated.
[note] https://blogs.worldbank.org/opendata/finding-missing-data-creating-actionable-information-solving-development-problems is an example of how ieConnect have developed the use of big data for their programmes and https://blogs.worldbank.org/opendata/hidden-potential-mobile-phone-data-insights-covid-19-gambia outlines the earlier work done in The Gambia under the WB parent trust fund and how it has led to COVID-19 analysis
Major lessons and recommendations for the year ahead
In June 2020, FCDO and ieConnect agreed recommended changes to the Logframe, which are included in the output recommendations sections. These changes will take effect from the next reporting period to January 2021 as ieConnect’s annual reporting is due in January. In addition, FCDO and ieConnect will agree appropriate output-level Value for Money (VfM) indicators for Outputs 2 and 3 by November 2020.
In order to better align with ieConnect’s annual reporting timeline, GRT should conduct the next annual review by March 2021.
COVID-19 is affecting the WB’s ability to conduct in-country data collection and some of the projects being evaluated are at risk of delays or cancellation. This will affect delivery of the impact evaluations. ieConnect and FCDO should closely monitor the COVID-19 situation and adjust the programme as necessary. FCDO should consider whether a no-cost extension to the programme is warranted to enable delivery of programme objectives post-COVID-19.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case
There has been no change to the theory of change in the review period and it remains valid.
[note] * Funding arrangements in table as per ieConnect business case, at programme launch. ** $13m attributed to DFID included commitments under the Fund for Impact Evaluation programme existing at the time of the ieConnect business case approval and reclassified to ieConnect.

ieConnect shares the theory of change with its parent trust fund, i2i. Specifically, ieConnect aims to improve development effectiveness of investments in transport infrastructure (increasing the use of evidence in policymaking and project development), contributing to faster, fairer and more inclusive economic development, and poverty reduction, by:
1. Increasing the amount of evidence available by conducting IEs.
2. Increasing the amount of evidence available by influencing governments and the MDBs to do IEs on their projects and improving their capacity to do and use the IEs.
3. Disseminating the evidence to policymakers and programmers through workshops, journal articles, publications.
Partners include the developing country governments as decision makers for transport projects and policies, the multilateral development banks as the major investors in the sector and civil society as implementers and influencers. ieConnect links to FCDO offices in Tanzania, Pakistan and Ethiopia to share findings and identify ways to inform programming and briefs the FCDO office in other countries when they conduct field visits.
Last year’s annual review reported that the Fund for Impact Evaluation programme IEs do affect policy dialogue and development intervention decisions. While most of ieConnect’s relevant outcome indicators will not be measured until 2020, the Fund for Impact Evaluation programme Annual Review for 2019 reported that 45% of the programme’s IEs generated evidence used to support scale up/down decisions accord to World Bank staff. IeConnect reports 58% (11/19) of IE baselines informed programme design or implementation (Indicator 1.3 below).
ieConnect is enabling evaluation of over $5 billion in transport investment projects to date. FCDO’s support has helped the WB attract new funding for ieConnect, reducing FCDO’s share to 44% of programme budget and increasing the VfM over time. Increases to some Logframe outputs agreed in June 2020 also increase the VfM, although the ambition of these increases had to be tempered a bit due to uncertainty from COVID-19.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme is on track to achieve the expected outcomes and impact, as shown in the table below. Three indicators, 1.4, 2.1 and 2.2, do not have milestones for this year. The programme has IEs that are in the early stages of commissioning and research and some that are at the later stages of uptake. Few are at the stage of impacting policy, which is expected in the last year of the programme (2021) and beyond. At the time of the reporting for this review there were only two of thirty IEs completed to the point of having research ready to publish. There is a risk of delays to IEs or cancellation of projects being evaluated from COVID-19 that might affect the end of programme results but the recent review of the Logframe chose not to change the targets yet. This will be reviewed at quarterly meetings.
Outcome	Indicator	Milestone 2019	Progress
Improved awareness, demand for and use of transport evidence in decision making	Proportion of transport project teams participating in ieConnect workshops that improve their knowledge of impact evaluation techniques.	75%	78% / Met
	Proportion of transport impact evaluations with multi-arm evaluation designs to test project innovations.	35%	42% / (8/19) / Exceeded
	Proportion of impact evaluations that influence transport project during design or implementation.	55%	58% / (11/19) / Met
	Proportion of completed transport impact evaluations that generate evidence used to support project adoption, scale-up, scale-down, continuation or cancelation decisions.	N/A
Improved effectiveness and impact of new and existing transport interventions from FCDO, MDBs and the wider community	Proportion of transport impact evaluations that have influenced the design or implementation of other transport projects outside of the IE itself.	N/A
	Proportion of transport impact evaluations that have influenced the design or implementation of other transport projects outside of the IE itself.	N/A
	Downloads of ieConnect research working papers.	500	0 / Significantly Not met
[note] In workshops where a pre-post knowledge test was administered.
[note] % of IEs that improved the design of a project based on clear understanding of the underlying theory of change or whose baseline results were used to stimulate policy dialogue or help identify problems and solutions.

The milestone for Outcome Indicator 2.3 was not met. Delays with HMG approval of ieConnect and a hiring freeze at the Bank in the early stages of the programme also delayed the production of project outputs, including research papers and the relevant outcome milestone was not sufficiently adjusted to reflect this. In addition, unlike the experience with economics journals, the peer-reviewed outlets for transport research papers often restrict pre-publication of working papers on websites or other platforms. This has led to an additional lag in when papers are available for download online. Progress has been made in the production of working papers this year, and the program is on track for these to be online and available for download by next year’s Review (as at September 2020 three working papers are online and a fourth is pending. One of the papers has already had 460 downloads).
Last year’s Annual Review (AR) recommended developing a possible additional theme of energy and / or climate change within ieConnect. This has been discussed with the WB but is pending approval of the new Climate Compatible Growth programme.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
This programme is performing well, provides good value for money, is innovative in using big data and looking beyond the normal aspects of transport programming and contributes to improving the effectiveness of World Bank and other MDB spending by building evidence for effective transport programmes. Due to delays from COVID-19, the programme should be extended to allow the IEs to be completed.

## C. DETAILED OUTPUT SCORING

Output Title	Increased quantity, quality and relevance of transport evidence available to improve policy design and implementation
Output number:		1	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicators	Milestones for this review	Progress
1.1 Number of Impact Evaluations across key sub-sectors (total): urban mobility, transport corridors, and road safety	Total: 22 / Urban Mobility; 20% / Transport corridors 25% / Road Safety; 20% / Rural roads; 15%	Total 25 / Urban Mobility; 32% / Transport corridors 40% / Road Safety; 36% / Rural roads; 20% / Indicator exceeded
1.2 Thematic knowledge reviews or technical notes for policymaking	1	1 / Indicator met
1.3 Number of cross cutting reviews in WEE and FCAS	Not measured in period	Milestones commence in 2020
1.4 Developed data infrastructure (with ability for scale up)	1	3 / Indicator exceeded
1.5 Developed and validated measurement framework that is able to disaggregate impact (male/female or rural/urban)	1	1 / Indicator met
1.6 FCDO burden share of ieConnect	Less than 45%	44% / Indicator met
1.7 Thematic distribution:	Gender (cross-cutting) 30%	32% / Indicator met
1.8 Geographic distribution:	Africa: 75% / South and South East Asia: 10% / FCAS: 50%	Africa: 76% / South and South East Asia: 12% / FCAS: 64% / Indicators met or exceeded
1.9 Income level distribution:	Low income, lower-middle income, or high fragility: 100% / DFID focus countries: 60%	Low income, lower-middle income, or high fragility: 100% / FCDO focus countries: 76% / Indicators met or exceeded
1.10 Women’s Economic Empowerment (WEE):	Proportion of IEs with WEE specific intervention: 30% / Proportion of IEs disaggregated by sex and age: 30%	Proportion of IEs with WEE specific intervention: 36% / Proportion of IEs disaggregated by sex and age: 52% / Indicators exceeded.
[note] Activities can be counted in more than one sub-sector.
[note] Measures methods of collecting data and the type of data collected.
[note] Measures the frameworks created to store and analyse data.
[note] This remains DFID focus countries for this review as there is not yet clarity on FCDO focus countries.

Briefly describe the output’s activities and provide supporting narrative for the score
This output measures how well the programme is contributing to improving the quantity and quality of evidence for transport programming (1.1 – 1.5). Indicators 1.7–10 ensure that the programme remains focused on key themes and issues of importance to FCDO (i.e. relevance). FCDO has been encouraging the World Bank to seek other sources of funding, and Indicator 1.6 measures how well they are attracting funding from other donors and partners. This output scores an A with all indicators meeting or exceeding the milestones. It is not an A+ because last year’s Annual Review recommended revising the milestones to be more ambitious and no changes were made to 2019 milestones. The programme is on track to achieve the end of programme targets although there is a risk some IEs may be paused or cancelled because of COVID-19 impacts. ieConnect and FCDO are watching this closely and will adjust the end of programme targets in the Logframe as necessary.
[note] 56% of the cost of ieConnect is from the owners of the projects being researched (partner countries, other MDBs) (20%), the EU Delegations in Rwanda and Mozambique (14%), external research funds and in-kind resources (12%), other World Bank Trust Fund grants (6%) and the World Bank (4%). Some of these sources are FCDO-funded programmes (e.g. IGC, PEDL and Global Road Safety Facility), which have high potential impact because of their reach and publication in top tier economic journals. Not all of this funding goes through the MDTF.
Prior to the COVID-19 outbreak the programme was performing well on Output 1.1 and was on track to meet or exceed the end of programme target (30). The categories ensure the programme spreads the research across areas, with more emphasis where there has been the least research and less emphasis where there has been the most. Twenty per cent remains unallocated to allow flexibility for important transport IEs that do not fit these categories (e.g. green transport).
While it is still early in the programme to have sufficient learning to prepare effective thematic knowledge reviews or technical notes (Output 1.2), ieConnect has developed the “Road Safety Conceptual and Accountability Framework: An Economic Perspective”, which complements and expands the World Health Organization framework for road safety and deepens the links to economic theory.
Transport IEs are typically on a larger scale, have more intensive data requirements, and present unique methodological challenges compared with IEs in other sectors, so ieConnect is piloting methods of collecting data (Output 1.4) using big data, remote sensing, crowd sourcing and new technologies. It is also developing and validating new measurement frameworks (Output 1.5) that can disaggregate impacts by sex or location (rural/urban). For example:
[note] For example, selection of project sites is not random and is often integral to project design.
- The Rwanda Feeder Roads IE combines existing administrative data from several line ministries and extensive primary data collection across the country’s districts to understand how the road rehabilitation is impacting the availability and price of goods across markets.
- In Malawi trauma registries at 10 health facilities collect data on post road-crash emergency response and medical care. Data on over 60,000 trauma cases has been collected since August 2018 and key data is fed back to health facilities weekly to improve data collection and trauma care.
  [note] 2 central hospitals including the largest facilities in the country; 7 district health facilities and 1 community health facility.
  [note] This includes all trauma cases, not just road traffic crashes but also falls, fractures etc.
- The smarTTrans Road Safety project uses multiple data sources including digitising police paper-based records, crowdsourcing (Waze, Twitter, Uber), weather information, video, and machine learning algorithms to build a geo-referenced, multi-year road crash dataset for Nairobi. The data is used to gain a better understanding of the characteristics of crash locations and create, improve, and validate new road safety measures. It is also generating open-sourced data and tools and providing initial validation of these methods, to enable testing these measures in other contexts.
  [note] https://blogs.worldbank.org/opendata/finding-missing-data-creating-actionable-information-solving-development-problems (same link provided in summary section)
As a direct result of data collection work outlined in Indicator 1.4, the ieConnect team have pivoted to include COVID-19 work. They are leading the Mobility Data Analysis Task Force in the World Bank, using mobile phone data to assess movements of people, identify possible virus transmission hotspots and assist governments to use this for policymaking. They have agreements in place for mobile phone data in three countries including Uganda and Mozambique and with Vodafone (covering several countries including Lesotho and South Africa) and have prepared and presented dashboards to two of these governments. They are also working on agreements for The Gambia and Ghana. Their plans are ambitious, and they are finding it is slower than expected to get agreements for access to the data due to privacy concerns and regulations.
[note] This blog on The Gambia explains some of the work being done there, financed by the Trust Fund for Statistical Capacity Building III with FCDO support. It is based on earlier work and agreements are pending for use of the data for further COVID-19 work. https://blogs.worldbank.org/opendata/hidden-potential-mobile-phone-data-insights-covid-19-gambia
ieConnect temporarily suspended field activities in March 2020 due to COVID-19. Some projects with planned IEs have pivoted to COVID-19 response and recovery activities, increasing country office workload and potentially delaying the start of new IEs.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
VfM Indicators from Business Case:
	Measure	Target	Achieved
Economy and Efficiency	Completed impact evaluation papers/reports	Average cost of final impact evaluation papers/reports <=$275,000	$262,000
Cost-Efficiency	Crowding-in of external funds	>= 60% of financing for impact evaluations coming from alternative sources by programme-end. (see Output 1.6, FCDO burden of share)	56% - ahead of milestone of 55%
[note] The average cost to FCDO of completed impact evaluation papers/reports assumes at least one paper per IE and includes the IEs under development as well as those underway, or $7.85 million direct cost of 30 IEs.
[note] Output 1.6 shows FCDO’s share (44%) where the business case showed the share of other financing.

Instead of just producing a report or paper at the end of the IE, ieConnect produce a large number of products per IE that include (i) briefs at several stages of the project, (ii) new innovations in data collection, including open source code to allow for replicability, (iii) papers and briefs that describe the new methods, allowing the work to be scaled, and (iv) papers based on the initial baseline data since even this can be useful for transport planning and policy given the dearth of existing data. The measure above for average cost of final papers/reports was not included in the Logframe since it has a more ambiguous interpretation and potential relevance vis a vis the other VfM measures.
The FCDO funds cover around $175,000 per IE, but an IE can cost up to $1 million depending on the project; therefore, the FCDO funds help to attract larger investments in research and impact evaluation in transport. Research staff and firms are all selected competitively with the highest standards for selection. ieConnect also have an internal system for checking quality of all final outputs as well as for ensuring quality of any data collection conducted.
ieConnect exceeded the expectations for the equity indicators (1.10) and the indicators for low income, low-middle income and fragile states (1.9). There are no indicators for disability.
Describe any changes to this output during the past year, and any planned changes as a result of this review
The past year has seen the start of implementing the costed extension agreed in January 2019, expanding from 22 to 30 IEs. The financial impacts of COVID-19 may result in the cancellation of some projects with an ieConnect IE, which would directly impact Indicator 1.1. ieConnect is closely monitoring the situation and assesses the risk as low in the short term and moderate in the medium term – depending on how long the lockdowns continue. During the slow down ieConnect staff are producing more reports using baseline and data work already under way, which will improve the value for money per IE.
For future reporting FCDO and ieConnect have agreed to add two indicators to Output 1.1: number of completed outputs and number of papers, reports or mobility case studies to improve value for money measurement; and to include low, medium and high milestones/targets for the current Indicator 1.1. We agreed to clarify the definition for 1.6, proportion of funding from GRT financing of ieConnect. For Indicators 1.7-10 milestones are static for all years. Once all IEs have been identified these indicators could be dropped as long as measures for equity are still included.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Last year’s Annual Review recommended stretching some of the targets. A review during 2019 did not increase milestones for this output for 2019 but did increase the ambition for Indicator 1.2 from 2020. A review of the Logframe was conducted in June 2020 for the next reporting cycle. Further Logframe revisions may be necessary to account for COVID-19 impacts but still be stretching enough to reflect the ambition of the programme. GRT should conduct the next Annual Review by March 2021 to better align with ieConnect’s annual reporting cycle.

Output Title	Increased capacity of transport policymakers, implementers, researchers, and partners to incorporate rigorous evidence/tools into policy making
Output number:		2	Output Score:	A+
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicators	Milestones for this review	Progress
2.1.a Number of MDBs involved at the operational level	4	5 / Indicator met
2.1.b Number of bilateral donor institutions involved at the operational level	5	5 / Indicator met
2.2 Number of IEs working directly with a non-WB implementing partner	10	10 / Indicator met
2.3 Proportion of co-financed transport programmes	90%	100% / Indicator exceeded
2.4 Spend on non-WB IEs or co-funded IEs where WB contribution <=25%	25%	28% / Indicator exceeded
2.5 Proportion of people participating in workshops that come from low or lower-middle income countries	75%	90% / Indicator exceeded
2.6 Proportion of people participating in workshops that come from FCASs	50%	58% / Indicator exceeded
2.7 Number of people trained in workshops and/or by ieConnect-supported teams/researchers	350	376 / Indicator exceeded
2.8 Number of workshops	4	9 / Indicator exceeded
[note] Non-World Bank MDBs, bilateral donors, partner governments, NGOs or other actors.

Briefly describe the output’s activities and provide supporting narrative for the score
The greatest impact of evidence comes if it is used by all MDBs, country roads departments and other donors. This output measures the capacity building outputs of the programme including the reach beyond the World Bank to other development banks and donors. This output scores A+ as ieConnect has met or exceeded every milestone.
FCDO has been pushing for a step-change in the transport sector’s ability to undertake and use impact evaluations by encouraging ieConnect to extend its reach beyond the World Bank, particularly with the regional Development Banks, bilateral donors and partner country governments (Output indicators 2.1-4). The programme is working at the operational level (Output 2.1) with the African Development Bank (AfDB), Islamic Development Bank (IsDB), Asian Development Bank (ADB), European Union funding, FCDO, Japanese International Cooperation Agency, Dutch Development Bank, United States Agency for International Development, EXIM Bank of China, and the Inter-American Development Bank (see Annex 1 for a list of projects). An example of an IE of a co-financed transport programme is the Dar es Salaam Bus Rapid Transit (BRT) project, which is evaluating the impact of the first line of the BRT financed by the World Bank, and enables ieConnect to educate and build the capacity of actors beyond the normal reach of the World Bank (Output 2.3). Twenty-eight per cent of the IEs in the portfolio are on non-World Bank or co-funded IEs where the World Bank contribution to the project is less than or equal to 25% (Output 2.4). This is an increase from 23% in 2018 and is on track to exceed the end of programme target of 25%.
[note] Work with FCDO projects is a small proportion of the programme because we do not fund transport infrastructure projects. ieConnect is supporting an FCDO project in Tanzania for road safety.
The programme builds the capacity of a broad set of stakeholders from developing countries to make systematic use of data and evidence through a collaborative learning-by-doing approach (Outputs 2.5 – 2.8). ieConnect uses different sizes and durations of national and international workshops (2.7-8) for government officials, MDB operations leads, NGOs, or bilateral donor stakeholders to build understanding of rigorous impact evaluation and research methods such as randomised control trials; outline existing transport research and results that can be applied to a project; train them IE design and initiate programme planning. In addition to these workshops the ieConnect team interact closely with stakeholders during the IE to build their understanding and ownership of the results. The size and duration of the workshops range from 10 to 150 participants and one day to one week.
For example, in January 2019 ieConnect co-hosted an impact evaluation workshop with the IsDB in Dakar, Senegal, incorporating six IsDB projects from across West Africa. The workshop brought together researchers, practitioners, and other stakeholders to design and assess IEs focused on transport, health and agriculture. This workshop is part of the broader effort to support development institutions to identify pathways from policy to results in collaboration with government clients and project teams, and to design and implement IEs that respond to operational learning needs. Similarly, The Bank held a large workshop in Marrakech for 39 participants representing eight potential projects. Of these, seven submitted proposals and six projects were selected for ieConnect support.
[note] This was not reported in the last Annual Review as ieConnect’s annual reports are provided in January.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
There are no VfM indicators for this output in the Business Case or Logframe. Future Logframe revisions will consider an appropriate measure. A possible measure is cost per workshop participant, although this is hugely variable between the large workshops and in-country workshops (which require less travel and accommodation). The average cost to date is $1,500 per participant and $60,000 per workshop as a benchmark. This could be refined using the number participants that increased their knowledge (based on pre and post training testing).
Describe any changes to this output during the past year, and any planned changes as a result of this review
In January 2020 FCDO and ieConnect agreed to clarify the definition for indicator 2.2, to count, cumulatively, the total number of engagements rather than distinct institutions. This will include each IE that has a non-World Bank MDB or bilateral donor involved at the operational level (either with or without the presence of a World Bank project), or is working directly with the government, NGO or other actor in the absence of a World Bank project. This gives a more accurate representation of the reach and influence of the programme than just counting distinct institutions and reflects that large transport investments often require funding from multiple donors, including the World Bank.
[note] To take effect from the next reporting period.
COVID-19 is impacting on ieConnect’s ability to conduct workshops. The ieConnect team have adjusted quickly to hold training events and engage with partners online, but this cannot fully replace the value of face-to-face workshops. This could especially impact the ability to conduct workshops with high participation from FCAS and low-income countries where connectivity may not permit extensive virtual engagement. FCDO and ieConnect should consider whether the programme can still deliver as expected on this. ieConnect is using alternative training formats and ieConnect and FCDO agreed new Logframe milestones and end of programme targets in June 2020 and will continue to monitor the situation.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
A key component of the extension agreed in 2018 and a recommendation from the last Annual Review was for ieConnect to expand its non-World Bank work. ieConnect has made progress over the review period and continues to strengthen existing collaborations.
The previous Annual Review recommended FCDO and ieConnect agree an additional indicator to further measure partner government engagement in the IEs and in ieConnect. Indicator 2.2 was added to address this. Indicators 2.1b, 2.7 and 2.8 were increased for 2019 and the new milestones were achieved.
While ieConnect makes strong efforts to ensure the training events and workshops build capacity of the right people, none of the indicators measure whether decision-makers participated or the quality of the workshops so it is difficult to know whether capacity has increased. While Outcome Indicator 1.1 measures the proportion of project teams participating in workshops that improve their knowledge of IE techniques, GRT and ieConnect will consider refining the output indicators to capture the quality of capacity building.
Output Title	Increased Communities of Practice and knowledge platforms for sharing of transport evidence and its application for policy making
Output number:		3	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicators	Milestones for this review	Progress
3.1 Number of organisations participating in ieConnect workshops	80	165 / Indicator substantially exceeded
3.2 Number of organisations, universities, research centres, and government agencies participating in ieConnect networks	50	50 / Indicator met
3.3 Number of non-WB hosted dissemination events	25	26 / Indicator met
3.4 Active MDB participation on DIME Steering Committee	1	0 / Indicator not met

Briefly describe the output’s activities and provide supporting narrative for the score
Output 3 measures the global outreach of ieConnect with the theory that more organisations participating in workshops and networks results in broader reach, (e.g. two people per 50 organisations in workshops has more potential influence than 50 people per two organisations) and more potential to affect policy-making. Three of four indicators were met or substantially exceeded, but the recommendations for Output 3.4 from last year’s annual review were not implemented and the milestone was not met. As the programme met the spirit of Output 3.4, on balance this indicator scores an A+, moderately exceeded expectation.
Output 3.1 more than doubled the expected milestone - 165 organisations, 27 more than last year, were represented at workshops to learn about IEs and applying evidence. ieConnect create a learning partnership with the country government, beginning with a workshop for country ownership of the process and defining the IE questions and then maintained through the life of the IE with learning and capacity building (learning by doing). Output 3.1 measures the workshop part of this journey. For example, an initial training event in Malawi on rigorous impact evaluation included the Ministry of Health, the National Police Service, the Department of Road Traffic Safety Services, and the Malawi Medical College. Of these, only the Ministry of Health and the Malawi Medical College are directly involved in planning and implementing the IE (Output 3.2), showing the workshops can reach beyond the organisations directly participating in the IEs. Given the very strong performance on Indicator 3.1, FCDO and ieConnect agreed to increase the milestone for 2020 and the end of programme target.
However, Output 3.4, having active non-World Bank participation on the DIME Steering Committee was not realistic and was not met. DIME does not have a steering committee so ieConnect attempted to form an advisory committee including MDB representatives. Only ADB agreed to participate. As a result, the last annual review stated that ieConnect would suggest a different mechanism to ensure ADB engagement with ieConnect. Due to staffing constraints in FCDO’s Growth Research Team, this mechanism was not agreed in this annual review period and the Logframe was not changed. However, to achieve the intent of the indicator, ieConnect has been presenting to MDB senior management at the MDB Transport Working Group meeting. This should be considered a success for ieConnect given the infrequency (twice a year) and brevity (two hours) of these meetings and the demand for space on the agenda. Also, the ADB’s first IE programme launch was on transport instead of health or gender as originally proposed, which can be attributed, at least in part, to ieConnect’s efforts advising ADB on IEs.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
There are no VfM indicators for this output in the Business Case or Logframe. Future Logframe revisions will consider an appropriate measure for VfM and equity. This might include an indicator for the number/proportion of female researchers or researchers from developing countries.
Describe any changes to this output during the past year, and any planned changes as a result of this review
In January 2020, FCDO and ieConnect agreed to increase the milestones for Output 3.1 to 185 in 2020 and 200 in 2021, and to increase the milestones for Output 3.2 to 55 in 2020 and 2021. In June 2020, FCDO and ieConnect agreed to change Indicator 3.4 to ‘Number (cumulative) of presentations in high-level meetings with multi-stakeholder MDB and/or bilateral transport leadership’ with an end of programme target of 3 (at least one per year from 2019) FCDO has also suggested, based on input from the ADB, that there may be an opportunity to propose an additional meeting of the MDB Working Group in order to share ongoing work in ieConnect. ieConnect will review feasibility for this in the coming months.
[note] To take effect from the next reporting period as ieConnect’s annual reports are provided in January.
No further revisions to this output are expected as a result of COVID-19 programme delays, but ieConnect and FCDO will keep a close eye on this.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The last Annual Review recommended ieConnect prioritise non-World Bank-led international events such as the World Road Congress and ADB transport week over World Bank-led events, to maximise influence outside as well as inside the WB. ieConnect have participated in 26 non-World Bank hosted events (Output 3.3), including seven in the past year. However, workload and other commitments prevented them from participating in the two events named above. They try to leverage the World Bank’s Transport Global Practice to mention ieConnect work at global fora. For example, the WB’s Vice President for Infrastructure was the only WB speaker during a formal session at the Global Ministerial Conference on Road Safety in Sweden in February 2020, and briefly mentioned the ongoing research in Kenya (https://www.youtube.com/watch?v=tr33CSfyE_Y ~ minute 56) and emphasised the importance of investing in research. This review continues to recommend ieConnect do more on presenting in non-World Bank-led fora, particularly when they are held online and do not require travel, and they should continue to leverage opportunities for Transport Global Practice members to emphasise ieConnect activities and evidence.
The last Annual Review also recommended an increase to the milestones for Indicator 3.1. The 2019 milestones for Indicators 3.1, 3.2 and 3.3 were increased and the new milestones were met. It was also recommended that ieConnect present at least annually at the MDB Working Group, which has been done.

D: RISK
Overview of risk management
ieConnect remains a Moderate risk for FCDO, although the delivery risk has increased because of COVID-19 delays to in-country face-to-face surveys and the potential that the projects being implemented are delayed or cancelled. The overall programme risk, and all individual risks, are within Research and Evidence Division’s risk appetite. GRT is closely monitoring the COVID-19 risks with ieConnect.
Risks with residual rating moderate or higher after mitigation
Risk	Mitigation	Residual Risk Rating
COVID-19 delays mean additional costs and time required to deliver IEs, particularly staff costs.	ieConnect is reordering tasks, reallocating staff, and writing more papers based on early findings to mitigate delays and deliver more outputs.	Major
Covid 19 delays project activities in countries, such as data collection, meetings and conferences	ieConnect is using alternative analytical products and secondary data including big/mobile data. They are using online meetings. FCDO is monitoring regularly.	Major
COVID19 related delays mean programme milestones or targets are missed	ieConnect are ahead of schedule on some milestones, which mitigates this risk. They are considering refocusing on high impact, low risk activities like generating more written products from secure IEs	Major
Security issues in partner countries limits access and delays deliverables	ieConnect have increased the number of countries selected to spread the risk and are monitoring each country situation closely.	Moderate

Since the programme is now at the point where some IEs are finishing and research is being published, we will add a risk to the register for research uptake - Findings from impact evaluations do not feed through into decision making and design of transport programmes. The gross and residual risk is rated Major based on ieConnect’s delivery approach to capacity building and stakeholder engagement outlined in Output 2.
Historically, WB’s Development Impact Evaluation team has shown that some IEs either are not completed or do not translate into useful results. This is mostly for reasons outside of ieConnect’s control, such as a change of government in partner countries, failed projects, and political instability. Because transport projects are larger and more complex than many of the Development Impact Evaluation team’s typical projects, and ieConnect works with a larger percent of non-Bank projects (12 of 30 IEs) at FCDO’s request, there is a major risk that not all ieConnect IEs will be completed and have results. ieConnect has intentionally added projects beyond the target to account for possible attrition to ensure they can deliver the expected outputs and outcomes in a timely manner. However, COVID-19 risks delays to data collection and dissemination of results, as well as cancellation of some projects with planned IEs, meaning milestones and targets may be missed.
As a result, FCDO should consider a no-cost extension to the programme. Logframe revisions agreed in June 2020 took into account early projections of COVID-19 risks to milestones and targets, but ieConnect and FCDO will need to monitor the impacts of COVID-19 on the programme quarterly.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.
The World Bank has clear financial management and procurement policies in place which have been agreed centrally by FCDO and the programme follows all relevant policies.
The World Bank programme team sends financial reports to FCDO twice per year, at the same time as their call for funds as agreed upon at the start of the programme. They also respond promptly to additional requests for information from FCDO. Delays to the workshop to design the most recent phase of IEs meant that funding disbursements to the programme from FCDO have been slightly behind schedule. The expectation is future calls for funds could return to the schedule as detailed in the agreement, but FCDO budget requirements mean the final payment may need to be extended into financial year 2021-22.
The World Bank programme team meet FCDO staff on a quarterly basis to discuss progress against the programme timeline, review finances and discuss any issues or concerns. This includes a face-to-face meeting in January during the World Bank Transport Week. As described elsewhere in the report, FCDO and ieConnect met in June 2020 to agree Logframe changes for future reporting. There is also the flexibility to have additional meetings if required to discuss any urgent issues. The reports are clear and consistent and the responses to ad hoc requests are quick and substantial. Both parties have found the meetings to be useful in contributing to a strong working relationship.
The ieConnect team have contact with FCDO offices in three countries: Ethiopia, Tanzania and Pakistan. The extent of the contact varies from bi-weekly discussions to ad hoc email updates. They also often meet with FCDO staff when conducting field visits (e.g. missions to Kenya prior to lock down) and invite FCDO staff to attend dissemination events in country. For example, in Ethiopia ieConnect speaks informally with the Senior Economic Adviser about every two weeks, to keep him up to date on the work, share findings as they are produced and recently have been discussing how to use their survey ability to support a new phase of FCDO industrialisation and economic transformation support.
GRT does not do field visits for the IEs but is in contact with some country offices where ieConnect is operating to ensure links between ieConnect and FCDO programmes (e.g. Tanzania). GRT will expand this to ensure we have contact with all FCDO country offices where ieConnect is operating and will seek their feedback on the quality of the work being done and will report on this in the next Annual Review.
As a World Bank Trust Fund this programme is included in the Single Audit of all World Bank trust funds. No issues regarding this programme were highlighted in the last Single Audit.
FCDO funds are not used to purchase any assets.

Date of last narrative financial report	March 2020	Date of last audited annual statement	September 2020

# Annex 1 – List of Collaborations outside the World Bank

- Ethiopia: Hawassa Industrial Park Community IE (FCDO and Enterprise Partners)
- Senegal: Measuring and Enhancing Construction Worker Welfare in Dakar (AfDB and IsDB)
- Senegal: Measuring and Enhancing Mobility in Dakar (AfDB and IsDB)
- Pakistan: Understanding the Impacts of CAREC Corridor Investments (ADB, FCDO, and EXIM Bank of China)
- Rwanda: Impact Evaluation of Rwanda Rural Feeder Roads (EC/EU, FMO, and USAID)
- Rwanda: Lake Victoria Transport Program Rwanda Corridor (JICA)
- Mozambique: The Route for Development (EC/EU)
- Kenya: smarTTrans (National Transport and Safety Authority and National Police Service)
- South Africa: Matching Youth to Jobs (Harambee NGO)
- India: Measuring Violence Against Women in Public Spaces (Hyderabad City Police)
- Peru: Impact Evaluation of the Peru Support of the Subnational Transport Program (Inter-American Development Bank)
  [note] Peru is not a FCDO priority country and thus is not included in Logframe figures but is worth noting as an example useful to priority countries.