## Sheet1
LOGFRAME 2020 - International Action Against Corruption
Smart Guide
PROJECT TITLE | International Action Against Corruption
IMPACT | Impact Indicator 1 |  | Baseline 2017 | Milestone 1 2018 | Milestone 2 | Milestone 3 | Target (date) | Assumptions
Poverty is reduced and greater prosperity is enabled through the financing for development made available from reduced theft and leakages from the public sector in developing countries; the return of stolen assets otherwise lost through grand corruption; and a less corrupt business environment attracting investment and job creation. | Progress in score against Human Development Index (HDI) Increase in gross national income (GNI) per capita. | Planned | Kenya .590 Tanzania .538 Ghana .592 Nigeria .532 Ken $2,961 Tan $2,655 Gha $4,096 Nigeria $5,231 | Kenya .590 Tanzania .538 Ghana .592 Nigeria .532 Ken $2,961 Tan $2,655 Gha $4,096 Nigeria $5,231 | Kenya .591 Tanzania .539 Ghana .593 Nigeria .533 Ken $2,965 Tan $2,660 Gha $4,098 Nigeria $5,235 | Kenya .591 Tanzania .539 Ghana .593 Nigeria .533 Ken $2,965 Tan $2,660 Gha $4,098 Nigeria $5,235 | Kenya .590 Tanzania .538 Ghana .592 Nigeria .532 Ken $2,969 Tan $2,665 Gha $4,100 Nigeria $5,236
Achieved
|  |  | Source |  |  |  |  | RISK RATING
|  |  | UNDP Human Development Report (yearly in arrears) |  |  |  |  | Moderate
| Impact Indicator 2 |  | Baseline 2017 | Milestone 1 2018 | Milestone 2 2019 | Milestone 3 2020 | Target (date)
| Improvement in score against CPI for selected IACT countries | Planned | Kenya 70 Tanzania 137 Ghana 120 Nigeria 145 | Kenya 70 Tanzania 137 Ghana 120 Nigeria 145 | Kenya 69 Tanzania 137 Ghana 120 Nigeria 145 | Kenya 69 Tanzania 137 Ghana 120 Nigeria 145 | Kenya 68 Tanzania 136 Ghana 118 Nigeria 144
Achieved
|  |  | Source |  |  |  |  | RISK RATING
|  |  | Transparency International Corruption Perceptions Index |  |  |  |  | Moderate
| Impact Indicator 3 |  | Baseline 2016 | Milestone 1 2018 (reflecting 2017) | Milestone 2 2019 (reflecting 2018) | Milestone 3 2020 (reflecting 2019) | Target March 2021 (reflecting 2020) | Assumptions
| Improvement in doing business as measured by World Bank. | Planned | Kenya 26 Tanzania 32 Ghana 43 Nigeria 28 | Kenya 28 Tanzania 36 Ghana 40 Nigeria 27 | Kenya 28 Tanzania 36 Ghana 41 Nigeria 28 | Kenya 29 Tanzania 36 Ghana 42 Nigeria 27 | Kenya 30 Tanzania 37 Ghana 43 Nigeria 29
Achieved
|  |  | Source |  |  |  |  | RISK RATING
|  |  | World Bank Doing Business Index |  |  |  |  | Moderate
OUTCOMES | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (date) | Assumptions
Reduced incentives for corruption due to international partners working better together across borders and in country to close down opportunities to hide the proceeds of corruption and increase transparency and integrity, and diminished impunity due to stronger cross-border financial investigations and greater accountability for compliance with international standards and commitments. | Number of businesses reached with dedicated information and guidance needed to do business with integrity in emerging markets and fast-growing developing countries. | Planned | Zero SMEs have requested services through BII hub, Zero visits to the Hub landing page. | DFID-Foreign and Commonwealth Office (FCO)-Department of International Trade (DIT) Business Integrity Initiative approach and resourcing agreed across Her Majesty’s Government (HMG); digital integrity content on GREAT.GOV.UK refreshed | Businesses have access to online guidance on great.gov.uk. Match-funded support on Anti-Corruption and human rights (for SMEs) from a consultant. Market and sector specific dedicated guidance through TA at post provided (for SMEs and HMG staff) for Pakistan, Kenya, Mexico. | At least 50 SMEs have requested services through the online platform (hosted by DIT) of the BII hub. | At least 70 (cumulative) SMEs have requested services with at least 35 doing things differently as a result. | There is little practical advice on how to implement business integrity responsibilities in frontier markets. There is need for better signposting to materials on specialist websites. SMEs are more vulnerable to bribery risks, and at the same time have fewer resources to prevent bribery. The 2018 learning day for IACT partners drove initial collaboration. The success of this outcome will be dependent on annual learning days held by the MEL agent when contracted.
|  | Achieved |  | Digital integrity content on great.gov.uk published - highlighting top integrity risks companies need to be aware of when doing business abroad. 3 markets (Kenya, Pakistan and Mexico) selected as the first batch of pilots to be supported based on a joint call for expressions of interest from DFID, DIT and FCO (August 2018). SMEs can access Anti-Corruption consultancy services on great.gov.uk (November 2018). | Digital integrity content on great.gov.uk published - highlighting top integrity risks companies need to be aware of when doing business abroad. 3 markets (Kenya, Pakistan and Mexico) selected as the first batch of pilots to be supported based on a joint call for expressions of interest from DFID, DIT and FCO (August 2018). SMEs can access Anti-Corruption consultancy services on great.gov.uk (November 2018). 6 SME have accessed support from BII consultancy service and received tailored guidance - ongoing.18 individual business attended peer to peer roundtable forum in Kenya. Series of workshops for local business in Pakistan have taken place. Champion network has been created to support UK business new to Pakistan. E-learning platform is under construction to allow businesses new to Kenya to access online guidance. | Indicator 2: was partially achieved, where 14 businesses have requested services through BII. This indicator is not appropriate as an outcome indicator for I-ACT as it relates to a new/untested feature of BII. BII is a relatively small component of I-ACT and its outcome indicator should not be one of the key indicators of I-ACT outcome. While the outcome statement is in line with the revised TOC, the indicators do not appropriately frame or measure the outcome statement or results of I-ACT components. I-ACT aims to improve framing and quantifying I-ACT effectiveness based on the 3 outcome areas identified in the TOC to be included in the programme completion report.
|  |  | Source |  |  |  |  | RISK RATING
[5 empty] | See nested BII Logframe |  |  | Moderate
| Outcome Indicator 2 |  | Baseline 2016 | Milestone 1 2018 | Milestone 2 2019 | Milestone 3 2020 | Target March 2021 | Assumptions
| IACT partners' international collaboration (all I-ACT partners e.g. TI-S ++). To influence policy and institutional changes at the international level. | Planned | Ad hoc collaboration | 2 new collaboration which leads to changes in international standards or policies or actions (e.g.; G20, UN, OGP) | 1 new collaboration, which leads to changes in international standards or policies or actions (e.g.; G20, UN, OGP) | 1 new collaboration (2 in aggregate), which leads to changes in international standards or policies or actions (e.g.; G20, UN, OGP) | 2 collaborations led to changes in international standards or policies or actions (e.g.; G20, UN, OGP)
|  | Achieved |  | No new collaborations took place leading to changes in international standards. | No new collaborations took place leading to changes in international standards. | 1 new collaboration met. Transparency International, worked closely with other stakeholders, to influence IMF to include anti-corruption measures for the COVID-19 relief financing provided to affected countries.
|  |  | Source |  |  |  |  | RISK RATING
|  |  | MEL Progress Reports |  |  |  |  | Moderate
| Outcome Indicator 3 |  | Baseline 2017 | Milestone 1 2019 | Milestone 2 2020 | Milestone 3 2021 | Target March 2022 | Assumptions
Achieved
|  |  | Source |  |  |  |  | RISK RATING
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (Jun 17) | Milestone (Jun 18) | Milestone 2 (Jun 2019) | Milestone 3 (Jun 20) | Target (March 21) | Assumptions
Opportunities for corruption are reduced due to less vulnerability to money-laundering, UK company compliance with the Bribery Act and stronger mitigation of corruption risk in defence and security institutions especially in Summit countries | Number of technical assistance (since our funding contribution) missions in low and lower middle income countries conducted through IMF topical trust fund on AML / CFT. | Planned | Zero technical assistance missions (with IACT funding) carried out in low and lower middle income countries. | 20 technical assistance (since our funding contribution) missions in low and lower middle income countries conducted. IMF Agreement signed. Availability of minutes from IMF May steering committee meeting noting agreement on methodology for impact. | 15 additional technical assistance (since our funding contribution) missions in low and lower middle income countries conducted through IMF topical trust fund on AML / CFT. % of respondents to evaluation survey assessing work funded through the IMF topical trust fund on AML / CFT as efficient or highly efficient. | 15 additional technical assistance (since our funding contribution) missions in low and lower middle income countries conducted through IMF topical trust fund on AML / CFT. IMF TTF on AML / CFT currently runs from 2014-19. FCDO will evaluate further contributions to any new TTF that the IMF develops | 50 (cumulative) of technical assistance (since our funding contribution) missions in low and lower middle income countries conducted through IMF topical trust fund on AML / CFT. | That IMF will focus work in FCDO priority countries, subject to FCDO engagement in the designation of IMF priority countries. HMG business support is fragmented, especially for SMEs. There is a reputational risk for the UK and financial/reputational risks for UK companies if the latter do not act with integrity when doing business abroad. There is a lack of consistency in approach to the provision of business integrity support from UK missions, and the quality of that guidance varies. This is the cumulative number of GI assessments produced and published with Fid's support with a total of 40 assessments by the end of the grant duration.
|  | Achieved |  | 23 technical assistance (21 bilateral TA & 2 research products) missions in low and lower middle income countries conducted. IMF Agreement signed. Minutes from IMF May steering committee meeting available and provided noting agreement on methodology for impact. | Milestone exceeded. The total No. of Missions to Low Income Countries funded through AML/CFT Phase II is 35, of which 3 are planned to take place in FY2020. The total No. of Missions to Lower Middle Income Countries funded through AML/CFT Phase II is 112, of which 9 are planned to take place during FY2020. 44% of respondents to evaluation survey assessed work funded through the IMF topical trust fund on AML as efficient or highly efficient. 56% of respondents to evaluation survey assessed work funded through the IMF topical trust fund on CFT as efficient or highly efficient. | Target substantially exceeded - 66 technical assistance missions conducted. 178 missions conducted since the beginning of the programme against a target of 50.
|  | Source | [5 empty] | RISK RATING
|  | IMF TTF and WB TF results frameworks | [5 empty] | Moderate
| Output Indicator 1.2 |  | Baseline (Jun 17) | Milestone Jun (18) | Milestone 2 (Jun 2019) | Milestone 3 (Jun 20) | Target (March 21) | Assumptions
| There is a lack of consistency in approach to the provision of business integrity support from UK missions, and the quality of that guidance varies. | Planned | Number of SME reached with quality advice through BII Hub. Number of country pilots operationalised for providing in country specific advice to SMEs. | DFID-FCO-DIT business Integrity Initiative approach and resourcing agreed across HMG; Digital integrity content on GREAT.GOV.UK refreshed | The Business Integrity Hub is established with a landing page on great.gov.uk and two civil servants located within DFID who effectively handle business enquiries. All 3 country pilots are operational, with local pilot managers recruited and work plans agreed. | Availability of study confirming the results to date for BII including satisfaction by SMEs, effectiveness of pilots and effectiveness of the Hub. A second batch of pilots is started taking on board lessons learned from study | At least 70 SME reached with quality advice through BII Hub. At least 3 country pilots operationalised for providing in country specific advice to SMEs. | HMG business support is fragmented, especially for SMEs. There is a reputational risk for the UK and financial/reputational risks for UK companies if the latter do not act with integrity when doing business abroad. There is a lack of consistency in approach to the provision of business integrity support from UK missions and the quality of that guidance varies.
|  | Achieved |  | DFID-FCO-DIT Business Integrity Initiative approach agreed across HMG. First Steering Group meeting completed and governance structure of the Initiative agreed. Prime Minister announced the Business Integrity Initiative in Kenya (August 2018). | The Business Integrity Hub is established with a landing page on great.gov.uk two civil servants located within FCDO who effectively handle business enquiries. All 3 country pilots are operational, with local pilot managers recruited and work plans agreed. Activities ongoing in each Pilot country with MEL Agents contracted to review, assess and adjust workplans. Steering meeting took place on 25/09/2019. Participation from business, government and public sector. Professional, consistent and tailored consultancy guidance services available for compliance, prevention, collective action and human rights and being accessed by SME's. | Target met - Evidence has been collated from the BII’s three pilots and UK activities, with high satisfaction scores. Target not met - A second round of pilots was not started due to COVID operational difficulties and budget cuts resulting from ODA reprioritisation.
|  | Source | [5 empty] | RISK RATING
|  | See nested BII Logframe | [5 empty] | Moderate
| Output Indicator 1.3 |  | Baseline (Jun 17) | Milestone 1 (June 18) | Milestone 2 (June 19) | Milestone 3 (June 20) | Target (March 21) | Assumptions
| Increased number of investigations for corruption offences, including money-laundering linked to wildlife crime both in origin states and third-party states through which linked illicit financial flows may have passed. | Planned | No support provided to law enforcement to complete financial investigations, including an asset forfeiture element. No typology report from UNODC available to increase understanding on the financial movements related to Illegal Wildlife Crime (IWC). No FIUs receiving mentoring (from ECOFEL) to improve their production of financial intelligence information related to wildlife crime. No regional events held by ECOFEL to bring together private sector and FIUs, to increase the quantity and quality of reporting. | N/A | UNODC - Inception phase completed (staff and consultants recruited; potential recipient countries identified). At least 2 recipient countries confirmed, including agreement on working modalities in those countries. ECOFEL - Inception phase completed (relevant expertise identified, mapping exercise of potential involved FIUs completed) with potential cases identified. | 6 ongoing or completed financial investigations, including at least 2 cases including an asset forfeiture element. UNODC - First version of the typologies report available, increasing understanding on the financial movements related to IWC and the business models used by wildlife criminals. Publication on sanctions available, providing guidance on alternative sanctions (visa bans etc.). ECOFEL - FIUs selected to be mentored to improve their production of financial intelligence related to wildlife crime number and quality), supporting operational needs of domestic LEAs. One regional event bringing together private sector and FIUs, to increase the quantity and quality of reporting and trigger a more proactive approach with the private sector on financial information that may relate to IWT cases. | 12 cumulative) ongoing or completed financial investigations, including at least 4 cases including an asset forfeiture element. UNODC - Advanced information on typologies available, providing information on the financial movements related to IWC and the business models used by criminals. Online resource on sanctions available, providing guidance on alternative sanctions (visa bans etc.). Selected FIUs completed their mentoring process increasing the number and quality of financial intelligence disseminations related to wildlife crime. 2 (cumulative) regional events bringing together private sector and FIUs, to increase the quantity and quality of reporting and trigger a more proactive approach with the private sector on financial information that may relate to IWT cases.
|  | Achieved |  | N/A | Milestone exceeded. UNODC - Inception phase has been completed. A team of staff members and consultants working in the project have been recruited, and the team will be expanded based on needs of the supported countries. Considering the great demand and growing number of activities, it is anticipated that a project coordinator based in Nairobi will be recruited in early 2020 A number of recipient countries have been identified. Case support is ongoing in many countries, including Uganda, Namibia, Ivory Coast and Botswana in which current support modalities have been agreed upon – modalities are tailored based on needs and structures of each country and are being adjusted as the team learns from the on-going work. The team has invested in building relationships and analysing the capacities and preparedness of a number of other potential recipient countries; support is expected to commence in 2020. ECOFEL - Inception phase completed. Search and outreach to experts completed: It was possible to identify that expertise that can support the implementation of the project is limited. There are experts in wildlife conservationism and experts in identification of financial flows, but there is a gap between those two expertise. In this sense, it was decided to conduct the research in-house, shaping the deliverables according to the findings and needs. Mapping exercise completed. Countries in the operational route of identified, distinguishing their place as source, transit and destination country. Analysis of FIUs that could be potentially involved completed. | Target substantially exceeded - 37 ongoing/completed investigations, including at least 14 cases with an asset forfeiture element. Target not met - A Case Digest report has been developed but is yet to be published. Target not met - A sanctions tool has been developed and is currently being developed as an online resource. Target met – Mentorship programme now has 15 mentees. Target not met – Due to the pandemic, no regional events of this nature were able to take place, partner has plans for this to happen in early 2021.
|  | Source | [5 empty] | RISK RATING
|  | IWT Joint logframe | [5 empty] | Moderate
| Output Indicator 1.5 |  | Baseline (Jun 17) | Milestone 1 (June 18) | Milestone 2 (June 19) | Milestone 3 (June 20) | Target (March 21) | Assumptions
| Governments are better able to identify and mitigate corruption risks in their defence and security institutions (TI Defence and Security) measured by quality and engagement on the GI and its findings, TI regularly publishing in-depth assessments of defence sectors' vulnerabilities to corruption and recommendations to improve defence governance. | Planned | N/A | 5 Global Defence Anti-Corruption Index assessments and recommendations published with DFID support. | 10 Global Defence Anti-Corruption Index assessments and recommendations published with DFID support. | 25 Global Defence Anti-Corruption Index assessments and recommendations published with DFID support. | 40 Global Defence Anti-Corruption Index assessments and recommendations published with DFID support. | This is a cumulative number of GI assessments produced and published with FCDO's support with a total of 40 assessments by the end of the grant duration.
|  | Achieved |  | 8 points based on the engagement matrix. | Government Defence Anti-Corruption Index (GI) continues with the data collected on 16 countries in the West Africa, Central and Eastern Europe, and MENA waves. All 16 assessments have been submitted for government | Target not met - 21 assessments and accompanying county profiles published taking the overall cumulative number of assessments to 37 against the overall target of 40 assessments.
|  | Source | [5 empty] | RISK RATING
TI D and S logframe engagement matrix: points are cumulative
IMPACT WEIGHTING (%) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
25% | IMF+WB+BII+TI D&S
DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (Jun 17) | Milestone 1 (June 18) | Milestone 2 (June 19) | Milestone 3 (June 20) | Target (March 21) | Assumptions
Corruption is exposed and detected through improved company beneficial ownership transparency and stronger financial intelligence units especially in London Anti-Corruption Summit countries passing cases to domestic and international investigations | Open national registers of company beneficial ownership are established and compatible with international Open Ownership (OO) Register; Number of entries on global register. | Planned | Zero entries on OO Register. No OO Register operational that includes data from UK PSC Register. [Plans for open national registers in Ghana and Ukraine.] | 4.8m entries on OO Register. Plans for open national register being developed in 1 additional Summit country and data compatible with OO register. | 200,000 entries on OO Register. 1 open national register developed in1 Summit or DFID priority country and compatible with OO register. | 500,000 entries on OO Register. 1 Open national register developed in 1 additional Summit or DFID/FCDO priority country and compatible with OO register. | 6m entries on global OO Register and open national register being developed in 2 Summit or DFID/FCDO priority countries and compatible with global register. | Continued political commitment to take forward Summit commitments even if governments change in county - need to work with new governments/cso's/business to maintain momentum.
INPUTS (HR) |  | Achieved |  | 4.8m entries on OO Register; Nigeria and Ghana have recently passed legislation for establishing national registers. | Milestone exceeded. Currently 5.9 million companies on the register. Four Countries currently have free to access beneficial ownership registers, these include the UK, Ukraine, Slovakia and Denmark. Continued support to Ukraine, Kyrgyz, Nigeria. Technical assistance beginning now with Armenia and Kenya. | Target substantially exceeded - This indicator has already substantially exceeded the entire programmes milestones with 6.8m companies on the register as of June 2020, and 7.6m beneficial owners identified across 14.2m records. Target met for one open national register developed in Ghana.
|  | Source | [5 empty] | RISK RATING
|  | Open Ownership reporting (register.openownership.org). | [5 empty] | Moderate
| Output Indicator 2.2 |  | Baseline (Jun 17) | Milestone 1 (Jun 18) | Milestone 2 (Jun 19) | Milestone 3 (Jun 20) | Target (March 21) | Assumptions
| Capacity and evidence on company beneficial ownership | Planned | Fragmented implementation, and limited understanding of company beneficial ownership transparency (BOT) | TORs for beneficial ownership scoping study on capacity needs and international architecture available. | 3 case studies of how/why to set up company beneficial ownership registers and use of information (OO/U4/EITI) | Enhanced UK and international technical assistance capacity in place | Robust UK and international technical assistance capacity in place
|  | Achieved |  | TORs for beneficial ownership scoping study drafted. | Open Ownership has assessed countries they are assisting to set up registers. A Scoping Study was completed in January this year on how to reach a global norm and that includes an assessment of progress in several countries on BOT. A private sector study has been commissioned and we are working to develop technical assistance via BEIS, Companies House and JACU. Some TA is already in place through Open Ownership. EITI - 8 countries receiving technical / financial support for the development of EITI BO roadmaps, commodity trading approaches, and undertaking mainstreaming activities that go beyond the EITI minimum standard (cumulative). These include Afghanistan, DRC, Myanmar, Zambia, Ghana, Liberia, Malawi, Nigeria). Specific support activities delivered in Ghana, Afghanistan, Malawi, Myanmar, and Nigeria. | Target met - OO have scaled up their TA to countries implementing BOT and established regional posts to facilitate technical assistance has been provided to a number of countries including Armenia, Ghana, Liberia, Mexico, Nigeria, Ukraine and Zambia.
|  | Source | [5 empty] | RISK RATING
|  | Scoping study and follow-up to recommendations | [5 empty] | Moderate
| Output Indicator 2.3 |  | Baseline (Jun 17) | Milestone 1 (Jun 18) | Milestone 2 (Jun 19) | Milestone 3 (Jun 20) | Target (March 21) | Assumptions
| Improvements in capacity and international collaboration by FIU members of Egmont. | Planned | ECOFEL being designed in 2016-17 under IACT Year 1 programme | Egmont Centre for Financial Intelligence Unit Excellence and Leadership (ECOFEL) central or peer support piloted on demand from 1 Summit / DFID priority country. | ECOFEL support results in improved capacity and cases passed to investigators from 1 summit / DFID priority country | ECOFEL support results in improved capacity and cases passed to investigators from 2 summit/ FCDO priority countries | ECOFEL support results in improved capacity and cases passed to investigators from 4 summit //FCDO priority countries
|  | Achieved |  | ECOFEL central or peer support piloted on demand in 1 Summit / DFID priority country. | Milestone achieved. ECOFEL support provided to the FIUs from Summit/DFID priority countries is demonstrated by extensive participation of the staff of those FIUs in ECOFEL capacity building activities, such as participation in training courses delivered and enrolment into eLearning platform and courses developed by ECOFEL. ECOFEL's capacity building activities resulted in increase in the number and quality of case disseminations by relevant FIUs to law enforcement agencies. | Target met – Cases passed to investigators from 2 summit/FCDO priority countries (Nigeria and Afghanistan).
|  | Source | [5 empty] | RISK RATING
|  | ECOFEL results framework priorities 1 and 3 | [5 empty] | Moderate
IMPACT WEIGHTING (%) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
25%
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (Jun 17) | Milestone 1 (Jun 18) | Milestone 2 (Jun 19) | Milestone 3 (Jun 20) | Target (March 21) | Assumptions
Corrupt actors are held to account and victims are reimbursed through the tracing, recovery and return of stolen public assets | Number of ICAR supported cases in DFID target countries completed leading to conviction and/or recovery with return of assets. | Planned | No ICAR supported cases completed leading to conviction, recovery and return of assets in DFID priority or Summit countries | 48% of cases have taken 4 or more steps towards conviction above baseline. | 48% have taken 4 or more steps towards conviction above Milestone 1 40 % have taken at least 4 steps toward conviction. | 48% have taken 4 or more steps towards conviction above Milestone 2 | 2 ICAR supported cases completed leading to conviction, recovery and return of assets in FCDO priority or Summit countries | Each country has its own number of steps towards conviction.
|  | Achieved |  | 47.1 % have taken at least 4 steps toward conviction. | For the period July 2018 to December 2018 11% to 13% of cases have made at least 4 steps toward conviction since 1 January 2018. For the period 1 January to 30 June 2019 9.3% of cases over 4.5 months have made at least 4 steps, so in total this equates to 20.3% in total so this is below the target for milestone 2 (June 19). This does not take into account a 12 months period. ICAR expect the number to go up significantly by the end of the year. A full 2019 draft report will be provided to donors in late November/early December, 49% of cases have made at least one step since the same date, together totalling 199 steps toward conviction, recovery, freezes, confiscation and return. Note on why milestone has not been achieved..(This is still a very new measurement tool which ICAR are currently revising to correct some of the weaknesses. Part of this weakness is that it catches all the cases that ICAR work on, including those that ICAR are involved in for a limited period of time. During that time it is for example not likely that a case makes 4 steps, and ICAR might not even be involved in 4 steps as their assistance is only required say, for a particularly complex MLA request, or for one piece of financial analysis. So it looks like this case is only making 1 step while that only applies to the time period during which ICAR were involved. These ad hoc advices that ICAR provide are quite important, and have increased significantly which in itself is a good sign, but it creates problem for the data gathering. ICAR will need to rethink their expectations on what type of data can be measured. The external review team will be looking further at the metrics for the results framework. | Target moderately exceeded - ICAR worked on a total of 87 active cases in 10 jurisdictions. 47 out of the 87 cases (54%) made four steps or more towards conviction or confiscation. Over £100m stolen assets recovered with ICAR’s support between 2017 and 2020.
|  | Source | [5 empty] | RISK RATING
|  | ICAR results framework output indicator 2.1 | [5 empty] | Moderate
| Output Indicator 3.2 |  | Baseline (Jun 17) | Milestone 1 (Jun 18) | Milestone 2 (Jun 19) | Milestone 3 (Jun 20) | Target (March 21) | Assumptions
| Number of policy events influenced on asset recovery through developing the knowledge base. | Planned | Zero global policy events (through IACT funds) influenced on asset recovery through use of WB developed knowledge products. | N/A | At least 1 knowledge product produced to address identified knowledge gap /emerging trend on asset recovery and used at least at 1 global leadership event on asset recovery. | At least 1 knowledge product produced to address identified knowledge gap /emerging trend on asset recovery and used at least at 2 global leadership event on asset recovery. | At least 4 (cumulative to date) global policy events influenced on asset recovery through use at least 2 (cumulative to date) WB developed knowledge products.
|  | Achieved |  | N/A | Milestone exceeded. Knowledge gaps and emerging trends identified and addressed in new knowledge products: 3 new knowledge products published over the past year: • E-filing Asset Declarations: Benefits and Challenges https://star.worldbank.org/publication/e-filing-asset-declarations-benefits-and-challenges • International Partnerships on Asset Recovery https://star.worldbank.org/publication/international-partnerships-asset-recovery • Financial Intelligence Units Working With Law Enforcement Authorities and Prosecutors https://star.worldbank.org/publication/financial-intelligence-units-working-law-enforcement-authorities-and-prosecutors.Concrete inputs into key global asset recovery policy themes through leadership at events and through use of knowledge products: Inputs/contributions on asset recovery policy issues to around 20 events, July 2018-June 2019 | Target met - 2 products produced by StAR: Going for Broke, Enhancing Government Effectiveness and Transparency: The Fight Against Corruption. StAR held a day of workshops at the UN COSP and participated in 23 national level events.
|  | Source | [5 empty] | RISK RATING
|  | WB StAR Results Framework | [5 empty] | Moderate
| Output Indicator 3.3 |  | Baseline (Jun 17) | Milestone 1 (Jun 18) | Milestone 2 (Jun 19) | Milestone 3 (Jun 20) | Target (March 21) | Assumptions
| Number of countries assisted by StAR have increased capacity to recover stolen assets. | Planned | Zero countries assisted (through IACT) by StAR have increased capacity to recover stolen assets. | N/A | 3 countries improving legislative framework on asset recovery. 3 asset recovery cases opened that include a proceeds of corruption component. 2 countries with improved domestic co-ordination mechanisms adopted as asset recovery action plan. | 3 additional countries improving legislative framework on asset recovery. 3 additional asset recovery cases opened that include a proceeds of corruption component. 2 additional countries with improved domestic co-ordination mechanisms adopted as asset recovery action plan. | 16 countries cumulative assisted by StAR have increased capacity to recover stolen assets.
|  | Achieved |  | N/A | Milestone met. Number of countries improving legislative framework on asset recovery: 3 countries (Ongoing process: 10 countries). Milestone exceeded. Number of countries with improved domestic co-ordination mechanisms: e.g. adopted an new country action plan, strategy or issued new MOU 3 countries (Ongoing process: 12 countries). Milestone exceeded. Number of asset recovery cases opened that include a proceeds of corruption component: Cases opened in 5 countries Cases concluded (assets returned) in 1 country. | Target met – Countries improving asset recovery legislative frameworks 2 (Ukraine, Armenia) and ongoing process: 10 countries. Asset recovery cases opened that include a proceeds of corruption component: 4. Countries improved domestic co-ordination mechanisms: 2 countries (Ecuador, Ethiopia) and ongoing process: 6 countries. Cumulative total is 19 countries assisted by StAR with 16 ongoing.
|  | Source | [5 empty] | RISK RATING
[5 empty] | WB StAR Results Framework |  |  | Moderate
IMPACT WEIGHTING (%) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
20%
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (Jun 17) | Milestone 1(Jun 18) | Milestone 2 (Jun 19) | Milestone (Jun 20) | Target (March 21) | Assumptions
IACT partners work effectively together internationally and in DFID priority countries to close routes for corruption | Governments in Summit countries are held to account internationally and in country for delivering Summit commitments (TI-UK) | Planned | 4 national Summit pledge trackers operational under Year 1 programme for Afghanistan, Ghana, Kenya and UK. | 4 national Summit pledge trackers operational and 4 more in development; National advocacy strategies developed by TI chapters and partner organisations in 1 partner country; 1 governments has advanced their commitments on BOT, Asset Recovery, law enforcement, up at least one category | 2 additional national Summit pledge trackers operational; National advocacy strategies implemented by TI chapters and partner organisations in 1 additional partner countries; 1 additional governments have advanced their commitments on BOT, Asset Recovery, law enforcement, up at least one category since previous year | 2 additional national Summit pledge trackers operational; National advocacy strategies implemented by TI chapters and partner organisations in 1 additional partner (at least 1 FCDO) countries; 1 additional governments have advanced their commitments on BOT, Asset Recovery, law enforcement, up at least one category since previous year | 8 national Summit pledge trackers operational; National advocacy strategies implemented by TI chapters and partner organisations in 5 partner (at least 2 FCDO) countries; 3 governments have advanced their commitments on BOT, Asset Recovery, law enforcement, up at least one category since previous year
|  | Achieved |  | 4 Summit pledge trackers are operational in Afghanistan, Ghana, Kenya and the UK and 4 more are being developed in Jordan, Mexico, Nigeria and Sri Lanka. The latter 4 are expected to be operational by October 2018. Advocacy strategies developed in 5 countries (Afghanistan, Sri Lanka, Jordan, South Africa, and UK). 3 countries meeting commitments on beneficial ownership (Afghanistan, Kenya, Ukraine). New Zealand law enforcement joined the International Anti-Corruption Coordination Centre. Global Forum on Asset Recovery rated UK and Spain complete in relation to their commitments. | Most recent iteration of the Global Anti-Corruption Pledge Tracker in May 2019, tracking 18 countries, including: Afghanistan, Australia, Brazil, Bulgaria, Georgia, Ghana, Indonesia, Kenya, Mexico, New Zealand, Nigeria, Russia, South Korea, Spain, Sri Lanka, Switzerland, UK and Ukraine. | Target met - 8 Summit pledge trackers are operational in Afghanistan, Ghana, Kenya, UK, Jordan, Mexico, Nigeria and Sri Lanka. Target Met - Advocacy strategies developed in 5 countries (Afghanistan, Sri Lanka, Jordan, South Africa, and UK). Target exceeded by 1 - 4 additional country meeting commitment on beneficial ownership (Afghanistan, Ukraine, Mexico and Kenya) - Target Met - 3 additional country meeting commitment on asset recovery (Nigeria, Ghana and Jordan)
|  | Source | [5 empty] | RISK RATING
|  | TI summit tracker logframe: outcome indicator 1 complete, underway, ongoing assessments for commitments; output indicator 2.2 on national advocacy strategies. | [5 empty] | Moderate
IMPACT WEIGHTING (%) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
15%
DFID (FTEs)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline (Jun 17) | Milestone 1 (Jun 18) | Milestone 2 (Jun 19) | Milestone 3 (Jun 20) | Target (March 21) | Assumptions
Evidence and lessons on how to reduce corruption are systematically collated, incorporated into the programme and used to evidence further UK and international action | Anti-Corruption evidence (ACE) programme research grants . | Planned | No systematic research on impact of international work on incentives for corruption | British Academy (BA ACE) completes second round grant completion and funds at least 4 new research grants on international Anti-Corruption | New agreement with Global Integrity signed and all ACE grants on international corruption are on track at end of year 1 (Jan 19); their research uptake strategies are on track (March 19) and have produced at least 1 public product (May 19). | All grants on international corruption are on track at end of year 2 ( Jan 20) research uptake strategies are on track (March 20) and have produced at least 1 additional public research and/or policy product (May 20). | All ACE grants on international corruption completed and at least 3 public products produced, including at least 1 research output ( March 2021).
|  | Achieved |  | Implementer could not complete second round of grants. | New agreement with GI was signed on 31st October 2018. A launch meeting with new grantees took place early in Jan 2019 in Washington. A range of high quality applications addressed the international dimensions of anti-corruption related to beneficial ownership. The research update strategies are on track as of March 19. The studies relating to Beneficial Ownership are: 1) Hiding the beneficial owner and the proceeds of corruption. Focussed on Nigeria, this project examines current approaches and system weakness for successfully identifying the beneficial owner, thereby, preventing the laundering of the proceeds of corruption and aiding asset recovery. https://ace.globalintegrity.org/projects/benowner/ 2) Testing and evidencing compliance with beneficial ownership checks. This study aims to investigate the laundering of monies and reputations by elites from African and Central Asian kleptocracies by looking at the due diligence requirements in the banking, real estate, charitable and public relations sectors https://ace.globalintegrity.org/projects/benownerchecks/ 3) Does transparency bring cleanliness? Offshore financial secrecy reform and corruption control. This study makes use of leaked and newly constructed datasets to understand the impact that offshore financial secrecy reforms are having on the use of shell companies for the hiding of developing country corruption proceeds https://ace.globalintegrity.org/projects/transparency/ Public products include, programme and information notes, various blogs and video evidence Before UK Parliament’s Foreign Affairs Committee – June 5, 2019. | This component is no longer part of our programme.
|  | Source | [5 empty] | RISK RATING
Moderate
| Output Indicator 5.2 |  | Baseline (Jun 17) | Milestone 1 (Jun 2018) | Milestone 2 (Jun 19) | Milestone 3 (Jun 20) | Target (March 21) | Assumptions
| IACT partners' international collaboration to share lessons. | Planned | Zero collaboration and lesson learning through IACT programme | MEL partner in process of being selected. | MEL agent contracted. | MEL partner in place coordinating systematic lesson-sharing; U4 recording and disseminating lessons. 2 learning events held for IACT partners to share lessons and form synergies.( U4 recording and disseminating lessons). | Midterm and end of project reports measuring the effectiveness of the programme produced. 3 learning events held for IACT partners to share lessons and form synergies.
|  | Achieved |  | Evaluability assessment carried out as a first step towards selecting a MEL partner. | Contract now signed with IPE Global and they will act as the Monitoring and Learning Agent for the I-ACT Programme from 21/10/2019 to 31/03/2021 They will attend the Learning Day event in Nov 2019 and 1st Milestone is due by 21/01/2020, the Inception Report will include revised I-ACT Logframe, revised Theory of Change, a VfM Framework, MLA reporting plan, MLA learning approach and a case study design. | Target Met – MLA and MEL partners has been contracted and is meeting all milestone expectations. Target met – 2 learning events held, one in November 19 and one in June 20 (virtually).
|  | Source | [5 empty] | RISK RATING
|  | MEL Agent Mid-term and PCR | [5 empty] | Moderate
| Output Indicator 5.3 |  | Baseline (Jun 17) | Milestone 1 - visits and sessions (Jun 18) | Milestone 2 - repeat visits (Jun 19) | Milestone 3 (Jun 20) Helpdesk | Target (March 21) | Assumptions
| Visits and repeat visits to U4 website and number of helpdesk responses. | Planned | Visits : - 117,322 Repeat visits 30%. Help desk enquires 25 | Visits: 104,970 repeat visits: 27.8% of visitors made repeat visits Number of helpdesk responses: 24 | Visits: 105,000 visits Repeat visits: 28% of visitors make repeat visits Number of helpdesk responses: 20 | Visits: 105,000 visits Repeat visits: 28% of visitors make repeat visits Number of helpdesk responses: 20 | 105,000 site visits with 33% repeat visits and 47 (cumulative) helpdesk responses provided.
| Target for helpdesk enquiries is 25 per year | Achieved |  | Visits: 102,016 visits Repeat visits: 25% of visitors make repeat visits Number of helpdesk responses: 22 | 1) Visits and repeated visits to the U4 website between July 2018 and June 2019: Visits: 159,705; Returning visitors: 23,5% (Due to the increase in sessions compared to the previous year, it’s natural that the repeat visitor rate is somewhat lower.) 2) Number of Helpdesk responses between July 2018 and June 2019: 30. 3) Number of enquires between July 2018 and June 2019: 41 | Target substantially exceeded - 332,713 Visitors to the website. Target not met - 11.4% returning visitors same period. Target substantially exceeded - 31 helpdesk responses.
|  | Source | [5 empty] | RISK RATING
|  | U4 results framework | [5 empty] | Moderate
IMPACT WEIGHTING (%) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
ACE+U4
15% | DFID (FTEs)