## POF Results Framework
Peacebuilding Opportunities Fund - Results Framework
Notes:
1 | Column 'I' shows end of programme targets, together with scoring criteria
2 | Columns 'L' to 'O' show quarterly milestones, to be reported against
3 | In column 'I', some activities link to outputs in the POF Workstreams Tab (reference 'Cx') | [6 empty] | Scores below reflect the POF-self-assessment. The Annual Review scoring is reflected in the Annual Review Report. CLICK for the full report.
[5 empty] | PROGRAMME TARGETS / STANDARDS |  |  | 2020 JUNE MILESTONES | 2020 SEPTEMBER MILESTONES | 2020 DECEMBER MILESTONES | 2021 MARCH MILESTONES | 2021 JUNE MILESTONES
Theory of Change element | Relevance (qualitative baseline) | Output 1 | Assumptions | Indicator 1.1 | Activities / Deliverables |  | At least 5 POF activity concept notes approved by FCDO and implemented. POF Learning Paper: POF approach to using evidence and learning in activity design and implementation. | As per gradations below | At least 3 concept notes approved; 1 concept paper reviewed by Expert Advisory Network | At least 2 concept notes approved; 1 reviewed by Expert Advisory Network | Evidence that activity implementation reflects concept design and approach | POF Learning Paper: effectiveness of POF approach to incorporating evidence and learning in activity design and implementation
If design is based on and generates analysis and learning, and facilitates sharing of learning across programme locations; | General approach tends towards reflexive (not reflective) application of models which do not have proof of concept. Where learning exists it is often decoupled from implementation, or only revisited once the impact potential of the learning has diminished or the context has so significantly that re-analysis is required. Few existing forums for cross-region engagement among implementers that includes national and international staff. | The POF uses evidence-based analysis and learning to drive and review decision-making. Weighting: 20% | Evidence POF is using is reliable. Evidence is being used in appropriate ways (i.e. correct lessons are being applied). Decision-making is timely. Despite differences in context, there is learning from each location that can provide focus for profitable areas of inquiry elsewhere and/or ideas from one area may be applicable in different areas. | Rigour of learning and evidence basis to activity selection. | Qualitative scoring Target for year end = A |  | C - Limited or no evidence that POF activities are based on evidence and learning. Activity concept notes not produced or incomplete. B - Knowledge and learning incorporated in POF activity design. A - Knowledge and learning incorporated in POF activity design, and iterative stakeholder consultation used to strengthen design and implementation. [source: concept notes and advisory network meeting records]. A+ - POF evidence and learning supports non-POF programming - other stakeholders using POF learning for programmatic thinking [source: interviews with other stakeholders] | 1 - Limited or no evidence of activities based in learning and/or concept notes are not produced, have key sections incomplete before starting activities, or include only perfunctory coverage of key sections, and/or are based on simplistic analysis. 2 - Concept notes and discussions around activity selection make use of evidence and prior lessons learned, including from other Areas, and conflict analysis, and are linked directly to the POF theory of change. Where activities are research oriented, concept notes clearly indicate the how the research links to the theory of change [source: concept notes]. 3 - Evidence from meeting records and other documentation of stakeholder consultation around specific activities that are planned, and review of concept notes by at least one relevant member of Advisory network. [source: concept notes and advisory network meeting records] 4 - Activities are delivered in partnership with local personnel (either consultants and/or organisations), who report a significant level of professional development through the implementation of the activities. [source: quarterly learning/reflection journal by POF direct partners] | Quarterly update Score achieved: A. This quarter, an example of activity selection that has been data-driven and informed by learning, is development of a new concept note “To reinvigorate Lakes state dialogue system” which started with a learning process on why previous dialogues among sections of the Dinka Agar had failed. Consulting with government officials, local chiefs, and Rumbek-based intellectuals, the POF team identified several factors responsible for the collapse of previous peace agreements including resolutions that were pre-drafted without the input of the parties in conflict, blood compensation not paid, lack of monitoring mechanisms, and no agreed consequences for violators. On the basis of this learning, POF will organize a pre-conference dialogue ahead of an internal annual cattle migration conference in November 2020. Similarly, the four dialogues in Bentiu (attended by 200 participants — 150 from the POCs and 50 from Bentiu town) were informed by evidence indicating a role of women in smuggling guns into the POCs and aiding revenge killings. The Magwi and Kajo-Keji Peace Forums were similarly informed by lessons learned from the Pageri Peace Forum and by evidence from meetings and consultations conducted with relevant actors in the two locations. Next quarter: the use of evidence-based learning to inform and review decision-making will remain central to POF management of interventions. This has been central to learning and the adaptation within the ‘Pageri’ conflict system, which has seen activities undertaken in Magwi and Kajo Keji. In the next quarter these activities will continue, and flex as needed if/when county level government is formed. Similarly, Jonglei-facing engagement will respond to opportunities currently being identified and discussed with HMG around discreet engagement with traditional leaders within the conflict system. This is a decisive adaption of the original concept, based on learning: where an iterative process of consultation has gradually distilled some of the key configurations of specific actors. In Bentiu, planning for three activities set out in the Area PECA will commence and adapt to new information from communities emerging as detailed consultation and planning commences. | Quarterly update (insert text) | Quarterly update (insert text) | Quarterly update (insert text)
[5 empty] | Actual | Q1 | A
Q2
Q3
[6 empty] | Q4 |  | SCORE: 3/4 There was ample evidence of high-level application of learning to activity selection. Altogether five concept notes were generated (i.e., Pageri Peace Forum; At-Risk Youth Cattle Camp Research; Logging Research; Learning Towards a National Agenda for Reconciliation; and Women, Peace, & Security: Strengthening Community Governance through Cultural Processes) during the quarter. The concept notes either generated evidence base to inform activity selection or were themselves informed by careful review of evidence and learning from previous peacebuilding efforts. For example, the at-risk youth study in Rumbek led to an evidence-driven identification of peacebuilding opportunities within the camps that will be elaborated and refined in a phase 2 concept note (e.g., cattle migration and governance conference in November 2020, agricultural and life skills training programs for youth, and inter-camp cultural and sporting exchanges). The reconciliation review provided evidence on what worked in previous initiatives and learning opportunities (e.g., an understanding of strengths and weaknesses of previous initiatives and common enablers and barriers to effective peacebuilding) for stakeholders involved in peacebuilding at the national level. In terms of learning from previous peacebuilding efforts, the POF team learned that there had been four previous attempts to resolve the conflict in the Pageri/Nimule area. The previous peacebuilding efforts failed because they were event-based, where resolutions were not followed up. Therefore for POF, the Pageri Peace Forum was designed with the accompaniment process and sustainability in mind right from concept note development. The key learnings from the initial assessment that informed the Peace Forum were sustained engagement when supporting peace dialogues, the need to have peace dialogues hosted by legitimate authority with experienced mediators leading the process, and the need to be aware of potential spoilers that can undermine key work done by others. POF also reviewed previous peace agreements between Agar communities and incorporated into the at-risk youth study questions about why these agreements failed and what could be done differently to preserve and deepen such agreements. Moreover, evidence from previous studies and policy briefs on peace building in South Sudan were used to inform the reconciliation review. Lastly, there was high level of consultation and engagement with stakeholders and local actors during the quarter. For example, the Pageri Peace Forum included an active role for the church and local county and state authorities including organized forces. In addition, responses from meetings with women groups informed the intervention for the Monyomiji initiative. .
|  |  |  | Indicator 1.2 | Activities / Deliverables |  | 4 Area Advisor meeting reports At least 4 POF Lessons Learned Papers (C3) 1 South Sudan Peacebuilding Practitioner paper | As per gradations below | 2 Area Advisor meeting reports; 24 Advisor teams posts and 60 replies | 1 Area Advisor meeting report; 2 draft Lessons Learned Papers | 1 Area Advisor meeting report; 2 finalised Lessons Learned Papers; 2 draft Lessons Learned Papers | 2 finalised Lessons Learned Papers; 1 South Sudan Peacebuilding Practitioner paper
|  |  |  | Functionality of learning, review and decision-making system that ensures adaptive management of the activities | Qualitative scoring Target for year end = A |  | C - Learning not applied to POF activity design or implementation. B - Learning reflected in POF activity design and implementation, and highlighted in quarterly meetings of advisors and through National Advisory network. [source: minutes from Area Advisor meetings, interviews with Advisors and other partners, National Advisory Network minutes] A - Learning acted on. POF Area Advisors demonstrate ways in which workplans were adapted based on learning and review. [source: Area advisor meeting minutes, POF quarterly reports narrative and emerging lessons] A+ - Learning transferred. Activities effective in one location considered for scale-up in the same area or roll-out in other regions. Activities found to be not effective are revised or stopped. [source: POF decision log and quarterly reports] | 1 - The 'learning system' (Area advisor meetings, Advisory Network consultations, HMG engagement, research products) is either incomplete and/or not applied in key dimensions and/or decisions are not based on learning and/or decisions are not implemented. 2 - Quarterly meetings of advisors incorporate routine learning; advisors share lessons learned from their work (e.g. from consultative meetings, implementation efforts, etc.); lessons are reflected upon actively, with discussion of how activities can be adjusted in response. National Advisory network is active. [source: minutes from Area Advisor meeting minutes, interviews with Advisors and other partners, national advisory network meeting minutes] 3 -Following completion of activity-specific evaluations, results are shared with area advisors and POF staff; time for dedicated discussion of lessons is provided; advisors and POF staff come prepared with comments on learning documents; evidence is provided of where recommendations and learning have been addressed. [source: Area advisor meeting minutes, POF quarterly reports narrative and emerging lessons sections] 4 - Activities found to be effective in one location were actively considered for scale-up in the same area or roll-out in other regions (with appropriate adjustment, as necessary, for the context). Activities found to be not effective are revised or stopped. [source: POF decision log and quarterly reports] | Quarterly update Score achieved: B. A score level of B was achieved by POF during the July-September quarter. There was an active discussion and exchange of ideas among area advisors both on POF’s Microsoft Team’s page and during this quarter’s advisors meeting. In these discussions, lessons and ideas were shared. For example, during this quarter’s area advisor meeting, it became apparent that cattle raiding was a primary driver of conflict across all four locations. In addition, one of the area advisors from Bor went back with the Torit advisors because one of the conflict actors in the Pageri/Magwi area is cattle keepers from Bor. POF: Further to the above, POF management actively manages Area Advisers, invites collaborative and creative solutions, works with advisers to shape these in appropriate responses. For example, Magwi engagement, though planned, was accelerated upon receipt of information on pending violence against cattle keepers and a request from SSCC for funding. Advisers and an approved budget were deployed to Magwi to conduct a conflict assessment. POF designed a COVID-19 broadcasting response, with a strong peacebuilding focus, where HPF, ISRAAID, SSCC contributed to programming. The Hujang-Mayya main intervention was paused for a period of time because of dynamics with a separate peace actor that entered the ‘dialogue’ space after POF’s initial engagement, which POF advisers and management navigated by allowing this actor profile the intervention as theirs on national TV. In Rumbek, each step unfolds more dimensions; for example, the grassroots peace committees were brought together for ‘training’, and it rapidly became clear that they needed a dedicated space for discussing their issues before we could return to the technical role of the peace committees. Looking forward, the Area Advisor engagement in the Teams page has been useful as an information sharing platform and can shift more to sensemaking and lesson learning orientation in the next two quarters. Investment in the shared HMG-POF Teams page has not resulted in the level of engagement anticipated. While POF will continue to engage the Teams page, a useful repository of POF documents for HMG consultation, POF wishes to revert to stronger email update communication and more strongly involving relevant HMG personnel in the learning process. POF PD-TLs engagement will continue to focus on adaptive management issues within weekly meetings. | Quarterly update (insert text) | Quarterly update (insert text) | Quarterly update (insert text)
[5 empty] | Actual | Q1 | B
Q2
Q3
[6 empty] | Q4 |  | SCORE: 2/4 Since no activity-specific evaluations have been conducted and only one quarterly advisors meeting has been held so far, the score for this indicator is quite low for this quarter. With more frequent virtual meetings for area advisors and two activity-specific evaluation planned, it is expected that the score for this indicator will improve. Nevertheless, during this quarter's area advisor meeting, several lessons learned were shared and reflected upon actively. These included; 1) The need to be aware of the role of external political interests (i.e., conflict actors outside of the project locations) in derailing local peacebuilding efforts (e.g., military commanders for the Pageri Peace Forum, and intellectuals in Juba and the diaspora for the at-risk youth in Rumbek); 2) the need to build sustainability into project activities. For example previous peacebuilding efforts tended to be event-based where a dialogue ends and resolutions may not be followed up leading to a high failure rate. POF at the very start has focused on a process-oriented approach (e.g.; the Pageri Peace Forum being led by the church and local authorities) and working with existing structures in the community such as the Monyomiji leadership); and 3) the need to revisit traditionally accepted methods of conflict resolutions that have since been superseded by more violent methods. For example, area advisors from Rumbek shared that blood compensation (through payment of cows) used to be an acceptable method of resolving conflicts in Rumbek. However, with a rise in the prominence of guns in resolving conflict and the resultant failure to compensate victims, there has been a failure in reconciliation and a cycle of revenge killings that continue to plague the people of Lakes state.
|  | Output 2 | Assumptions | Indicator 2.1 | Activities / Deliverables |  | 4 x JACS quarterly monitoring reports 4 PECAs 1 Conflict Trends Review paper (July 2020 - June 2021) | As per gradations below | 1 JACS monitoring report submitted; 4 PECAs updated | 1 JACS monitoring report submitted; 4 PECAs updated | 1 JACS monitoring report submitted; 4 PECAs updated | 1 JACS monitoring report submitted ; 4 PECAs updated; Conflict Trends Review paper (July 2020 - June 2021).
...and if the programme team engages local actors in the conflict system and works with cultural and traditional actors; | Local actors often not integrated at the outset and shoe-horned into pre-determined initiatives, affecting effectiveness and acceptance of programmes. Other programmes often targeting 'wrong' actors - when you arrive deep on the ground, clear rejection of authority of actors chosen by peacebuilding actors (e.g. for peace conferences) There has been less familiarity amongst implementers with the cultural and traditional actors in different actors in areas; partly because they are not immediately visible or accessible, partly because there has not been a focus, partly because they are dismissed (e.g. on religious grounds). | The POF engages with local actors in the conflict system, targeting those who can most influence conflict, especially cultural and traditional actors Weighting: 20% | Programme team have the contextual knowledge to engage actors in a meaningful way and navigate the complexity of network structures in a given conflict system. Traditional actors still have influence and/or authority in the conflict systems. POF correctly identifies 'those who can most influence conflict'. | Quality of iterative conflict and actor mapping. | Qualitative scoring Target for year end = A |  | C - Conflict and actor mapping not undertaken. B - Conflict and actor mapping undertaken as part of quarterly Political Economy and Conflict Analyses (one per location). [source: PECA documents] A - Mapping undertaken in each location and updated to capture lessons and changing context. Conflict monitoring tracks conflict incidents and trends over time. [source: PECAs and conflict monitoring quarterly updates] A+ - Mapping informs non-POF programming and FCDO strategy and engagement. [source: Microsoft Teams discussions and/or minutes of relevant other meetings; quarterly reports] | 1 - Conflict and actor mapping is not conducted. 2 - Evidence of conflict system actor mapping, including assessment of actor influence on identified conflicts, as part of quarterly updated Political Economy and Conflict Analyses (one per location). [source: PECA documents] 3 - Conflict monitoring tracking monthly reports and presentations are tracking conflict incidents and type, trends (over time), and indicators are being amended / added as appropriate, including responsiveness to HMG requests [source: conflict monitoring updates quarterly] 4 - POF conflict mapping and analysis is stimulating ongoing HMG conversations. [source: Microsoft Teams discussions and/or minutes of relevant other meetings; quarterly reports] | Quarterly update Score achieved: A. A score level of A was achieved by POF during the July-September quarter. POF does conflict monitoring under the Joint Assessment on Conflict and Security (JACS) component. This includes a nine-month trend analysis. Nevertheless, there was an active recognition within POF that the PECAs need to be updated and that new actors in the conflict system needs to be engaged. For example, in Rumbek, intellectuals were consulted when the POF team was collecting evidence on why previous peace agreements between Dinka Agar sections had failed. In Bentiu, POF engaged various actors including chiefs, the diaspora (Nuer living outside South Sudan), women leaders, youth leaders, and local authorities (e.g., county commissioners) in pre-dialogue meetings with the ultimate goal of a having a main dialogue between different Nuer sections. Similarly, in Bor, extensive consultations were conducted with various conflict actors including people in POCs. POF: Further to the above, Lakes, EES, Jonglei, GPAA governors/ administrators have been engaged; Pageri Peace Forum has engaged governor, local government, traditional and religious leaders, SSPDF and Tiger Division commanders, SPLM-IO, IDPs, and refugees. In Rumbek, the Governor, Secretary-General, RRC, National Security, local chiefs, galweng youth, women’s leaders, Ministry of Gender and Social Welfare have all been engaged. There was an important process around engaging with the new Governor, given he is from a different part of the State outside the POF-identified conflict system and his acceptance of the POF emphasis wasn’t guaranteed. POF has been able to identify where the mutually supportive agenda lies, and maximising that. In Bor, the respective community leaders of the PoC communities and outside the PoC have been engaged in initial consultations on the returns process. POF increasingly using the media to reach local actors. Looking forward, POF sees engagement with local actors as a key strength, which it wishes to build on and deepen moving forward. The delivery methodology to deliver the Q3 JACS report, trialled in the last quarter, will continue. We will also experiment with the monitoring of ‘peace incidents’ in the POF conflict systems and see what emerges. POF management now uses the quarterly monitoring as a political analysis capacity building tool with Area Advisers, supporting analytical capacity development, and cross-location learning. POF will also continue to collaborate with CSRF and REACH on conflict analysis, with a commitment to meet in the next quarter to explore key learning from individuals conflict analysis approaches. POF plans to strengthen the positive working relationship with UNMISS CAD moving forward, across all areas. | Quarterly update (insert text) | Quarterly update (insert text) | Quarterly update (insert text)
[5 empty] | Actual | Q1 | A
Q2
Q3
[6 empty] | Q4 |  | SCORE: 3/4 There was evidence of conflict mapping which was iterative in nature with the PECA for each area being regularly updated whenever new evidence or learning becomes available. Whenever possible, the PECAs included an assessment of actor influence as well. One of the learnings that came out during the mapping exercises was the influence of elites based in Juba and the diaspora on peacebuilding efforts in the study location — for instance, scoping analysis in Bentiu confirmed an initial sense that rivalries between Riek Machar and Taban Deng Gai at the national level would have implications for intra-Nuer communal relations in the wider Bentiu area. In terms of the mapping, provisional mapping in Rumbek identified several actors including various sub-sections of the Agar community (Pakam, Rup, Kuei, Aliam-Toc 1, Aliam-Toc 2, etc.) and several neighbouring communities (Dinka Gok, Dinka Ciec, Dinka Jalwau, Dinka Luach-Jang, Dinka Atuot, and Nuer Mayendit), youth leaders, spiritual leaders/spear masters, and intellectuals (in Rumbek town, Juba, and the diaspora). Similarly the Pageri Peace Forum identified refugees in Uganda, local communities in Pageri, organized forces stationed in Pageri, commanding officers of these forces, cattle keepers living in the area, and owners of the cattle which include senior government and military officers as the actors in the conflict system in the area. During the quarter, POF provided inputs for the development of the South Sudan HMG JACS. This involved conflict monitoring and tracking incidents related to the JACS’ five thematic areas, particularly at sub-national level. The tracking is of open source information available through key media sources. Quarter 2 reporting will include the contribution of area advisor analysis sourced in the four locations in addition to open source information.
|  | Output 3 | Assumptions | Indicator 3.1 | Activities / Deliverables |  | 1 sustainability strategy paper Implementation of 4 peace dialogues monitored (C12, C26, C33) 1 Expert Advisory Network sustainability discussion paper 3 project proposals developed 1 local peacebuilding governance mechanism meeting with co-contribution; | As per gradations below | 1 sustainability strategy paper | 2 peace dialogue resolutions monitored; 1 Expert Advisory network sustainability discussion paper | 2 project proposals developed; 2 peace dialogue resolutions monitored | 1 project proposals; 1 local peacebuilding governance mechanism meeting with co-contribution;
...and implements sustained action arising from learning; | Most peacebuilding programmes, whether government or Church-led, foreign government or international agency funded, have not been sustained, at a minimum with losses of efficiency (e.g. Vistas, Access to Justice, etc). Capacity building programmes have had minimal impact to date. | The POF incorporates sustainability into its implementation approach Weighting: 10% | If POF can present a coherent forward plan, there will be appetite to fund it. Sustainability will not be achieved without some measure of ongoing material support. POF personnel will invariably end up working in successor programmes at some point. | Level at which sustainability is incorporated into the decision making process for engagements and activities. | Qualitative scoring Target for year end = A |  | C - Little evidence of sustainability being considered in POF activity design and implementation. B - Sustainability built into activity design and implementation. POF actively considers sustainability in funding decisions and POF activities promote sustainability. Structures and institutions supported by POF report sustained increase in level of activity during the life-cycle of the programme. [source: concept notes, activity reports, advisor interviews] A - Sustainability beyond the programme life-cycle. Evidence that activities and or institutions/structures will be sustained beyond the lifecycle of the programme. [source: quarterly strategy paper, quarterly reports] A+ - Evidence of POF influence on other actors' (local, national, or international) intervention design and/or funding decisions [source: finance reports, Advisor quarterly learning journals; quarterly reports] | 1 - There is negligible evidence in concept notes, meeting records and monitoring interviews with personnel and beneficiaries that sustainability is being considered in decision-making. 2 - POF actively considers sustainability in funding decisions, and engagements and activities specifically incorporate follow-up within activities (e.g., follow-up meetings to verify adherence to cross-community peace agreements; refresher engagement sessions; etc.) to encourage sustainability; concept notes also, as relevant, address why any previous similar activities may have proved unsustainable. [source: concept notes, activity reports, advisor interviews] 3 - POF develops and updates quarterly a sustainability strategy paper that identifies approaches to increase likelihood of POF progress being carried forward beyond the end of the programme and engages at least two non-DFID donors per quarter on activities or activity budget streams that could be financed outside DFID. [source: quarterly strategy paper, activity budgets] 4 - At least one activity per quarter includes in-kind or financial support from a non-POF entity; POF personnel report perception of being better equipped to deliver adaptive peacebuilding programmes. [source: finance reports, Advisor quarterly learning journals] | Quarterly update Score achieved: B.A score level of B was achieved by POF during the July-September quarter. At this point of the programme, it is not possible to determine if sustainability will be achieved within the programme’s life cycle, a key criterion for a score level of A. However, POF actively considers sustainability in its decision-making process for engagement of actors and selection of activities. For example, the work with the Monyomiji cultural institution and Gelweng youth leaders in Torit and Rumbek during this quarter facilitates the continuation of peacebuilding activities beyond the programme’s life cycle. The Torit area advisors reported that members of the locally-led and independent peace committee in Pageri use their own bikes to follow up resolutions from the forum. Similarly, the peace committee monitoring implementation of the resolutions from the Hujang-Mayya peace dialogue has put in place a system where community members contribute 1000 South Sudanese Pounds to support the work of the committee. In addition, POF continued to work very closely with church leaders and local government officials, many of whom are actively involved in POF activities by chairing committees (e.g., the Pageri Peace Forum), following up on resolutions, and engaging various actors. The grassroot peace committees in Rumbek, with participants drawn from the cattle camps, are likely to continue to act as an early warning system after POF has ended. POF: Further to the above, POF notes that recommendations from POF-SSCC logging research have been adopted by SSCC, which has incorporated these within its three advocacy pillars (source – SSCC). POF’s Learning from Peace and Reconciliation Initiatives has reviewed past peace processes, has explored the sustainability of peace and reconciliation processes from a strategic perspective, and made recommendations on how investment in this important area can be strategically directed. Looking forward, where possible, sustainability is placed central within activity design. Peace Dialogues are commissioned as a process that reaches beyond the initial dialogue, which invite divided communities to agree a structure to oversee implementation of agreements made between them. To date these structures of Committees have largely been self-organising and self-funding. A one-off peace meeting void of follow-up activities are deemed not to be sustainable, and not conflict-sensitive. POF’s learning agenda will also explore issues related to ‘how and why things work’, likely to inform some communications work. As POF develops its work, and increases its effectiveness, the stakes raise around this dimension – the community expectation that it will be sustained, and the increased cynicism that may result if it is not. This challenge creates the space for a conversation around resource sharing and co-contribution, also taking insights from other areas, for example Eastern Equatoria. | Quarterly update (insert text) | Quarterly update (insert text) | Quarterly update (insert text)
[5 empty] | Actual | Q1 | B
Q2
Q3
[6 empty] | Q4 |  | SCORE: 2/4 During the quarter, there was some evidence (albeit at a moderate level) that sustainability was incorporated into decision-making processes for the engagement of stakeholders and implementation of activities. It is expected that in the upcoming quarters, the POF leadership will develop a sustainability strategy that will include approaches for survival of the project's activities beyond its lifecycle (e.g., through engagement of non-DFID donors and incorporation of activities into existing peace structures). Nevertheless, sustainability was an important part of the decision-making processes during concept note development and implementation of activities during this quarter. For example in Torit, the area advisors established a process-oriented approach learning from the failures of previous event-based peacebuilding efforts. Inclusion of all relevant stakeholders (including security forces) in intervention design and implementation (e.g., participation in radio talk shows) ensured local ownership of the peace process. The Torit team also established an inclusive peace committee and its advisory body under the county authority to facilitate implementation of the resolutions from the forum. Moreover, the forum is set up such that follow up of resolutions by the local authorities is possible. For example, the forum arrived at a resolution around the management of pastoralist cattle. Initially this was not honoured by the pastoralists, but the monitoring of the agreement meant this was swiftly followed up and the resolution ultimately respected. For the logging study, the focal persons and members of the Justice and Peace Commissions and ICCs are permanent residents of the research areas. They are present in the locations and will continue to facilitate advocacy with the affected communities and other stakeholders upon completion of the research. In Rumbek evidence from the at-risk youth cattle camp study could guide decisions about sustainable activities in the camps. These could include improvement of food security and livelihood through farming skills, and reconciliation of the different camps/communities for peaceful coexistence. POF’s approach will generate sufficient body of evidence and learning that can be rolled over to a willing donor when the program phases out. By focusing implementation and strategic development at the area advisor level, POF is, at a minimum, building human resource that can be transferred into future initiatives after the end of the current project (for instance, three of the area advisors worked previously on a project similar to POF).
|  | Output 4 | Assumptions | Indicator 4.1 | Activities / Deliverables |  | 1 peace structure supported; 10 consultative meetings conducted with action points documented for monitoring 6 peace dialogues facilitated 2 local institutional mechanisms supported to meet 1 location map of actor collaboration | As per gradations below | 1 peace structure supported; 10 consultative meetings conducted with action points documented for monitoring | 4 peace dialogues facilitated | 2 local institutional mechanisms supported to meet; 2 peace dialogues facilitated | 1 location map of actor collaboration
...and strengthens coordination and response between local actors; | At the national and sub-national level there is considerable siloed working on peacebuilding, with many defunct or inactive or under resourced Peace Commission structures, and equivalent working groups often not functional. Inter-Church Committees are an exception, but are not functional in all locations and are often not drawing all the appropriate participation. | The POF strengthens coordination and engagement between diverse local actors to promote peace and responsiveness to conflict triggers Weighting: 20% | POF identifies actors who have authority and or influence to respond to conflict triggers. POF or other resources actors to respond. Coordination is substantive and not only formal (meetings per se ≠ coordination). FCDO will authorise engagement with state actors. | Frequency of interaction and collaboration between all relevant groups and organisations, including government (national and local), NGOs, INGOs, traditional leadership, etc. | Qualitative scoring Target for year end = A |  | C - Interactions are rare, do not include all relevant parties, and fail to adequately address core issues. B - Interactions are frequent and diverse, but may not include relevant actors. [source: meeting records/minutes] A - Interactions are frequent and diverse, with evidence that POF has identified networks of relevant actors and POF actively supporting actors to convene. Gender inclusion reported in Quarterly Reports. [source: meeting records/minutes, QRs]. A+ - Interaction with impact. Decisions taken between relevant actors are implemented and sustained. [source: meeting records/minutes] | 1 - Interactions/collaboration rarely occur between groups and organizations and when they do, not all relevant parties are invited and/or they include only perfunctory discussions of current issues. 2 - Interactions/collaboration occurs occasionally with most relevant parties in attendance. Most current issues are discussed but some issues only include a perfunctory discussion and there lacks a clear action plan towards moving topics forward. [source: meeting records/minutes] 3 - There is frequent interaction/collaboration with most of the relevant parties in attendance, including linkages between actors not previously affiliated. A majority of the current issue are discussed in depth and action plans have been outlined but may not yet be solidified. [source: meeting records/minutes] 4 - There is frequent interaction/collaboration between all relevant groups and organizations which include in depth productive conversations around current issues as well as concrete action plans to promote peace and responsiveness to conflict. Collaborations include a learning agenda to highlight lessons learned. [source: meeting records/minutes] | Quarterly update Score achieved: A. A score level of A was achieved by POF during the July-September quarter. There was ample evidence that POF continued to coordinate and engage with diverse local actors to promote peace and responsiveness to conflict triggers. In Rumbek, the grassroot peace committees (akut de door), comprising 45 Gelweng youth leaders (9 per Dinka Agar section) trained by POF will become peace ambassadors in their respective cattle camps with the primary responsibility of serving as an early conflict warning system and facilitating cattle exchanges in the event of cattle raids. In addition, during the quarter, the POF leadership continued to work with other partners in mitigating conflict. For example, POF worked closely with the Catholic Radio Network (CRN) and Health Pooled Fund (HPF) on coronavirus disease (COVID-19) messaging/talk shows that engaged a health expert and a peacebuilding expert. This programming was guided by a concept note that identified conflict risks (e.g., repressive and violent government response, local peace deals collapsing under COVID-19 pressure, and state actors manipulate COVID-19 for political purposes) associated with COVID-19. POF: a strong sense of momentum is emerging here, which will be actively managed next quarter. As a result of POF engagement, the Lakes Governor met the gelweng youth for the first time, a meeting the gelweng had not had previously. This afforded the opportunity for a direct interface, not through intermediaries, between the state apparatus and those with direct authority over the key conflict actors. POF wishes to keep moving forward on this, given the potential for this engagement to reduce violent conflict. The women’s engagement approach for Rumbek expects to coalesce existing actors more concretely in the next quarter, after initial engagement this quarter. The CRN model of public broadcasting, of health and peacebuilding professionals together in the same space, has been validated, and can be reactivated quickly in the need arises. Opportunities for increased collaboration in Rumbek will be explored further with the State Government. POF is liaising with UNMISS Civil Affairs in Lakes and EES, and supporting both Peace Commission and Inter-Church Committee structures, where they exist; the Pageri Peace Forum Phase 2 activity in Kajo Keji is working closely with other humanitarian actors. There is an important distinction between the work in Torit/Rumbek, where there is a readiness for collaborative processes between key actors, and Jonglei/Bentiu, where that is much less the case. Importantly, for the former the frequency of interaction becomes important. For the latter, unless developed in a carefully coordinated manner, more frequent interactions can lead to less collaboration and diminished conditions for peace outcomes. | Quarterly update (insert text) | Quarterly update (insert text) | Quarterly update (insert text)
[5 empty] | Actual | Q1 | A
Q2
Q3
[6 empty] | Q4 |  | SCORE: 3/4 There is ample evidence that POF has strengthened coordination and engagement between diverse local actors to promote peace and conflict resolution. For example, in Torit, relevant stakeholders met regularly through weekly and monthly peace and security meetings. During this quarter, the Torit POF team conducted six collaborative meetings involving local actors. The actors include cattle keepers, chiefs, and armed forces. In Rumbek, area advisors reported occurrence of both informal and formal interactions with groups and organizations relevant to POF’s activities. Formal meetings occur monthly at the state government headquarters. During this quarter, one collaborative meeting was held with youth and women groups, peace committees from the various communities (Rup, Kuei, etc.), the State High Peace Committee, and the State Secretary General. In addition, since January 2020, the POF leadership has engaged NGOs and international agency forums actively supported by HMG. These entities supplement the existing key advisory network that POF draws on for ongoing feedback. Lastly, POF’s strengthened relationship with the CSRF has resulted in the creation of an informal peacebuilding working group which meets remotely every two weeks. Working to a flexible agenda, the working group share updated analysis on conflict dynamics, and discuss emerging trends particularly with reference to COVID-19. Recorded clips of local actors from radio talk shows and phone calls of appreciation from county authorities, armed forces, and community members were some of the anecdotal evidence on the POF’s contribution to coordination and engagement between diverse actors.
|  | Output 5 | Assumptions | Indicator 5.1 | Activities / Deliverables |  | Selected activities from POF workstreams: # Learnings from past national level processes translated into strategic priorities paper (C7) # Agreement reached on cattle migration patterns to guide the movement of cattle and people (C25) # Trust-building initiative in Bentiu (C33) # Women's engagement coordination meeting in Rumbek (C24) # Radio programmes disseminating results of dialogues (Torit) (C13) | n/a (Output 5 added for 2020 Q3) | Minimum of 3 activities under implementation | 1 National level reconciliation follow-up paper (national); 1 migration agreement delivered (Rumbek) | 1 trust building workshop for government (Bentiu); 1 women's engagement coordination meeting (Rumbek) | 4 radio programmes disseminating results of dialogues
...and is creative and courageous in exploring potential responses, supporting existing peace engagement and identifies new and/or enhanced opportunities… | The norm is not for activities to be delivered in iterative adaptive manner. Incentives and biases (esp. against certain risk categories) mean that there is an overall sectoral bias against creativity and risk taking, even where clear opportunities arise. | POF identifies and implements activities across locations and funding windows Weighting: 30% | POF identifies activities with a sound theory of change. There conflict system force majeure to There are many flaws in existing peacebuilding engagement, but there is some good work and imperfect work that can be built on | Extent to which POF-funded activities are making expected progress through implementation and/or strengthening understanding of effectiveness principles. (See POF workstreams tab) | Qualitative scoring Target for year end = A |  | With reference to selected POF activities (above): C - Substantial failure to implement activities. B - At least 75% of activities delivered. [source: meeting records/minutes] A - At least 75% of outputs delivered [source: Quarterly reports] A+ - At least 75% of outputs delivered with evidence of exceeding expected outputs [source: meeting records/minutes] | n/a | Quarterly update Score achieved: A. A score level of A was achieved by POF during the July-September quarter. During the quarter, POF identified and implemented several activities where the expected outputs were achieved. For example, the Rumbek team identified 45 youth leaders from the cattle camps who will be trained as peace ambassadors in preparation for the internal cattle migration conference (172 delegates) in November 2020. The POF team also developed a concept note (strategy document) to guide the direction of their engagement on women’s peace and security across all four project locations. The document provides guidance for area advisors on what focus areas (i.e., women’s meaningful leadership and participation, measures to prevent gender-based violence, and engagement with men and boys) to design interventions around. One example of this engagement was the four peace dialogues that took place in the protection of civilians (POCs) in Bentiu where women’s role in aiding revenge killing was addressed. Anecdotal evidence indicates a reduction in revenge killings in the POCs following POF’s engagement of women. POF: the proposed evolution of the approach based on the learning to date is captured in the Implementation and Sustainability Strategy paper, summarised in section 2.3 above. The critical point to emphasis here is that getting these processes up and running, having the trust to convene these dialogues, is an outcome in itself. Importantly, this takes us back to a key feature of the cattle camp research, where the findings were important, but the foundation of relationships that it laid was as important, if not more important. There have been a number of key actors who have explicitly said they would support the process because they trust POF, and they trust POF because of the manner in which it conducted the research and the fact that it said it would come back and indeed did return. For other actors, it may be useful to consider ‘trust’ markets more actively as a factor in the success of peace processes. POF saw this recently in Eastern Equatoria where there was resistance from the cattle herders to attend the dialogue, concerned it was either a trap or simply a forum to insist on their return to Bor. At the last minute, POF was able to redeploy our Bor advisor to the Forum to assuage the concerns of the cattle keepers so that they could feel the dialogue was a good faith exercise in trying to accommodate the underlying concerns on all sides. | Quarterly update (insert text) | Quarterly update (insert text) | Quarterly update (insert text)
[5 empty] | Actual | Q1 | A
Q2
Q3
[6 empty] | Q4 |  | n/a
[5 empty] | ANNUAL TARGETS / STANDARDS - Note regarding baselines and targets: POF activities were underway in some locations during the baseline period; in most cases these activities were exploratory in nature. This may result in POF's impact being under-estimated. |  |  | JUNE 2020 NARRATIVE OF OUTCOME TRAJECTORY | SEPTEMBER 2020 NARRATIVE OF OUTCOME TRAJECTORY | DECEMBER 2020 NARRATIVE OF OUTCOME TRAJECTORY | MARCH 2021 NARRATIVE OF OUTCOME TRAJECTORY | JUNE 2021 NARRATIVE OF OUTCOME TRAJECTORY
Theory of Change element | Relevance (qualitative baseline) | Outcome 1 | Assumptions | Indicator 1.1
Then opportunities to address conflict and promote peace are supported; Structured, sustained engagement consolidates the impact of interventions; | Targeted communities have deep conflict issues that are impeding positive peace and security, as well as economic development. Engagements in the last decade, while structured, have tended not to be sustained. | Targeted communities are more harmonious and resilient to conflict | A peacebuilding lens with this level of budget (e.g. which doesn't allow for infrastructure projects), if well implemented, is sufficient to disrupt the sub-optimal equilibrium in the conflict system. Accompaniment from outside locations is perceived to, and does add value to the quality of interventions. More continuity in approach will create greater peace dividends. | Contribution of POF activities on reported frequency of violent conflict and/or insecurity since start of targeted activity | Target |  | At least 20% reduction in reported violent conflict incidents in project locations since start of POF activities [Source: ACLED & POF; triangulated against primary data collection] | Pageri Peace Forum: Adviser monitoring visit in June 2020 highlighted an easing of tension between cattle herders and farmers in the Pageri area, since the herders stopped carrying weapons, and the development of respectful and cordial relationships between them. This reflects a change directly attributable to the Pageri Peace Forum. Harassment by off-duty armed uniformed soldiers had been a major community grievance and disharmony. The enforcement of a Forum resolution by military commanders requiring off-duty soldiers to wear civilian clothes and not carry a gun, has had a positive impact on civilian-military relations and led to an increase in security at night, as people now travel with greater confidence. Cattle Camp Research: The research project has established a solid foundation for activities that can support more harmony and resilience to conflict in the non-urban communities of western Lakes, and through these efforts to the urban centre. POF sees the strength of the research as much in these relational foundations that have been laid, and the trust built (including simple measures: having a local, communally representative enumerator team, staying in the camps during the data collection, promising to return for validation and actually returning, consulting beyond just the leaders). It has helped us surface some key findings, including that the majority of the communities appear to be clearly against the violence, and willing the removal of guns. Whilst there are difficult questions around how to go about this, this underlying desire of the communities is critical, especially as it counters the narrative of a wilfully violent cattle camp youth. More broadly, by focussing on the broader values of the cattle camps, we have begun to shift the conversation away from cattle camps as 'the problem' to cattle camps with a range of strengths and capabilities that are under-leveraged, and also often diverted to violent activity. But this violence doesn't inhere in the values. This in turn has created space for conversations among urban 'intellectuals' where they also acknowledge their role in contributing the violence and begin to explore alternative approaches. Hujang-Mayya Dialogue: The intervention is at an early stage of development, already following the first dialogue there are reports of increased harmony between the two kingdoms. There has been a ban on revenge attacks and cattle raiding while the dialogue is underway, the creation of security mechanisms to strengthen road safety on the Torit-Kapoeta route, a commitment to open a footpath between Oguruny and Haforiere, two communities in conflict; the creation of a commission investigating historical injustices and compensation claims at the heart of traditional reconciliation processes. | No activity-specific evaluations have been conducted but testimonies from the area advisors indicate a reduction of violent conflict and/or insecurity following implementation of POF activities. For example, following the dialogues in the Bentiu POC, area advisors reported a reduction in revenge killings. In Leer, the pre-dialogues let to removal of security checkpoints which had created fear of safety among citizens. In Kajo Keji, SPLM-IO rebuilt a bridge permitting humanitarian access and instructed soldier at checkpoints not to harass civilians entering the area. Following the Hujang-Mayya Dialogue, local people reported increased travel at night along the road previously affected by insecurity. The Rumbek team has completed training of grassroots peace committees, and established the relevant foundations to begin pre-dialogues, leading to a cattle migration conference in mid-November, from which a system will be already be in place to follow-up, reducing the likelihood of violent incidents.
[5 empty] | Baseline |  | Jul 2019-Jun 2020: TBC
[5 empty] | Endline |  | Jul 2020-Jun 2021:
Change
Narrative
Indicator 1.2
|  |  |  | Contribution of POF activities on respondents' perceived likelihood of conflict with other groups | Target |  | 20% reduction in number of respondents in locations with POF activities reporting that conflict with other groups is somewhat likely or very likely in the next 1-3 months [Source: REACH; triangulated against primary data collection] |  | Starting next quarter, area advisors will be providing expert opinions on the outcome indicators as we await more robust data to come from the activity-specific evaluations. Nevertheless, in Pageri, area advisors reported that as a result of the forum resolutions, no more crops were being destroyed by cattle, indirectly indicating a reduced likelihood of conflict in the future between cattle keepers and farmers. Similarly, soldiers no longer wear military uniform, nor carry weapons, when off-duty. In Bor, area advisors reported improved relations between communities living in the POCs and those in Bot town following exchange visits facilitated by POF where people from the POCs came to visit those outside and those outside went to the POCs. This trust building process will likely lead to reduced likelihood of conflict in the next six months. In Pageri, area advisors reported improved relations between the local community and security forces following the peace forum. The area advisors reported that local youth working as boda-boda drivers (motorcycle taxis) can now carry soldiers on their bikes which used not to be the case before the peace forum. The Bentiu area advisors reported that Leer and Mayendit Nuer communities were collaborating to stop cattle raiding and returning stolen cattle to their rightful owners following the pre-dialogues/community consultations.
[5 empty] | Baseline |  | Jun 2020-Nov 2020: TBC
[5 empty] | Endline |  | Dec 2020-May 2021:
Change
Narrative
|  | Outcome 2 | Assumptions | Indicator 2.1
Interventions are more grounded in traditional good practice; Local actors are better resourced and draw on cross-system learning; Responsiveness to early warning capacity is strengthened across the states… | Traditional practice, apart from COTAL initiative, have largely been sidelined in peacebuilding ToCs and design. Local actor structures are often in place but in abeyance owing to lack of funds (to which they have no access - i.e. not per se corruption issues with respect to those institutions). Early warning identification has regularly been a focus: response capacity to avert conflict has not been demonstrated | More inclusive political, socio-economic, and cultural institutions, which are key for handling conflict and establishing the conditions for sustained peace, are strengthened at all levels. | Traditional practice overall has a net positive peace dividend to offer, if properly leveraged. Frequent, regular interaction and collaboration between local actors and international actors, as well as sharing across locations, is in and of itself a credible proxy of progress against outcomes (as distinct from one off, sporadic, infrequent interactions, or interactions only in response to violence) Early warning actors, with proper resources, have influence and authority to avert impending conflicts. | Contribution of POF activities on community perceptions that leaders are effective at reducing conflict and desire to prevent conflict | Target |  | 15% increase in respondents in locations with POF activities reporting that their leaders are effective at reducing conflict/15% increase in respondents in locations with POF activities reporting that their leaders desire to prevent conflict [Source: primary data collection] | Pageri Peace Forum: The design of the Pageri Peace Forum intentionally sought to bring all relevant stakeholders together to discuss what needed to be done to facilitate the return of refugees. These stakeholders included local authority personnel, religious leaders, national security, military commanders, police officers, traditional leaders, women’s representatives, youth representatives, business community representatives, refugee representatives, cattle herder and farmer representatives. The fact that the Forum is chaired by local government has been key in conferring authority and legitimacy; the creating of the Forum Committee to implement the resolutions has established an important mechanism for sustaining the Peace Forum. The Forum has also implemented an important communications process with local and refugee communities through engagement with local radio, where 4hrs of programming is sponsored per week. This has strengthened the communication process where Forum members communicate with the public on project activities and seek to build trust and confidence in the Forum process. Cattle Camp Research: The interaction of the political, socio-economic and cultural institutions in the conflict system of western Lakes are compromised and largely dysfunctional. State capability is limited, and access issues undermine efforts to be more effective. However, a blind spot in the apparent 'chaos' of the system (such that it is considered off-limits for many peace and development actors) is that the 'institution' of the cattle camps is one of the more functional institutions in the country. With all its imperfections, there is a system, discipline and level of organisation that arguably surpasses many of the 'modern' state apparatus. The way in which the research has created some ground for highlighting this opens new opportunities for intervention that can treat this key institution not as a problem to be solved, but as a counterpart in the sub-national state building that has its own particular challenges. In terms of institutional stability in this system, we now move to a challenging but potentially impactful conversation around what effective governance looks like in the very particular political economy. The political economy of western Lakes is in many respects an inversion of the received wisdom: that systems orient around a core and periphery, and this is reflected geographically. Here the geographical periphery is the thread that weaves, and at other times unravels the stability of the core and the system as a whole. This understanding is a key step towards Outcome 2 progress. Lakes is very particular in this respect. This is not a system that is dictated by the Juba level, albeit influenced at times. At a more practical level, the strength of the findings in the report provide useful support to wider institutional efforts. In an hour long discussion with the Minister of Defence, we explored the implications for disarmament efforts, currently being pursued with blunt tools, as well as for community peace and security mechanisms. Further discussions along these lines are planned. Logging Research: Two report recommendations point to this outcome, which is being operationalised by the SSCC, and have yet to be implemented. These are directed to the Minister for Environment and Forestry, and read: The Minister should work with the national government to ensure the Forest Act and Environment Act are passed, to strengthen the legislative and institutional framework to manage logging and charcoal production, and to ensure environmental safeguards. The Minister should strengthen collaboration and coordination between institutions dealing with natural resources in order to effectively manage forests. National level reconciliation review: Although the number of interviewees was reduced vis-à-vis the plan, following the COVID-19 travel restrictions, the Reviewer was still able to reach central figures from each of the four main national level reconciliation processes to date. Rather than attempting a historical account of each, in the early stages the Reviewer suggested that it made more sense to focus on patterns and themes from experiences so far; that these could be a more useful input for further conversations and design. A number of these patterns and themes were 'institutional', including: a questioning of the notion that certain actors have natural 'ownership' of the reconciliation agenda, the misplaced attempts by some actors to completely depoliticise an inherently political process, competition between agencies that have at times perhaps seen carriage of the reconciliation agenda as zero-sum, and a deterioration of relationship among some of those same actors, inconsistencies within the international community itself, and a possibly unrealistic expectation placed on large structures that were, in the language of state capability 'prematurely loadbearing'. These discussion points are potentially significant, subject to the follow-up of the review. Whereas there is extensive analysis in a number of areas where POF is engaged (arguably an over-emphasis on analysis), there has been no documented attempt to date to synthesis learnings from the national level reconciliation processes. This allows each initiative to believe, or claim, or both, that they are starting from scratch and to be given the latitude on that account. Now we have at least the beginning of a documented foundation for informing national level efforts, as the new Ministry of Peace begins its work. Hujang-Mayya Dialogue: The Peace Dialogue is led by the Hujan king, with the support of state government, two key actors in establishing the conditions for sustained peace. The Dialogue also includes all relevant stakeholders: traditional and religious leaders, women’s representatives, youth representatives. | Starting next quarter, area advisors will be providing expert opinions on the outcome indicators as we wait for more robust data to come from the activity-specific evaluations. This quarter, in Rumbek, after the training of 45 Gelweng youth leaders (9 leaders per Dinka Agar section) as peace ambassadors, stolen cattle were returned to their rightful owners, indirectly indicating the desire of cattle camp leaders to prevent conflict. Torit area advisors reported refugees sent a delegation from the camp to their home area to assess security and livelihood options, a direct response to security assurances provided by military commanders on POF’ funded Pageri Peace Forum radio programme.
[5 empty] | Baseline |  | Jan 2020: TBC
[5 empty] | Midline |  | Nov 2020:
[5 empty] | Endline |  | Jun 2021:
Change
Narrative
Indicator 2.2
|  |  |  | Change in inclusive interaction and collaboration (strength and density) between key institutions | Target |  | At least 30% of key institutions/actors (Women, churches, gelweng leaders, chiefs, etc.) in locations with POF activities report increased frequency of interactions (meetings, calls, emails, etc.) among themselves and with other peacebuilding stakeholders/At least 30% of key institutions/actors (women, churches, Gelweng leaders, chiefs, etc.) in locations with POF activities report increase in collaboration among themselves and with other peacebuilding stakeholders. [Source: primary data collection] |  | The data for this indicator will come from interviews with key actors. From discussions with the area advisors, there is frequent engagement and collaboration between key actors such as the peace commission, inter-church committee, chiefs, and other local authorities (e.g., county commissioners). Evidence from Kajo Keji points to increased collaboration between government and SPLM-IO in the areas, a result of their interaction during POF dialogues. One of the areas where POF is focussing in is also in arriving at the correct configuration of these interactions between key institutions; the work in Rumbek and Torit has shown progress in this regard, by establishing mechanisms for including key actors in ways that haven’t been attempted in recent times. Importantly here the POF is not defining ‘institutions’ simply as modern state institutions, but also the traditional and cultural institutions that in some cases have both comparable (or greater) legitimacy, authority and effectiveness: e.g. the Monyomiji in Eastern Equatoria, the respective Kingdoms of Huyang and Mayya, or the Cattle Camps themselves in the Dinka Agar.
[5 empty] | Baseline |  | Jan 2020: TBC
[5 empty] | Midline |  | Nov 2020:
[5 empty] | Endline |  | Jun 2021:
Change
Narrative
ANNUAL TARGETS / STANDARDS
|  | Impact Statement | Assumptions | Impact Indicator 1 | [7 empty] | INSERT TARGET
Leading towards… |  | Enhanced South Sudanese capacity to manage conflicts without violence, and reduction in violence in targeted areas | New channels and means of violence do not emerge that are not being collectively targeted by peacebuilding interventions. Other actors with significant influence and authority are not actively undermining, or mobilising others to undermine peacebuilding outcomes. | Change in level of community perceptions of safety | Target |  | 20% reduction in four month rolling average proportion of assessed settlements reporting that most people in the community felt unsafe most of the time [Source: REACH]
[5 empty] | Baseline |  | Jun 2020-Sep 2020: TBC
[5 empty] | Endline |  | Mar 2021-Jun 2021:
Change
|  |  |  | Impact Indicator 2 | [7 empty] | INSERT TARGET
|  |  |  | Change in level of conflict impact in POF locations | Target |  | 10% reduction in four month rolling average 'impact of conflict' data (composite measure) for areas where POF is active [Source: REACH]
[5 empty] | Baseline |  | Jun 2020-Sep 2020: TBC
[5 empty] | Endline |  | Mar 2021-Jun 2021:
Change

## POF workstreams
# | Workstream | Draft outcome | Corresponding Programme Outcome Indicator | Target | Draft output | Draft activities | Sources
1 | Learning Facility | National and international level conversation incorporating nuanced lessons from grassroots processes into programming decisions. | 2.2 |  | Learnings papers produced and published on local peace dialogue systems. | Cross-location learning workshops;
Sharing and discussing learning paper drafts with National Advisory Network;
Collaboration with CSRF on products.
2 | National Agenda | An active network of peacebuilding and transitional justice actors connecting to develop input into national level conversation. | 2.2 |  | Learnings from past national level processes translated into strategic priorities paper; | Commissioning iteration of reconciliation review reflection;
[5 empty] | Local and international stakeholders consulted on challenges and opportunities of implementing strategic priorities. | Discussing strategic priorities with National Level Advisory Network;
Extending POF conversations to key national and sub-national institutions.
3 | Peace Dialogue System - Torit | Reduction in violent conflict between host and visiting communities in Hujang, Mayya, Nimule, Magwi and Pageri and peaceful sharing of natural resources. | 1.1 |  | Dialogues implemented among relevant authorities of conflicting communities; | Magwi Peace Forum | ACLED 2019 | UCDP 2019
|  | Improved relationship between armed forces and civilians; | 2.2 |  | Follow-up mechanism identified and implemented; | Pageri Peace Forum | HSS 2017/2018
|  | Effective participation of women in peace building, security and decision making. | 2.2 |  | Peace related messages from dialogues received by community through radio dissemination. | Huyang-Mayya Dialogue | HSS 2017/2018
Kajo-Keji Peace Forum
Media engagement for socialisation of dialogue approach
Women engagement dialogues
4 | Peace Dialogue System - Jonglei | Reduction of violent conflict, cattle raiding, child abduction and death in Jonglei and greater Pibor Administrative Area as caused by armed youth | 1.1 | 1 | Consultative meetings completed | Consultative meetings with influential persons and armed youth leaders individually | HSS 2017/2018 | ACLED 2019 | UCDP 2019
|  | Peaceful return of civilians from Bor PoC into host community | 1.1 |  | Armed youth leaders and other influential leaders engaged | Pre-meetings with armed youth leaders at their localities | HSS 2017/2018 | ACLED 2019 | UCDP 2019
[5 empty] | Pre-dialogues conducted in each location | Armed youth leaders meet their groups members
[5 empty] | Intra- Agreements reached to meet other communities armed youth | Pre-dialogues with armed youth per location
Inter-group armed youth dialogue
5 | Peace Dialogue System - Rumbek | Reduction in revenge killings, conflict incidents and fatalities caused by competition over grazing land and water points. | 1.1 |  | Women’s participation meaningfully reflected in dialogue processes; | Pre-Dialogues across five sections of Dinka Agar; | HSS 2017/2018 | ACLED 2019 | UCDP 2019
|  | Strengthening of traditional peacebuilding mechanisms and social interaction among galweng. | 2.2 |  | Agreement on cattle migration patterns that guide the movement of cattle and people; | Main Cattle Migration Conference; | P-AX
|  | Coordination among peacebuilding actors to encourage communities to dialogue; | 2.2 |  | Oversight monitoring committee formed and equipped to deliver; | Revitalising old agreements and identifying other conflicts needing resolution; | P-AX
|  | Increased dialogue between cattle camp leaders and local authorities. | 2.2 |  | Reduction of conflict caused by competition over grazing land and water points; | Interviews with traditional and intellectual leaders on history of Dinka Agar. | P-AX
Akut de door (grassroots peace committee) has led pre-dialogues between sections and sub-sections;
History of Dinka Agar published.
6 | Peace Dialogue System - Bentiu | Increased willingness to dialogue between main intra-Nuer groups; | 2.2 |  | Women engaged in pre-dialogue process; | Pre-Dialogues meetings in Leer, Payinjiar, Rubkona Koch, Mayendit, Mayom; | P-AX
|  | Increased collaboration among political leaders; | 2.2 |  | Resolutions agreed at Intra-group dialogue event; | Main dialogue bringing together intra-Nuer groups; | P-AX
|  | Increased community cohesion transferred from PoC to communities after return. | 1.1 |  | Mechanisms for follow-up identified and resourced; | Trust-building initiative with State Cabinet, County Commissioners and other key state officials; | P-AX
[5 empty] | PoC Community Watch Group capacity developed. | Support to the PoC Community Watch Group.
7 | Women's Engagement Strategy - Cross-cutting | Existing structures creating space for increased women's leadership and participation in decisions affecting community peace and security; | 2.2 |  | TBC | TBC
|  | Women, men, girls and boys engaging in public and private conversations on positive gender roles; | 2.2
|  | Women's advocacy/service groups working collaboratively on a strategic set of priorities; | 2.2
|  | Relevant state authorities are proactively engaged in responding to GBV incidences, supporting victims and strengthening justice for offences. | 1.1