Annual Review

Title: Centre of Excellence for Development Impact and Learning (CEDIL)
Programme Value £ (full life): £20 million		Review date: 24 December 2020
Programme Code: 203569	AMP start date: 15/09/13	AMP end date: 14/04/2023

Summary of Programme Performance
Year	2014	2015	2016	2017	2018	2019	2020
Overall Output Score	C	B	A	B	A	A	A
Risk Rating	Medium	Medium	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-1-203569/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-1-203569/documents

A. SUMMARY AND OVERVIEW

Description of programme

The Centre of Excellence for Development Impact and Learning (CEDIL) programme has established a high quality, inter-disciplinary academic centre to; innovate in the field of impact evaluation and evidence synthesis; design, commission and implement impact evaluations; and promote the uptake and use of evidence from impact evaluations. CEDIL’s ambition is to act as an international focal point and is developing and demonstrating new and innovative methodologies for impact evaluation and evidence synthesis.

CEDIL is delivering against 3 key requirements:
1. Adapt and develop evaluation methods for impact evaluations of development programmes;
2. Develop a rigorous evidence synthesis, impact evaluation and data sciences research programme – known as the Programme of Work (PoW) - to combine and model evidence generated through monitoring and evaluation of development programmes, using new and existing methods (drawing from social, natural, bio-medical sciences and potentially other fields); and
3. Promote the use of these better methods for impact evaluation and evidence synthesis in international development.
Within each of these, CEDIL is bringing its academic and inter-disciplinary intellectual leadership to the forefront in delivery.

Better evaluation of FCDO (previously DFID before the creation of FCDO) programmes will lead to higher quality results across the Department. The work of CEDIL will also assist accountability and value for money (VfM) through more effective deployment of resources based on uptake of findings and lessons about ‘what works, how, when and for whom’. CEDIL will do this through the evaluation of FCDO funded programmes, through uptake of the evidence produced in its Programme of Work, and through providing methods that can be used by FCDO and others to fill gaps in the evidence base in under-evaluated sectors and geographical areas.

The outputs from CEDIL will demonstrate FCDO’s commitment to transparency and results, as well as assisting in FCDO’s aim to become a world-class commissioner and user of evidence to drive improved value for money and development impact.

The programme is being implemented by the CEDIL Directorate. The CEDIL Directorate consists of:
- Programme Directorate (PD), led by Oxford Policy Management (OPM) with sub-contractor Scriptoria (Sustainable Development Solutions)
- Research Directorate (RD): London School of Hygiene and Tropical Medicine (LSHTM), leading a consortium of five cutting edge research institutions.
The Research Director is the CEO of the Campbell Collaboration, one of the members of the CEDIL consortium. The other consortium members are the EPPI Centre (UCL’s Institute of Education), the International Initiative for Impact Evaluation (3ie) and the Centre for the Evaluation of Development Policies in the Institute of Fiscal Studies. RD’s wider Intellectual Leadership Team (ILT) includes a further 14 multi-disciplinary experts.

The governance structure for CEDIL includes: an FCDO Executive Board, which is a management board providing oversight, strategic direction and high-level decision making; and an Advisory Board consisting of international experts on evaluation methods and evidence use. The latter represents the perspectives of a range of stakeholders with an interest in CEDIL’s activities and outputs, advising how to increase the usefulness of findings and championing CEDIL to the wider research and development community.

Summary supporting narrative for the overall score in this review

This Annual Review sets out progress made in the second year of implementation across three key areas of establishing and running the programme; selecting and operationalising research projects; creation of user-orientated products; and activities to generate broad interest in CEDIL’s work among the research, evaluation and user community.
[note] A difficult and unsatisfactory outcome of the first procurement phase and a longer than expected second procurement meant that procurement for CEDIL was not finished until 2018. PD then completed a 6 month inception stage before implementation began. .

Despite the year being overshadowed by the Covid-19 pandemic, the programme has met the majority of its delivery targets. Highlights of the year include:
- CEDIL selected thirty-two high quality evaluations, synthesis and methods research projects.
- 90% of the contracts for these projects are now signed and are operational.
- The earliest research projects are already delivering outputs, with three of the Fast Track Studies completed or very near completion.
- Six user-orientated summary products produced.
- Twenty-two dissemination and training events held, the overwhelming majority of which were attended by over 30 people, with three attracting more than 100 attendees.
- CEDIL has increased the number of Twitter followers to 1260 over the course of the year.
At the beginning of this reporting year, the commissioning process for the Programme of Work was well advanced. CEDIL has commissioned thirty-two high quality evaluation, synthesis and methods development projects. The CEDIL evidence synthesis projects use cutting edge techniques to accumulate evidence on how the interventions work and who they work for. The impact evaluations will address a range of different types of project complexity: multi-component programmes, long causal chains and multiple stakeholders. Projects will also explore use and usefulness of evidence.

Much of CEDIL’s work during this year has been focused around getting the research projects operational and ensuring they are well managed both technically and operationally. An early priority was issuing contracts; over 90% are now signed or ready to be signed, with the outstanding contracts being held up by slow responses in the sub-contractee institutions. CEDIL Directorate has made substantial progress in setting up processes and systems for managing the PoW. To ensure good quality research, and to encourage synergies between projects and increased innovation, RD has run workshops with project teams and is peer reviewing the research design papers. Feedback from the research teams on CEDIL’s management was mostly positive. The earliest research projects are already delivering outputs, although at a lower level than originally planned due to a range of factors including contracting delays and Covid-19. Currently, three of the Fast Track Studies are completed or very near completion.

CEDIL has also produced six, high-quality user-orientated summary products. While short of the milestone for this year, these outputs have been well received, with the majority of the respondents in the stakeholder survey saying they found the methods papers and guidelines to be useful. The number of dissemination and training events was overachieved; the overwhelming majority of these events were attended by over 30 people, with three attracting more than 100 attendees. During this reporting period, CEDIL hired a Research Uptake Manager, who developed a prioritised outreach plan and has increased their communications activities. The programme has increased the number of Twitter followers to 1260 over the course of the year and the CEDIL website had 10,232 visitors over the year.

CEDIL has been pro-active in addressing the implications of the Covid-19 pandemic on the programme. CEDIL Directorate is monitoring delays to the research due to the pandemic. RD has been encouraging research teams to adjust the research design so that it is deliverable under current conditions and to incorporate Covid-19 relevant issues.

There have been improvements in the delivery model over the last year: a better co-ordination and accountability model, and more emphasis being placed on ensuring that resources are allocated to high priority tasks. There are areas where there is still a need for progress: CEDIL’s focus on, and timeliness of, their budgeting and better use of programme management tools such as the workplan and logframe to ensure more effective management.

Major lessons and recommendations for the year ahead

R1: PD should continue to develop its processes for management of the research projects in order to minimise delays in delivery. This could include a) reminders before deliverables are due for projects that have delivered late in the past; b) systematic escalation and intervention for teams where there are repeated delays or quality problems. (Process to be developed by February 2021)

R2: For managing the uncertainty and delivery constraints due to the Covid-19 pandemic: CEDIL Directorate should consider the likely operating conditions in developing countries for the remaining duration of the project and assess which projects are at risk of delivery failure, given the operating conditions. Establish a timeline and process for making decisions about these at-risk projects. (CEDIL to develop timeline and process by February 2021)

R3: The CEDIL Directorate should capitalise on the progress it has made to date on its outreach plan by dedicating more time to strategic communications, and the proactive targeting of key audiences in order to raise its profile. FCDO to support CEDIL on internal communications, particularly through identifying key areas of strategic interest for the FCDO audience. (CEDIL to develop initial plans for this recommendation by February 2021)

R4: CEDIL to produce accessible summary versions of key inception papers by the end of June 2021 (the expectation is that CEDIL will produce summaries for two key inception papers).

R5: CEDIL and FCDO to review the logframe as follows (by end of January 2021):
- R5a: Refine the impact and outcome indicators
- R5b: CEDIL and FCDO to re-test whether future years’ logframe indicators are feasible, given the current status and likely impacts of the pandemic.
- R5c: CEDIL to use other similar organisations as comparators to set the level of ambition for future year milestones for outreach.
R6: FCDO and CEDIL to ensure that the issues affecting RD salaries are addressed (the issues are the partial funding in future years and the RD contract finishing before the PD contract) and to ensure the sustainability strategy is taken forward.

R7: CEDIL Directorate should increase the use of programme management tools such as the workplan and logframe in directing their management of the programme. (CEDIL and FCDO to review progress in February 2021 and agree further review points)

R8: CEDIL Directorate to make improvements in its focus on, and timeliness of, their budgeting and programme invoicing. (CEDIL and FCDO to review progress in February 2021 and agree further review points)
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case

A summary of the programme’s theory of change is as follows. The CEDIL Directorate, using a consultative process, assesses current theory and practice in international development impact evaluation, identifies strategic gaps and designs a ‘Programme of Work’ to address them. Projects within the Programme of Work conduct research and evaluation activities. These generate outputs that provide recommendations to improve development interventions and policies, as well as guidelines to enable others to deploy the innovations in methods that have been developed.

Stakeholder engagement at both a programme (CEDIL) and individual project level occurs through three channels to generate outcomes:

- Implementers and designers of interventions which are being evaluated by CEDIL, or those involved in similar interventions where CEDIL recommendations are relevant, receive actionable, well-evidenced recommendations to improve interventions from evaluation reports, policy briefs and evidence syntheses;
- The wider community of evaluation practitioners and academics receives methodological tools (e.g. guidelines) and training to strengthen their capacity to conduct other evaluations in the gap areas addressed by CEDIL;
- Organisations which commission impact evaluations of development interventions and users of evidence will be provided with evidence on lessons learned and guidelines on how to commission evaluations in areas where gaps in methods previously existed.
These will lead to the outcome of “increased access, awareness and uptake of high-quality evidence from impact evaluations in key policy and programme areas” and the impact of a “strengthened evidence base and understanding of what works in international development built around more and better impact evaluations”. One of the assumptions underlying CEDIL’s theory of change is that many of the thematic evidence gaps exist because current methods are poorly suited to evaluating programmes within them.

This high-level theory of change has not changed since the business case. Since the programme began, CEDIL and FCDO have significantly developed the theory of change to tease out the pathways to impact, the assumptions and risks. CEDIL and FCDO are working to define the breadth of CEDIL’s reach and depth of impact that is reasonable with the programme’s resources and timescales; as part of that the impact and outcome indicators are being refined, while ensuring they meet the aims of the theory of change (Recommendation 5a).

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

This Annual Review confirms that the programme is on track to contribute to the expected outcomes and impact. At this stage of the programme, it is not expected that CEDIL will be able to show progress against most of its outcome and impact indicators. The following questions were explored in the review process to judge whether CEDIL is on track to contribute to its expected outcomes and impact:
- Do the research projects in the Programme of Work represent potentially useful innovations and frontier methods, with the potential to fill gaps in evaluation and evidence synthesis methods?
- Has CEDIL made good progress on getting the research projects operational?
- Are the research projects being managed effectively to maximise the impact against CEDIL’s aims?
- Is CEDIL reaching the envisaged audience including researchers, evaluation practitioners, evaluation commissioners and users of evidence?

In this review’s assessment the answer to the first three questions is ‘yes’ (see Output 1 for further evidence). The research projects do have potential to advance cutting edge methods in both impact evaluation and evidence synthesis. They address several of the evaluation gaps identified during CEDIL’s inception stage. They are being managed for quality and to maximise learning across the portfolio. PD have processes and systems for managing these projects; this review recommends additional actions to minimise delays in delivery. As detailed in Output 2 & 3, progress is being made in reaching the intended audience of CEDIL, and the measured outcome indicator (1.3) has exceeded its milestone.

Indicator(s)	Milestone(s) for this review	Progress
1.3 Number of downloads of working papers, evidence syntheses and maps from CEDIL website	500	602

The review also considered progress on equity. This has been integrated as a cross cutting theme for the Programme of Work. Projects have been asked to disaggregate data according to gender and disability, as a minimum. It is important to note, however, that evaluations might not always have a large enough sample to make reliable conclusions about the impact on different groups. While CEDIL’s research agenda does not have an explicit focus on disadvantaged groups, many of the projects across the PoW certainly do. For example, in terms of gender, the PoW has two studies focused on maternal health and family planning, one on gender and social outcomes of WASH interventions, and another which evaluates the outcomes of the FCDO Work in Freedom Phase 2 programme through a gender lens. One of the Fast Track Studies (FTS) is also focused on disability, having produced a Disability Evidence Portal. This output has received a lot of attention from within the relevant policy team in FCDO and more broadly from the Social Development Advisory Cadre.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Given the stage that CEDIL is at currently, it is making good progress towards its expected outcomes and impact and represents good value for money. The programme is contributing to FCDO’s commitment to become a world-class commissioner and user of evidence to drive improved value for money and development impact. The programme should continue.

## C. DETAILED OUTPUT SCORING

Output Title	Relevant, high quality evaluations and methodological papers / outputs produced
Output number:		1	Output Score:	A
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of high quality evaluation, synthesis and methods development projects commissioned	32	32
1.2 Number of working papers published on CEDIL website, including synthesis and lessons learned papers	5	2
1.3 Number of peer reviewed academic papers produced by PoW and RD	0	0
[note] Indicator also includes finished research projects, even if no working paper has been planned for this project. In 2019/20 this applies to the disability portal.

Briefly describe the output and provide supporting narrative for the score.

CEDIL has met its target for the first indicator and partially met the target for the second. The quality of the commissioned projects and outputs is good. No achievement is expected for the third output this year. On balance, CEDIL therefore scores an A for this output.

Commissioning: Last year’s AR reported that the commissioning process for the Programme of Work was well advanced; Seven Fast Track Studies and fifteen Small Projects were already approved, and there were recommendations for the remaining possible projects. The DFID Executive Board approved all recommended Large Projects as well as one Large and one Small Project from the reserve list. In total, CEDIL has commissioned thirty-two high quality evaluation, synthesis and methods development projects (nine Large Projects; sixteen Small Projects and seven FTSs). This is a weighty portfolio and has met the milestone for indicator 1.1.

Impact Evaluations: The impact evaluations will address a range of different types of project complexity; multi-component programmes, long causal chains and multiple stakeholders. Five of the nine projects are evaluating FCDO funded interventions. The research approaches include machine learning, better use of mixed methods (integration of quantitative and qualitative data) and more systematic ways to model the causal chains. With the research projects on mid-level theory, they will produce good exemplars of how to do causal chain analysis, showing better ways to understand the mechanisms that are causing impact and how to improve the transferability of this knowledge.
[note] A mid-range theory (also known as mid-level theory) is a theory of change (ToC) which is designed to apply to a range of settings; unlike a project specific ToC which is only applicable for that specific project. A mid-range theory helps predict whether a programme can be expected to work in a new setting, offers insights into what design features are needed for success, and provides invaluable information for monitoring to see if the programme is on track and to fix problems that arise.

Evidence synthesis: The selected CEDIL evidence synthesis projects move a long way beyond traditional systematic reviews of impact evaluations. While traditional systematic reviews concentrate on whether an intervention works and the average effect in the population, the CEDIL research projects use cutting edge techniques to accumulate evidence on how the interventions work and who they work for. The CEDIL research projects develop new ways to integrate non-RCT forms of evidence, while keeping a rigorous evidence standard. They also use frontier methods to streamline the implementation of the synthesis, such as using machine learning to do the initial evidence search.
[note] Including mediation analysis, network metanalysis and machine learning techniques for assessing the heterogeneity of impact.

As intended, a smaller proportion of the funds is being allocated to the research projects exploring use and usefulness of evidence.

Research management: Much of CEDIL’s work during this year has been getting the research projects operational and ensuring they are well managed both technically and operationally. The early priority was to improve the speed of contracting, a concern expressed in last year’s AR. PD increased the amount of staff time working on contracting and improved management processes to resolve delays. This started to speed up contracting during the first half of 2020. However, the Covid-19 pandemic added delays due to staff absences, disruption and adapting ways of working in both OPM and the institutions being contracted. Currently twenty-nine of the projects are signed or ready to be signed, with the outstanding contracts being held up by slow responses in the sub-contractee institutions.

Programme management: CEDIL Directorate has made substantial progress in setting up processes and systems for managing the PoW, although some of this was done while projects were already implementing. PD now has a database to monitor progress of the portfolio of projects. Research teams produce quarterly reports and PD is now reviewing these quarterly reports against a standardised checklist. FCDO would like PD to use these processes to proactively manage the timeliness of research teams, including encouraging research teams to anticipate and deliver to deadlines and to use the database to flag projects which are falling behind for more intensive oversight [recommendation 1].

To ensure good quality research and to encourage synergies between projects and increased innovation, RD has run workshops with project teams and is peer reviewing the research design papers. It is also ensuring that research teams follow good research practice, such as adding their research plans on appropriate research registries.

The FCDO review team interviewed members from three of the research teams. Feedback was mostly positive; CEDIL was felt to be a prestigious programme addressing important areas, the communications with CEDIL directorate had been good and the meetings useful. Concerns were expressed about the level of paperwork needed and delays in receiving feedback on the design reports.

Covid-19: CEDIL has been pro-active in addressing the implications of the Covid-19 pandemic on the programme. CEDIL Directorate is monitoring delays to the research due to the pandemic; delays have been caused by reduced staff working hours, often due to increased childcare duties; delays to fieldwork due to travel bans and restrictions on conducting fieldwork; and delays to the interventions being studied. RD has been encouraging research teams to adjust the research design so that it is deliverable under current conditions and to incorporate Covid-19 relevant issues.

The number of working papers published by CEDIL has been affected by the issues discussed above. This milestone for this year was intended to be achieved by the Fast Track Studies. These projects were the worst affected by the contracting delays and two of the three currently uncontracted projects are Fast Track Studies. Several of the Fast Track Studies were operating before PD set up their processes and were not being monitored for timely delivery. Finally, one of the projects has now been severely delayed due to Covid-19. Currently, three of the Fast Track Studies are completed or very near completion, although only two have reached the stage to count under the indicator 1.2. The quality of the outputs is high.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
Previous Annual Reviews have expanded the Business Case’s VfM assessment using FCDO Research and Evidence Division’s ‘quality and value at each step’ approach to value for money, which is most suitable for investments which do not and cannot have entirely pre-determined outputs (in terms of research and evaluation findings), outcomes and impacts. Key features of this approach include:
- Working through strong partnerships
- Always requiring good quality
- Procurement - controlling quality and costs via open, competitive processes
- Programme Management – tight oversight of programme delivery.

The open call for proposals and the review process of the Programme of Work was crucial to ensuring its VfM potential. The FCDO’s review for relevance strengthened the Programme of Work’s potential VfM, as it included consideration of whether each research project’s evidence output will fill existing, high priority evidence gaps.

The research projects do have potential to advance cutting edge methods in both impact evaluation and evidence synthesis. They are being managed for quality and to maximise learning across the portfolio. The management for timeliness is being strengthened. Quality for the Programme of Work will also be incentivised by the professional settings of most participants.

Describe any changes to this output, and any planned changes as a result of this review.

There were no major changes to this output. During this year the logframe was updated; as the PoW projects were commissioned, this information was used to set milestone targets.

Planned changes as a result of this review: CEDIL and FCDO to re-test whether future year’s logframe indicators are feasible given the current status and likely impacts of the pandemic. CEDIL and FCDO to agree feasible milestones that maintain the momentum for delivery. [Recommendation 5b]

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The recommendations in the last AR have been implemented:

Previous AR recommendation	Progress
PD to ensure that the speed of its sub-contracting is improved rapidly (November 2019 – January 2020). Speed is being judged against agreed performance standards.	Met. / PD increased the amount of staff time working on contracting and improved management processes to resolve delays.
RD to develop their plans further for involving the Intellectual Leadership Team (ILT) and CEDIL’s Advisory Board in ensuring coherence from the Programme of Work (by end March 2020)	Met / CEDIL Directorate has presented the PoW to CEDIL’s Advisory Board and the CEDIL consortium partners and gathered their feedback. ILT members were invited to support the research teams by reviewing the research design papers, including providing advice about how their individual research projects can contribute further to emerging PoW themes. As plans for key outputs and products from the PoW are further developed, FCDO would like to see these shared with the Advisory Board, as the diversity in the its membership can add value by recommending how to make these products useful for a wider audience.
DFID and CEDIL Directorate to consider options for use of the remaining funding to address areas less well covered by the current set of proposals (initial thinking December 2019 onwards, decision on direction by June 2020).	Partially met / Initial discussions have taken place on this. Further work has been paused due to the implications of the Covid-19 pandemic on FCDO staff.

The recommendations for this year are as follows:

R1: PD should continue to develop its processes for management of the research projects to minimise delays in delivery. This could include a) reminders before deliverables are due for projects that have delivered late in the past; b) systematic escalation and intervention for teams where there are repeated delays or quality problems. (Process developed by February 2021)

R2: For managing the uncertainty and delivery constraints due to the Covid-19 pandemic: CEDIL Directorate should consider the likely operating conditions in developing countries for the remaining duration of the project and assess which projects are at risk of delivery failure given the operating conditions. Establish a timeline and process for making decisions about these at-risk projects. (CEDIL to develop timeline and process by February 2021)

Output Title	User-oriented outputs produced by Directorate or Programmes of Work which provide clear policy recommendations and enable broader take-up of methodological innovations
Output number:		2	Output Score:			A
Impact weighting (%):		30%	Weighting revised since last AR?			No
Indicator(s)				Milestone(s) for this review	Progress
2.1 Number of user-oriented summary products produced and published on CEDIL website, including policy briefs, portals/maps and methodological guidance notes				9	6 – consisting of 4 guidelines papers and 2 outputs from the Fast Track Studies (one methods brief and the disability evidence portal)
2.2 Number of dissemination and training events held with FCDO or other users by the Directorate or individual projects within programmes of work				17	22 events, including 6 guidelines webinars, 1 COVID-19 panel discussion, 5 presentations from 3 of the Fast Track Studies, 3 dissemination events held by PoW teams, and 7 seminars in CEDIL’s lecture series

Briefly describe the output and provide supporting narrative for the score.

This output has had mixed results. While CEDIL slightly underperformed on the first indicator, it overperformed on the second, giving an A overall for this output. The products and events delivered are of high quality.

For output indicator 2.1, CEDIL aimed for a total of nine evaluation reports, policy briefs and methodological guidance notes to be published within this reporting period. Six of these were expected to come from the Fast Track Studies, which were originally intended to all be completed by end of July 2020. As detailed under output 1, these studies were subject to delays, and mean that CEDIL has not met the target set out in the logframe. Nonetheless, CEDIL produced six, high-quality user-orientated summary products over the course of the year, including:

- CEDIL guidelines on impact evaluation that are sensitive to disability
- CEDIL stakeholder engagement and evidence use guidelines
- CEDIL guidelines for good impact evaluation practice
- CEDIL guidelines for the conduct and reporting of mixed methods in quantitative impact evaluations
- Disability Evidence Portal: a user-friendly web-based database of existing impact evaluations and evidence synthesis related to disability, making it easier for users to access evidence in this important policy area.
- Methods brief on using middle-level theory to improve programme and evaluation design; provides a practical, how-to approach by outlining ten steps for building a more robust theory of change based on mid-level theory.

One further methods brief, which draws on the findings of a Fast Track Study that mapped the use of big data in impact evaluation, is very close to being completed. This is despite the research team having experienced staff turnover due to the departure of the lead author.

The outputs CEDIL has produced so far have been well received. In the stakeholder survey, 68% of respondents said they found the methods papers and guidelines to be useful – a percentage which would be far higher if those respondents who reported not having engaged with any of the publications had been removed (10 of the 79 respondents).
[note] The Stakeholder Survey was administered in October 2020 to gather feedback on the programme’s work to ensure it stayed as relevant, interesting and useful as possible. Several indicators are expected to draw on the findings from the survey and questions are phrased accordingly.

Until the Small and Large Projects are able to publish, output 2 is overly reliant on the Fast Track Studies and therefore quite sensitive to delays in their implementation. We expect to see an improvement in this output over the next reporting period, as the other PoW teams start publishing results.

The second indicator under output 2 relates to dissemination and training events held by CEDIL’s RD, ILT or the Advisory Board, or project teams from the Programme of Work. The target here was 17, but the total number achieved was 22. This total includes:

- Public-facing seminars that have been hosted by CEDIL as part of the CEDIL seminar series. A number of recent seminars have had a Covid-19 theme.
- Guidelines webinars, aimed primarily at research teams in the PoW.
- A special, one-off Covid-19 panel discussion, which considered impact evaluations during the time of the pandemic.
The overwhelming majority of these events were attended by over 30 people, with three attracting more than 100 attendees.

Going forward, it will be useful to better define what activities can be counted under each indicator, e.g. should 2.2 include events that are primarily discussions with stakeholders

CEDIL’s performance in indicator 2.2 shows they have made great progress in promoting their seminars, as well as ensuring their content is relevant and interesting to their audience. Value in this area could be increased further through consistently ensuring relevant events can be promoted within FCDO.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The publications produced represent good VfM. They have been well received by the target audience and provide early outputs that can highlight the value of the programme’s research within FCDO and more broadly. Meanwhile, the dissemination and training events have far exceeded the target. During AR interviews, respondents from the PoW remarked how useful they had found CEDIL’s training and guidelines webinars, highlighting their effectiveness. The CEDIL seminar series is also well organised and attracts high attendance, particularly since they were shifted online due to Covid-19. The VfM could be further improved by ensuring that such events are better publicised around FCDO.

Describe any changes to this output, and any planned changes as a result of this review.

One indicator has been removed from this output as it was deemed to be not relevant. This was the “percentage of projects which include research users as core members of the project team or as members of project Advisory Boards”. The other revisions have been to refine the text to make it more specific and/or relevant. For example, output 1.1 has been expanded from a narrow focus on “evaluation reports, policy briefs and methodological guidance notes” produced and published, to “user-oriented summary products produced and published on the CEDIL website, including policy briefs, portals/maps and methodological guidance notes”. This ensures that the broad range of CEDIL outputs can be included under this indicator.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Previous AR recommendation	Progress
CEDIL and DFID to review and adjust the milestones for future years for the first and second indicator	Met: In particular, these milestone updates were expected to draw on CEDIL’s experience over the last year and the commitments outlined in the outreach plan. This was achieved, although it is clear that there needs to be some clearer definition of what can be included under each indicator, and to ensure events are not double counted.

The recommendations for this year are as follows:

R3: The CEDIL Directorate should capitalise on the progress it has made to date on its outreach plan by dedicating more time to strategic communications and the proactive targeting of key audiences in order to raise its profile. FCDO to support CEDIL on internal communications, particularly through identifying key areas of strategic interest for the FCDO audience (CEDIL to develop initial plans for this recommendation by February 2021)
Output Title	A range of communication products and activities to disseminate its objectives, activities and outputs effectively to generate broad interest in CEDIL among the research, evaluation and user community
Output number:		3	Output Score:		A
Impact weighting (%):		20%	Weighting revised since last AR?		No
Indicator(s)				Milestone(s) for this review		Progress
3.1 Number of blog and vlog posts published on the CEDIL website				8		6 (5 blogs and 1 vlog)
3.2. Total number of CEDIL Twitter account followers				1250		1260
3.3 Total number of 'attendees' at CEDIL events, including post-event online viewing				1020		1594

Briefly describe the output and provide supporting narrative for the score.

While CEDIL slightly missed its target on published blogs and vlogs, it met or exceeded its other targets. CEDIL therefore scores an A for this output.

CEDIL only produced 6 blogs/vlogs, compared to a target of 8. Given delays in the PoW this is perhaps not surprising. The PoW teams have been busy finalising their communication plans over the last few months and, once these plans are being implemented, there will be far more outputs being produced. Blog and website-related analytics are therefore expected to improve over the next reporting period.

CEDIL marginally exceeded the target on Twitter account followers by a total of ten. The programme has substantially increased the number of followers from 956 to 1260 over the course of the year. This is due to continuous engagement with the Twitter platform, which has been used to promote seminars and other events, as well as providing updates on the PoW. Hiring additional comms support at the end of this reporting period indicates that this indicator will continue to improve going forward. Other evidence of CEDIL’s reach is the high number of website visitors (10,232) over the year.

During this reporting period, CEDIL hired a Research Uptake Manager who had responsibility for developing a prioritised outreach plan. While CEDIL did have a communications strategy before this, it was high level and did not have details on actions and activities. The plan sought to fill in these gaps and demonstrate how CEDIL would achieve its aims. The deadline for this was originally March 2020, but this slipped back, in part due to the onset of Covid-19. By the end of the reporting period, the prioritised outreach plan is near completion (the only outstanding issue is the need to benchmark CEDIL’s communications targets against similar organisations within the sector).

Implementation of the plan is making good progress. For instance, the Research Uptake Manager has been ensuring all the project teams are using the stakeholder engagement and evidence use guidelines and have good plans for outreach, which is laying the building blocks for impact in the coming years.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

In the last AR, the only area of concern in terms of the programme’s effectiveness was communications and outreach. This was because this area of work was not sufficiently resourced and therefore in danger of going off track. During this reporting period, the recruitment of the Research Uptake Manager has improved performance, highlighting how an increase in resources can improve VfM. As the PoW starts producing evidence, we can expect many more publications. With adequate support from CEDIL to ensure quality, VfM should increase in the next reporting period.

Describe any changes to this output, and any planned changes as a result of this review.

Changes have been made to the wording of all three indicators, with the aim of adding clarity to what may be counted under each one. For example, a focus on blogs and vlogs in 3.1 rather than “substantial comms reports”. One indicator, which measured the number of CEDIL blogs republished on other sites, was removed. This decision was made because indicator 3.1 was felt to be the single most relevant indicator. Milestones have been added for each indicator, as these had previously not been determined. The milestone for indicator 3.2 is likely to be revised as currently the targets are not benchmarked against similar organisations. This should be completed by January 2021.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The recommendations set out under this output in the last Annual Review were:

Recommendation from previous AR	Progress
CEDIL to ensure the outreach strategy’s framework is turned into a prioritised plan which maximises reach and ensures diversity of reach extending across the range of CEDIL’s stakeholders (by March 2020).	Mostly met: / Although the prioritised outreach plan has not yet been completely finalised, almost all of the work has been completed and the plan is being implemented. The plan describes how CEDIL will engage various stakeholders through implementing a broad range of well-targeted activities. The issue preventing final sign off of the document is the lack of benchmarking targets against similar organisations, see below
CEDIL to use other similar organisations as comparators to set the level of ambition for future year milestones in this output.	Not met: / This is not something that CEDIL has yet been able to achieve.
CEDIL to produce accessible summary versions of key inception papers (one per month from February 2020, three to five in total).	Not met / To date, no summaries have been produced. This is partly due to competing priorities for the Research Uptake Manager, which led to the summaries being deprioritised for much of the year. Furthermore, since the last AR, CEDIL has started to produce working papers from the Fast Track Studies and this has taken priority. Further discussions need to be had on which of the inception papers merit a summary brief, with the understanding that the ideas in some of the papers have already been moved forward through CEDIL’s other work. A good example of this is the stakeholder engagement paper, which is very much a precursor to the work that UCL is currently doing on their Fast Track Study. In such cases, it may be wise to focus time on writing briefs that capture the essence of this more recent work.

The recommendations for this year are therefore as follows:

R4: CEDIL to produce accessible summary versions of key inception papers by the end of June 2021 (the expectation is that CEDIL will produce summaries for two key inception papers).

R5c: The CEDIL Directorate to use other similar organisations as comparators to set the level of ambition for future year milestones in this output. These should be reflected in the outreach strategy, allowing it to be signed off by end of January 2021.

D: RISK

Overview of risk management

CEDIL risks have continued to be monitored and updated regularly throughout 2019-20 by both FCDO and CEDIL; the Annual Review team reviewed risks and sought the views of the interviewees. As a result of this, several new risks have been added and other risks and mitigation strategies have been adjusted or strengthened.

New risks have been added around potential delays to the CEDIL programme caused by the Covid-19 pandemic (especially to the PoW projects, where there have been delays to projects getting underway and changes made necessary by field work no longer being possible) and the possible effects of prioritisation savings (caused by the UK Government’s Covid-19 response) on the CEDIL programme. Savings were found in the budget for 2020/21 from delays caused by pandemic-related operating constraints and putting on hold plans for further research. The risk remains in 2021/22, given further spending pressures.

The risks adjusted by FCDO include increasing the level of risk around sustainability, partly due to the lack of full funding for RD staff salaries in future years and that the RD contract finishes earlier than the PD contract. Some progress has been made over the year on developing a sustainability strategy for CEDIL, although this is still at an early stage. This will continue to be a risk and focus of work in 2020/21.

For the ongoing risks covering “building awareness of CEDIL among stakeholders” and “ensuring the focus of the CEDIL’s work is not too academic”, PD’s progress on producing a prioritised outreach plan and the continuing work to ensure the coherence and relevance of the Programme of Work are important mitigations. Given the project’s tight timescales, another important risk to mitigate is “delays or quality of work problems due to increased fragility in Programme of Work locations or political or operational issues”. The longer-than-anticipated time taken to complete the contracting process and get the PoW projects underway has in itself increased the risk that the projects will not be able to complete by the end date of the current programme in April 2023. PD has improved its processes for monitoring this risk over the past year, which will improve CEDIL’s ability to mitigate this risk.

For the risk “CEDIL Directorate not being strong enough to deliver the programme”, progress has been made on improving the delivery model for the year, but some risks remain (as detailed in Section E). RD and PD both expressed the view that the volume of projects in the Programme of Work is large compared to the resources they have available to manage it and is more than PD originally planned for. The risk remains that “FCDO does not have adequate management resources to ensure effective delivery and management of CEDIL”, particularly given the pressures of Covid-19 and the re-organisation of FCDO. On the “risk of misuse of funds through research teams working in high fraud environments”, FCDO confirmed in last year’s AR that PD was conducting proportionate due diligence assessments as part of the contracting process. CEDIL reinforced the importance of fraud and safeguarding processes at the introductory meetings for the research teams. FCDO and CEDIL will continue to work together to ensure that CEDIL takes an effective approach to managing this risk.

Recommendation

R6: FCDO and CEDIL to ensure that the issues affecting RD salaries are addressed (the issues are the partial funding in future years and the RD contract finishing before the PD contract) and to ensure the sustainability strategy is taken forward.

Update on Partnership Principles (delete this section if not relevant)

The Partnership Principles risk table was used to inform decisions around the selection of CEDIL’s large and small projects.
E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

Delivery and performance of partners

This was the second year of implementation and has again been a busy year with a demanding timetable, which was testing for the delivery model. As can be seen from this review, much has been delivered through the year at good quality and the delivery model has again held up for the most part. However, there continue to be some areas in need of adjustment and improvement, such as delays to invoicing and the delivery of certain requirements and products.
[note] A difficult and unsatisfactory outcome of the first procurement phase and a longer than expected second procurement meant that procurement for CEDIL was not finished until 2018. PD then completed a 6 month inception stage before implementation began.

FCDO and CEDIL Directorate have worked together to address last year’s AR recommendation to implement an improved coordination and accountability model. Key to this has been the instigation of quarterly reports, with the first report covering October to December 2019. These reports are now being delivered in a timely fashion and cover progress in the PoW and against the key work areas. This has enabled FCDO and CEDIL to streamline the number of meetings and refocus them to high value areas.
[note] Full recommendation - DFID, PD and RD to implement the improved coordination and accountability model (initial changes to be made December 2019 – March 2020).

PD has made changes to improve delivery, including more emphasis being placed on ensuring that resources are allocated to high priority tasks and changing the balance of the team by increasing the amount of administrative support to then free up some programme management and management time. Combined with setting up improved processes and systems for managing the PoW, this means that as the year progressed PD has increased the speed of responsiveness for a number of areas of CEDIL programme management.

There are areas where there is still a need for progress: speediness of strategic budgeting (covered under financial below) and using programme management tools such as the workplan and logframe to ensure more effective management.

Financial

Speed of invoicing and the quality of forecasting and budgeting has continued to be an issue for both PD and RD. For PD, the invoicing and short-term forecasting issues have been caused by the delays in some areas of delivery and the degree to which they have prioritised this programme management area. FCDO and CEDIL are working to resolve these issues. For RD, difficulties in getting invoices from downstream partners and preparing approved summaries of finances have resulted in delays to submitting and approving invoices. RD’s full-time project coordinator was appointed in January 2020 and has been working closely with FCDO to get RD finances back on track.

The CEDIL Directorate realised at the start of the reporting period that part of their long-term financial budget is incorrect in one key assumption. Work has been ongoing to provide a resolution on this, to ensure that forward budgets and associated deliverables are clear between FCDO and the CEDIL Directorate, but over the year responses from CEDIL have been slow. FCDO would like to see improvements in CEDIL’s focus on, and speediness of, their budgeting.

Delivery and Financial recommendations

R7: CEDIL Directorate should increase the use of programme management tools such as the workplan and logframe in directing their management of the programme. (CEDIL and FCDO to review progress in February 2021 and agree further review points)

R8: CEDIL Directorate to make improvements in its focus on, and timeliness of their budgeting and programme invoicing. (CEDIL and FCDO to review progress in February 2021 and agree further review points)

Other Commercial matters

FCDO’s new cost and transparency requirements: When the current contract amendment is completed, PD and RD will move onto the updated terms and conditions, including the new cost and transparency requirements.

OPM is one of the suppliers covered by FCDO’s Strategic Relationship Management programme, brought in to drive VfM for FCDO contracts. It continues to be rated as a Gold Supply Partner through the Strategic Relationship Management (SRM) Scorecard process.

Asset monitoring and control.

RD has provided an updated asset register and confirmation that the existing assets (laptops for core staff) are still in their possession.

PD has also provided an asset register showing items that have been purchased since the contract commenced in April 2018.

FCDO as a partner for the programme.

Feedback on FCDO as a partner was solicited from CEDIL and other interviewees in the AR. Most of the feedback was positive, with CEDIL appreciating the involvement from FCDO in bringing CEDIL closer to potential users and policy issues. Concern was expressed that the FCDO T&Cs used for research teams, which come from standard FCDO commercial clauses, are not appropriate for research institutions operating model.

Monitoring

FCDO’s Senior Responsible Owner (SRO), Programme Manager and other staff have had regular contact with CEDIL staff over this year. Many matters of substance and administration have been discussed openly and constructively, both in regular CEDIL Directorate meetings and through e-mail and telephone conversations. FCDO staff have attended several of CEDIL’s seminars and workshops for research teams and have received feedback about others.

This Annual Review was conducted during October and November 2020. It was conducted by a team of three FCDO staff: the SRO for CEDIL (Evaluation Adviser, Evaluation Unit), an Evaluation Manager working on CEDIL and the Programme Manager. FCDO conducted a document review as part of this process. As well as speaking to FCDO staff and CEDIL Directorate staff, the review team spoke to members of the CEDIL Intellectual Leadership Team, the CEDIL consortium and research teams in the Programme of Work. The Head of Evaluation Unit has reviewed a draft and the Head of Evidence Department signed off the Annual Review.

Date of last narrative financial report(s)	October 2020
Date of last audited annual statement (s)	PD: Oct 2018 - Sep 2019
Date of last audited annual statement (s)	RD: Aug 2018 – July 2019