## Annual Review Template – September 2020

Title: Sustaining lives and securing a sustainable future for refugees and migrants in Western Tanzania
Programme Value £ (full life): £58m		Review date: October 2020
Programme Code: 204805	AMP start date: )1 October 2017	AMP end date: 30 September 2021

Summary of Programme Performance
Year	2018	2019	2020
Overall Output Score	B	B	A
Risk Rating	Moderate	Major	Major

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/20298933.odt
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-1-204805/documents

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

The business case aimed for the programme to support the Government of Tanzania to manage short and long-term refugee populations, increase capacity to better manage migration between Burundi and Kigoma and in doing so provide increased protection for irregular migrants already present in Tanzania.

Since the approval of the business case, the operating context in Tanzania has changed significantly. In 2018, the Government of Tanzania toughened its refugee policy, withdrawing from the Comprehensive Refugee Response Framework (CRRF). Today, strict encampment policies are enforced, limiting refugee’s movements and access to markets. Although the situation in Burundi seems to have improved following the May presidential elections, Tanzania has effectively closed its borders to new refugees and asylum seekers and access is heavily restricted. No new arrivals have been recorded to date. These shifts in operating context warranted a change in the programme scope to a primary focus on protection issues, managing voluntary repatriation processes, provision on emergency support and engaging in policy dialogue.

By August 2020, a total of 11,961 refugees and asylum seekers had been repatriated over 2020. Actual repatriation fell well short of the target of 2,000 people a week set by the Tripartite Commission in 2017. The May 2020 Presidential election in Burundi and COVID-19 pandemic outbreak resulted in a slowdown in the voluntary repatriation process. However, the number has picked up since the end of August to over 1,000 per week. This increase followed GoT high level ministerial visits to the camps, visits that re-emphasized repatriation and indicated that humanitarian agencies should support the Governments of Tanzania and Burundi to sensitize refugees so that more would return home.

With threats of highly infectious disease outbreaks, firstly the Ebola outbreak in Congo in 2019, and probably case in Tanzania in late 2019, and subsequently with COVID-19 declared a global pandemic early in 2020, the programme’s mandate was widened to provide immediate short-term support to respond to the public health emergency.

Main programme partners can be summarised as follows:

S/n	Partner	Activities	Agreement	Budget
1	UNHCR	Unearmarked funding for camp-based refugees in Tanzania	MoU	£18.4m
2	WFP	General Food Distribution and Supplementary / Feeding in Nyarugusu, Nduta and Mtendeli refugee camps	Contribution Arrangement	£17.5m
3	IOM	Support to Government of Tanzania for the implementation of registration of mixed migration living in Tanzania	MoU	£1.9m
4	DRC	Camp Management and WASH in Nduta and Mtendeli refugee camps	Accountable Grant	£6.1m
5	NRC	Camp management and WASH activities in Nyarugusu camp.	Accountable Grant	£4m
6	IRC	IRC – lead partner of a consortium (include Plan International and CARITAS Kigoma Diocese). Provision of education services to refugees’ children in Nyarugusu, Mtendeli and Nduta camps.	Accountable Grant	£5.5m
7	WHO	Strengthening Ebola Virus Disease (EVD) operational preparedness in 8 regions in mainland Tanzania and 2 main Islands in Zanzibar	Contribution Arrangement	£0.5m
8	UNICEF	Scaling up COVID-19 preparedness and response activities in Tanzania	Contribution arrangement	£1.5m
9.	WHO	COVID-19 preparedness and response support to Rapid Response Teams, Surveillance and Co-ordination capacity.	Contribution Arrangement	£0.5m
10	BMF	Benjamin Mkapa Foundation support to Government of Tanzania COVID-19	Accountable Grant	£1.62m
[note] At the time of the Annual Review, all partners listed had active components.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

Overall, an A score has been awarded for the programme. The policy environment has remained difficult, putting pressure on the implementation of programme activities. Despite the difficult environment, provision of essential services and emergency preparedness has been the focus of the programme and positive results are observed on WASH and education activities. In the reporting period, positive trajectories were also observed through a localised advocacy component and good progress is observed on registering irregular migrants.

A continued push for repatriation remains to be a concern as regards protection space. Reports of lack of access to territory also pose a wider concern on plight of future asylum seekers and refugees. The encampment policies and restriction of livelihood activities continue to limit potential for refugees to be self-reliant. Significant shortfalls in resources, with WFP and UNHCR having recently released appeals, has the potential to exacerbate the current risks.

The outcome of the Burundi elections has been peaceful and currently there is no influx of refugees into Tanzania. There is a significant number of Burundi refugees repatriating, which could ease the resource constraints. There is a stronger focus on voluntary repatriation of refugees and consequently reintegration in Burundi. Even though the western border has not experienced an influx of refugees, concerns loom over a potential humanitarian crisis in the southern border following the unrest in Northern Mozambique. The programme continues to monitor developments and plan for a potential response in coordination with other development partners.

Since the last annual review, the programme has shifted its focus from addressing long term durable solutions to catering for essential services in the camps. The programme was also able to flex its resources to provide for both Ebola Virus Disease preparedness and COVID-19 responses.

Major lessons and recommendations for the year ahead [1/2 page]

Tanzania refugee policy environment remains difficult. The government continues to enforce strict encampment policies, restrict access to territory for refugees and asylum seekers and emphasise repatriation of Burundi refugees. It is unlikely for this position to change past the October 2020 Tanzania election. Despite the difficult environment, FCDO, should continue to advocate for a change in policy context emphasising on voluntary repatriation whilst providing essential services in camps.
Programme SRO, Humanitarian Advisor, ongoing.

The programme coming to an end provides an opportunity to reflect on experiences, opportunities and lessons which should be incorporated in the design of a regional programme Concept Note. A Regional approach to future programming should consider these lessons and focusing on provision of services in refugee camps, support voluntary repatriations, ensure cross border coordination and reintegration of returnees in Burundi.
Programme SRO in Tanzania and Rwanda, Humanitarian Advisor, March 2021

Resource shortfalls are negatively impacting the response and could lead to operational constraints, major political risks, deterioration of the protection space and insecurities for the refugee populations. FCDO in coordination with other development partners should continuously track and map resources available for the response whilst ensuring the UK responds within it burden share limits.
Programme SRO, Humanitarian Advisor, ongoing / end March 2021

The UK must assess its humanitarian response and make contribution within its burden share. Globally, the humanitarian needs are growing massively with only a few development partners playing a vital part in sustaining refugees. Burden share assessment will not only prevent donor fatigue but also create a sense of shared responsibility. However, there is a risk of not making meaningful contribution to a much-needed support because of burden share and accountability.
[note] Burden share Table in Annex 1
Programme SRO, Humanitarian Advisor, December 2020

Difficulties in the operating environment calls for more coordination of development partners and local organisations to advocate for refugee rights and protection space. FCDO should continue to seek avenues to have constructive engagement with the Government of Tanzania by effectively coordinating like-minded donors and local organisations on advocacy for improved protection space.
Programme SRO, on going

Continued unrest in Northern Mozambique could create a humanitarian and security crisis in the South of Tanzania. Working across HMG, FCDO should continue to monitor and report on the growing concerns, develop a joint assessment of the situation and plan towards emergency response
Programme SRO/ Humanitarian Advisor- On going

With the current COVID-19 support programmes coming to an end, FCDO should ascertain key priority areas for potential future support in conjunction with the Human Investment Team and ensure that the advances made (for both EVD and Covid-19) are sustainable and link with wider support to essential service provision and Health Systems strengthening activities.
Programme SRO, Humanitarian Advisor and health Advisor, Feb 2020

Given the programme’s complexity, with growing number of components, the programme team should to align all reporting timelines to improve general flow of activities, ease access to information and further improve on financial management.
Programme SRO- December 2020

A resource reallocation is necessary for UNHCR and WFP in order to meet our annual commitments towards the support. WFP and UNHCR continue to play a vital role in service provision in the camps. These Multilaterals MoU that are revised annually. We recommend a cost extension for WFP and UNHCR to be done within agreed budget allocations.
Programme SRO, end October 2020

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

Following the changes made in the last reporting year, the theory of change has not been amended. The Theory of Change recognises the strict refugee policy environment in Tanzania and underpins that progressive approaches to support the refugee population through integration into local service delivery structures and through better access to income generating activities is not likely under the current policies. This being the final implementation year of the programme, the theory of change will not be amended. However, the work on EVD preparedness and COVID-19 response and our engagement with the government on the response will provide an opportunity to assess and reflect on Tanzania’s ability to cope with emergencies. In the final implementation cycle of the programme, there is an opportunity to reflect on lessons and experiences in the changing context and supporting durable solutions for long term refugees as the team embarks on writing a successor Business Case.

Since the last Annual Review, the programme’s logframe has been changed twice. In late 2019, the logframe was updated reflecting recommendations to halt outcomes and outputs associated with support to long term refugees and adding outcomes and outputs relating to the Ebola Virus disease preparedness support. With the programme playing a central and key role in the COVID-19 emergency response, the logframe was changed in June 2020 with additional outcomes and outputs. Likewise, across the programme, the different components had to realign their support to include the COVID-19 response. Outputs relating to these outcomes and realignments have been amended accordingly.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

Tanzania’s refugee policy environment continues to deteriorate. Although the programme has seen significant achievement at output levels, there will be a partial achievement against the originally envisioned outcomes. This equally implies that it will be a lot harder to fully achieve impact level results. Whilst the government of Tanzania has signed up to the Global Compact on Refugees, this has set the government position with reservations that Tanzania will not ratify goal number 2 of the compact, which seeks to enhance refugee self-reliance. This stance has been observed through the encampment policy and strict restrictions on livelihood activities. Equally, we envisage a partial achievement against outcomes relating to durable solutions for long term. Although we have seen positive progress made in plans to register irregular migrants, the government of Tanzania’s position is still unclear on fully naturalising the 1972 caseload, long-term refugees, and providing them with legal status.

There is room to achieve outcome results relating to protection assistance, maintain camp conditions within emergency thresholds by the ongoing provision of services, achievement of education outcomes and registration of irregular migrants. These however could be limited by funding constraints and by the general timeframe to carry out the programme.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph

Provision of basic services for the underserved refugee populations is an important element to protecting the rights of refugees. Based on the above analysis, there is enough evidence for the programme to continue despite the constraints in the operating environment. We will continue monitoring the operating context and advocate for improvements in the protection space.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Provision of durable solutions for vulnerable migrants
Output number:		1	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
Updated Comprehensive Migration Management Strategy is finalised, available and implemented by immigration officials	Strategy workshops held, COMMIST2 copies available to immigration services offices	-Strategy workshops held / -COMMIST 2 was signed and approved by the Minister of Home Affairs / -100 copies of COMMIST were printed and disseminated to the Tanzania Immigration Services Departments Headquarters and Regional and District Immigration offices in Kigoma
Immigration Government personnel have the skills and knowledge to conduct migrant registration using latest and updated peripherals and technology	Registration equipment from Phase 1 has been assessed and new equipment is available accordingly	-E-registration mobile kits have been procured and available in country. / -New equipment is available accordingly

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

The overall score under this set of indicators is A. In this reporting year, IOM has made significant strides towards supporting the identification, registration and documentation of irregular migrants in Tanzania. The updated Comprehensive Migration Management Strategy (COMMIST 2) was approved and signed by the Minister of Home Affairs of the United Republic of Tanzania. The COMMIST 2 document provides guidelines and procedures for the implementation of migrants e-registration in the country, which includes registration, documentation, status determination and assisted voluntary returns (AVR). The official signing of the document by the minister signalled that the COMMIST 2 can now be made available for use by officials across the country. Immigration government person were trained and 100 copies of COMMIST 2 were distributed in Kigoma and Kagera regions. These two regions host the largest numbers of migrants.

In order to kick start the registration process, IOM was able to carry out outreach activities through a select number of providers - both print and electronic media. They also procured 22 e-registration mobile kits which were installed with government approved software. Government officials in the immigration departments have been trained on e-registration and use of COMMIST 2 guidelines, the effectiveness of this training will be determined when registrations commence. Registration kits ready to be deployed marks a step towards the process of issuing Government identity cards which will provide migrants with access to services as well as reduced risk of deportation.

The global impact of the COVID-19 pandemic has created major delays in the implementation of activities exacerbating some of the original challenges the project was facing. Delays were experienced in conducting outreach activities, decisions made on the IT infrastructure to use for the e-registration and procurement of the mobile registration kits. As a result of the delays, a decision was made to extend the project timeline by five months to give it ample time to achieve outcomes.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

The project objectives response to the commitments of leaving no one behind by supporting underserved refugee populations. Economy factors, particularly cost of procuring e-registration kits and capacity building for over 100,000 staff from different authorities involved in the management of migrants in the country, comprise of the major cost drivers under the project. VfM markers of efficiency and effectiveness will be assessed after the registration exercise and issuance of identity cards begin. There are significant gender considerations in the capacity building activities, ensuring women participate in the capacity building sessions and in the community outreach activities. Gender equality has been factored in to ensure women, young adults and elderly are sensitised to come forwards and register. An end year summative evaluation will give a gender disaggregated data on registration.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Following the 2019 annual review recommendations, both the output indicators and impact weighting were revised. Due to changes in policy environment and government of Tanzania’s stance on long-term refugees, a decision was made to reallocate funding that was once going towards support for naturalisation of the long-term refugees. FCDO continues to monitor the space to make a future determination on support for long-term refugees.

Given that the current indicators have been achieved 100%, we recommend a change of indicators and milestones ahead of the next annual review. Change to include tracking of actual numbers of migrants that have been registered and issued with identity cards.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The last annual review recommended a revision on the ToC and reallocation of resources that was aimed at supporting the naturalisation of long-term refugees. All the changes were done, and the revisions took effect in January 2020. FCDO continues to monitor the trends and Tanzania’s appetite to revisit the issues relating to long term refugees in providing them with durable solutions.

Recommendation
On registration of irregular migrants, no further evaluation has been done to document the numbers of people who have concluded their immigration status in order to measure final impact of the programme. Now that the IOM project has received an extension, we recommend this to be included in the outputs and an internal evaluation to be conducted before the end of the project
Programme SRO - March 2021

Continue to monitor the policy environment and advocate for protection space, access to territory for asylum seekers and durable solutions for the long-term refugees
Programme Lead - ongoing

In drafting a new Business Case for the successor programme, FCDO should conduct a full assessment of Tanzania’s position on refugees, drawing lessons from the implementation of the current programme
Humanitarian Advisor / Programme SRO - ongoing

Output Title	Assistance and protection provided to new refugees to sustain lives and livelihoods
Output number per LF		2	Output Score	A
Impact weighting (%):		50%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone for 2020	Progress
% of refugees with adequate shelters UNHCR	85%	87.5% of Burundi Refugees live in adequate shelters while 72% of Congolese refugees have adequate shelters
WASH: average # of litres of water available per person per day / UNHCR / NRC	21	On average 28l/p/d : The current water production for each camp is 128.308.m3 for Nyarugusu with effective coverage of 27 l/p/d, (Burundian and Congolese caseloads), 9481.5m3/week for Mtendeli Camp with effective coverage of 29l/p/d and 77,721 m3 for Nduta camp with effective coverage of 27l/p/d
% of live births attended by skilled health personnel UNHCR	100	97%
% of refugees with access to semi-permanent sanitation facilities at a ratio of 1:15 in in Nduta camp (DRC)	80%	88%
# of leaders elected and actively fulfilling their role as community representatives within Nduta and Mtendeli camps (DRC)	6,300	DRC has reported 8,395 community leaders elected and active in their roles
# of HH receiving Core Relief Items (CRI) at least twice during the implementation period (DRC)	55,000 HH	28,802 households received clothes & hygienic supplies. UNHCR provided CRI to 84 households of persons with special needs
% of beneficiaries who report using a sufficient amount of safe water for daily use (e.g. drinking, cooking & hygiene) in Nyarugusu camp (NRC)	100%	85% - whilst the water system in Nyarugusu has sufficient capacity to provide sufficient water, limitations on water containers (part of the CRI package) mean that inadequate storage exists at household level
# of individuals in Nyarugusu referred to camp service provider(s) per month as part of multi-agency complaints and feedback mechanism (DRC)	24,000	3,433 cases from January to June 2020 across all three camps. Community Based Protection teams are reporting 100% of cases received were responded to. Overall target numbers were overestimated as part of original planning and will be revised down
% of households with Acceptable food consumption score (WFP)	85%	81%

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

In this reporting period, progress has been made in improving conditions in the camps, particularly in regard to WASH and camp management activities. As a result of overall positive trends in achieving results, the output has scored A.

Among the Burundian population, there was an increase in the coverage of adequate dwellings to 87.5% from the planned 85%, while 72% of Congolese refugees reside in adequate shelters. The reduction in the refugee population contributed to an increase in adequate shelter coverage as vacated shelters (following repatriation) were reallocated to those in need. Initially planned to cater for a potential influx of new refugees following the Burundi presidential elections, this output indicator focus was changed from provision and construction of semi-permanent shelters to percentage of refugees with adequate shelters. UNHCR and partners also focused on maintaining and upgrading a total of 13,212 transitional shelters across the three camps through a community-based shelter approach. UNHCR has been using this approach to support those refugees who can construct their own shelters with the support of materials, tools and technical guidance from UNHCR and partners. In the reporting period, UNHCR provided more than 332 shelter maintenance kits. Despite the successes, the impact of COVID-19 was mostly felt in the shelter sector as only ten transitional shelters for Burundian population were constructed.

While UNHCR maintained the lead role to ensure water supply in the three camps, some of the WASH activities were designated to DRC and NRC. In the reporting year, UNHCR conducted activities to upgrade and improve the water systems in order to ensure safe and clean access to potable water. As a result, the water system in the camp averaged at 28 litres per person per day as reported by NRC. The current water supply for each camp is Nyarugusu 27 l/p/d covering both Burundian and Congolese populations, Mtendeli Camp 29l/p/d and Nduta camp 27l/p/d.

During the reporting period, a total of 371 household latrines and 201 household bathing shelters were constructed in Nduta camp, which now makes a total of 806 household latrines and 533 household bathing shelters constructed using a community participatory approach. The constructed latrines serve a population of 2,821.

On health, 1,904 new births were recorded in the camps amongst the Burundian population. Among them, 97% of the total live births were attended by skilled health workers in health facilities. The WHO standard is at least 95%. In addition, UNHCR trained 60 health personnel on Basic Emergency Obstetric and Neonatal Care (BEmONC) and Comprehensive Emergency Obstetric and Neonatal Care (CEmONC).

In terms of community representation in the camps, the project run by DRC has met the target for leaders fulfilling their roles with 8,395 leaders in place across all three camps. Of that total, 4,201 are women reaching the 50% parity of female to male representation and participation in community leadership. This target was achieved despite challenges of COVID-19 activity restrictions which suspended elections for vacancies in leadership positions. There are also further concerns of the numbers of community leaders achieved dropping due to the ongoing repatriation processes and resignations.

The Burundi Refugee crisis is generally underfunded. There has not been a wider distribution of Core Relief Items (CRI) and priority has been given to persons with special needs. A total of 65 Burundian and 19 Congolese persons with special needs households received CRI in the camps. For the wider refugee populations, some of the core relief items distributed included clothes and soap. Cumulatively, in Nduta Camp a total of 727,442 items of clothing was distributed to 20,766 households comprising of 73,658 (18,817 men, 20,062 women, 17,741 children aged 5-12 years and 17,038 children aged below 5 years) individual persons of concern. In Mtendeli Camp, a cumulative total of 363,748 items of clothing were distributed to 8,036 households comprising of 32,253 (8,025 men, 8,980 women, 7,582 children aged 5-12 years and 7,666 children aged below 5 years) individual persons of concern. A total of 241,467 persons received hygienic supplies mainly through general distribution of soap. Due to funding constraints, UNHCR was distributing 250g of soap per person. This was later increased to 500g of soap per person as part of UNHCR’s COVID-19 prevention and response strategy.

On food consumption, a slight decrease in the acceptable threshold of food consumption score was observed at household levels, where the score declined to 81% from 86 percent reported in 2019. There is equally little indication of dietary diversification which exposed refugees to potential food insecurities and malnutrition. WFP food rations have fallen significantly since the beginning of 2020. Faced with funding shortages, they have cut rations from 95% at the beginning of the year to a 72% at reporting time. A further cut to mid-60% is anticipated if WFP is not able to mobilise resources. With limited livelihood activities, coping mechanisms for the refugees are limited bringing about potential health, protection and security concerns. In this financial year, FCDO assessed the UK’s burden share, committed and approved a £1.5m extension as a response towards the USD 33m WFP appeal.
[note] The total funds raised towards the appeal is still unknown. At the time of the AR WFP had successfully raised about £2.5m from the UK and other donors.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]
The overall progress across the output indicators signals there is VfM. The different project components have been able to attain and surpass output targets aimed at improving basic services to marginalised communities amid resource constraints. Some components have had to adjust in operations due to cuts in resources, for example, reallocating shelters to refugees rather than constructing new shelters (linked to increased repatriation). Across the board there is a special focus on gender and people living with disabilities. A special focus must be placed on how the different components within the output flex to meet resource demands.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Some of the original quantitative and qualitative targets have been affected by the ongoing voluntary repatriation programme. Equally, there are changes in delivery partners for some of the outputs, for example, the number of individuals in Nyarugusu referred to camp service provider(s) per month as part of multi-agency complaints and feedback mechanism. Going forwards, these indicators will be revised to reflect the actors and accurate targets.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Most recommendations from the previous annual review are marked as completed. In completing the recommendations, some qualitative targets were changed, the proposed gender audit was also conducted, and the DRC component of the project allocated WASH resources to host communities. Recommendations for the year ahead are similar to the wider policy framework recommendations made last year.

Whilst the policy environment continues to have negative impact on some activities, particularly on livelihoods activities and access to market and territory, UNHCR and WFP need to identify and take forward policy dialogue opportunities through component 4 of the programme.
Programme SRO, Ongoing

Although not targeted under this programme, insecurity in Northern Mozambique has the potential to create a humanitarian crisis in the area. Development partners and implementing partners, especially multilaterals, should be encouraged to track the situation of concern, ensure they are communicating with the government of Tanzania and have contingency preparedness plans to respond to the potential emergency response crisis.
Programme SRO and Humanitarian Advisor, ongoing

Resource shortfalls are negatively impacting the response and could lead to operational constraints, major political risks, deterioration of the protection space and insecurities for the refugee populations. FCDO in coordination with other development partners need to have an advocacy plan, and map resources available for the response whilst ensuring the UK responds within it burden share limits. A cost extension for WFP has been approved. Programme team should seek to finalise the extension by November 2020.
Programme SRO, Humanitarian Advisor, ongoing / end March 2021

Indicators for INGO partners should be revised to ensure targets are realistic and are correctly labelled. For example, the output indicators on numbers of individuals in Nyarugusu referred to camp service provider(s) per month as part of multi-agency complaints and feedback mechanism (DRC). The milestones must be revised downwards. Similarly, output corresponding to percentage of beneficiaries who report using enough safe water for daily use (e.g. drinking, cooking & hygiene) in Nyarugusu camp (NRC) need to be updated.
Programme SRO, December 2020

Output Title	Increased access to, and quality of, education for refugees in camps
Output number per LF		3	Output Score	B
Impact weighting (%):		15%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone for 2020	Progress
% of secondary students achieving passes in standardized exams (disaggregated by grade, gender, nationality, disability, and camps)	G14 = 61.59%; G15 = 10.17%; G12 (DRC) = 77.6%	Delays in achieving output results
% of students surveyed who perceive their classroom environment to be responsive and safe.	55%	Surveys conducted periodically but results to be reported at the end of project cycle
# of classrooms constructed or rehabilitated (disaggregated)	30 new classrooms constructed / 40 classrooms rehabilitated	Progress underway- full narrative below
% supported schools with improvement plans that include improvements to increase enrolment and attendance jointly developed by school management, PTAs and communities.	No milestones for this review	Assessment to be done at the end of project cycle.

Provide supporting narrative for the score

Activities under this programme have experienced significant delays because of challenges with the examination systems and school closure as a result of COVID-19 pandemic. For the reporting period, this output has scored B.

The Burundian and Congolese academic year usually runs from September – June. However, for the 2019/2020 academic year, this has changed due to the COVID-19 pandemic. All schools across Tanzania, including those in refugee camps, were closed from March 2020 – June 2020. As a result, the academic year was extended until October 2020. Standardized exams set (across the camp) and marked by teachers are usually held at the end of the academic year. The exams were held in the first week or October 2020 and results are still being calculated. There is a strong likelihood that the results of these exams are affected by the disruption to the school year.

National exams are set and delivered by the Congolese Ministry of Education for Congolese students and by the National Examinations Council for Tanzania (NECTA) for Burundian students. The Congolese national exams, which are usually held in May, were postponed until August 2020, the results are still pending. The NECTA exams for the Burundian students, which were to be conducted in May 2019 (before the start of FCDO grant) were significantly delayed and students sat for their exams in January 2020.The results of these exams have just been announced, project is still collecting the data for analysis. The 2020 exams are due to be conducted in October 2020, pending confirmation. Again, it is likely that the examination results for 2020 will be impacted by the disruption to the academic year and the examination timetable.

Construction and rehabilitation across all geographical locations and in all schools is now underway. Following site selection for 30 new classrooms and 43 classrooms for rehabilitation, approvals were sought from the appropriate government offices, including PO-RALG and MHA, with the additional support and approval of UNHCR. There were some challenges and delays due to COVID-19 and camp access, but this has now been resolved and all sites are active. The table below provides and overview of progress as of 7th October. All progress is carefully tracked and documented, with weekly meetings with contractors to discuss progress and any challenges.

Location	Construction progress	Rehabilitation progress
Host Community	38%	59%
Mtendeli	26%	3%
Nduta	31%	10%
Nyarugusu	7%	26%

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

This is among the newest additions to the programme, with agreements signed off in July 2019. An VfM assessment is underway. Given the activity types, the major cost driver for the project is construction and rehabilitation of classrooms in all the three camps. The project envisages to do significant procurements of construction materials over the course of the project. Efficiency and effectiveness indicators will be assessed as the project picks up pace. There is significant consideration of marginalised groups in the provision of education, especially in ensuring the project creates suitable learning environments for girls. Equally, there is an expectation that data produced will be disaggregated by gender, nationality, disability and camps.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

With clear disruption of the school calendar years, especially for exam sitting classes, FCDO has agreed with the partners to monitor current trends until November of 2020 and if there are no significant improvements in administering the exams, then a change will be made on some of the outputs by December 2020.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Significant delays have hampered successful delivery of the tracked output results. Despite these delays, the project is performing satisfactorily across other set of outputs not tracked under this annual review. Lessons and recommendations from last year focused on fulfilling all compliance requirements for the new implementing partner. These have been met and marked completed.

Recommendations for the year ahead
FCDO to continue monitoring the exams cycle and assess alongside the implementing partners the feasibility of retaining output indicator one. With no significant improvement on the current situation, FCDO should consider changing the outputs tracked
Programme SRO, December 2020

Continue to monitor process and pace of construction and rehabilitation of classrooms with the view that with repatriation process picking up pace, no construction will be made in soon to be decommissioned zones
Programme SRO, Ongoing.
Output Title	Continued advocacy to protect asylum space in Tanzania
Output number per LF		4	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestone	Progress
Number National Consultative Forum on Refugee Issues held	1 National consultative forum held	1 National Consultative Forum on Refugee Issues held
Research on refugee issues held in 10 regions of Tanzania	Research conducted	Research underway following the national consultative forum
Conference held on findings of refugee research and approval of publication of a book on findings approved	No milestones for this review	To be assessed at the end of the project
Tanzania Refugee and Migration Management Network re-invigorated and meeting regularly	Development Partners Coordination Meetings.	Continue to track, monitor and convince development partner coordination meeting. Mapping responses and ensure UK contributes fair share in humanitarian space

Provide supporting narrative for the score

The project is a subset of activities conducted by UNHCR. Originally planned to start in October 2019, the project experienced several delays with the COVID-19 pandemic outbreak and authorisation from the Ministry of Home Affairs. The delays in signing a Project Partnership Agreement between the local implementing partner, UNHCR and the Ministry of Home Affairs, pushed the project start date to July 2020.

The aim of this output intervention is to continue placing an emphasis on localization of refugee programming and ongoing engagement with the Tanzania government on the application of the Global Compact on Refugees. In the short implementation period, the project was able to put together a set of work plans that were approved by the relevant authorities and called for the first National Consultative Forum in Refugees - an event that had traction from top policy makers led by the Minister of Home Affairs. The National Consultative forum ignited a conversation of Tanzania’s history in hosting refugees, and provoked lessons from the experience that can be used in future policy decisions. The forum opened doors to engage the Government of Tanzania on these sensitive issues that otherwise will not be discussed.

Equally, the forum has also been the much-needed platform to kickstart national research on refugee issues, covering 10 regions. It is through this research that we will be able to document and share finding as a basis for future policy thinking. Successfully coordinating and achieving this output earns the component an A.

On coordinating other development partners, the UK continues to lead and support initiatives that contribute towards maintaining asylum space and improving camp conditions in Tanzania. The current camp and southern border contexts raise concerns. FCDO monitors issues of concern and actively advocates for voluntary returns and reintegration in Burundi. FCDO also plays a proactive role in co-ordinating key positions across the donor community and pushing UNHCR, IOM and WFP for improved communication on refugee related issues to the donor community.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

Engaging local partners in the refugee response has potential for massive gains in the refugee dialogue and advocacy space. Under the Project Partnership Agreement, a modest £200k is earmarked for the landmark assignment of documenting Tanzania’s experience in hosting refugees whose lessons will benefit the future. The project approach also opens further opportunities to do advocacy and influencing with the Government of Tanzania, providing a clear case for effectiveness on VfM. The full potential of localising response is yet to be assessed and depending on results achieved and effectiveness, the modalities could be considered in the future regional programming.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Given the overall changes in the programme, the impact weighting of this output was adjusted downwards to reflect the current set of outputs proposed across the programme. No further future changes are anticipated under the current output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

No recommendation from the last annual review. Going forwards, this component will play a strategic role in localising the humanitarian response and prompt real Tanzania-led solutions. Some of the recommendation include

The UK to continue leading the developing partners on setting the agenda on advocacy for protection space. Through its support, UK can easily convene UNHCR and other multilateral partners in the protection space to advocate further on refugee rights.

FCDO should revaluate the role local partners play in the protection space and assess their viability in enhancing the advocacy messages especially with the Government of Tanzania. With the policy environment changing drastically, it is more likely that the Government of Tanzania responds more to locally led initiatives and solutions. There is an opportunity to consider modest funding to local organisations who have the capability of implementing and engaging with relevant ministries.

Output Title	Strengthen capacities to rapidly respond to Public Health Emergencies (EVD and COVID-19)
Output number per LF		5	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N/A (New output indicator)

Indicator(s)	Milestone	Progress
Conducting trainings of health workers including surveillance teams & Rapid Response Teams on Standard Case definition, contact tracing and active case search in the priority districts / EVD - WHO	-30 HCWs including surveillance teams trained on Standard Case definition, contact tracing and active case search in the priority districts / -35 district RRTs trained on contact tracing / -92% of priority districts that conducted drills on contact tracing and active case search	-29 HCWs including surveillance teams trained on Standard Case definition, contact tracing and active case search in the priority districts / - 41 district RRTs trained on contact tracing / -100% of priority districts that conducted drills on contact tracing and active case search
Households, communities, key staff, and key institutions are enabled to prevent and control COVID-19 (UNICEF)	-120 clinical and ancillary staff in isolation centres trained on COVID-19 WASH IPC / -15 isolation centres provided with an agreed package of COVID-19 WASH/IPC supplies / -20 isolation centres assessed, and WASH infrastructure repaired	- 689 clinical and ancillary staff in isolation centres trained on COVID-19 WASH IPC and other key SOPs / -17 isolation centres provided with an agreed package of COVID-19 WASH/IPC supplies / -25 isolation centres assessed, and WASH infrastructure repaired
Ensure placement of health workers within the health facilities BMF	- Recruit and conduct orientation to newly 367 recruited health care workers / - Recruit, train and deploy 1072 community Health Care workers	-365 Health care volunteers were recruited and deployed in health facilities / - Recruitment of 1072 community health care worker underway- delays in achieving targets
Rapidly detect, respond appropriately to slow and contain the current COVID-19 outbreak / WHO	Support deployment of COVID-19 case investigators and contact tracing teams in affected districts / - Proportion of investigations conducted in districts (29%) / - Proportion of affected districts where contact tracing conducted (10%) / -Proportion of affected regions with deployed health officers (10%)	52.1% of all grant targeted districts were supported to conduct investigations and contact tracing. / 3 (10%) regions (Dar, Arusha and Tanga) were supported to deploy heath officers to support contact tracing

Provide supporting narrative for the score
This output responds to public health emergencies including COVID-19 and Ebola Viral Disease (EVD.) With COVID-19 declared a global pandemic, the overall programme had to flex its resources in order to respond to a potential public health crisis. Across the board, all components reallocated resources to cater for the response. On a wider UK response to COVID-19 pandemic in Tanzania, this programme was used as a vehicle to deliver support setting aside funds for short-term six months support. The ability for the programme to adapt and provide a quick response and see those outputs achieved has earnt the output A score.

In response to Ebola Virus Disease Readiness and Preparedness in Tanzania, WHO worked closely with the Ministry of Health to draw preparedness frameworks that would enable the government of Tanzania to respond to outbreaks of highly infectious diseases. Under the support, WHO was able to build capacity of 328 healthcare workers (HCWs) comprising of multi-disciplinary rapid response teams (RRT) and build skills for 340 specialized Ebola virus disease case management and infection prevention and control (IPC) personnel at national and priority districts respectively. Additionally, 852 public and private health workers including 115 port health environmental health officers were trained in Ebola Virus Disease epidemiology and surveillance.

In efforts to rapidly detect and contain the current COVID-19 outbreak, WHO supported the deployment of COVID-19 case investigators and contact tracing teams in affected districts. Working alongside the Ministry of health officials, experts in epidemiology were deployed in various regions to carry out case investigations, surveillance, contact tracing and mentorship supervisions. A total of 97(52.1%) districts versus 53(29%) grant targeted districts were supported to conduct investigations, and 97(52.1%) districts versus 10 (5.5%) grant targeted districts were supported to conduct contact tracing while 3 (10%) regions (Dar, Arusha and Tanga) were supported to deploy heath officers to support contact tracing.

Activities of placing health care workers within facilities is still on going. Through Benjamin Mkapa Foundation, the project was able to recruit and deploy 365 health care workers to different health facilities. These healthcare workers comprise of different cadres and are placed in facilities on needs basis. Although the project funds the placement of these essential health care personnel for a short period of time, there are commitments from the Government of Tanzania Ministry of Health that these health care professionals will be absorbed into the government pay systems. Progress on recruiting 1072 community health care workers has been slow due to extended government working sessions for standardizing recruitment and training of the CHWs across the country. However, the recruitment is underway, and the 1072 community health workers will be deployed by the end of October 2020.

FCDO also provided funding to UNICEF to support COVID-19 interventions aimed at enhancing capacity of the community, health workers, schools and health facilities to gain access to hand washing facilities, prevent and control infections and transmission of COVID-19 as well as increased access to knowledge and awareness creation on COVID-19 through Risk Communication and Community Engagement. During the reporting period, a total of 689 clinical and ancillary staff in high risk regions were trained in on essential WASH IPC behaviours, community and household drinking water treatment options, community-based disease surveillance strategy, solid wastes management and environmental sanitation, and hand hygiene. UNICEF also supported the procurement and distribution of WASH IPC supplies to 25 COVID-19 isolation centres in mainland Tanzania and Zanzibar. All isolation centres received handwashing and hygiene kits as well as waste management equipment and PPEs. The WASH/IPC supplies play a significant role in the reduction of infection and transmission of COVID-19 and protected health workers from contracting the virus.

In addition to provision of IPC/WASH facilities, UNICEF supported the Ministry of Health in developing a rapid assessment tool, which was used to collect and analyse WASH service conditions and identify gaps in the COVID-19 treatment and isolation facilities. Following the assessment findings, repairs and maintenance of WASH infrastructure was done in 25 COVID-19 isolation centres. Even though isolation facilities were officially closed, these centres are continuing to provide basic health care services under the improved conducive condition for both the health staff and those seeking for services.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

Due to the urgency of the response, VfM matrixes were not formulated. However, robust budget analysis was done across all components to ensure investments have a value for money justification. A conscious decision was also made to keep the agreements short term in due to the nature of emergency response, new partners involved and to be able to track progress and Tanzania’s position on COVID-19 response before allocating more resources.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

This is a new outcome indicator. In the next annual review, a lot of the activities under the output would have ended. The outputs will be retained, however, tracking on activities will stop in January 2020 and all recommendation and lessons will be captured in the next Annual Review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Tanzania has taken a different approach toward the COVID-19, testing was stopped late April 2020 and the government announced the country as COVID-19 free. This programme can no longer provide support for the wider long-term COVID-19 response as proposed in the National Response Plan 2. A decision must be made on where future COVID-19 activities will be financed from- beyond Dec 2020.
Programme SRO, Health Team - by January 2021

D: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The overall risk rating is: Major. The most significant risks are summarised below:

Policy Environment: Since the signing of the Business Case, the policy and operating context has changed significantly. Although Tanzania ratified the Global Compact on Refugees, it has placed reservations on enhancing refugee self -reliance objective - employing an encampment policy and limiting livelihood activities and access to markets for refugees. A lack of engagement from the Government has also impacted on support to land titling for naturalised Tanzanian citizens as well as the naturalisation of long-term refugees in Kigoma. The government position is clear, and it is unlikely that progress will be made in these areas. FCDO cut funding previously allocated to support land titling and naturalisation of long-term refugees in Kigoma. Despite the resource reallocation, FCDO will continue to monitor the naturalisation processes of the 1972 caseload and advocate for livelihood activities resumption in the camps.

Forced return: The government of Tanzania has been very vocal on repatriation of Burundi refugees. In 2019, the Governments of Tanzania and Burundi signed a joint declaration committing them to the continued repatriation of Burundian refugees outside of the current voluntary repatriation agreement in the ongoing Tripartite Process. If implemented, the declaration could potentially diminish the prominence placed on the voluntary nature of repatriation and consequently increases the risk of refoulement. FCDO continues to raise the need for the repatriation to remain voluntary in nature with the Governments of Burundi and Tanzania and co-ordinates closely with UNCHR and other donors on this issue. FCDO will continue to monitor the situation in Mozambique where refoulment has been reported.

Asylum seekers’ access to territory: There are reasonable concerns on access to territory as evidence shows that Tanzania’s borders currently remain closed to asylum seekers and the Refugee Status Determination process does not meet international standards. Although borders between Tanzania and Congo, Burundi and Mozambique have remained open for economic activities, asylum seekers from those countries have been refused entry at the Tanzanian borders upon arrival. FCDO will refresh its advocacy lines to continue raising the need for access for asylum seekers.

Resource Constraints: The Burundi Refugees remain to be among the most underfunded refugee populations in the world. With increase in humanitarian crises globally, there is a general sense of prioritising emergency responses and allocation of resources. Insufficient funding of the Burundi refugee response leads to significant decline in living conditions for refugees and could potentially bring about deterioration in the protection space. Food shortages could also be linked to safeguarding, fraud and security risks. Current food scarcity within the camps heightens health related risks and could exacerbate forced repatriation and insecurities. FCDO will continue to play a pivotal role in coordinating development partners efforts towards the response, continue communication with partners to understand gaps and advocate for resources within burden share.

Integrity Issues: The context remains high risk for a range of integrity issues including fraud, corruption and Sexual Exploitation and Abuse. FCDO regularly meets with partners to update on any suspected cases and up to date due diligence reports are maintained for all partners. In 2019, and in collaboration with partners, UNHCR developed the Prevention of Sexual Exploitation and Abuse (PSEA) Interagency Protocol and Work Plan and established an Interagency PSEA Taskforce in Kigoma. The work plan among others include SEA training for Partner staff and refugee incentive workers, encourages SEA reporting by Partners and prompt referral of cases, and ensures awareness raising and sensitization events for persons of concern on SEA. UNHCR protection staff ensure confidential and effective case management of reported incidents of SEA, linking survivors to appropriate services, while monitoring trends to increase accountability and inform preventive interventions. FCDO continues to track all concerns reported and ensures that there is a satisfactory level of response and accountability.

Update on Partnership Principles (delete this section if n/a) [1/2 page]

Principle tracked under this programme relates to commitments and respect of human rights and other international obligations. Tanzania has had a long and proud history of hosting refugees. In the recent years, the Tanzania government agreed to naturalise over 160,000 long term Burundi refugees and continue to provide protection for many hundreds of thousands. Despite the long history, Tanzania’s refugee policy has changed taking a tougher position in refugees management. Hosting more than 280,00 refugees, Tanzania has been clear that it will is employing strict encampment policies and not ratify on enhancing the refugee self -reliance objective of the Global Compact on Refugees. This limits refugee movements, access to markets and hampers livelihood activities.

Pressure on repatriations of refugees already in the country is high. Several high-level government visits to the camps have vastly advocated for repatriation which brings to question the voluntary nature of returns. Equally concerning is the country’s position on asylum seekers. There are reported concerns regarding access to territory for asylum seekers with borders remaining effectively closed with most asylum seekers refused entry on arrival in Tanzania. More recently, similar concerns have been voiced with potential influx of asylum seekers and refugees in the Southern borders following violence in in neighbouring Mozambique.

The change in operating context has significant implications for the protection space, including the risks related to refoulment. The programme has responded by tracking the changes in policy environment, continued advocacy with the relevant government ministries and will continue monitoring over the last 8 months of programme implementation.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency. [max 1 page]

Since the last reporting period, the programme’s scope increased moving from six direct ‘tier 1’ partners to ten (10) direct ‘tier 1’ partners under the programme. This increase in number of components is attributed to the programme flexing and adapting to respond to Ebola Viral Disease preparedness and COVID-19 pandemic outbreak, where four of the ten tier 1 partners respond to EVD or COVID-19 outbreaks. These partners include multilateral partners (UNHCR, IOM, WFP, WHO, and UNICEF) and NGOs (DRC, NRC, IRC and Benjamin Mkapa Foundation).

The overall performance of all partners is satisfactory. With a better part of the implementation period falling during the COVID-19 restrictions on operations, all partners were able to quickly adapt and flex their operations to deliver against set targets. Despite the COVID-19 pandemic and restrictions, activities in the camps were delivered to quality and all partners produced quality and standard reports within set timelines. With further restrictions on travel for FCDO staff, there were no field visits conducted in the reporting period. However, regular review meetings were instituted, giving some level of confidence on delivery.

The quality of financial management differs between partners nonetheless, the general trend of financial management is satisfactory across the board. With COVID-19 pandemic outbreak, adjustments were made on budgets and forecasts to ensure all partners especially NGO’s manage their variances across the year as they operate under COVID-19 restrictions. Due to internal ODA prioritisation exercises, there were delays in spends against the approved budget. NGO’s have robust financial management and reporting mechanisms giving FCDO sight on detailed financial reporting. Low level of details in reporting for multilaterals continues to present a challenge. The programme team continues to track these trends and advise on appropriate levels of details in reporting.

For all new partners, enhanced due diligence assessments were conducted. Equally, due to COVID-19 restrictions, spot check visits for asset control and monitoring were not conducted. The programme management team is planning for a comprehensive field visit in in November and December of 2020 to conduct further assessments of partners and assets. On safeguarding, partners have made positive strides in strengthening controls and implementing new safeguarding policies and procedures. UNHCR developed the prevention of sexual exploitation and abuse (PSEA) Interagency protocol and the SEA Work plan and established an Interagency PSEA Taskforce in Kigoma. The workplan among others include SEA training for partner staff and refugee’s incentive workers, encourages SEA reporting by Partners and prompt referral of cases, and ensures awareness raising and sensitization events for person of concerns.

The Fiduciary Risk assessment for the programme is updated periodically. Chief risks highlighted comprised of large cash management risks, procurement risks, potential fraudulent inclusion of beneficiaries or ghost workers and control of assets. All partners are evaluated to have effective mitigation strategies in place, which are reviewed during the quarterly meetings.

Narrative and financial reporting
	UNHCR	WFP	IOM	DRC – WASH/CAMP	NRC	IRC	WHO	UNICEF	BMF
Date of last narrative financial report(s)	Sep 2020	Sep 2020	Project started in April. 1st Report due in Nov. 2020	June 2020	July 2020	Project started July 2019. Report due Nov. 2020	Interim Report July 2020	Interim Report August / 2020	Interim Report Sept 2020
Date of last audited annual statement(s)	OIOS report - June 2019	Due in October 2020	N/A	WASH and CAMP management activities - September 2020	Report published in February 2019	N/A	N/A	April 2021	N/A
[note] WHO – counted twice, providing both EVD (204805-112) and COVID-19 (204805-115) support

Financial Table – Overall Approved Budget, Spend to date and rate of expenditure

Component	Partner	Agreement type	Overall Budget (Millions)	Spend to date (Millions)	% of expenditure on budget
204805-101	UNHCR	MoU	£ 18.40	£ 13.70	74%
204805-102	WFP	Contribution Arrangement	£ 17.50	£ 16.00	91%
204805-103	IOM	MoU	£ 1.90	£ 1.90	100%
204805-107	DRC	Accountable Grant	£ 6.10	£ 3.80	62%
204805-108	NRC	Accountable Grant	£ 4.00	£ 1.30	33%
204805-111	IRC	Accountable Grant	£ 5.50	£ 2.80	51%
204805-112	WHO	Contribution Arrangement	£ 0.50	£ 0.50	100%
204805-113	Palladium	Call down contract	£ 0.09	£ 0.02	22%
204805-114	UNICEF	Contribution arrangement	£ 1.50	£ 1.50	100%
204805-115	WHO	Contribution Arrangement	£ 0.50	£ 0.50	100%
204805-116	BMF	Accountable Grant	£ 1.62	£ 1.15	71%

Progress on recommendations from previous reviews

Recommendation	Progress
We have seen limited progress following the completion of the verification exercise for long term refugees in Kigoma. Some funds are set aside to support durable solutions for these individuals, but no progress can be made unless a decision is made by the Government of Tanzania on the recommendations following this exercise. The Global Refugee Forum to be held in December 2019 provides an opportunity for the Government of Tanzania to provide clarity on this issue. If no clarity is provided by the end of the year these funds will be cut from the programme and either re-allocated to other activities or returned to the centre. / Humanitarian Advisor, end January 2020	GRF was held. The situation for those long-term refugees seems to remain quite precarious. / Funds were reallocated
Given the ongoing changes in the operating context and the significant changes to the programme as a result, an Information Note should be provided to Ministers setting out how the programme has adapted to the operating context in line with Smart Rules requirements. In parallel the overall Business Case and logframe should be further adjusted to reflect the current operating context. / Humanitarian Advisor end December 2019	An information note was sent to ministers alongside request for funding extension / Logframe was adjusted
Despite the difficult operating environment DFID should continue to support constructive engagement with the Government of Tanzania through appropriate advocacy and dialogue, drawing on local organisations to continue this longer-term process with the Government of Tanzania. Agreements with relevant organisations to support such activities should be finalised by end of October 2019. / Programme Manager, end October 2019	UNHCR has Project Partnership Agreement with Dignity Kwanza Foundation as part of localising the response and amplify advocacy for refugees
A cost extension for the programme should be approved to provide additional flexibility to respond to potential new arrivals from Burundi should there be further violence associated with elections in 2020 as well as expanding the scope of the programme to incorporate EVD preparedness. / Humanitarian Advisor, end October 2019	A cost Extension was approved
Given ongoing uncertainty in Tanzania and in Burundi, DFID Tanzania should work with DFID Rwanda to develop a more regional approach to managing its support to the impact of the ongoing situation in Burundi on neighbouring countries. / Humanitarian Advisor, end March 2020	A regional humanitarian Programme has been considered as the successor for the current programme. The team is in the process of finalising the concept note

Annex 1: Funding overview – Tanzania – UNHCR and WFP operations 2020: Burundian refugees in Tanzania
	UNHCR	WFP**
Total requirement	$ 150.7m	$72m
Funding to date	$ 51.4m	$22.4m
Funding gap	$ 99.3m	$49.6m

Donor overview: (contributions over USD 0.3m)
Donor contributions in 2020	UNHCR	Burden share towards UNHCR (%)	WFP-**	Burden share towards WFP (%)
United States	$ 41.9m	82%	$ 15.9m	71%
United Kingdom	$ 4.1m	8%	$ 1.9m	8%
Ireland	$ 1.6m	3%	$ 0.8m	4%
EU	$ 1.4m	3%	$ 1.1m	5%
Canada	$ 0.72m	1%	$ 0.4m	2%
Finland	$ 0.59m	1%	$ -	0%
Germany	$ -	0%	$ 1.6m	7%
France	$ 0.28	1%	$ -	0%
Republic of Korea	$ -	0%	$ 0.30	1%

**WFP operations / donor contributions as relate directly to Refugee Operations (SO1) in 2020

Annex 2: Funding overview – Burundi HRP 2020 (UN OCHA): Burundian refugees in Rwanda
Total requirement	$197.9 million
Funding to date	$79.8 million
Funding gap	$118.1 million

Donor overview: (contributions over USD 1m)
Donor	Funding (USD/$m)	% of overall funding to the HRP
United States	$42.3m	53.1%
Germany	$11.3m	14.2%
European Commission	$8.7m	10.9%
UN CERF	$6.7m	8.4%
United Kingdom	$2.97m*	3.7%
Ireland	$1.1m	1.38%
France	$1.05m	1.32%

*Approximately $1.5m or 50% went towards refugee repatriation & reintegration activities in Burundi (main partners: UNHCR, FAO, IOM, Concern)