 Programme Completion Review

Title: Programme Evidence Facility (PEF)
Final Programme Spend £ (full life): 2,391,440	Review Date:	December 2020
Programme Code: [AMP ID#] 204793	Start Date: / 8 August 2014	End Date: / 30 October 2020

Summary of Programme Performance

Year	2014-15	2015-16	2016-17	2017-18	2018-19	2019-20
Programme Score	A	A	A+	A+	A+	A+
Residual Risk Exposure Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	http://devtracker.dfid.gov.uk/projects/GB-1-204793/
DevTracker Links to all logframes used during programme lifetime:	http://devtracker.dfid.gov.uk/projects/GB-1-204793/

A. Summary and Overview

Description of the programme and what it has achieved

FCDO Rwanda’s Programme Evidence Facility was a £2.4 million programme that was initially designed for the period from August 2014 to March 2017 with a total budget of £1 million to fund evidence products that fill identified gaps for better policy dialogue and programming. The policy shift from the Government of Rwanda’s (GoR) Economic Development and Poverty Reduction Strategy (EDPRS II, 2012-2016) to the first National Strategy for Transformation (NST1, 2017-2024) involved efforts to drive significant changes in Rwanda’s growth model alongside a step change in the financing instruments for the strategy. This created a large need for evidence and analytical work to inform policy dialogue between GoR and its Development Partners (DPs), as well as to support the design and implementation of relevant bilateral programmes in support of GoR’s growth and poverty reduction agenda. As a result, subsequent programme cost-extensions were made, respectively taking the overall programme’s budget to £2.4 million over 6 years. The purpose of the facility was to improve the effectiveness of programmes and interventions in support of the NST1 by helping the GoR and DPs design and deliver policies and interventions that are evidence-based and offer value for money. The facility focuses on core cross-cutting themes that will underpin Rwanda’s equitable and inclusive growth and broader NST agenda. They types of support provided by PEF include:
- evaluations of interventions;
- data gathering exercises;
- analyses of data;
- expert advice on emerging issues; and
- studies that provide policy options/recommendations to support the EDPRS and NST priorities.

PEF was an internally managed facility for which outputs are delivered through short-term consultancy contracts where payment is made only upon the delivery of the agreed output. Interactions with government and other relevant stakeholders were carried out through existing policy dialogue platforms such as sector working groups (SWG), or the Development Partners’ Coordination Group (DPCG). As the facility enabled FCDO to be responsive to stakeholders’ requests for pieces of work to fill knowledge gaps, interactions also took place between FCDO and the relevant government agency/ministry, both to establish demand for a particular evidence product and to develop the terms of reference once it had approval to proceed. For all proposals, the funding decisions were carefully assessed by the internal PEF management committee based on a number of criteria related to the pertinence and relevance of the proposed study (see Annex 2 for the criteria used). The PEF management committee comprised of team leaders from across the office (governance, social protection and economic growth), as well as the Deputy Head of Office, to ensure good strategic fit with FCDO Rwanda’s overall priorities and existing workstreams. Programme funding mechanisms and respective roles of the PEF management committee and the Steering Committee for the Effective Development Cooperation for Results Project (see below) were designed to ensure that PEF is aligned with GoR’s relevant needs, thus supporting effective delivery of the EDPRS-2 and the NST.

A component of PEF to support the Ministry of Finance and Economic Planning (MINECOFIN)’s Effective Development Cooperation for Results project was approved in June 2016. It took the form of a UNDP/FCDO Contribution Agreement for up to £550,000 by March 2019. Under the contribution agreement, PEF supported MINECOFIN’s action plan to improve evidence analysis, capacity and systems for better resource mobilisation and aid effectiveness in Rwanda. The relevance of prospective studies and evidence products was assessed and approved by the Steering Committee made of Government of Rwanda and DPs supporting the project (UNDP, UK and Switzerland).

The programme has performed well against its two outputs. However, it is important to note that during the final year of the programme (2019-20), following COVID-19 related UK budget cuts, PEF’s uncommited budget was fully cut. As a result, only one study was commissioned and completed in the final year. In total, during the programme’s timeframe (6 years), twenty-six studies and evidence products were commissioned by FCDO and eight others by UNDP under the Effective Cooperation for Results Programme (see Annex 1 for a summary list). All completed studies were discussed in appropriate policy dialogue forums such as Sector Working Groups, Steering Committee Meetings and FCDO bilateral meetings with relevant government agencies.

Major lessons learned, evidence generated and recommendations

PEF has proven to be of important use through the provision of much-needed evidence and analytical works for better stakeholder engagement, policy dialogue and evidence and context-based programming. Products from consultancies undertaken have been reported by both FCDO sector lead advisers and stakeholders (including GoR, DPs and private sector) to be significantly useful in terms of improving their knowledge base and potential to influence policy work and project execution.
The following key positive achievements were made by the Programme Evidence Facility:
PEF was a low-cost facility but with high impact on policy influencing: PEF has been effective in generating evidence at a relatively low unit cost but with valuable influence on government policy and FCDO’s programming and dialogue with GoR. Examples include the update of Rwanda’s privatisation law and strategy to address significant policy shortfalls; the development of the Rwanda Social Secutiy Board (RSSB) 5 year strategic plan, shaping the future of the biggest financial institution in Rwanda; the review of Rwanda’s Aid policy and policy dialogue forums resulting from a study to assess the effectiveness of Sector Working Groups (SWGs); shaping of the new Private Sector Development Strategy and Youth Employment Strategy (PSDYE) through analysis of constraints and facilitation of private sector engagement with GoR; strengthened economic linkages between the agriculture and the hospitality sector through a study on enhancing the local content of Meetings, Incentives, Conferences and Exhibitions (MICE) in Rwanda – policy actions from which have informed the implementation of the Made in Rwanda Strategy and campaign; and a study on blended finance whch is helping GoR to identify and access alternative sources of NST financing beyond traditional development assistance. The cost of these studies, strategies and intiatives has been relatively low, but the expected impact is significant (although measurement of the impact is outside the scope of PEF). An agile, responsive and demand driven facility like PEF therefore represents stong value for money. While a successor programme to PEF was initially discussed, in the end in the spirit of prioritization, it was agreed to harness the lessons learned from PEF and use these to shape the FCDO’s new Policy Engagement Programme (due to commence in 2021). A greater focus on measuring outcome level impact would be beneficial in future programming, for example, more explicitly capturing the changes in government policy resulting from the evidence products.

PEF has proven to be a rapid and flexible entry point for policy influencing and engagement with GoR beyond existing individual programmes. Flexibility to respond to emerging and demand driven needs has provided FCDO with an opportunity to engage with GoR on a number of policy issues that would be hard to achieve otherwise. Examples include a recent review of the privatisation law and strategy which allowed stakeholders to undertake frank and informed discussions on how the process could be improved and proceedings from privatisation of State owned Enterprises maximised; or the support to the National Institute of Statistics Rwanda (NISR) to expand the integrated household living conditions survey (EICV4) sample, including social protection aspects of the national household survey.

Being a demand-driven facility, PEF has strong potential to generate appetite for evidence to support policy changes. One of the key constraints to effective evidence-based policy influencing is the lack of appetite to use the generated evidence and adjust accordingly. PEF responds to demand from GoR to bridge the knowledge gaps for improved policy responses and reforms. Therefore, in most cases, demand for PEF support is underpinned by government’s willingness to improve, hence increasing the responsiveness of GoR to evidence. For example, following a stakeholder validation workshop, the revised privatisation law and strategy has now been approved by the cabinet. In response to the study, which indicated significant gaps in the existing policy dialogue forums following suspension of budget support, GoR has undertaken the revision of the national aid policy and policy dialogue landscape in reflection of new developments in the broader development assistance field.
Key lessons learnt during PEF implementation:

Translating evidence into policy change can be challenging. It is important to recognise that translating evidence generated into ultimate policy change is hard to achieve and requires effective consideration of various factors, including a deep understanding of political and contextual dynamics. This is an area for improvement for any future programming – ensuring regular and dynamic political economy analysis; flexibility to respond to rapidly emerging opportunities (“planned opportunism”; understanding the levers of change and the way change happens in a country context and for an organisation like the FCDO, being able to utilise collectively all available sources of influence.

Follow up on the use of the generated evidence/findings is challenging without a proper action plan. In many instances, producing good evidence products has not been accompanied by a well-structured follow up to ensure the outputs are used to improve policy and programming. As a result, good studies are not necessarily translated into anticipated policy changes. Going forward, a proper action plan to use the findings of any study commissioned should be included as part of the criteria for approving proposals. This is important as evidence isn’t enough-how and when it is used to improve policy and programming matters. Therefore, cross-team, multi-disciplinarywork is be key to ensure that evidence generated is an important input to the process of broader policy influencing.

The evidence-focused scope, while a strength of PEF, has made it challenging to be immediately responsive to demand for supporting relevant events such as horticulture connect, a disability summit, and International Aegis Trust Impact Event. Any future programming should have a sufficiently broad scope to enable it to respond to demand for policy related events and others (beyond just studies) that can contribute to evidence gathering and sharing of experience for policy influencing.

The FCDO’s Economic Growth Team (EGT) has used PEF more than other programme teams: possible reasons include (a) the original focus on pure evidence generation was in higher demand across the economic growth portfolio, (b) some other teams’ programmes had an embedded mechanism to commission studies in their areas (e.g. social protection and education), and (c) varied level of awareness and ownership across teams. Improved communication and cross-team working should be strengthened in the process of generating and implementing evidence products.

How this report was conducted

This PCR was conducted internally based on desk reviews of programme Annual Reviews and evidence products generated. Findings were further confirmed by meetings with Key Informants including FCDO Rwanda’s sector advisers and GoR’s institutions to gather their views on the programme’s usefulness and the extent to which evidence generated has contributed to improving policy and programming. Given the constraints on movement and meetings at the time of writing arising from COVID-19, more extensive consultation with key stakedholders and beneficiaries was unfortunately not possible. This would have added greater richness to the lessons learned on the approach taken and the impact achieved by PEF during its lifetime.

Actions following approval of this report
While PEF is ending, there is still a growing demand for new pieces of evidence products from various stakeholders. Being able to respond to these demands has proven to be extremely useful in building relationships and influencing policy in areas beyond FCDO Rwanda’s portfolio. Therefore, options to incorporate flexible evidence components across FCDO Rwanda’s portfolio would be worth considering.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£ 1,000,000	£ 2,391,440
Timeframe	2014-2017	2014-2020
Outcomes	Number of Programme Evidence Facility products used to inform policy and programme discussions with Government of Rwanda and other development partners	34 evidence products (against a target of 22) were used to inform policy and programme discussions with GoR and other development partners.

Overall assessment of programme outcomes, sustainability and VfM

The PEF’s outcome of informing policy and programming has been achieved: all 34 studies/evidence products completed were used to inform discussions with GoR and Development Partners through a number of fora including sector working groups, FCDO policy meetings, and various bilateral meetings. While the output indicators are unsophisticated (measuring simply the number of products produced and disseminated), the studies and evidence products delivered by PEF are rich and varied. Products from consultancies undertaken have been reported by both FCDO sector lead advisers and stakeholders (including GoR, DPs and private sector) to be highly useful in terms of improving their knowledge base and potential to influence policy work and project execution. Furthermore, beyond discussions, there is evidence that the reports and analysis generated by PEF have concretely shaped a number of policies and strategies in Rwanda. Examples include:

- The new Privatisation Policy and Strategy approved by Cabinet in September 2020 – this was revised following an assessment by PEF which suggested policy recommendations and procedures to improve the process and maximise proceedings from the privatisation of state own enterprises.
- The approval by the RSSB Board of the new 5-year strategic plan (2020-2025), following detailed design work funded by PEF.
- Publication of a new Private Sector Development and Youth Employment Strategy (2018-2023) following analysis of constraints to private sector development and youth employment, and consultations with relevant private sector forums, delivered under PEF.
- Validation of the City of Kigali’s Integrated Development Strategy (2018-2024), which built on detailed design work and consultation funded by PEF.
- Findings from the PEF-funded study on blended finance informed discussions on the options for financing NST beyond traditional development assistance.
- The Meetings, Incentives, Conferences and Events (MICE) study funded by PEF suggested specific policy actions to strengthen economic linkages between the agriculture and the hospitality sector, which relevant public institutions have started implementing through different policies including the Made in Rwanda strategy.
- Evidence gathered under PEF on the production and demand for textile products has triggered policy discussions on measures to promote textile sector in Rwanda.
- Evidence gathered under PEF on the status of disability in Rwanda resulted in critical documentation to inform Rwanda’s inputs to the Global Disability Summit 2018, including a) a summit report that draws together evidence of Rwanda’s progress in advancing the rights of persons with disabilities, and highlights knowledge and implementation gaps, and areas of future commitment for GoR, Civil Socierty Organisations, disabled persons organisations and DPs; and b) an evidence-based Communique of Recommendations from the Rwanda summit that informed GoR’s commitments and engagement at the Global Disability Summit.

PEF has proven to be of important use through provision of much-needed evidence and analysis for better stakeholder engagement, policy dialogue and evidence and context-based programming. Studies and evidence products funded through PEF have mainly been short term products with low unit costs (often under £30,000). As highlighted above and reported by different stakeholders, PEF’s products have contributed to filling the knowledge gap, and influencing policy work and project execution through the generation of the needed evidence. The extent of the influence of a given study or evidence product (despite its size) on policy and programming has been based on a thorough assessment of relevance of the proposed study/evidence product before it is commissioned, and discussions of findings at the appropriate forum once complete. Therefore, PEF has delivered good value for money as low cost evidence products resulted into better policies, strategies and programming.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The starting point of the PEF’s theory of change is that GoR’s development plans (EDPRS II and NST) have set ambitious goals across sectors, yet in many instances there is a lack of evidence to support the development of a roadmap with detailed interventions to support their realisation. This in turn has an impact on the design and execution of GoR and development partner policies and projects. The purpose of this facility is to help address the evidence gaps. It has the potential to influence the design of evidence-based interventions, thus improving the implementation of GoR’s policies and DPs’ projects in support of EDPRII and NST. However, for the evidence products to effectively influence policy and programming a number of conditions have to be met, including: clear plans on how the output of any commissioned work will be used, outputs delivered at the appropriate point in the project cycle so that there is scope to be acted upon, and strong appetite by stakeholders to be receptive to new evidence and act in a way that improves effectiveness since the outputs by themselves will not deliver change. Therefore, learning-by-doing and willingness to adapt/respond to evidence are paramount.

The purpose of the facility is therefore, through demand-driven evidence generation, to improve the effectiveness of programmes and interventions in support of the National Strategy for Transformation (NST) by helping the GoR and development partners to design and deliver policies and interventions that are evidence based and offer value for money. There have been no changes to the Theory of Change during the programme’s timeframe.

## C: Detailed Output Assessment

Output Number and Title	Output 1. Evidence Products
Output Score	A+
Impact weighting (%)	70		Impact weighting revised since last AR?	No

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
Number of activities completed such as evaluations, data gathering exercises to fill knowledge gaps, analysis of existing datasets, and studies that provide policy options and/or recommendations to support economic growth and poverty reduction		18	30	34

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

Output 1 has exceeded expectations over the programme lifetime. Initially, a target of three studies per year ( i.e. 18 studies/evidence products in six years) was set, but revised up to five studies per year( i.e. 30 studies over six years). By October 2020, 34 studies/evidence products in total were completed, twenty-six of which commissioned by FCDO and eight other studies/evidence products commissioned by UNDP under the Effective Cooperation for Results Programme.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

To ensure that consultancies deliver the best possible products that effectively fill the identified knowledge gaps, strategic discussions on the exact need to be filled were held in the PEF management committee meetings, and Terms of Reference were carefully reviewed. For studies procured by UNDP under the contribution agreement, policy relevance of the studies and knowledge gaps to be filled were assessed by the Steering Committee comprised of representatives from MINECOFIN, UNDP, FCDO and Switzerland. These management and procurement arrangements in place have ensured that high quality work is achieved at an optimum cost. All of this has ensured greater value for money out of commissioned studies.

Lessons learned through this output, and recommendations for future programming.

A number of lessons can be drawn in terms of ways of ensuring relevance, usefulness and value for money from evidence products:

- The PEF internal management committee and the UNDP Steering committee have provided stakeholders with a very important platfom to ensure studies commissioned are relevant to the evidence gaps, that there is demonstrated demand for the products, and that they align with strategic objectives (e.g. within the overarching NST).
- This has increased the likelihood of use of evidence for policy design and programming, and ensuring VFM.

Output Number and Title	Output 2. Dissemination activities
Output Score	A+
Impact weighting (%)	30		Impact weighting revised since last AR?	No

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
Number of presentations made on Programme Evidence Facility Products (e.g. at office wide policy meetings, Sector Working Groups, Development Partners' Coordination Group)		18	30	34

Output 2 has exceeded expectations over the programme timeframe. Initially, a target of three presentations of PEF evidence products through relevant platforms was set, but was revised up to five studies per year in the second year. By October 2020, 34 studies/evidence products in total were discussed through different forus including FCDO wide office meetings, Sector Working Groups, Steering Committee Meetings and Development Partners’ Coordination Groups.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

Studies/evidence products were procured comptetively through FCDO and UNDP procurement systems, with strategic oversight from FCDO Rwanda PEF internal management committee and UNDP Steering committee respectively. Studies completed were effectively discussed through relevant forums to ensure findings are used to inform policy design and implemntation, and programming. As discussed above, PEF studies/evidence products have significantly contributed to shaping a number of policies and strategies across GoR’s departments ands sectors.

Lessons learned through this output, and recommendations for future programming.

While there is evidence on the positive contribution of PEF to improving policy and programming, the impact of PEF on policy could been improved by:
1. A proper political economy analysis and advocacy strategy to improve policy usefulness of the evidence.
2. Targeted grants to GoR and other actors to respond/implement the changes proposed from the evidence generated, or at least a clean mechanism/action plan for follow up.
3. Strenthened cross-team work within FCDO throughout the process of identifying and implementing evidence products.

D: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

Overall of programme risk: Moderate

Overview of programme risk and mitigation

Key delivery risks were around delays in spending linked to sometimes long and inefficient contract management, especially for studies with oversight by public institutions. In fact, since the facility was managed by FCDO, procurement of consultants was relatively quick and responsive. But once the contract was signed and a government institution is leading on the execution of the study, the process of interaction with the consultant and other stakeholders (such as providing inputs, feedback and agreement on the findings of the study) was generally long and inefficient. As a result, payment schedules were slow during the early phase of the programme’s implemntation, putting the programme at risk of under spending. Furthermore, as a flexible and demand driven facility by nature, predictability of PEF spend was always a challenge (resulting in FCDO having difficulties in forecasting financial disbursements accurately). It required the SRO to be proactive and robust in generating proposals and ensuring close collaboration with different institutions for a timely completion of the commissioned studies.

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

In terms of output delivery, programme timescales have been regularly disturbed by delays in completion of commissioned studies, particularly those that involved GoR institutions. Despite this, the programme’s expected milestones have been surpassed. Completed studies have been discussed in appropriate forums involving Government of Rwanda and Development Partners. While the programme has done well on the output delivery, challenges have persisted on the commercial and financial performance sides (mainly delays). The programme was also granted multiple cost and non-cost extensions, and the cost extensions enabled PEF to deliver more studies and greater impact.

Throughout PEF implemntation, PEF has exceeded its outputs and delivered its outcome of improving policy and programming at a relatively low cost. VfM was achived against relevant indicators proposed at the time of business case development as follows:
- Daily rates of any externally hired consultants. For all consultancies, FCDO procurement procedures were used under an existing FCDO framework contract to attract highly skilled teams to deliver high quality work. Using a framework agreement ensured that daily rates for the consultants were kept in line with the agreement benchmarks that offer VFM. To further drive costs down where possible, the programme team negotiated down fee rates and costs further.
- A repository capturing the number of days required to deliver a piece of commissioned work alongside daily rates has been established in order to enable even better benchmarking of fee rates/days for comparable kinds of work. The same process of negotiations on fee rates was followed by UNDP’s procurement unit for studies undertaken under the contribution agreement to support the Ministry of Finance. These practices helped ensure PEF’s economy (ensuring we buy the right inputs, of appropriate quality, at the right price).
- In order to ensure that consultancies deliver the best possible products that effectively fill the identified knowledge gaps, constructive strategic discussions on the exact need to be filled were held in the PEF management committee meetings, and Terms of Reference were carefully reviewed. The guidance criteria used by the committee (see Annex 2) ensured that only proposals with strategic relevance, and that had high likelihood to impact policy issues of relevance to Rwanda’s development were taken forward. For studies procured by UNDP under the contribution agreement, policy relevance of the studies and knowledge gap to be filled are assessed by the Steering Committee comprised of representatives from MINECOFIN, UNDP, FCDO and Switzerland. These processes helped ensure PEF’s effectiveness (how well the outputs produced are having the intended effect).
- These management and procurement arrangements in place ensure that high quality work is achieved at an optimum cost. This supports Efficiency of the programme.

Programme-level approach to monitoring and evaluation

The PEF logframe was developed primarily to monitor and measure results of the programme. The performance against annual targets was regularly assessed as part of the PEF Anuual Reviews. Following recommendations from respective Annual Reviews, the log-frame was updated and respective cost and non-cost programme extensiosn were made to respond to emerging needs and increasing demand for evidence products. This Programme Completion Review was mainly based on the programme’s performance against its logframe indicators and lessons learnt from respective Annual Reviews.

Annex 1. Full list of PEF studies and evidence products
	Project
1	Performance and VfM assessment of Rwanda’s public procurement system
2	Analysis of the performance of Sector Working Groups (SWGs)
3	Womens’ Empowerment in Agriculture Index (WEAI)
4	Mapping Development Finance Institutions in Rwanda
5	National Employment Policy review for a potential DFID apprenticeship programme
6	DFID Rwanda programme climate risk screening
7	Land Market sustainability report
8	Gap analysis for the Export Growth Facility (EGF)
9	Fiduciary risk assessment 2016
10	Social and economic impact of the Northern Corridor Initiative
11	Rwanda Land Tenure Reform assessment
12	Evaluation of strategic Capacity Plan Building Initiative (SCBI)
13	Rwanda Social Security Board (RSSB) Strategic plan 2020-2025
14	EICV Poverty Dynamics Research
15	Support to Aegis Trust Peace and reconciliation Research in Rwanda
16	Enhancing the local content of the Meetings, Incentives, Conferences & Exhibitions (MICE) sector
17	Strategic Advisor support at MINALOC
18	Blended Finance Study
19	Support for the development of Kigali City Integrated Development Strategic Plan
20	Horticulture Connect Conference
21	Leather and Textile Sector in Rwanda Study
22	UNDP Effective cooperation for results
23	Unilever Phase II tea investment studies
24	Garment sector profiling and analysis on feasible policy options
25	Volunatry Service Overseas (VSO) Disability Summit
26	Support to UNDP Sector Working Group
27	Rwanda Privatisation Strategy

Annex 2. Guidance criteria used by the PEF management committee to evaluate proposals

	Criteria
1	Will the proposed output support the delivery of Government of Rwanda’s policy and development objectives?
2	Is the proposal in line with FCDO’s priorities for Rwanda?
3	Have local partners/stakeholders been engaged in the identification of knowledge gaps?
4	Is the proposal sufficiently strategic and underpinned by a clear conceptual framework with appropriately defined outputs?
5	Are the proposed outputs likely to result in significant economic, social, or political implications if they result in changes to the status quo?
6	Will the outputs have long lasting policy and evidence implications or will they quickly become obsolete?
7	Is there a plan to disseminate and discuss findings (e.g. validation meetings with stakeholders)?
8	Does FCDO have a comparative advantage in supporting the proposal compared to other possible funders in Rwanda (i.e. is FCDO best placed to fund this piece of research)?