ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Volunteering for Development (V4D)
Country or region targeted	Multiple
Type of cost extension (if applicable)	Bridge funding
Original project budget	£50,007,503
Original project start and end dates	31 March 2017 – 31 March 2020
Cost extension value (if applicable)	£4.5 million
New project end date (if applicable)	31 July 2017
Business Case Quest Document No.	Vault ID 17347569

INFORMATION
What is the project’s purpose?
The Volunteering for Development (V4D) grant supports the delivery of the UK Aid strategy through the use of British and international expertise to improve basic services and livelihoods for vulnerable and extremely poor people, building their resilience to the shocks and stresses that threaten their advancement from poverty. The grant recognises VSO's extensive experience of putting volunteers in the right places to tackle poverty and inequality and forms a key part of the UK’s well-respected international development brand. The accountable grant has been designed to provide targeted support over three years, 2017 – 2020, to enable VSO to galvanise change across the volunteering for development sector. V4D continues to drive stronger volunteer impact and develop Britain’s reputation as a global leader to deliver improved health, education and livelihoods outcomes for over two million of the poorest and most marginalised people across 24 developing countries by: / Enhancing the practices and effectiveness of at least 350 partner organisations and deploying more than 4,000 expert volunteers in 24 developing countries / Mobilising a global volunteer alumni network of more than 5,000 former VSO volunteers and professional bodies to champion volunteering as a tool to help deliver the Sustainable Development Goals (SDGs) and the UK Aid strategy / Developing and driving the widespread adoption of a global set of minimum volunteer standards across the rapidly growing, but still unregulated volunteering sector
What is the objective of the cost extension or other changes?
The second phase of the Volunteering for Development (V4D) programme is due to commence in the coming months. The business case is currently being finalised including amendments to take account of and respond to new government priorities, particularly girls’ education. The delays to the business case finalisation and sign off will mean there is a funding gap between the end of the V4D1 grant (ends 31 March) and the start of the V4D2 grant (projected to start between June and September). VSO and DFID have been having close conversations about the transition, however there has been a misunderstanding about what a “funding gap” entails which came to light on Friday 13 March. VSO had interpreted the funding gap to mean that funds spent during the gap would be reimbursed in the first payment under V4D2 (as was the case at the start of the V4D1 grant following the shift from strategic core funding to an accountable grant) however DFID is not in a position to reimburse any work done outside of a funding agreement and was using the term “gap” to mean no funding from DFID at all during this period. To protect continuity and momentum between programmes and maximise the VfM of both the first and second phase of the grants (e.g. not losing the momentum built up on workstreams such as the Global Standard for Volunteering for Development) it is in our interest to provide a reduced sum to VSO as part of a bridging extension. This amendment sets out to do this.
What is the additional and total support the UK will provide?
With this £4.5 million cost extension to Phase 1, the UK’s total budget support to VSO for the Volunteering for Development (V4D) programme from 2017 to 2020 will increase from £50 million to £54.5 million. Funds in the Business Case for Phase 2 for the Quarter April – June 2020 will be transferred to the current programme, phase 1, to cover this bridging for the period April - July. The funds for V4D2 remain unapproved until the business case is formally signed off and funds agreed by Management Accounts Group.
What are the expected results?
This additional £4.5 million over the period April – July will: / avoid loss of learning/momentum between the two phases / maintain key staff and operations to be operationally ready and well prepared to deliver on the V4D2 grant outcomes from day one of the new grant. / protect relationships between DFID and VSO as a key strategic partner / establish best VfM by providing a reduced sum rather than funds that match the full V4D1/V4D2 quarterly costs (£5m - £6m) / support core activities including those which will add value to the covid-19 response both directly and indirectly; / maintain key staff and operations to be operationally ready and well prepared to deliver on the V4D2 grant outcomes from day one of the new grant.
What is the approach to implementation?
The cost extension will enable V4D to continue to deliver against its three outputs: / A global programme focusing on social inclusion, social accountability and resilience that: Extends the reach of services to the poorest and most marginalised by providing a bridge between communities and service provision; Strengthens accountability by facilitating local ownership of development processes and building citizen-led accountability / Global partnerships and social accountability actions brokered by VSO to strengthen quality of services for the poorest / Global uptake of standards for responsible and impactful volunteering towards the achievement of the SDGs / V4D follows a community-led development approach that empowers the poorest to be involved in decisions and hold development actors and governments to account. / Gender Equality / This cost amendment will continue to directly contribute to reducing gender inequality by addressing existing educational, health and livelihoods inequalities. This additional funding contributes to ensuring all VSO programmes are underpinned by a rigorous social exclusion and gender analysis based on data disaggregated by socio-economic status, sex, disability. DFID will continue to monitor VSO’s delivery on gender equality through the management of the programme and data will be disaggregated in the log frame. VSOs ‘People First’ framework establishes an expectation among all VSO staff that gender matters and should be taken into account in all policies, practices and procedures - in programming and evaluation, finance and procurement, funding and business development, corporate services, human resources and volunteer recruitment and management. In addition to this, a DFID Social Development Advisor will support the annual review of the programme to assess progress during implementation. VSO will also ensure that new research evidence generated by the programme on what works to improve gender equality is shared with the V4D sector and DFID to shape other programmes.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The original approach and theory of change are still in use, however an additional Volunteering Model Framework has been introduced to support the understanding of how change happens which will form the basis of the ToC for the next phase of the programme. In the meantime this framework has been used to support the current ToC. / Since the original business case, VSO have greatly refined the range of monitoring and reporting tools and methodologies for tracking the indicators in the V4D log frame.. VSO have also revised measurement methods on scale and reach, volunteer survey, partner capacity assessments, particularly during the last year bringing in learning and feedback from countries and practitioner to inform and strengthen the tools and processes developed and applied. / VSO’s programmes continue to pilot and develop the MILE (Measuring Impact for Learning and Empowerment) methodology as an inclusive, beneficiary-focused and participatory M&E process. MILE orientation and training have been completed in Bangladesh, Nepal and Malawi in addition to Uganda in year 1, these pilots have facilitated and strengthened engagements with beneficiaries and project stakeholders in VSO programmes’ M&E plans. The beneficiaries and stakeholders will continue to have an active participation in actual monitoring, evaluation, and learning exercises in VSO’s programmes. / 2019 saw the completion of the independent Mid Term Evaluation. The mid-term evaluation (MTE) set out to: / Provide accountability to DFID on its investment in accordance with the V4D grant agreement. / Generate learning for VSO to adapt and improve its work and strengthen the evidence base for volunteering for development and potentially inform any second phase of the V4D grant. / Strengthen monitoring and evaluation capabilities for learning and programme improvement / The Volunteering for Development Grant Mid-Term Evaluation has been completed and VSO have submitted the final evaluation report to DFID for review. The evaluation, which was informed by the Theory of Change for the V4D Grant, assessed progress in the delivery of the grant, emerging outcomes and patterns for sustainability. The MTE was completed successfully, although there were minor delays due to external context. The review found that integration of the core approaches has enabled VSO to work in a more systemic way, particularly in its programming and support to partners and beneficiaries.