Annual Review
1 April 2018 – 31 March 2019

Title: / Humanitarian Access in the Occupied Palestinian Territories (OPTs)
Programme Value £ (full life): £27,800,000		Review Date: 30 July 2019
Programme Code: / 300001	Start Date: 3 June 2016	End Date: 31 March 2019

Summary of Programme Performance
Year	2016/2017	2017/2018	2018/2019
Programme Score	A	A
Risk Rating	Moderate	Major	Major

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300001/documents
DevTracker Link to Log frame:	N/A

A. Summary and Overview

Context

Although prolonged armed conflict in Gaza was limited in 2018, there was a sharp deterioration in the humanitarian, human rights, security and political situation; and an enormous rise in Palestinian casualties, as a result of the “Great March of Return” demonstrations. According to the UN, between 30 March 2018 and 31 March 2019 a total of 277 people (including 52 children) were killed by Israeli forces. Over 31,000 Palestinians were injured (including 6,846 wounded by live ammunition). Some participants in the demonstrations launched incendiary and explosive devices and breached the perimeter fence into Israel, however the UN still raised concerns about excessive use of force by the Israelis. This was because of the large number of casualties among unarmed participants, who posed no imminent threat of life or deadly injury to Israeli soldiers.

The enormous rise in casualties is overwhelming Gaza’s health sector, which has already been impacted by the longstanding restrictions on the movement of people and goods, the deepening intra-Palestinian political divide, an energy crisis, inconsistent payment of medical personnel, and shortages in medicines and disposables. Approximately 8,000 elective surgeries were postponed due to the massive influx of trauma casualties, a lack of bed capacity and limitations due to electricity shortages, with patients discharged early every week to make room for the next wave of casualties. Patients referred outside for medical treatment unavailable in Gaza, especially those injured in the demonstrations, continue to face major access constraints on exiting through the Israeli-controlled Erez crossing.

For much of 2018, power cuts of 18-20 hours a day impeded the delivery of basic services and crippled productive activity, with hospitals, water and sewage treatment facilities, and solid waste collection services almost completely reliant on UN-coordinated emergency fuel to maintain essential services. In October, the delivery of fuel funded by Qatar provided temporary improvement in the electricity supply. The coastal aquifer, Gaza’s sole water source, has been virtually depleted by over-extraction and the intrusion of seawater, forcing the impoverished population to buy trucked water, often of poor quality, at up to 20 times the expense of water from the network.

Gaza’s economy is in ‘free fall’ according to the World Bank, with unemployment reaching 54% in the second quarter of 2018 and over 70% of young people and 78% of women unemployed. Poverty has risen to 53% and food insecurity to 68%. Severely reduced purchasing power was compounded by the Palestinian Authority’s (PA) policy of withholding the payment of salaries and allowances to employees, alongside a cut in reconstruction and development aid - particularly by the US government. According to OCHA’s Financial Tracking System (which only captures funding against the Humanitarian Response Plan), the US provided $3m in 2018 compared to $112m in 2017 and $115m in 2016.

In 2018, Palestinian refugees in Gaza continued to face the socioeconomic and humanitarian consequences. These factors together have resulted in an increased number of Palestinian refugees who require UNRWA assistance.

In the West Bank, including East Jerusalem, Israel’s direct military occupation continues, severely restricting Palestinians’ access to land and resources. While the humanitarian situation is less grave than in Gaza, the economy “is expected to slow considerably in the coming period,” according to the World Bank. Standards of living, economic growth and employment prospects continue to be undermined by limitations on access to land. Freedom of movement is also significantly restricted by a multi-layered system of administrative, bureaucratic and physical constraints, with the GoI citing security concerns as their reasoning for such measures. The demolition of residential, livelihood and service infrastructure has continued in the West Bank, including in East Jerusalem.

During 2018, humanitarian organisations faced a range of obstacles on the movement and access of affected people, humanitarian personnel and humanitarian goods as a result of political, security and administrative measures implemented by Israeli and Palestinian authorities. Access restrictions hampered the delivery of materials needed for the implementation of humanitarian projects, including projects that involved building, expanding or rehabilitating infrastructure in Gaza and in Area C of the West Bank, and responding to demolitions of housing or essential infrastructure.

Description of Programme

The Humanitarian Access programme in the Occupied Palestinian Territories OPTs has two components:

Ongoing support for humanitarian access and Gaza reconstruction through funding to United Nations Access Coordination Unit (UN ACU) and the Gaza Reconstruction Mechanism/Materials Monitoring Unit (GRM/MMU).

The ACU provides operational support to humanitarian agencies to help resolve access and permit issues for personnel and goods, thereby increasing their effectiveness and reducing the time and money agencies spend working to resolve access issues. The ACU also provides comprehensive data and analysis on access trends to support the international community’s advocacy on increased humanitarian access.

The GRM is a temporary agreement between the Palestinian Authority (PA) and the Government of Israel (GoI) brokered by the UN in September 2014. The GRM aims at allowing the entry of large amounts of some ‘dual use’ materials into Gaza for the purposes of reconstruction following the conflict in 2014. The GRM established the MMU which oversees the supply chain of materials to ensure they are used for their intended civilian purposes.

A scalable humanitarian response, as part of preparedness and contingency planning, delivered through pre-selected partners to allow for speedy response in a case of spikes in humanitarian need. These partners have been chosen based on the following criteria: delivery mechanisms, evidence of success, capability to absorb a significant level of funding; strong Multilateral Aid Review (MAR) assessment; strength of evidence on impact; and proven experience in delivering results. The scalable humanitarian response includes the following:

Support to United Nations International Children’s Emergency Fund to respond to humanitarian needs by improving access of the most vulnerable communities in Gaza to water supply and adequate sanitation services.

- Funding allocated to the 2018 International Committee of the Red Cross (ICRC) Appeal in Israel and Occupied Territories (ILOT), to support its emergency/ humanitarian relief operation.
- Support to United Nations Relief and Works Agency (UNRWA’s) delivery of emergency food assistance in Gaza, in response to increased food security.

This annual review covers DFID funding to the ACU, GRM/MMU, UNICEF, the ICRC and UNRWA’s OPTs Emergency Appeal.

Summary supporting narrative for the overall score in this review

The overall score of this review is A indicating that the programme has achieved expected results for 2018. Where indicators have missed milestones, this is largely driven by external factors such as the tightening of access restrictions, a general decline in the economic activity in Gaza, and a change in the humanitarian context.

DFID funding to the ACU and MMU has facilitated humanitarian access and enabled the entry and use of materials on the GoI’s ‘dual use’ list to help ensure they are used for civilian purposes. Without an agreed monitoring mechanism, construction materials necessary for the reconstruction of Gaza will not be granted entry into Gaza.

The MMU has successfully completed all its monitoring requirements for the entirety of the reporting period. The MMU has enabled 175,666 beneficiaries to purchase reconstruction materials.

Activation of the contingency component has allowed the UK to promptly respond to both the spike in humanitarian needs and the energy crisis in Gaza. This led to increased food insecurity and an increased strain on the health system and hospitals in Gaza which were under immense pressure to cope with the increased number of casualties who needed medical and surgical care. In response to the spike in humanitarian needs in Gaza in 2018, the comprehensive humanitarian response enabled:

- UNICEF to support 572,248 people in Gaza by improving the quality of their water supply and providing 101,000 people with piped water and improved sanitation.
- The ICRC to provide life-saving care at 10 hospitals in Gaza –including medical supplies and equipment, and training for medical personnel to ease the strain. The ICRC also provided physical rehabilitation services for 3,344 people with disabilities.
- UNRWA to provide emergency food assistance to 933,979 beneficiaries including 18,116 female-headed households; and thus meeting 80% of caloric needs for the abject poor and 43% of caloric needs for the absolute poor through food distributions.

Recommendations for the year ahead

- The ACU 2018 survey concluded that 24% of respondents reported that the support provided by ACU was ‘very good’, while 29% stated that the support was ‘good’. It is recommended to look into the reasons behind the relatively low satisfaction rate.
- In February 2018, the PA and the GoI agreed to perform a ‘joint review’ of the GRM in order to improve its functionality, transparency and predictability. The review resulted in agreement to expand the remit of the MMU beyond monitoring to take on a more active role in management and facilitation of projects in Gaza. It has been renamed the Project Management Unit (PMU). It is recommended to continue funding the PMU (former MMU) for the next two financial years (2019 and 2020), and revisit output milestones in line with conclusions from the ‘joint review’.
- UNICEF is planning to conduct an in-depth VFM analysis for the WASH activities in Gaza. This is to assess whether programme results considered good investments and provide evidence on whether the programme made the most value out of the available funds while ensuring the best possible outcome. We have reported on cost effectiveness to demonstrate optimising the use of resources (in Section D Value for Money), but since it was not possible to identify appropriate comparators, it is recommended to use the in-depth analysis in order to identify VFM milestones and feed into next year’s review.
- DFID has contributed to the 2018 ICRC Appeal in Israel and Occupied Territories ILOT. For 2018, the ICRC’s implementation rate (expenditure/yearly budget) was 94%, due to the need for ICRC to respond to needs on the ground and have flexibility to respond to any unforeseen changes. It is recommended to review ICRC’s Mid-term Report, which is usually published by end of June each year, in order to check whether there is a need to amend the milestones in line with any contextual changes.
- It is recommended to support UNRWA’s prioritisation of the provision of in-kind food assistance in Gaza under its 2019 Emergency Appeal.
- It is recommended to review the logframe to ensure milestones and targets reflect the deteriorating context and ensure the indicators better capture quality of the activities.

## B: DETAILED OUTPUT SCORING

Output Title	Technical access co-ordination provided for humanitarian actors.
Output number per LF		1	Output Score	B
Impact weighting (%):		15%	Impact weighting % revised since last AR?	Yes ↓

Indicator(s)	Milestone(s) for this review	Progress
1.1 Percentage of humanitarian access incidents resolved by Access Coordination Unit (ACU).	71%	65% (184 out of 281 incidents)
1.2 Levels of 'satisfaction' expressed by beneficiaries using the ACU's 24/7 access hotline.	63% "very satisfied" / 20% "satisfied"	28% “Very satisfied” / 35% “Satisfied”
1.3 Number of cases where information on access provided by ACU is included in high level reports (e.g. Ad Hoc Liaison Committee reports, Security Council briefings.)	64	48

Provide supporting narrative for the score

The programme did not meet expectations for this output and has therefore been marked a ‘B’. Reasons for not meeting expectations were mainly due to external factors; the introduction of new security measures and tightening restrictions on movement and access. Measures by the Israeli authorities included a rise in denials and one-year bans on permits, and searches and restrictions on the type of items allowed to be taken out of Gaza.

Output Indicator 1.1
The ACU provides support to UN, International and National non-governmental organisations’ personnel during access incidents at crossings and checkpoints. The work of the ACU includes direct intervention and follow-up on cases of delays of Israeli-issued permits, liaison with relevant government or military counterparts, as well as local authorities, and provision of access briefs. During the reporting period 65% of access incidents reported resulted in successful ACU intervention; 6 percentage points below the target. A successful ACU intervention is defined for this purpose as any intervention that did not result in denial of entry and confiscation of UN property. Unresolved incidents are due to the increase in access difficulties experienced by humanitarian personnel as a result of the introduction of new access restrictions by the Israeli authorities; and additional access restrictions imposed by the Gaza de facto authorities. During the reporting period, the type and level of access restrictions, outside the control of the ACU, have contributed to a harder operating environment and hence the underachievement of the milestone.
Output Indicator 1.2
During the ACU survey to beneficiaries conducted in August 2018, 24% of respondents reported that the support was ‘very good’, while 29% stated that the support was ‘good’. With regards to Advice and Information provided by the ACU, 28% of respondents reported that they were ‘very satisfied’, 35% were ‘satisfied’ and 20% found the support to be ‘acceptable’. This indicator did not meet the milestone, however 74% of the survey respondents reported that their organisation was able to save on time and/or operational cost due to the ACU support and 76% of the respondents reported that the ACU had been effective in improving the access or personnel and/or goods.

Output Indicator 1.3
The ACU provided input for 48 high level reports including Security Council Briefings, Ad-Hoc Liaison Committee and UN Special Coordinator for the Middle East Peace Process UNSCO Socio Economic reports. Access issues and incidents affecting humanitarian space were regularly brought to the attention of the UN Resident Coordinator and the Humanitarian Coordinator either through monthly reports and/or verbally at meetings with recommendations for action. DFID assesses these products to be of high quality and they have been used regularly by DFID and other stakeholders. The output indicator did not meet the milestone due to changes to OCHA reports, as some reports are being published on biweekly basis.

Lessons identified this year, and recommendations for the year ahead linked to this output

Despite the underachievement of indicator milestones, the ACU has been instrumental in facilitating needs assessments and coordinating responses to access issues.

It is therefore recommended to revisit indicators, milestones and targets to ensure they fully capture the success of the ACU’s work and to reflect the changing and deteriorating access and movement situation. It is also recommended to explore why a fifth of the ACU survey responders felt ACU’s support was poor or very poor, and whether this may be a reflection of the deteriorating access situation, especially when ACU was not successful in resolving the responders’ issues.

Output Title	Materials Monitoring Unit (MMU) enables beneficiaries to access 'dual use' materials necessary for reconstruction of Gaza.
Output number per LF		2	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	Yes ↓

Indicator(s)	Milestone(s) for this review	Progress
2.1 Total number of beneficiaries enabled to purchase 'dual use' materials to reconstruct homes.	175,000 beneficiaries / (Cumulative indicator for three years)	175,666 beneficiaries
2.2 Number of large-scale projects under the Gaza Reconstruction Mechanism (GRM) receiving 'dual use' materials for construction.	600 active projects in the year.	232 projects
2.3 Number of vendors approved and able to import and sell 'dual use' materials for reconstruction of Gaza.	400 active vendors in the year.	588 vendors

Briefly describe the output and provide supporting narrative for the score

Two out of the three output indicators have moderately exceeded expectations, whereas output indicator 2.2 substantially failed to meet the expectation. The main driver behind this underperformance is due to a lack of donor funding for projects and the general decline of economic activity in Gaza, linked to the ongoing movement and access restrictions imposed by the Israeli Government.

Output Indicator 2.1
The GRM-MMU has four streams through which applications can be made: Shelter, Residential, Finishing and Projects. Beneficiaries with approved applications can visit any GRM vendor and purchase an amount of construction material up to their approved allocation. The MMU then conducts monitoring and works surveys for 10% of active shelter/residential/finishing projects as agreed by parties of the GRM agreement. MMU has slightly overachieved the 2018 target cumulative target, meaning that MMU has enabled a total of 175,666 beneficiaries to purchase construction materials.

Output Indicator 2.2
The Project stream enables access to materials for large scale construction and infrastructure projects. Through its monitoring role, the MMU continues to enable the implementation of an increasing number of vital construction and infrastructure projects within Gaza. Large scale projects are visited by MMU monitors at least once every three months per active project stage. This target (of at least 400 projects receiving ‘dual use’ materials as a result of monitoring conducted by MMU) was not met during the reporting period. A total of 232 projects received ‘dual use’ materials for construction, and thus underachieving the milestone by 61.3% due to external factors. The lower level of activity in the project stream is mainly due to the ongoing difficulties for project implementers, especially in the private sector, to obtain funding. In addition, a general decline in economic activity in Gaza also contributed to lower project activity during the 2018 as the economy in Gaza was described by the World Bank as in ‘free fall’, with a 7% contraction.

Output Indicator 2.3
As facilitated by the MMU 588 GRM registered vendors including contractors, batching plants, and block makers were able to import cement during the reporting period. The total number of vendors active in the GRM was above the target of 400, due to the increased number of vendors approved under the GRM scheme.

Lessons identified this year, and recommendations for the year ahead linked to this output

In February 2018, the PA and the GoI agreed to perform a ‘joint review’ of the GRM in order to improve its functionality, transparency and predictability. It is expected that this review will lead to functional improvements to MMU’s operations. The review resulted in agreement to expand the remit of the MMU beyond monitoring to take on a more active role in management and facilitation of projects in Gaza. It has been renamed the Project Management Unit (PMU). It is recommended to continue funding the PMU (former MMU) for the next two financial years (2019 and 2020), and to revisit output and value for money milestones in light of the joint review and deteriorating context.

Output Title	The most vulnerable communities in Gaza are accessing WASH facilities.
Output number per LF		3	Output Score	A
Impact weighting (%):		25%	Impact weighting % revised since last AR?	Yes ↓

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of people with improved access to domestic and drinking water through: chlorination of water, distribution networks, water wells and desalination plants.	600,000 people	572,248 people / (50% children)
3.2 Number of households/individuals with rehabilitated sanitation facilities and connected to water and wastewater network.	15,000 households (90,000 beneficiaries) connected to water and wastewater networks.	16,860 households / (101,160)
3.3 Number of households provided with water tanks.	1,300 households	1,400 households
3.4 Number of public awareness and hygiene training courses.	N/A / Result will be reported against in the coming review.	On track according to interim reports.

Provide supporting narrative for the score

Two out of the three output indicators have moderately exceeded expectations, whereas output indicator 3.1 moderately did not meet the expectation. The main driver behind this slight overachievement is the efficient management of project deliverables, whereas, the slight underachievement of indicator 1.1 is due to an overestimation in the number of beneficiaries with improved access to drinking and domestic water. DFID contracted independent third-party monitors who were on the ground in Gaza complementing DFID’s existing monitoring and oversight. Post implementation monitoring revealed that the figure is lower.

Output Indicator 3.1
This activity aimed to supply and distribute sodium hydrochloride, chlorinators and associated spare parts, and chemicals to distribution networks, water wells and desalination plants in Gaza. 251 cubic meters of hypochlorite was delivered and used for water disinfection. Thus, access to domestic water has been improved for 572,248 people (50% children) in Gaza through the ongoing chlorination of 140 water wells (instead of the planned 70 wells) and 20 desalination plants. In addition, all chlorinators required for the operation of water wells have been supplied. All activities were delivered as planned, but this output indicator did not quite achieve the milestone due to an overestimation of the number of people directly benefiting from the activity.

According to the Independent monitors, chlorination systems were operated in a satisfactory manner given the intermittent electricity supply. For quality assurance random samples were taken from the supplied hypochlorite solution and chemicals for chemical testing. Results provided evidence of compliance with the standardised specifications.

Output Indicator 3.2
Overuse of old water/wastewater infrastructure results in network leakages and negatively impacts the system’s efficiency. To improve access to piped water and sanitation systems, rehabilitation of this infrastructure is the most cost-effective way to sustainably address the immediate and long-term WASH needs of vulnerable households. Access to piped water and sanitation for 16,860 households (moderately exceeding the target of 15,000) was improved through the completion of rehabilitation and upgrading of 11,330 meters of water networks and installation of 480 water connections. In addition, UNICEF installed 4,244 meters of wastewater networks and 467 sewage connections in different localities Gaza.

According to the independent monitors, the activities planned under this output were successfully delivered through a local contractor. Independent monitoring verified the successful implementation of this output indicator. It confirmed that 16,860 households in various communities have improved access to better quantities of drinking water and better sanitation services. The activities have been implemented according to Palestinian and international standards as specified in the tender documents. All beneficiaries interviewed were satisfied with the general project implementation and the contractor’s attitude.

Output Indicator 3.3
UNICEF supplied and installed 1,400 water storage tanks of 1,000 litre capacity to 1,400 households benefitting around 12,485 people (moderately exceeding the milestone by targeting additional 100 households). This allowed families to increase their resilience through water storage and a buffer for household consumption at times of intermittent power supply. This activity has contributed to improving the safety and quality of water storage for the most vulnerable households in Gaza.

Independent monitors verified the successful implementation of output indicator 3.3. Feedback from families who received the water tanks was very positive, since the installation of water tanks solved a severe water storage capacity issue which affected their households.

Lessons identified this year, and recommendations for the year ahead linked to this output

It is recommended to consider including an indicator on sustainability and quality of the WASH facilities.

Output Title	The most vulnerable communities in Gaza have access to adequate treatment, including physical rehabilitation services.
Output number per LF		4	Output Score	B
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N/A / New Output

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of hospitals in Gaza supported with medical equipment and supplies.	11 hospitals	10 hospitals
4.2 Number of persons with disability in Gaza supported with physical rehabilitation and livelihood support.	4,000 persons with disabilities	3,344 persons with disability (405 women and 1,439 children)

Provide supporting narrative for the score

The two output indicators slightly underperformed in comparison with the set milestones for the reporting period.

Output Indicator 4.1
To ease the strain on the healthcare system, the ICRC provided life-saving care at numerous hospitals – particularly the largest hospitals in Gaza, as these had the largest influx of patients. The ICRC provided medical supplies, equipment, and training for medical personnel to 10 hospitals. ICRC surgeons worked alongside staff to help them handle the rise in protest-related casualties. ICRC training helped doctors and nurses expand their abilities in managing trauma and to enhance their capabilities in vascular surgery, diabetic care and mass-casualty management. In August 2018, the ICRC set up a surgical ward at the Shifa hospital, which was run by an ICRC medical team, and renovated the electrical infrastructure at this hospital.

Output Indicator 4.2
The ICRC-supported the Artificial Limb and Polio Centre ALPC which provided physical rehabilitation services (including the provision of prostheses and orthoses) for a total of 3,344 people with disabilities (including 405 women and 1,439 children). Moreover, ICRC provided training to help physiotherapists expand their skills, and develop their ability to deal with large numbers of patients. This output indicator did not meet the milestone.

Lessons identified this year, and recommendations for the year ahead linked to this output

DFID has contributed to the 2018 ICRC Appeal in Israel and Occupied Territories ILOT, which includes a range of protection and assistance activities and is also funded by other donors. For 2018, the ICRC’s implementation rate (expenditure/yearly budget) was 94% (Implementation rate = expenditure based on total year end/budget * 100). The reason for this is that ICRC responds to needs on the ground and have flexibility to respond to any unforeseen changes in the context. It is recommended to review ICRC’s Mid-term Report which is usually published by end of June each year in order to check whether there is a need to amend the milestones to align with any contextual changes.

Output Title	Food requirements of food-insecure refugees met.
Output number per LF		5	Output Score	A
Impact weighting (%):		40%	Impact weighting % revised since last AR?	N/A / New Output

Indicator(s)	Milestone(s) for this review	Progress
5.1 Percentage of caloric needs for the abject poor met through food distributions.	80%	80%
5.2 Percentage of caloric needs for the absolute poor met through food distributions.	43%	43%

Provide supporting narrative for the score

The two output indicators have met expectation; in 2018, UNRWA provided emergency food assistance to 933,979 beneficiaries (184,993 families), including 18,116 female-headed households. Households received food baskets containing flour, rice, sugar, sunflower oil, whole milk, chickpeas, lentils and canned sardines. UNRWA was able to overachieve its target of meeting the food requirements of 924,310 food-insecure refugees.

Output 5.1
The target for this output has been met; 584,574 refugees (111,439 families, including 12,597 female-headed households), living below the abject-poverty line of US$ 1.74 (£1.43) per person per day received food parcels covering 80% of their required daily caloric needs.

Output 5.2
349,405 refugees (73,554 families), including 5,519 female-headed households, living below the absolute poverty line of US$ 3.87 (£3.81) per person per day received 43% of their daily caloric requirements, and therefore meeting the target.

In order to determine a family’s poverty status, an UNRWA social worker visits the family and undertakes an objective assessment of their situation, using the Poverty Survey. Following the visit, the family is classified as abject poor, absolute poor or non‐poor. Those who are abject poor do not have the means to meet even their most basic food needs. Those who are absolute poor are able to meet their most basic food needs, but unable to meet other essential needs, such as clothing and transportation. Those who are non‐poor have been found to be able to meet their essential food and non‐food needs.

Lessons identified this year, and recommendations for the year ahead linked to this output

It is recommended to support UNRWA’s prioritisation of the provision of in-kind food assistance in Gaza under its 2019 Emergency Appeal. It is also recommended to consider different indicators that better capture targeting and quality of food distributions.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

The theory of change is based on the assumption that funding the ACU and MMU will ensure that humanitarian actors are able to access and assist vulnerable Palestinians across the OPTs. This will help ensure that during spikes in humanitarian need, partners are able to deliver assistance at scale and in a timely manner. Summary of the theory of change as in business case:

- Movement and access restrictions are the major factor limiting effective humanitarian assistance and economic development across the OPTs.
- Specific restrictions on the import of construction materials into Gaza have proven an impediment to the reconstruction and recovery effort.
- Without a political solution, there is a likelihood of spikes in humanitarian need being caused by outbreaks in violence. Palestinians are vulnerable to protection concerns caused by disrespect for International Humanitarian Law.
- The OPTs is also at risk of a large-scale earthquake, which could disproportionately affect vulnerable / overcrowded areas with poor infrastructure such as Gaza and refugee camps.
- The ACU helps facilitate humanitarian access, while the MMU has enabled reconstruction materials and ‘dual use’ items to enter Gaza faster, at higher scale and more cost effectively than before.
- Pre-positioned partners provide immediate and effective humanitarian assistance during emergencies. e.g. WASH kits, psychosocial support, nutrition, emergency medicines and health care.
- Scalable emergency response in place to respond to humanitarian needs with agreed partners.

In the OPTs there has been a protracted crisis with a recurrent cycle of shocks reflected by three major escalations of hostilities in less than ten years. Within the business case and the theory of change we have therefore built a contingency component in order to respond flexibly to spikes in humanitarian need and enable us to respond to rapid-onset emergencies – such as a further escalation of violence in Gaza or a major earthquake. The contingency component also includes the flexibility to conduct third party monitoring and/or evaluation to help manage our humanitarian response effectively.

This has allowed the UK to promptly respond to the spike in humanitarian needs and respond to the energy crisis in Gaza. Increased food insecurity and the increased strain on the health system meant that hospitals in Gaza were under immense pressure to cope with the increased number of casualties who needed medical and surgical care. In response to the spike in humanitarian needs in Gaza, the contingency component was activated to enable a comprehensive humanitarian response through providing urgent support to three pre-positioned partners: UNICEF, the ICRC and UNRWA’s Emergency Appeal.

A change in context (a spike in humanitarian needs as a result of the electricity crisis and the ‘Great March of Return’) has put the theory of change to the test and our planning scenario was held true; thus enabling DFID and the three pre-positioned partners to meet humanitarian needs through providing immediate and effective assistance to the most vulnerable individuals in Gaza.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and what action is planned as a result in the year ahead

The project impact is: UK aid saves lives during emergencies in the OPTs and helps rebuild Gaza.

Impact Indicator 1: Percentage of people displaced by 2014 Gaza conflict provided with permanent shelter solutions. As of March 2019, 12,200 individuals (out of 100,000 Internally Displaced Persons IDPs) remain internally displaced since the 2014 Gaza conflict, and thus 87.8% of people displaced were provided with permanent shelter solutions (12.2 percentage points towards achieving the target by March 20121). Good progress has been made so far as it is expected that by March 2021, 100% or all internally displaced people from 2014 will be provided with permanent shelter solutions.

Impact Indicator 2: Food insecurity rate in the OPTs (45% of the overall donor humanitarian response in 2015, when this project was designed, was spent on food aid, so the food insecurity rate provides a proxy indicator for the overarching humanitarian response). In 2015, the baseline for food insecurity rate in the OPTs was 27%, in 2018 Food Insecurity in the OPTs has reached 32.7% and in Gaza 68% according to the 2018 Socio-economic and Food Security Survey. This indicates a clear deterioration in the levels of food insecurity in the OPTs in general and in Gaza in specific.

The first outcome of this programme is: Humanitarian access is improved and ‘dual use’ materials are available for the reconstruction of Gaza. UNOPS has performed well and was able to bring-forth positive achievements against the outcome, despite the fact that two outcome targets were slightly underachieving and one target exceeding the set milestone.

Outcome Indicator 1.1: During the reporting period, as a result of the work of the MMU, two policy changes were achieved: a clear agreement was reached to process all dual use items within 45 working days only, in addition to agreement by both parties to improve the online application form for ‘dual-use’ items, by creating a ‘catalogue’ of all ‘dual-use’ items which have already been uploaded. The catalogue introduced a standardised description of the items, that users can chose from. As more and more people use the dual-use catalogue, it will become more and more effective - leading to increased efficiency for all stakeholders over the year ahead. These achievements do not remove items from the list but are certainly a major step forward, as the import of dual-use items (other than building materials) has been more challenging and unpredictable, impeding the implementation of urgently needed interventions - especially in the field of water and sanitation. Having a set timeframe for the approval and entry of ‘dual use’ materials into Gaza in addition to a ‘catalogue’ will help the private sector and humanitarian and development organisations to better plan for implementation of projects, which will also cut down on operational costs. The Gaza reconstruction mechanism is a step in the right direction; however, a more comprehensive lifting of restrictions as part of a political agreement is the only long-term solution.

Outcome Indicator 1.2: The average waiting time per access incident was 1 hour and 8 minutes (1:08h). This is determined by dividing the total time lost to access incidents by the total number of access incidents. The average staff hours lost (1 hour and 8 minutes) is well below the projected target of 2 hours, which contributes not only to saving staff time and efforts, but also saving on operational costs of humanitarian and development organisations. It is worth mentioning that for outcome indicator 2, the shorter the time the better, reflecting a positive achievement towards the outcome.

Outcome Indicator 1.3: The total amount of cement held by the Gaza Reconstruction Mechanism (GRM) approved vendors was 16,901 tonnes (average during reporting period) which is below the set milestone of 20,000 tonnes. This decrease is due to the continuing deterioration in the economic situation in Gaza, with reduced public sector salaries and very high levels of unemployment; creating less demand on cement.

The second outcome of this programme is: Acute humanitarian needs met during emergencies. This target is not only limited to UK (DFID) action but reflects humanitarian response in the OPTs. The target set for this outcome indicator was overachieved during 2018, as humanitarian actors were able to meet urgent humanitarian needs and respond to the energy crisis, food insecurity, and easing the strain on the health sector.

Outcome Indicator 2.1: Progress will be measured by calculating the percentage of people with acute needs provided with humanitarian assistance from the total number in need as identified by the UN Humanitarian Needs Overview. An analysis of each target sector is below, which suggests that most people in need of humanitarian food security received food or cash/vouchers, but that there was more limited coverage of water and health needs.

Sector	Number of people in need in Gaza	Number of people reached	Extent humanitarian needs met
WASH Sector	1.46m	Over 1.43m people in Gaza partially reached through ICRC, UNICEF and UNRWA	Most people in need likely to have had some improvements in water quality. / However, there was 77 litres of piped water per person per day in 2019 and 73 in 2018, compared with the WHO recommended minimum of 100.
Health Sector	350k in need of emergency and trauma care; 44k people with disabilities acutely vulnerable / A further 850k in need of other humanitarian health interventions (eg mental health, non-communicable diseases, pregnancy).	Over 162,000 people with disabilities or in need of surgery supported by ICRC. Over 750,000 consultations in ICRC supported hospitals / 1,968 refugees received emergency health care from UNRWA, compared with the target of 14,000	Difficult to judge, but likely that roughly half of the emergency/trauma care need being met by DFID partners. / Significant gaps in health care still exist. In 2018 the plan to respond to emergency health needs was 70% funded. In 2018-2019 47% of essential drugs had less than one month’s supply and 20% of UNRWA health centres had stock outs of one of 12 essential items over the last year.
Food Security Sector	1.19m	1.18 m / 934,000 (refugees in Gaza through UNRWA) / 243,000 (non-refugees through WFP)	Over 99%
[note] Based on numbers provided with improved water and sanitation by ICRC from refurbishing water and sanitation facilities.
[note] UN Gaza Strip Early Warning Indicators, June 2019

Outcome Indicators

Indicators measuring outcomes	Baseline (2015)	Milestone 2018/2019	Progress 2018/2019
Number of positive policy changes in relation to the ‘dual use’ list (e.g. removal of items or categories from list).	N/A	2	2
Average number of UN and NGO staff hours lost per access incident.	1 hour and 35 minutes	2.5 hours	1 hour and 8 minutes
Tonnes of cement held by Gaza Reconstruction Mechanism (GRM)-approved vendors.	28,831 tonnes	20,000 tonnes	16,901 tonnes
2.1 Number of people with acute needs provided with humanitarian assistance in Gaza. / (Number of people reached/total number of people in need of sector support).	N/A	80%	99% for food security; partial support provided for health and wash.

Overall, outcomes for the reporting period met expectations with the exception of outcome indicator 1.3 due to external reasons explained above.

Overall output score and description

The overall output score is A, indicating that the programme is achieving expected results. The ACU is increasingly acting as a centralised platform to address policies and practices that restrict humanitarian space in the OPTs. The ACU’s growing role in coordinating with donors and diplomats is seen as another valuable function, linking humanitarian and development access needs (especially in Gaza). The MMU’s role is to facilitate and monitor the approvals, entry, supply, and use of ‘dual use’ construction materials and equipment into Gaza. As facilitated by the MMU, all GRM registered and cleared households were able to access to cement and rebar to undertake reconstruction and/or construction of their homes. There is a risk, however, that delays could impact the final outcome on reconstruction, as this is dependent on donor funding and approval processes by the GRM parties (the PA and GoI).

The three humanitarian actors (UNICEF, ICRC, and URNWA EA), provided timely humanitarian assistance to the most vulnerable individuals in Gaza in the sectors of Water Sanitation and Hygiene (WASH), Health and Emergency Food Assistance.

During the reporting period, implementing partners delivered on the outputs laid out in the log frame and achieved its targets for 3 outputs and did not moderately meet expectation on 2 outputs.

Output Indicators

Output number	Output Description	Impact Weight (%)	Output Performance	Risk
1	Technical access coordination provided for humanitarian actors.	15%	B	Minor
2	Materials Monitoring Unit (MMU) enables beneficiaries to access ‘dual use’ materials necessary for reconstruction of Gaza.	10%	A	Major
3	The most vulnerable communities in Gaza are accessing WASH facilities.	25%	A	Major
4	The most vulnerable communities in Gaza have access to adequate treatment, including physical rehabilitation services.	10%	B	Major
5	Food requirements of food-insecure refugees met.	40%	A	Major

Major changes to the logframe in the past year

Following the change in context and the activation of the humanitarian contingency component, two new outputs which correspond to the achievement of outcome 2 were added with relevant milestones. This was in order to capture and assess activities implemented by the ICRC and UNRWA’s Emergency Appeal through the humanitarian response in Gaza.

Planned changes to the logframe as a result of this review

As the logframe is a living document and the contingency component is flexible, new output indicators may be identified to assess new activities should there be a need for further humanitarian funding in response to arising needs and/or change in the context. The following changes to the log frame will be considered:

- Improving disaggregation of indicators by vulnerable groups (e. g. sex, disability) where appropriate.
- Incorporating indicators of the quality and sustainability of outputs when possible and relevant (e.g. beneficiary feedback).
- Revising milestones and targets to reflect the changing and deteriorating context in Gaza.

## D: VALUE FOR MONEY

For the support to humanitarian access and reconstruction via the ACU and MMU we have conducted a cost-effectiveness analysis, given that international/national benchmarks are not appropriate. The ACU facilitates the movement of humanitarian personnel and goods, whereas the MMU is a monitoring mechanism to oversee the supply chain of construction materials entering into Gaza. For the humanitarian response, we have used a cost per beneficiary cost comparators from the local context in addition to calculating cost savings achieved through the UNICEF WASH activities.

The cost drivers for the ACU and MMU (also funded by other donors) are mainly staff salaries due to the nature of the interventions, whereas the main cost drivers for the humanitarian WASH response (DFID-funded only) include procurement and delivery of WASH related materials (hygiene kits, sodium hypochlorite, water tanks, chlorinators and chemicals etc.).

ACU
It is difficult to find a comparator to benchmark the ACU against, however we identified a range for an acceptable cost per successful intervention; £281.80 - £388. The ACU cost drivers and performance are measured against several indicators: the average cost per staff member, the number of ACU interventions on beneficiary access, successful ACU interventions and the number of personnel impacted by such interventions. ACU interventions on staff access include support, resolving of access incidents and negotiations related to major access issues. The three types of interventions are linked to an estimated time span so as to provide an idea of the costs linked to each intervention. The more time required for a successful intervention to be achieved, the more of staff time is spent on resolving the intervention and thus resulting in increased costs. A ‘Successful ACU Intervention’ is therefore defined for this purpose as ‘any intervention that did not result in denial of entry/access for humanitarian personnel and confiscation of UN property’.
[note] Identified acceptable range based on the baseline of the previous programme.

MMU
The MMU’s role is unique to this context and there are no other known comparable situations. DFID therefore compares the cost per tonne of monitored cement entering into Gaza before the creation of the MMU, and the cost per tonne monitored afterwards.

UNICEF
For UNICEF’s WASH response, we will report on cost effectiveness to demonstrate optimising the use of resources, while successfully achieving outcomes. However, it was not possible to identify appropriate comparators.

ICRC
As a comparator, we will use the cost per beneficiary from 2014 when DFID supported the 2014 ICRC Israel and Occupied Territories ILOT Appeal. In 2014, ICRC’s total expenditure was 65,612,000 Swiss Francs and it supported a total of 2,082,260 beneficiaries. The cost per beneficiary in 2014 can therefore be calculated as 65,612,000 Swiss Francs / 2,082,260 beneficiaries = 31.50 Swiss Francs or £21.56.

UNRWA Emergency Appeal
To assess the cost per beneficiary against similar programmes we drew upon Coffey’s assessment of nine African countries in 2012 (Coffey, 2012, Value for Money in Humanitarian Repose). This is not a perfect comparator as the context is very different, however there is a limited evidence base from which to draw. They found that for food assistance interventions, the range of cost per beneficiary per year of food assistance is $41 - $136 which equates to £9.80 – £95.80. We can complement this comparator by calculating the cost per beneficiary for the UNRWA food assistance intervention implemented in 2017. In 2017, UNRWA spent $74,141,669 on food aid in Gaza and supported 894.232 beneficiaries. Therefore, the cost per beneficiary can be calculated as $74,141,669 / 894,232 beneficiaries = 82.9 which equates to £68.05.

VfM performance compared to the original VfM proposition in the business case

ACU
Below is a table which shows 2017/2018 costs in comparison with the baseline.
	Baseline	2018/2019
No. of total ACU interventions	7,100	5,776
Support	6,805	4,578
Negotiations	41	62
Access Incidents	254	1,082
No. of successful interventions	7,050	4,818
Support	6,805	4,578
Negotiations	34	14
Access Incidents	211	184
No. personnel impacted per successful interventions	10,122	6,195

The marginal cost per staff member has remained stable and even decreased since 2015, while the number of incidents requiring intervention subsequently declined, and number of long-term access negotiations and personnel affected increased. As shown in the table, in 208/2019 the ACU achieved 5,776 successful interventions with a budget of £773,474. Therefore, the cost per successful intervention = £773,474/ 5,776= £133.9which is below the target of £281.80 by 52.4%.

MMU
To assess VFM based on actual MMU expenses and actual number of construction materials imported through the GRM we divide the total MMU project expenditure by the amount of construction materials (aggregate, bar and cement) facilitated by the MMU. The total project expenditure up to March 2019 is $22,886,096. The amount of construction material that was facilitated to enter Gaza by the GRM and MMU was 3,293,712 tonnes. This leads to a cost per tonne of $6.95. This is a slight increase to the cost of the MMU as of end 2015 ($6.60 per tonne[[1]]). Other bilateral arrangements between UN agencies and the GoI continue to operate to facilitate entry of cement and other construction materials into Gaza. Based on publicly announced figures for the amount of material processed through these arrangements and the associated project costs, comparable cost per tonne figures have ranged from $21 up to $96 per tonne. As such, the MMU represents excellent value for money in comparison to other similar projects.
[[1]] MMU presentation at MMU Board Meeting.

While the MMU maintains around 80 people, the monitoring regime has been and remains ‘light touch’ in nature as required by GoI under the GRM agreement, with activities performed on a random sampling or periodic basis. This is a key differentiator from previous and other currently existing monitoring agreements for material entry, which require a constant presence of monitoring personnel at all times leading to increased human and operational costs.

UNICEF
By working with partners, UNICEF was able to reduce the costs of delivering a wide range of WASH interventions. Costs were rationalised as far as possible so that overhead costs and partners’ unit costs were kept within the range while accomplishing project activities within the budget.

Below is a Table with the cost per unit for Deliverables

Deliverable	Unit Cost in GPB
Provision of sodium hypochlorite solution for water purification and chemicals for water treatment.	£0.78 per m³
Provision of fittings and accessories for water and wastewater networks including needs assessment, installation and supervision.	£116.78 per rehabilitation of water/wastewater network.
Provision of domestic water tanks (Cost includes needs assessment, installation and supervision)	£66.6 per unit

This was achieved through UNICEF’s expertise in the WASH sector, long experience of working in the context of the OPTs, and knowledge of market prices in addition to UNICEF’s prudent management of resources by aligning programme expenditure with the initial budgeted amounts. UNICEF also ensured that technical quality was maintained. Moreover, UNICEF promoted equity through fair and accurate selection processes considering the vulnerability assessment of households, including through weighted selection criteria to determine household conditions.

It was not possible to identify VFM milestones as comparators were not available for an assessment. Therefore, UNICEF is planning to conduct an in-depth VFM analysis for the WASH activities in Gaza in order to assess whether programme results considered good investments and provide evidence on whether the programme made the most value out of the available funds while ensuring the best possible outcome. This analysis will feed into the value for money assessment for next year’s review.

ICRC
In 2018, ICRC’s total expenditure through the 2018 ILOT Appeal was 51,205,000 Swiss Francs and it supported a total of 2,427,671 beneficiaries. The cost per beneficiary in 2018 can therefore be calculated as 51,205,000 Swiss Francs / 2,427,671 beneficiaries = 21 Swiss Francs or £17.75, which is significantly lower than our comparator of 2014 (£21.56).

UNRWA Emergency Appeal
In 2018, UNRWA’s total expenditure on the food assistance component in Gaza was US$ 76,675,842 and it supported a total of 933,979 beneficiaries. The cost per beneficiary in 2018 can therefore be calculated US$ 76,675,842 / 933,979 beneficiaries = US$82 or £67.55, which is within the range of the food assistance interventions comparator and slightly lower than the 2017 comparator (£68.05). Consequently, we assess that the programme represented reasonable VFM.

Assessment of whether the programme continues to represent value for money

All components of the programme continue to represent value for money, outperforming their comparators where comparators were available.

Assessment of whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

Access incidents have been on a steady decline since 2009 as a result of a number of factors, most notably due to ACU efforts invested in improving access of humanitarian personnel and goods in Israel and the OPTs. This has been through direct engagement and advocacy with relevant authorities, as well as provision of timely support, information and advice to international organizations and their personnel.

The GoI considers a range of materials and equipment to be ‘dual-use,’ i.e. with the potential for a military application. Entry of these materials is heavily controlled or banned. The GoI has published a list with 117 materials considered ‘dual-use’. Prior to the GRM agreement, some international agencies were able to negotiate the entry of materials on a project-by-project basis, but the private sector and smaller organisations had no involvement or ability to engage with this process.
Since its inception, the GRM has facilitated the entry of large quantities of cement and other building materials for the reconstruction and repair of housing and infrastructure. The decline in cement imports during 2018 is due to a number of factors unrelated to import restrictions: the general economic decline, decreased purchasing power in Gaza, reduced donor funding and the fact that the reconstruction process is drawing to an end. Nearly 100,000 people were displaced due to the destruction or severe damage of their homes during the 2014 conflict, but more than 85% of these homes had been rebuilt by the end of 2018.
The UN sees a continued need for the role of GRM and a need for the mechanism. According to UNSCO, both parties (GoI and PA) reiterated the desire for this project to continue.

Key Results from the Humanitarian Response:

- The ICRC was able to ease the strain on the health care system in Gaza and provide necessary material and technical support to hospitals in order to treat people injured during the protests. The ICRC also helped the physically disabled, including those injured during protests obtain rehabilitative services and improve their mobility.
- Children, women, and men gained improved access to domestic water and a total of 16,860 households were connected to piped water and wastewater network.
- UNICEF continued to supply chlorine for water purification. Reduced access to water and adequate hygiene services in vulnerable communities has placed economic strain on affected families.

E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation

Overall risk rating: Major

The risks to the success of the programme are moderate. The overall risk, however, is Major reflecting a humanitarian intervention operating in the context of a protracted crisis. Mitigating measures include strong due diligence, working with partners with proven capacity, ensuring we link the programme with diplomatic efforts for a political solution to a two-state solution and that all parties have respect for International Humanitarian Law.

Overview of programme risk

ACU: The following risks were highlighted during the reporting period:

ACU funding: Funding gap remains. Efforts by the ACU to reach out to other potential donors should continue, since the ACU project is contingent upon stable and predictable funding stream.

Uncertain political and security environment: The precarious political and security situation could easily lead to events that would result in greater access restrictions. Without any political solution on the horizon, tensions continue to ferment in such a way that the risk of a Gaza escalation or unrest in the West Bank could easily occur.

MMU: The following risks were highlighted during the reporting period:

Resumption of conflict: there are a number of conflict drivers that cannot be mitigated by the success of the GRM. Additional external drivers such as the lack of a permanent ceasefire could lead to a sudden deterioration of the security situation. This would mean monitoring activities will be halted.

PA role: The lack of progress by the PA to resume governance functions in Gaza could constitute a risk to the GRM and MMU; especially after the October 2017 agreement between the PA and De facto authorities was not implemented.

MMU funding: Current funding available for the MMU project’s operations is sufficient only until the first quarter of 2020, while there is no indication that the GRM will end or be adapted before this time.

The MMU Project Board continues to assess risks to the project on an ongoing basis, and where necessary determine the need for diplomatic support from donors to help mitigate them.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues

ACU and MMU
UNOPS is the implementing partner for both the ACU and the MMU. UNOPS is an operational arm of the UN which supports the implementation of development projects. UNOPS is a fully self-financing organisation, which covers direct and indirect costs by charging a small fee on each project supported. UNOPS has been active in the OPTs since 2006.

UNOPS procurement policies and procedures are included within its Organisational Directives and Administrative Instructions, in alignment with UN procurement manuals. Procurement is managed by a separate team. Financial transactions are recorded by the finance assistants and are verified by the finance officer. Project expenditure is allocated to project codes. These project codes are attributed when registering a commitment; this step is implemented by the procurement team with the project manager’s approval. The system does not allow duplication of expenses or charges. UNOPS procurement principles and policies include a commitment to maximise VFM. UNOPS defines VFM as “the trade-off between price and performance that provides the greatest overall benefit under the specified selection criteria”, which fits with DFID’s understanding of VFM.

DFID and other donors participate in a Project Board as designed by UNOPS, based on this project management methodology in accordance with its objectives. The Project Board meets on a quarterly basis and provides overall guidance and direction to the project, as well as reviewing, monitoring, and evaluating activities.

UNOPS financial management has met the high standards expected. Interim and certified financial reports have been issued on a timely basis, and financial reports are presented at each quarterly MMU board meeting, and every 6 months for ACU. UNOPS has demonstrated proven capability and capacity on the ground.

UNOPS is managing the ACU and MMU’s assets in accordance with UNOPS rules and regulations. UNOPS provides quarterly updated asset lists for the ACU/MMU- last updated lists were shared in July 2019.

UNICEF

For the WASH response implemented by UNICEF, a Steering Group was established consisting of DFID and UNICEF representatives in order to (1) advise and direct the overall management and implementation of the project by providing strategic guidance and oversight (2) oversee Independent Monitoring work to ensure that it meets DFID and UNICEF standards; and (3) ensure that Independent Monitoring findings and recommendations are considered by both agencies.

During the reporting period the Steering group has met three times, during which UNICEF presented progress against implementation plan, expenditure against planned budget, and updated progress against UN reform commitments. In line with the contribution arrangement, UNICEF has provided quarterly updates on progress and financial reports. Annual detailed narrative and financial reports were submitted in June 2019.

UNICEF’s internal procurement process is centralised and takes place in Copenhagen. Due diligence assessments are conducted for all suppliers and vendors. Assessments also include technical and financial capabilities in order to verify contractors’ ability to conduct the work, in line with the set quality standards and specifications.

UNRWA
At UNRWA Headquarters’ level, the Department of Planning is responsible for the planning and coordination of emergency response activities. Under this Appeal, a senior emergency officer oversees monitoring and reporting of activities and supports the development of an Agency-wide emergency response framework. Reporting is managed through an online results-based monitoring system that allows the Agency to track actual results against planned priorities on a quarterly basis and facilitate regular consolidated reporting. UNRWA also maintains other HQ functions in support of emergency operations, including procurement, external relations and legal services (including engagement with relevant international human rights system mechanisms), promoting accountability, and legal support regarding the protection of the rights of Palestine refugees.

The HQ Amman Finance Department, headed by the Director of Finance, consists of Accounts, Budget, Treasury and Programme Units. SFO Finance Department is headed by a Finance Officer who reports directly to the Director of UNRWA Affairs, Syria and the HQ Director of Finance.
UNRWA has detailed procurement policies and standard procurement procedures. Further, Standard Operating Procedures (SOPs) have been developed for various procurement processes such as receipt of tenders, opening of tenders, evaluation of bids and review and award; ensuring that procurement policies of the UNRWA Procurement Manual are clearly understood and complied with.

The ICRC
In the most recent Multilateral Development Review of 2016, ICRC scored very good on matching UK development, and good on their organisational strength.
ICRC financial systems and procedures are heavily centralised, with country delegations drawing on those employed at the Geneva headquarters. The general format for financial reporting draws on ICRC’s planning for Results framework. The ICRC prepares financial statements on an annual basis, in compliance with the International Financial Reporting Standards (IFRS) as adopted by the International Accounting Standards Board.

ICRC applies global/institutional procedures for Delegation-level procurement. Globally, approximately 47% of procurement is done locally, with internal reporting processes allowing direct HQ oversight over local purchasing to ensure that it conforms strictly to corporate tendering procedures and other guidelines. ICRC’s HQ Department of Financial Resources and Logistics works closely with its Department of Operations to ensure value for money in the field.

Date of last narrative financial report(s)	ACU and MMU: April 2019 / UNICEF and ICRC: June 2019 / UNRWA: July 2019
Date of last audited annual statement (s)	ACU and MMU: June 2019 / UNICEF and ICRC: June 2019 / UNRWA: August 2019

G: MONITORING, EVIDENCE & LEARNING

Monitoring

Communication has been good between the ACU, MMU, UNICEF, the ICRC and UNRWA EA programme staff in Jerusalem and Gaza. DFID has participated actively in all MMU Project Board meetings and fed in comments which resulted in changes being implemented. DFID staff participated in various monitoring field visits facilitated by partners. Moreover, meetings with partners’ senior management and programme staff were conducted in order to follow up and discuss day-to-day programme management issues.

Monitoring progress throughout the programme

ACU: Project progress against the log frame indicators is updated monthly based on an online database maintained by the ACU. This allows the project to capture any issues as soon as they arise and act on them accordingly. In addition, ACU conducts a bi-annual satisfaction survey as mentioned above.

MMU: Project Board Meetings are held every three months. Progress can be viewed in real time is public and can be accessed using the website:https://grm.report/#/.

UNICEF: Access to Gaza is severely constrained. Restrictions on movement and access are in place especially within Gaza. Movement in and out of Gaza is controlled by physical (the ‘Separation Barrier’, checkpoints, roadblocks) and bureaucratic barriers (permits, closure of areas). DFID staff’s ability to access and observe programme activity is limited with short field visits. DFID has contracted independent third-party monitors who are on the ground in Gaza to complement DFID’s existing oversight to verify the quality of the activities and collect beneficiary feedback. It will not replace standard programme monitoring which is the responsibility of programme implementers.
UNRWA EA: UNRWA’s monitoring and results reporting are derived from the UNRWA Results-Based Monitoring System, which enables data collections and analysis against the Medium-Term Strategy strategic outcomes. The results-based monitoring system also hosts monitoring structures for Emergency Appeals, projects and other results frameworks used by the Agency. Data is collected and analysed on a quarterly basis at the field level, and on a semi-annual basis through Agency-wide results reviews. Indicators, baselines and targets in UNRWA’s Annual Reports are based on Agency-wide internal monitoring arrangements, Emergency Appeals and the Results System. Moreover, results are disaggregated by field office and, where relevant, by sex, poor/non-poor and disability in accordance with UNRWA guidelines for defining disability, spatial distribution (camp, non-camp, urban, rural), and key age groups (e.g. youth). Activities have been verified through roughly monthly field visits by DFID staff.
ICRC: As part of organisation-wide reform, the ICRC implemented new monitoring and planning processes both at headquarters and in the field. The new planning and monitoring framework helped the ICRC estimate its future needs better and secure longer-term funding commitments from donors. The Office of the Director-General helped improve the relevance, efficiency and effectiveness of the ICRC’s strategic planning, monitoring and reporting. It helped guide the roll-out of a new monitoring-for-results process in all delegations in 2018. Updated on a quarterly basis, the new process helped standardise monitoring across the organisation and make it more efficient. The office also oversaw the beginning of the roll-out of a similar planning and monitoring process for headquarters units. These important milestones marked the final step of the ICRC’s business transformation to outcome-based programming – as set out in the Institutional Strategy 2015–2018.
Evidence

No planned Evaluation.

Learning

Progress on recommendations from previous reviews

Summary of Recommendations from Annual Review 2017/2018

During the reporting period, there has been deterioration in permit processing for national UN and INGO personnel, resulting in a significant increase in Gaza-based personnel being denied exit permits and being banned by the Israeli authorities from submitting applications for 12 months. The ACU received assistance from the Humanitarian Coordinator in raising the issue with the relevant interlocutors at the Israeli Authorities; however, there is a need for the UK to continue to call on the GoI to ensure that they adhere to humanitarian principles.

Action: DFID has engaged with UK missions based in Jerusalem and Tel Aviv to lobby governments to ensure movement of humanitarian goods and personnel in accordance with humanitarian principles and UN resolutions.

In February 2018, the PA and the GoI agreed to perform a ‘joint review’ of the GRM in order to improve its functionality, transparency and predictability. It is expected that this review will lead to functional changes in the MMU’s operations. It is recommended to continue funding the MMU for the next year with the same funding level as financial year 2017/2018. Milestones for the coming year will be identified and the necessary changes will be reflected in the log frame.

Action: DFID continued to fund the MMU for financial year 2017/2018. Changes to the log frame were not made as there were no functional changes to the MMU operations. However, milestones and targets will be revisited after the completion of the ‘joint review’ of the GRM.

DFID is piloting an independent monitoring function to perform observations and collect data on the WASH response in Gaza to ensure that results are delivered at the scale reported and to agreed standards. The monitoring function will provide assessments on results, evidence-based recommendations, and lessons learned. It is recommended that findings and lessons learned from the independent monitoring are shared across the office for wider learning.

Action: Findings and lessons learned from independent monitoring were shared across the office, and the programme team fed into a cross-office session on monitoring.

It is recommended to revisit the value for money milestones for the humanitarian WASH response to ensure that the assessment encompasses DFID’s value for money framework- economy, efficiency, effectiveness and equity (including gender equality, disability and leaving no one behind).

Action: Although UNICEF reported on value for money during the last reporting period; however, it was not possible to identify VFM milestones as comparators were not available for an assessment. Therefore, UNICEF is planning to conduct an in-depth VFM analysis for the WASH activities in Gaza in order to assess whether programme results considered good investments and provide evidence on whether the programme made the most value out of the available funds while ensuring the best possible outcome.