FINAL REPORT
Contrat  : CAR/2019/MENTOR/001
Pays 	: Central African Republic
Client : MENTOR

The content of this report is the sole responsibility of the contractor and can in no way be taken to reflect the opinion of
 Mentor and members of the DFID consortium
Oversee Advising Group (OAG)
info@myoag.org |www.myoag.org
Final Evaluation
DFID supported Emergency Assistance to Crisis-affected Communities of C.A.R. Phase II 2016-2018

TABLE OF CONTENT

Liste des graphiques
Liste des tableaux

# Version tracking

Prepared by:	Oversee Advising Group (OAG) – www.myoag.org
Version status:	Final
Date of submission:	30/04/2019

Acknowledgements
At the moment of the submission of this of the mid-term evaluation report of the project to reduce deaths and suffering caused by tropical diseases, OAG would like to express its thanks to The MENTOR Initiative and other members of the consortium (International Medical Corps, Cordaid).
The mission wishes to express its thanks to coordinator of the consortium for the perfect organization of the mission.
The mission would also like to appreciate the valuable contributions of the consortium members to the data collection tools, which have helped to make these tools relevant to the CAR context. It is equally an occasion to reiterate our thanks to the data collectors for their exemplary participation in this evaluation, to the households and key informants interviewed, who made themselves available to answer provide information to the mission. Through the quality of their responses and exchanges, they made this evaluation pleasant and exciting.
NGOs operating in CAR (COOPI, ACF, MSF France), as well as UN agencies (UNICEF, WHO, OCHA), enriched this mission with valuable information during the interviews given to the evaluation team. The mission wishes to pay particular tribute to each member of the consortium, for its contribution to this mission and the documentation provided, which contributed to facilitating the work. The core teams of the consortium members in the localities visited (Ouham and Ouham Pendé, Haute Kotto and Basse Kotto prefectures) have been very professional in facilitating the data collection exercise. We remain grateful to them.
Special thanks for the language review and translation of this report in English

Abbreviations
ACF	Action Contre la Faim
ANJE	Alimentaires du Nourrisson et du Jeune Enfant
CHW (ASC)	Community Health Worker (Agent de Santé Communautaire)
QIB (BAQ)	Quality Improvement Bonus
CMAM	Community Management of Acute Malnutrition
COGES	Management Committee (Comite de Gestion)
CONGES	Management Council (Conseil de Gestion)
COOPI	Cooperazione Internazionale
DFID	Department for International Development
FGD	Focus Group Discussion
FOSA	Health Unit (Formation Sanitaire)
FPF	Female Focal Point (Femme Point Focal)
IEC	Information Education and Communication
IMC	International Medical Corps
MAS	Severe Acute Malnutrition (Malnutrition Aiguë Sévère)
MAM	Severe Moderate Malnutrition (Malnutrition Aiguë Modérée)
MINUSCA	United Nations Multidimensional Integrated Stabilization Mission in the Central African Republic
MSF	Médecins Sans Frontières
OAG	Oversee Advising Group
OCHA	Office for the Coordination of Humanitarian Affairs
WHO	World Health Organisation
NGO	Non - Governmental Organisation
PASS	Health System Support Project (Projet d’Appui au Système de Santé)
PBF	Performance base financing
HRP	Humanitarian Response Plan
CAR	Central African Republic
RECO	Community Relay Agent
SNIS	National Health Information System (Système National Information Sanitaire)
SPSS	Statistical Package for the Social Sciences
UK	United Kingdom
UMM	Mobile Medical Unit (Unite Medicale Mobile)
UNHAS	United Nations Humanitarian Air Service
UNICEF	United Nations Children's Fund
GBV	Gender Based Violence
VFM	Value for Money
WASH	Water, Hygiene and Sanitation

Executive summary
Context
The crisis that the CAR has been experiencing for several years has prompted development partners to take action to help the affected population. In this context, MENTOR, IMC, Save the Children (replaced by Cordaid in 2016) and Oxfam formed consortium for the implementation of the DFID program. This consortium aims to prevent and reduce morbidity and mortality in the prefectures of Ouham, Ouham Pendé, Haute-Kotto and Basse-Kotto as part of the multi-sector program covering health, nutrition and WASH in these prefectures for nearly 474,372 people in phase II.
Purpose of the evaluation
The mission had a three-fold objective: evaluation of the program's achievements, progress in achieving program objectives and results, and evaluation of strategic priorities for its implementation in terms of optimization of resource. In addition, the identification of best practices and lessons learned at mid-term to enrich the development of phase III of the program.
Methodology
The methodology consisted in combining qualitative and quantitative methods. In terms qualitative methods, in addition to an in-depth literature review, 29 focus groups were organized with direct beneficiaries, CHWs and RECOs. 50 semi-structured interviews were conducted with stakeholders (consortium NGOs, Ministry of Health actors, community leaders, other NGOs, etc.). There was an observation of the WASH infrastructures of the FOSA. The quantitative part consisted of a survey with the aid of a questionnaire of 109 direct beneficiaries in Paoua, Bria and Alindao. The data collected was analysed through descriptive statistics, content analysis and triangulation
Limitations
Some localities were not visited for security reasons (Pavica axes, North Paoua etc.). This limitation leads to the absence of primary information on these localities and therefore a limitation in terms of appraisal by the evaluators of the outcomes of the project in these localities.
Main conclusions
Relevance
The program is implemented in a context where CAR is subject to successive security crises and ranked last (188th / 188th) in the world according to the HDI (UNDP 2016). The country also has a prevalence of Global Acute Malnutrition of 18%, above the emergency threshold of 15% (SMART Survey 2016), a 50% increase in the number of IDPs and a prevalence of food insecurity of 48%.
The consortium's intervention approach is aligned to the CAR's national health strategy in terms of tools (ministry image boxes and national medical protocol) and indicators (mortality rate, hospital utilization rate, etc.). The areas of intervention (Ouham, Ouham Pende, Haute-Kotto and Basse-Kotto) and the sectors (Health, Nutrition, WASH) targeted by the program are also those of the HRP.
The re-adaptation of the target values ​​and calculation methods of some key indicators to the Central African context allowed the program to readjust itself, thus improving the coherence of activities with the achievement of objectives. Among the revised indicators are the number of inhabitants for 01 CHW which has been reduced from 3700 to 1000 and the utilization rate which has been reduced to 0.6 consultation / staff / year.
The program also finds its relevance in the alignment of the action plan with the Central African SNIS and the choice of intervention areas which is consistent with the priority needs in terms of health and WASH, as reported by local stakeholders.
Effectiveness
Excluding activities that are not applicable by the program, the overall achievement rate of activities can be estimated at nearly 90% (57% completed and 30% on the right track). The activities that are lagging are among others those dedicated to OXFAM, despite a significant improvement after the mid-term review thanks to the WASH achievements of Mentor, IMC and Cordaid. The invitation of the representatives of the Central African Government to the Consortium review meetings is also part of the unrealized activities.
The implementation of the activities has led to a quarterly average increase of 5.7% in the use of health services (October - December 2018), a decrease in the rate of severe acute malnutrition from 2% (mid-term) to 1%, as well as an improvement in the comprehensive follow-up of antenatal care by pregnant women (131%) against 128% mid-term value. In contrast, joint supervision is still very weak (19%) and has even deteriorated compared to the mid-term (39%). It is the same as the vaccination coverage of children (40%) against 41% during mid-term, the average duration of stock-outs of essential drugs (5.5 days) against 5 (target value) and 3.3 (mid-term value). Attendance at IEC sessions is still low (55%), but significantly better than at mid-term (48%).
The strong involvement of local community leaders contributed to the results, "local leaders show us their willingness to see project activities unfold in their communities" a field supervisor from Mentor in Paoua. The same is true of the improvements made by Mentor and IMC in the referral system, the visits of the reinforcement team and the redeployment of Mentor to Markounda.
On the other hand, the absence of a drug supply system in CAR, the inadequacies of the referral system for patients, the low level of qualification of health care providers, insecurity in the axes, the reduction in the number of CHWs (resignations, deaths, etc.) hindered the effectiveness of the program. The bad weather and the deterioration of the roads also slowed or prevented the access on the axes and references by taxi-motorbike, as evoked during the discussion groups in Paoua "When the condition of the roads is not good, the taxi-motorcycles often refuse to bring patients to hospital ".
The Consortium managed to a certain extent the withdrawal of OXFAM in the sense that IMC continued with WASH works in Bria, MENTOR in Paoua and Cordaid in Alindao. Cordaid also conducted WASH activities in the sub-prefectures of Paoua, Markounda and Alindao. It has thus constructed or rehabilitated water points, latrines, incinerators, placenta pits in eight health facilities supported by Mentor.
Efficiency
In Phase II, partners implemented cost-saving practices; raising the expenditure per beneficiary to 6.5 pounds sterling (in the thirteenth quarter). The factors of this optimization are the implication of the relatively inexpensive local labour force in the realization of the infrastructures, the operation of the purchases and the recruitment of personnel according to documented norms and procedures. The same is true of the exchange of experiences via regular reinforcement visits and joint quality control.
However, the Consortium has weaknesses including the use of rental vehicles to the detriment of the purchase of vehicles, the weak application of the VFM due to low ownership of the DALY. The lack of a drug supply system in CAR and insecurity are threats to value for money. In addition, the consortium has experienced three mangers in 2.5 years; however, the current manager could work continuously for the phases II and III, and thus lead a new dynamic within the consortium.
The consortium has always coordinated with the other actors (UNICEF, MSF, ACF, COOPI, etc.) present, which enabled not only to optimize the interventions and to acquire inputs with the best quality-price ratios but also avoid duplication.
The application of the VFM approach is still weak (only 04 were filled out of 12), although the methods for calculating indicators and simple and reliable verification sources are in place. The weak ownership of the VFM procedures and the late recruitment of a dedicated Financial Manager to the consortium at the end of phase II were real obstacles to the efficiency of the program.
Impact
The support of the program to the FOSA led to an increase in the use of health services with a quarterly average increase rate of 13% (Cordaid), 10% (IMC) and 7% (Mentor). It follows that communities have a high propensity to follow treatment in case of malaria, diarrhoea, ARI, etc. Women in an FGD in Bemal attest that; "Since our health centre was rebuilt, we have the opportunity to provide medical care to and our children do not get sick anymore".
The program has brought health services closer to vulnerable populations living far from FOSA through CHWs / RECOs, mobile units and the practice free medical care, thus reducing mortality (especially that due to malnutrition among children under 5 years of age with a rate of 1% lower than the 2% at mid-term) and as indicated by the Chief of Nzélété Health Centre, "With Cordaid's activities, mortality has decreased because people now have access to quality health care and for free”.
In addition to the decline in mortality, other positive effects have been observed. Populations have at least one health resource person who are CHWs, RECOs, FPFs trained by the program in their milieu. Job creation at the local level is significant, as is the reduction of cases of witchcraft charges. In this regard, the Paoua CHWs affirms "The number of cases of accusations of witchcraft has decreased in the village because the children fall less sick [...]".
It should be noted, however, that people's lack of understanding of the free medical care can create a threat to social cohesion in that the support of IDPs hosted in Alindao's Christian camps gives Muslims living outside IDP camps a feeling to have been forgotten by the program.
Sustainability
The DFID program is likely to sustainably reinforce local knowledge as CHW / RECO and matron / FPF are recruited locally and trained in malaria and diarrhoea awareness, screening and management. In addition, the program recruited and trained repairmen equipped with toolboxes for the maintenance of the pumps as is the case in Paoua and Taley.
The main threats to the sustainability of the program are the security context, the weak commitment of the Government and the lack of an exit strategy. The PBF approach has advantages such as overall performance and reinforcement of infrastructure. However, the risk of using drugs of doubtful origin in the FOSA and the difficulty of recovery of costs by the poor are shortcomings of the PBF.
Some readjustments should be made, namely the recruitment of qualified personnel in the FOSA, the development of strategies for the creation of income generating activities (IGAs) and the supply of community actors CHW / RECO with equipment and working materials.
Accountability
According to 95% of the beneficiaries, the consortium's NGOs communicate well and are quite receptive to complaints and grievances. Suggestion boxes and toll-free numbers available in the IMC and Mentor databases are highly appreciated by communities, although the placement of these numbers inside and not outside the FOSA reduces their visibility.
Local leaders are quite involved in the selection of the members of the CGPEs, CHWs / RECOs and in the validation meetings of the CHW / RECO reports. The communities are represented in the COGES which manages the facilities of the FOSA and the medicines.
Consortium NGOs have a well-known commitment to accountability to donors through meetings such as the one held in February 2019 on the VFM. Although we should note weaknesses related to DALY metrics, the presence of a full-time Financial Manager having good prospects for optimization and better accountability.
Accessibility
The DFID program has improved the accessibility of health services (with an increase in the use of these services as mentioned above) and WASH by reducing geographical, financial, cultural and security barriers. Thanks to the community approach adopted, the DFID program benefits all populations regardless of income level, religion, ethnicity or purchasing power.
The main obstacles to the accessibility of the services offered are insecurity, the length of the distances to be covered, the poor condition of the roads and the shortage of medicines.
Quality
The consortium's alignment with the tools and indicators of the Ministry of Health, to the 2017 PRH 2017 and SNIS systems and reference documents gives quality to the intervention of partners. The key personnel of the consortium have a seniority level that is compatible with the targeted results, but not all the health care workers are qualified, notably in Ouham, Ouham Pende and Haute Kotto.
From the point of view of the beneficiaries, the services offered by the program are of good quality and satisfactory to them; 84% are satisfied with the quality of care, 87% of the latrines built in the FOSA, 90% of the water quality in the FOSA and 97% of the sensitization sessions. The activities of the DFID program are thus ethically and socially accepted at the local level.
The main impediment to the quality of care is the low level of qualification of the nursing staff in some FOSA (the heads of the FOSA of Bemal, Dokabi, Kadjama, etc. are only first-aid care givers).
Recommendations
To improve on relevance, the consortium will need to:
- Share with the Ministry of Health the project proposal in order to coordinate on the activities to be carried out by the consortium and the targeted areas;
- Create openings for collaboration with the Ministry of Energy, Mines and Hydraulics through its Department for Water as part of the WASH activities
To improve on effectiveness, it will be necessary to:
- Develop a contingency plan with a budget (Consortium);
- Do some advocacy with the Ministry of Health would be important to support to the FOSA with qualified staff (Consortium);
- Include the travel expenses of the authorities of the Ministry of Health for supervision missions in the phase III budget (Consortium);
- Provide community relays with equipment and mobile equipment to facilitate travel (Cordaid and IMC)
To improve on efficiency, the consortium needs to
- Continue work on the implementation of the DALY metrics, which would assist in the implementation of the VFM indicator framework;
- Define a common methodology for recording expenditures and harmonize the budget structure at the level of all partners;
To improve on the impact of the program, we suggest that the consortium:
- Equip pharmacy managers with inventory management skills and define a stock limit for drug alerts;
- Sensitise communities on the free system practiced to guarantee social cohesion.
To improve on the program accountability, it should:
- Discuss with the Ministry of Health to delegate within it a focal point for the DFID program (Consortium);
- Strengthen the capacity of the Consortium on the VFM (The donor);
- Post the toll-free numbers outside the FOSA (Mentor).
- To improve on the program quality, it would be necessary for the Consortium to set up an early warning system for the rapid detection of urgent cases of disease in the axes and to refer them rapidly.
- To improve on the sustainability of the program, we suggest the following:
- Develop a contingency plan (The Landlord) and an exit plan (Consortium);
- Analyse the feasibility of ensuring the transfer of knowledge from qualified health personnel to first aid givers and CHWs (Consortium);
- Advocate with the Ministry of Health, the Global Fund and Humanitarian Coordination actors to set up a supply system for drugs and vaccines in the CAR (Consortium).
To improve on the accessibility of the program, IMC should share its experience with Mentor and Cordaid on remote management tools for FOSA in case they become inaccessible.
1. Project context
  1. Introduction
In the context of the humanitarian crisis that the Central African Republic has experienced in recent decades, numerous humanitarian initiatives are being initiated to improve the food, safety and, above all, the health conditions of the populations.
It is in the same vein as in 2015, The MENTOR Initiative, International Medical Corps, Save the Children (handed to Cordaid in 2016), and Oxfam partnered with the consortium for the first phase of the current program, with International Medical Corps as head of the Consortium. Phase I aimed to implement a health, nutrition and WASH response reaching out to 432,665 people in four prefectures in the Central African Republic (Ouham, Ouham Pendé, Haute-Kotto and Basse-Kotto) aimed at preventing and reducing morbidity and mortality among populations affected by the crisis. A final evaluation of the Phase I program was conducted to enrich Phase II of the program.
The four partners have therefore developed phase II, with MENTOR as leader, since October 2016 for a duration of 30 months. Oxfam, as a specialized WASH partner, was ousted from 1 February 2018. However, the remaining three partners, decided to finalize WASH activities for Phase II.
Currently, the program components namely health, nutrition and WASH are implemented in the four prefectures. However, the security situation in CAR has drastically deteriorated since the beginning of Phase II and the Consortium partners have adapted and revised the program in order to be able to implement relevant emergency activities if necessary.
This assessment will permit the Consortium to develop Phase III based on the results and lessons learned from Phase II.

  1. Project Summary
Program title	Emergency assistance to crisis-affected communities of Central African Republic-Phase II
Donor	Department for International Development (DFID)
Duration	24 months
Budget	£ 9 080 000
Location	Ouham, Ouham Pendé, Basse Kotto and Haute Kotto prefectures
General objective	Contribute to the emergency health response of the population affected by the conflict in the Central African Republic
Specific objectives	Prevent and reduce the excessive morbidity and mortality of the population affected by the ongoing crisis in CAR
Results	Quality primary and secondary health care is accessible and used. / Communities prevent and respond to common health problems. / Nutritional status of children under five is improved through prevention, screening and treatment. / Collaboration between the consortium and relevant partners (especially health authorities) is improved at all levels.
Target	Children under 5 years of age, pregnant women, women of childbearing age
Key activities realised	Revitalise community-based structures - IEC / BCC (including WASH, nutrition, basic protection and GBV) at the coordination level, deploy reinforcement teams to implement the changes / Streamline training modules (including WASH) and services provided (where appropriate) at the coordination level, deploy strengthening teams to implement changes / Provide medical care to survivors of rape / Train health personnel in nutrition (CMAM / CAR guidelines, IYCF, etc.) / Provide treatment to children aged 6 to 59 months with acute malnutrition (SAM) at the level health facilities / Provide training for ASC (CHWs) and Community Relays (adapted guidelines from MCAM / C.A.R., IYCF, etc.) / Ensure that children are screened for acute malnutrition at the community level and at the level health facilities / Ensure the participation of government personnel in the training of health workers and ASC (CHWs)

Methodology
The evaluation methodology was based on a mixed approach (quantitative, qualitative survey and direct observation).
  1. Data collection
The qualitative survey consisted of conducting a series of semi-structured interviews with partners, stakeholders and focus groups (FGDs) with beneficiaries, CHWs. In total, 50 individual interviews were organized and 29 FGDs completed (beneficiaries and CHW / RECO).
A total of 109 patients were surveyed in the FOSA. A questionnaire for patients was used under KoboCollect which is an application used on Smartphone. In addition, an observation matrix for FOSA was also used on KoboCollect. (See table below).
Prefectures	Sub-prefectures	Localities visited	Number of key interviews	Number of questionnaires	FGD
					Female	Male	CHW/RECO
Bangui	Bangui	Bangui	8	-	-	-	-
Basse Kotto	Alindao	Alindao- Centre, Nzelete, Poudjio, Elim	16	30	2	5	2
Ouham Pende	Paoua	Paoua city, Taley, Bémal	14	45	4	4	2
	Markounda	Dokabi, Kadjama Kota	12	34	4	4	2
Total			50	109	10	13	6

  1. 2.2	Data processing and analysis
Data collected are processed and analysed in two forms: data from the qualitative survey (interviews using the guide), was processed manually; data from the quantitative survey (questionnaires), was processed on computer.
The processing of qualitative data was done through an analysis of the information from data collection tools and the notes taken during the discussions. Quantitative data was cleaned, processed and analysed using STATA, SPSS and Excel software. Descriptive statistics were used for data analysis. The results of the data collected from the different sources were triangulated.
  1. 2.3	Evaluation team
The evaluation was conducted by a team consisting of a senior evaluation expert assisted by a junior evaluation expert and a quality controller. The evaluation team designed the methodology and tools, and the data collection agents carried out the fieldwork. Data collection from partners and stakeholders in Bangui was conducted by the evaluation experts. The field teams were made up of men and women without distinction of origin, gender or religion, all speaking the local language, in this case “Sango”. Fieldwork took place in March 2019.

  1. Difficulties encountered
Difficulties were encountered during this evaluation. However, measures were taken by the evaluation team in collaboration with the coordination to overcome them.
- Breakdown of the rented vehicle at Bele village on March 29, 2019 which slowed the data collection;
- Cancellation of UNHAS flight which caused shifting of travel dates on the ground and as a result, the organization on the ground was destabilised;
- Some localities have not been visited for reasons of insecurity (Ax Pavica, Batangafo, North Paoua, etc.):

3. Results
The literature review, interviews and focus groups in the field were conducted in order to take stock of the strengths and weaknesses of Phase II of the program according to the following criteria: relevance, effectiveness, efficiency impact, sustainability, accessibility, eligibility, quality, lessons learned. The level of taking into consideration the recommendations of Phase I and analysis of gaps are also addressed in the evaluation.

3.1 Pertinence
In this subsection is aimed to elucidate the extent to which the DFID program is consistent with local needs and priorities, and how activities contribute to the achievement of program outcomes.
A program planned in a context marked by vulnerability
The socio-political context of the Central African Republic for several years has been marked by numerous conflicts between armed groups, thus weakening the economic and social fabric of the country and putting populations in an urgent humanitarian situation in terms of indicators. In 2018, the CAR was ranked at the bottom of the scale in terms of human development index (188th / 189 countries). Since then, the situation has deteriorated, resulting in more than half of the country's population in need of humanitarian assistance. Nearly 40% of the population in CAR is in a situation of food insecurity. In 2018, the prevalence of Global Acute Malnutrition is above the emergency threshold of 15% (55%).
In terms of population movement, the upsurge of armed attacks, inter-religious conflicts and the resulting psychosis in CAR resulted in the displacement of 640,969 and 655,956 people in December 2018 and February 2019. Despite the presence of many humanitarian actors, the vulnerability of populations in terms of security, economic, social and especially health has steadily increased.
In addition, the weak presence of state institutions in conflict zones has led people to be doomed to their own fate, without any protection, especially for women and children under 5 years of age. These populations live in an unhealthy environment and are therefore prey to diseases such as malaria, diarrhoea, malnutrition, etc. The situation has also allowed the development of all sorts of violence, especially those based on gender.
A program that meets local needs and priorities
The DFID program is implemented in a context of successive social and security crises that leads to economic, social and health vulnerability of the population.
During field surveys, local stakeholders and communities reported recurrent health problems (eye problems, untreated wounds, fevers, births unattended to by trained personnel, etc.), nutrition (low food to feed children under 5 years of age, etc.) and WASH (remoteness and scarcity of drinking water points, lack of containers for water management, defecation in the open air, etc.). These needs correspond well to those targeted (health and WASH) by national strategies (Humanitarian Response Plan 2019). In addition, the discussions with the Medical Directors of the various partners and the chief medical officers (notably in Bria, Markounda and Paoua) made it possible to point out that the FOSA are deprived of qualified health personnel who are mostly in Bangui. The program is thus implemented in areas where not only the health and WASH needs are enormous, but also the provision of health care and WASH infrastructure is low.
A program consistent with the reduction of morbidity and mortality
The program targets four prefectures (Ouham, Ouham Pendé, Upper Kotto and Lower Kotto) listed in the PRH as areas in acute / chronic humanitarian crisis (map below) whose immediate consequence is high mortality and morbidity.

Map for humanitarian needs (2019)

Source: CAR Humanitarian Response Plan revised in June 2019
Similarly, the overall objective of the DFID program (prevention and reduction of excess morbidity and mortality of the population affected by the current crisis in CAR) is consistent with the desire to save lives, which is one of multi-year strategic objectives identified in CAR for 2017-2019 in the HRP. The activities of the program are likely to lead to this goal in the sense that they revolve around the strengthening of health services and local capacities, the mass awareness, the improvement of accessibility to health services, the construction or the rehabilitation of water points, etc.
The re-adaptation of the target values ​​and calculation methods of certain key indicators to the Central African context enabled the program to readjust itself, thus improving the coherence of activities with the achievement of its objectives. Among the revised indicators are the number of inhabitants for 01 ASC which has been reduced from 3700 to 1000, the utilization rate which has been reduced to 0.6 consultation / staff- / year.
In addition, the key indicators of the project were aligned to the RCA SNIS (mortality rate caused by age, hospital attendance rate, proportion of children under one year of age who received 3 doses of pentavalent vaccine and 1 dose of measles vaccine, ...), the use of image boxes of the Ministry and the national medical protocol combine to align the project activities with the national health strategy. These activities are consistent with the humanitarian strategy of the HRP.
Although it should be noted that the participation of the Ministry of Health at the central level (Bangui), as well as at regional and district levels has improved, the lack of capacity and the small staff of the Central African health system remain a challenge to achieving the set goals.

3.2 Effectiveness
The effectiveness of a program lies in its ability to achieve the objectives or outcomes for which it was designed. The purpose of this evaluation is to review the degree of achievement of pre-established results and to identify the factors that have accelerated or hindered the flow to these outcomes and the adaptive measures to the security and political context. In addition, the effectiveness analysis assesses the level of coordination between relevant actors in each intervention area and also how the Consortium managed the withdrawal of Oxfam in early 2018 in order to maintain the initial objectives.

3.2.1. Level of implementation of activities and status of program indicators
In terms of effectiveness, it is advisable to take stock of the activities carried out as part of the results of the project, to identify and explain the gaps observed.
The graph below shows that out of thirty activities planned by the program, 57% are considered completely completed and 30% on the right track. Those that are out of program or not applicable represent 13% of global activities.
Graph 1 : Level of implementation of program activities

Source: Final Evaluation DFID supported Emergency Assistance to Crisis-affected Communities of C.A.R. Phase II

- The completed activities represent 57% of the activities and involve the rationalization of the IEC community packages at the coordination level coupled with the deployment of the reinforcement teams to implement the changes, the training of CHWs and RECOs on the CMAM, ANJE guidelines. etc. In addition, other activities being completed in December 2018, can be considered as completed by 31 March 2019. These include: FOSA support for essential drugs, basic medical equipment and supplies: the program is 15 out of 19. For security reasons in the Begouladje, Ouin, Kakouda, Irrabanda, Pavika and Kongbo (near Alindao) and Bejangala (near Paoua) axes remain inaccessible;
- Training and supervision of the FOSAs supported by the program;
- The provision of outpatient consultations, observation services and hospital services: 50,826 consultations were conducted during the fifteenth quarter by all partners, representing an achievement rate of 85%;
- Providing Sexual and Reproductive Health (SRH) care and establishing a 24/7 reference system for emergency obstetric and new-born care;
- Rehabilitation and maintenance of WASH infrastructures in the FOSA: work is underway in all the FOSA except Begouladje, Bejangala and Irrabanda because of the inaccessibility;
- The sensitization of the communities on malnutrition through the ASC / RECO and the FOSA: Mentor, IMC and Cordaid were able to sensitise 2,732 people during the fifteenth trimester, giving an improvement of 156% compared to the mid-term.
- Strengthening the management capacities of the COGES of the FOSA: while Cordaid and Mentor trained all their COGES at the beginning of the phase 2, IMC for its part had to face security challenges and in particular in the Irrabanda F OSA.

The activities on track are mainly concerned with the management of MAS for children under five years old by Cordaid, Mentor and IMC, the rehabilitation of FOSA in Bria and Alindao, the medical care of survivors of rape by Cordaid and IMC;
The activities considered as non-applicable, which represent 10% of the activities, relate on the one hand to those dedicated to OXFAM and on the other hand the activity relating to the residual spraying which is conditioned by the validation of the protocol to be used by the Minister of Health.
An activity is outside the program: this is the invitation of representatives of the Central African Government to the Consortium's review meetings. A meeting scheduled for the thirteenth quarter with the representatives of the Government was cancelled. However, it should be noted that the Consortium participated in meetings organized by the Ministry of Health during the last quarter.

The following development compares the final situation of the program's key indicators with the target and mid-term values ​​of the program indicators.
Result 1: Quality primary and secondary health care is accessible and used. The following table summarizes the level of key outcome for measuring of DFID outcome 1.

Table 1: Level of indicators for outcome 1
Indicators	Target value	Situation at mid-term	Final situation	Level of achievement
Number of new severe acute malnutrition cases that gained access to treatment, proportion over expected cases	186	713	530	285%
Number of new malaria cases, proportion over expected cases, disaggregated by severity	12,948	18,181	13,830	107%
Number of new diarrhoea cases, disaggregated by type	//	4,506	3,036	//
Number of new IRA cases disaggregated by type	//	8,406	6,283	//
Number and proportion of children under 1 year who received 3 doses of pentavalent and 1 dose of measles vaccine	1,246	509	495	40%
Number of pregnant women who delivered assisted in supported HUs, and proportion over expected deliveries	884	610	//	//
Number of pregnant women who started and completed an ANC cycle (at least 3 visits) at primary level or mobile clinics	1,381	1,762	1,815	131%
ANC Completion rate	50%	36%	39%	78%
Number of rape survivors who report and request medical care before 72 hours / total reported cases	//	17	16	//
Number of patients who visited a secondary HF after referral from a primary HU against patients who came back with a counter referral ticket	1 355	889 / 339	1441 / 155	//
Number of U5 deaths / number of U5 hospitalisations in Alindao hospital	//	38 / 760	15 / 445	//
Number of pregnant women deaths / number of pregnant women hospitalised in Alindao hospital	//	0 / 15	0 / 10	//
Average number of days of stockout for five tracer essential drugs (days / month)	5	3.3	5.5	//
Number of persons reached during Information Education and Communication (IEC) sessions, disaggregated by theme	43,161	20,898	23,138	54%
Number of joint supervisions with participation of a government representative	57	22	11	19%
Number of HFs where the harmonized supervision package is implemented	19	19	19	100%
Percentage of U5/pregnant women declaring they were charged money (consultation or drugs)	0% of surveyed patients	no survey	no survey	//
Percentage of patients expressing their satisfaction with the quality of care received at the supported HF	100% of surveyed patients	75%	84,4%	84,4%
Percentage of patients expressing their satisfaction with the safety, maintenance and cleanliness of WASH facilities at the HF	100% of surveyed patients	72,1%	89%	89%
Number of maintenance interventions on water supply systems done by a community technician / Number of total maintenance interventions	TBD (Oxfam to confirm)	8	0	//
Number of COGES that held monthly meetings (with available minutes of meetings) and proportion over the supported health facilities	19	8	8	42%
Number and proportion of the supported health facilities where the COGES has been trained using harmonized package	19	11	8	42%
Number of new health facilities with secured access to clean water (samples of water with <1 E.coli / 100mL)	19	11	12	63%
Number of health facilities with access to sanitation with a ratio of 1 latrine / 20 users and hand washing facility	19	11	11	58%
Number of people with improved access to water	48,123	2,928	//	//
Number of health facilities with a pilot program of chlorine water production established / 2 (Dokabi + Taley)	2	//	//	//
[note] Nombre de patients qui ont visité une FOSA secondaire après référence d'une FOSA primaire / Nombre de patients qui sont revenus avec un ticket de référence
[note] Enquête de satisfaction Mars 2018

Source: Final Evaluation DFID supported Emergency Assistance to Crisis-affected Communities of C.A.R. Phase II
The level of achievement was calculated for twelve indicators out of the 26. For the remaining 14, the consortium did not provide either the target value or the final value, which makes it impossible to analyse their evolution. Good performances have been noted and as shown in the table above, it should be said that:
- The new cases of severe acute malnutrition with access to treatment rose to a 285% achievement rate well above the target value. This performance can be attributed to the supply of FOSA in MAS treatment kits, the training of CHWs / RECOs and health personnel on the CMAM, IYCF guidelines. The beneficiaries' satisfaction with the care offered in the FOSA and the maintenance of the WASH facilities of the FOSA increased between the mid-term and final situation, rising respectively to 75% and 89%, lower than the target (100%);
- The number of pregnant women who started and completed an antenatal care cycle (at least 3 visits) at the primary level or in mobile clinics rose to 1815 from 1381 (target value), a completion rate of 131%. However, births are not always attended to by health personnel as noted at mid-term with a rate of 69%. The security challenges can be mentioned as an explanatory factor because preventing women from visiting the FOSA at night for deliveries, as mentioned by a FOSA chief in Markounda,

« The women are afraid to come to give birth in the FOSA especially at night because of the permanent presence of ex-seleka»

- Some poor performance can be noted; the main ones are:
- The number of children less than one-year-old vaccinated (3 doses of pentavalent and 1 dose of measles vaccine) remains at 495, still far from the target value (1,246), a rate of achievement 40 %, below the mid-term rate (41%). This situation is related to the difficulties in the supply of inputs, as explained by the Cordaid project team;
- The number of people having access to an improved water source has risen to 2.928 since the mid-term, a very low achievement rate compared to the target (2.1%). The latter is explained by the withdrawal of Oxfam, which has delayed the establishment of drinking water points and the pilot chlorine production program planned for the FOSA of Taley (Paoua) and Dokabi (Markounda) which requires some expertise that partners do not yet have (DFID Consortium Quarterly Report 15);
- The number of people reached by the IEC sessions not been attained and remains at 54% of the target value. This situation is explained by insecurity that has led to the suspension of mobile clinics and some IEC sessions in Bria and North Paoua (DFID Consortium Quarterly Report 15);
- Joint supervisions with the ministry team are also lagging behind (11 instead of 57, i.e. a completion rate of 19%). The inaccessibility of some FOSAs and the low number of ministry staff in the sub-prefectures as well as the less motivation can be mentioned as the main challenges at this level, such are the cases of the Irrabanda, Begouladje and Bejangala FOSAs (DFID Consortium Quarterly Report 15);
- The number of FOSAs whose COGES was trained using a harmonized program remained at 8, or 42% of the target value, and below the mid-term (11). Similarly, the number of COGES holding monthly meetings with minutes available was 8 or 44% of the target value (Log frame data January 2019);
- The average monthly number of out-of-stock days for five essential screening drugs was 5.5 days while the program was planning an average of 5 days. This is due to the fact that there is no drug supply system in CAR and inventory management shortcomings such as lack of alert stock.

Result 2: Communities prevent and respond to common health problems.
Table 2: Level of indicators do outcome 2
Indicators	Target value	Situation at mid-term	Final situation	Level of achievement
Malnutrition screening results, disaggregated by severity	//	Moderate (313) Severe (723)	Moderate (1631) Severe (541)	//
Number of malaria severe cases / total cases	7,350	101 / 8193	91 / 14049	191%
Number of new diarrhoea cases disaggregated by type	//	1,478	1,576	//
Number of pregnant women who started and completed an IPT cycle (at least 3 visits) with a CHW	784	965	1,049	134%
IPT Completion rate	50%	34%	47%	94%
Average number of days of stockout for five tracer essential item (ACT, paracetamol, iron/folic acid, amoxicillin, albendazole)	max 5 days /month	1.3	1	//
Number of persons reached in Information Education and Communication (IEC) sessions held, disaggregated by theme	24,500	9,587	27,136	111%
Number of CHWs who received at least one on-site coaching per month, using harmonized procedure	98	38	54	55%
Number of CHWs trained using the harmonized training package	98	//	106	108%

 Source: Final Evaluation DFID supported Emergency Assistance to Crisis-affected Communities of C.A.R. Phase II
The table above calls for the following comments:
The number of cases of severe malnutrition is low compared to the mid-term situation (723 against 541). This satisfaction can be justified by the improvement of access to drinking water, especially in the FOSAs of the Paoua and Markounda sub-prefectures where Cordaid built or rehabilitated water points. In addition, the sensitization enabled women to adopt good practices, as was noted during discussions in Taley,

« Mentor taught us that you should wash your hands with soap before eating, feed children, and wash hands after using the toilet»
Women FGD Taley

- The number of people who participated in IEC sessions and CSA coaching using a harmonized procedure rose to a 55% achievement rate, which is an improvement over 39% at mid-term. This situation is justified by the inaccessibility of the CHWs of Markounda, the departure of some people from Paoua to Chad, the deaths and resignations of CHWs. Logistical issues in Batangafo were also highlighted (DFID Consortium Quarterly Report 15);
- The proportion of women who have completed their IPT is 94%, which corresponds to a marked improvement compared to 68% at mid-term. However, the number of pregnant women who completed an IPT cycle with a CHW is well above the 134% target value. As with delivery in the hospital, intermittent preventive treatments have been weakened by security concerns (DFID Consortium Quarterly Report 15);

Result 3: Nutritional status of children under five is improved through prevention, screening and treatment services

Table 3: Level of indicators for outcome 3
Indicators	Target value	Situation at mid-term	Final situation	Level of achievement
Number of new malnutrition cases that gained access to treatment, proportion over expected cases	186	713	530	285%
Number and proportion of the supported HFs/ MMUs who managed severe acute malnutrition for U5 during the month	10	7	6	60%
Cure rate of malnutrition	75%	81%	52%	69%
Death rate of malnutrition	10%	2%	1%	1000%
Dropout rate of malnutrition	15%	16%	47%	313%

Source: Final Evaluation DFID supported Emergency Assistance to Crisis-affected Communities of C.A.R. Phase II
The table above presents the following observations:
- Access to malnutrition treatment has risen above the target value (530 against 186), thanks to the support of FOSA in nutritional inputs, this situation is coupled with a decrease in mortality due to malnutrition (1% against 10% target value). However, the number of malnourished children who have access to treatment has declined compared to the mid-term, which is combined with the number of lost to follow-up cases whose rate has increased from 16% to 47%. This situation is linked to the insecurity that has provoked the temporary and even definite suspension of certain mobile clinics. The good performances noted can be attributed in part to the network of CHWs and RECO set up, which, through the axes, sensitize and refer cases of malnutrition to the FOSA. Similarly, mobile clinics have contributed to the success of activities on malnutrition, as mentioned by Mentor field supervisors in Paoua;
- The indicator with the lowest level of achievement is the number of FOSA and UMM that support severe acute malnutrition for children under 5 which is only 6, and is far from the target value 10. This situation is a result of difficulties in the supply of inputs in CAR following an interview with the Mentor Field Coordinator in Paoua.
Result 4: Collaboration between the consortium and relevant partners (especially health authorities) is improved at all levels
Table 4 : Level of indicators for outcome 4
Indicators	Target value	Situation at mid-term	Final situation	Level of achievement
Proportion of training sessions with participation of a government representative	0	100%	0%	//
Number of meetings with MoH attended by a Consortium representative	3	7	//	//
Number of Consortium coordination/review meetings attended by a government representative	0	0	0	//
Number of joint multisector (minimum Health and WASH response) “emergency action plans” in place / 5 total sites (Paoua, Markounda, Batangafo, Bria, Alindao)	N/A	2/5	//	//
Number of “emergency action plans” acted on / total emergencies during the quarter in Consortium project sites	N/A	1/2	//	//

Source: Final Evaluation DFID supported Emergency Assistance to Crisis-affected Communities of C.A.R. Phase II
Outcome 4 involves overall action plans and collaboration with ministry authorities. At mid-term, it was noted that the consortium held 7 meetings (against 3, target value) with the Ministry of Health. The interviews revealed that collaboration with the ministry at the district and regional level is fruitful, which is still not the case with the central level actors (Bangui). It should be pointed out that the other indicators have not been entered in the log frame January 2019.

Level of achievement of indicators related to the specific objective on the use of health services
Tableau 5 : Progress in the use of health services
Indicators	Target value	Situation at mid-term	Final situation	Level of achievement
Health service utilization, disaggregated by service delivery channel and by age	19,884	30,046	51,570	259%

 Source: Final Evaluation DFID supported Emergency Assistance to Crisis-affected Communities of C.A.R. Phase II
Regarding the use of health services for the last quarter (October-December 2018), the number of consultations recorded in the DFID-supported health facilities experienced an average quarterly growth of 5.7% (calculated from quarterly data). monitoring program indicators). More specifically, the number of consultations for children under 5 has a realization rate of 259%. This indicator shows a greater capacity of the program to get closer to the youngest populations (under 5 years) and thus to prevent and reduce morbidity and mortality among this population in the intervention zones. However, this situation is not the same for all partners. Despite the security challenges, the DFID program has helped to increase people's access to primary and secondary health care through CHWs, RECOs and mobile clinics across the intervention area. As shown in the graph below, the number of consultations in the Cordaid and IMC FOSAs increased overall in Phase II, with average quarterly growth rates of 13.2% and 10.4% respectively. Mentor's FOSA recorded growth of 6.9% over the period, with a sharp decline during the period July-September. This sharp drop may be related to conflicts between armed groups in Batangafo in July 2017 that led to insecurity, so that Mentor and other NGOs suspended their activities in July-August. This situation lasted until September and slowed down the use of health facilities. In addition, during this period, Mentor was unable to collect data from health posts in Kakouda in August and September and health posts in Ouin in September.

Graph 2: Variation of the quarterly number of consultations in the FOSA

        Source: Final Evaluation DFID supported Emergency Assistance to Crisis-affected Communities of C.A.R. Phase II
The program indicators are well adapted to the Central African State's SNIS, thus, the performances of the FOSAs supported by the DFID program are comparable to those of the PASS project's FOSAs. The overall goal is to increase the use of maternal and child health services and improve the quality of maternal and child health services in targeted rural areas of the Central African Republic.

3.2.2. Factors Affecting Program Delivery
Both exogenous and endogenous factors have influenced (positive or negative) the achievement of program objectives.
Table 6: Drivers and obstacles to achieving program objectives
Drivers for achieving the objectives	Brakes to the achievement of the objectives
Free healthcare that breaks financial barriers in a context of poverty and patient referrals in a context of insecurity and inaccessibility of the FOSA; / The partners have not only supported the FOSA, but they have gone further by involving people that the communities know and accept (community leaders, CHWs / RECOs), which builds community trust and good collaboration; / The partners have each specialized in their respective strengths, which makes them more effective; Mentor and BMI through CHWs and mobile clinics adopt the community-based approach while Cordaid strengthens the health system by enhancing the FOSA's technical platform; / Visits of the reinforcement team (technical staff) are organized in the sites of the different partners by rotation. These visits allowed the partners to discuss the progress of the activities and to take corrective measures necessary to improve the work. Reinforcement visits were made to Paoua in March 2017, Alindao in March 2018 and Bria in June 2018; / MENTOR and IMC have set up an extensive network of CHWs through villages that do not have access to a FOSA. This contributes to expanding the scope of the program and, in turn, the number of beneficiaries. The MENTOR ASCs are in the 5 km perimeters on the axes and IMC has set up a ratio of 1 CHW for 500 to 1000 inhabitants in the axes. CHWs conduct door-to-door sensitization, mass outreach, awareness raising in public places, malaria screening and administer drugs, etc. Cordaid has set up a RECO network according to the ratio of a RECO for 15 to 20 households. / Following the events that have caused a large population flow in the sub-prefecture of Alindao, Bria and Paoua DFID has granted a contingency line that has since the last quarter enabled the carrying out of WASH activities in the FOSA and in the hospitals in communities. This flexibility of DFID was also observed in the health component, which enabled IMC to respond in Bria in 2017 and MENTOR in Paoua in 2018. / Involvement of local actors: RECOs, ASCs, FPFs who make primary health care available to the population, and mayors, sub-prefects, religious leaders who facilitate community activities and as mentioned by a field supervisor from Mentor in Paoua, "Local leaders show us their willingness to see project activities unfold in their communities”	The rupture of drug stocks that are attributable globally to delays in the delivery of drugs. The weakness of pharmacy managers can also be cited. Mentor suffered delays in expedition some of the drugs that were finally delivered only in December. IMC faced a stock-out of antimalarials, paracetamol in October and albendazole in October and December. However, an exogenous factor is the lack of a drug supply system in the Central African Republic, which would have made it possible to lighten the procedures for the purchase of drugs; / Some DFID activities have been slowed down or even removed for security reasons. In December, 07 FOSA were inaccessible: Begouladje (near Paoua), Ouin and Kakouda (near Batangafo) inaccessible in November due to renewed conflict, Irrabanda (near Bria), Pavika and Kongbo (near Alindao) and Bejangala (near Paoua) remain inaccessible. / Bad weather and poor state of roads make it access to the axes difficult. In the rainy season the roads are degraded, the tracks are muddy, making the movements of motorcycles and vehicles complicated and perilous. In the dry season the degraded state of the roads increases the shock to the patients using motorcycles. These poor road conditions very often delay or prevent referrals by taxi-motorcycle, the CHW at the FGD in Paoua spoke on the condition of the roads saying "When the condition of the roads is not good, the taxi -motorcycles often refuse to bring patients to hospital “; / The low level of qualification of the nursing staff in some FOSAs (the chiefs of the FOSA of Bemal, Dokabi, Kadjama, etc. are only first aid care givers)

 Source: Final Evaluation DFID supported Emergency Assistance to Crisis-affected Communities of C.A.R. Phase II
Some efforts made by the consortium have helped to improve the negative points of the mid-term situation. These efforts have proven to be strengths in achieving program objectives.
Mid-term weaknesses Improvements made
IMC's community activities are inspired by Mentor's experience with its network of CHWs
The experiences and expertise of the partners are not implemented throughout the program's intervention area

The taxi-motorcycles that transport the referees to Paoua are paid every Tuesday. A motorcycle taxi from Taley says "[...] Mentor pays us every week and we are happy"
Long delays in the payment of transportation costs (one month after delivery), which demotates the taxi-motorcycles that transport the referred patients

Cordaid is building water points, latrines, placenta pits, etc. in the FOSA of Paoua (Taley, Bemal, etc.), Markounda (Dokabi, Kadjama Kota and Alindao)
Most of the WASH facilities (latrines, water points, handwashing devices, etc.) were not built due to the withdrawal of OXFAM

3.2.3. Consortium coordination with relevant stakeholders
In general, the field surveys revealed a great synergy in the actions of the consortium partners with the other humanitarian actors present the area, which makes it possible to optimize interventions and avoid duplication.
It should be noted overall that the Consortium's NGOs, each in its area of ​​intervention, regularly participate in existing coordination mechanisms (Health and Nutrition clusters) with government actors, UN agencies, international NGOs and MINUSCA.
In Ouham and Ouham Pendé, Mentor's community-based approach is complementary to MSF's activities in that Mentor's community-based actors refer patients to MSF for care, particularly cases of Severe Acute Malnutrition. MSF has also built the tents for the consultations made in the MENTOR mobile clinics. During the Paoua crisis in January 2018, MENTOR coordinated with ALIMA and UNICEF for the nutrition component.
MENTOR continues to work closely with the WHO-led health cluster and the UNICEF-led nutrition cluster. The good collaboration with the Ministry of Health at the national, regional and district levels has been beneficial to the parties in the conduct of several activities: immunization campaigns and IEC activities focused on behavioural changes.
In the case of Bria, the DFID program is complemented by UNICEF support in the treatment of malnutrition, with UNICEF providing the necessary care for the subjects. IMC regularly participates in various meetings in Bria, including the civil-military coordination meeting, the general coordination meeting of humanitarians and the coordination meeting with the Ministry of Health. An appeal was launched to MINUSCA with the effect of organizing regular patrols to facilitate access on the Irrabanda axis. In addition, joint missions were organized with MSF to ensure a humanitarian space. With regard to patient care, discussions with PLAN International and WFP led to the allocation of funds to the management of MAM. NGO Intersos played an important role in caring for IDP camp managers.
In Lower Kotto, notably in Alindao, Cordaid contributed to the joint and coordinated response to the humanitarian crisis during November-December 2018 in collaboration with UN agencies, NGOs, humanitarian groups, the ICRC and MINUSCA. She played a major role in providing logistical support to a large delegation from the OCHA Office. Cordaid also participates in daily crisis management meetings held with all partners present in the field. Collaboration with WFP has been beneficial in the acquisition of adequate nutritional inputs, collaboration with ETC has facilitated the provision of emergency communication equipment. Coordination with COOPI enabled the registration of IDPs. Good collaboration with MINUSCA has been important to ensure the safety of staff, property, the base and the hospital at the height of the crisis.
However, the coordination of the consortium with the Ministry of Health suffers from an insufficiency namely the fact that there is no focal point for the DFID program in the Ministry. Thus, the Consortium does not have a specific interlocutor at the Ministry of Health, making coordination meetings very often difficult.

3.2.4. Adaptation of the consortium to the evolution of the security and political context
The consortium's NGOs are usually notified in real time of a security incident in the intervention areas through their collaboration with the populations and the informants in the field. In the event of a security incident, activities in the area are suspended and the situation is closely monitored until calm returns. For cases of real danger, NGOs opt for the relocation of staff.
This agile management has been used by the consortium on a number of occasions, depending on the security context, resulting in the updating of the action plan of the program during the implementation of phase II.

3.2.5. Managing Oxfam's withdrawal from the WASH sector in early 2018.
Following the release of Oxfam, IMC continued with WASH work in Bria, MENTOR in Paoua and Cordaid in Alindao. However, in agreement with DFID the contingency line for health in Alindao has been used to rehabilitate the WASH infrastructure in Alindao. In addition, Cordaid put its expertise in WASH at the service of FOSA in the sub-prefectures of Paoua, Markounda and Alindao. It has constructed or rehabilitated water points, latrines, incinerators, and placenta pits in eight health facilities supported by Mentor. This permitted the improvement of some indicators related to access to water, sanitation, etc.

3.3 Efficiency
Efficiency analysis assesses how inputs (human, financial, material) have been translated into results and whether results have been achieved at an acceptable cost. In addition, it assesses the extent to which the Consortium's approach and program management have added value or hampered the achievement of objectives.

3.3.1. Optimization of resources
Inputs (human, financial, material) have been used to help reduce the mortality and morbidity of populations affected by the crisis in CAR, particularly in Bria, Alindao, Batangafo, Markounda and Paoua. This through support for construction and rehabilitation, staff and logistical support, drug support and various endowments in the health, nutrition and WASH sectors.
Cost of results
In the spirit of value for money, the DFID program is full of strengths and weaknesses, and also faces risks and opportunities. The data recorded in this table come from the documentary review, interviews and field observations.

Strengths	Weaknesses
Each consortium member makes purchases and recruits staff according to documented procedures; / The international and local human resources put in place by each partner are adequate for the implementation of the activities. The local work force is used to perform hard manual tasks (dig digging, mount walls etc), local staff, national and international staffs are strongly involved; / The Consortium has a full-time Financial Manager; / The establishment of a contingency plan to deal with shocks and unforeseen events; / The constructions and rehabilitations are done according to CAR and international instructions and norms.	Unavailability of VFM indicators due to the non-appropriation of all DALY parameters by NGOs in the Consortium; / Long-term use of rental vehicles is more expensive than buying a car.
Opportunities	Menaces
The presence and availability of key partners that can facilitate the supply of input such as UNICEF, WFP, etc. / Group purchases of medicines for which a pilot market is scheduled for April 2019 are not appropriate as the needs of the partners are not similar and are not expressed at the same time;	Pharmacists have weak capacity to manage drug stocks / Situations of insecurity that lead to resource requirements for the rehabilitation of FOSA. A supervisor of Mentor in Paoua declares "Due to the events, the FOSA and the WASH infrastructures are often vandalized and money is still spent for rehabilitation"

In resource optimization, the Consortium's NGOs face permanent threats such as insecurity that they cannot get rid of, but rather adapt to them. The presence and availability of key partners is an opportunity that can be used to mitigate weaknesses and threats.
Value for Money (VFM)
On an organizational level, each member of the consortium has a policy and procedures for financial management, procurement and prevention and fight against corruption that are indicators of cost rationalization.
For the monitoring of the VFM indicators, the consortium has defined 12 indicators of which only 4 are calculated and available since April for each partner.
These are:

Percentage of satisfied recipients of health care services provided in DFID-supported facilities broken down by level of health service

Table 7 : Percentage of satisfied beneficiaries of health care services provided in DFID-supported hospital facilities
Indicator	FOSA Mentor	FOSA Cordaid	Total
Mid-Term: Percentage of Beneficiaries satisfied with health care services offered in DFID- supported FOSAs	77%	71%	75%
Final: Percentage of Beneficiaries satisfied with health care services offered in DFID-Supported FOSAs	89,7%	100%	94,5%

 Source: Final Evaluation DFID supported Emergency Assistance to Crisis-affected Communities of C.A.R. Phase II
This indicator is obtained from the satisfaction survey conducted in March 20198 and the final evaluation survey of beneficiaries. The table above makes it possible to understand that the satisfaction of the beneficiaries with the services offered in the FOSA increased from 75% to 95%.
Percentage of health facilities and MMUs without a cost recovery system
Table 8 : Percentage of health facilities and MMUs without a health cost recovery system
Indicator	Mentor	IMC	Cordaid	Consolidated
Mid-term: Percentage of health facilities and MMUs without a health cost recovery system	20%	100%	100%	63,6%
Final: Percentage of health facilities and MMUs without a health cost recovery system	20%	100%	100%	63,6%

 Source: Final Evaluation DFID supported Emergency Assistance to Crisis-affected Communities of C.A.R. Phase II
This indicator is derived from DFID program monitoring reports. In PASS's intervention zones in Paoua, Mentor is targeting the poorest populations much more by fully covering the cost of health care. Those who benefit from free treatment are decided on a case-by-case basis in the health facility. The program also offers some recipients the opportunity to come back and pay for care later.
Total budget spent by each partner in year I and II
Table 9 : Total budget of each partner spent by the Consortium's NGOs during Phase II
Indicator	Mentor	IMC	Cordaid	Oxfam	Consolidated 2
Mid-term: Total budget of each partner spent in year 1 / number of beneficiaries directly reached by each partner in year 1	£3.4	£16.6	£5.7	£121.9	£6.5
Final: Total budget of each partner spent in year 2 / number of beneficiaries directly reached by each partner in year 2	Not yet available	Not yet available	Not yet available	Not yet available	Not yet available

 Source: Final Evaluation DFID supported Emergency Assistance to Crisis-affected Communities of C.A.R. Phase II
This indicator has a limit in that the number of beneficiaries of the program is difficult to estimate.
For example, the number of people reached by mass sensitization is difficult to define accurately, the beneficiaries of WASH facilities cannot be accurately defined. As such, it would be important to define an indicator based on targets that can be clearly identified. For example, the consortium can define an indicator as "total budget of each partner spent during the year for the care of children under 5 malnourished".

Level of implementation of activities
Indicator	Activities completed	Ongoing activities	Activities on track	Not applicable or out of program
Level of achievement of activities at mid-term	3%	43%	27%	27%
Level of achievement of activities in the final phase	13,4%	43,3%	30%	13,3%

This indicator is calculated from data in the quarterly program reports and excludes non-program activities. This indicator has been developed in terms of efficiency.
However, in the context of resource optimization, it is difficult to make comparisons of these indicators in time and space to the costs and results insofar as there is no reference system for all members organizations of the consortium (each partner makes his calculations according to his approach). In addition, each partner records expenses in different ways, which makes the consolidation work more tedious. This situation may be justified by the fact that the Consortium only had a Financial Manager at the end of Phase II and therefore did not have the necessary time to put in place a consolidation system applicable to the phase II.

3.3.2. Consortium approach and program management
Mentor's current coordination of the Consortium, compared to that of Phase I, is marked by an intensification of joint monitoring and evaluation. This was favourable to the achievement of the program's objectives and improved the efficiency of the actions as the consortium managed to pool expertise and cover several humanitarian emergency areas in CAR. This good coordination is characterized by:
- Communication is fluid at the coordination level between the lead (Mentor) and its partners (Cordaid and IMC). This fluidity is observed especially in terms of feedback on reports and solicitations from each other;
- Increased collaboration and effective sharing of information to maximize the use of each partner's specific expertise;
- DFID's resource availability and flexibility in adapting resources to different contexts. This allowed the consortium's NGOs to improve their interventions without additional costs;
- Organized reinforcement visits that create room for some exchange of experience. This practice permits partners to gain knowledge from each other and this contributes to cost optimization.
- Quality is jointly controlled by program coordination and government representatives at the local level.

However, the main weakness of the consortium observed at the level of coordination is the multiple changes made at the head of the Consortium: over a period of 2.5 years, three people succeeded one another at the head of the Consortium, and this was not a positive point for the continuity of activities. These large movements at the head of the consortium have hindered the continuation of the VFM indicators calculations initially defined by the consortium. However, the new coordinator continued to monitor progress on the sites and coordinates reporting, general monitoring and evaluation activities using the tool developed by MENTOR, lead of the Consortium. This tool allowed all partners to consolidate data each quarter. The availability of this lead for phase III of the program should bring a new dynamic within the consortium.

3.4 Impact
The DFID program is designed to improve the health situation of the populations affected by the crisis in the targeted areas. It is important to understand the extent to which the program contributes to reducing excessive morbidity and mortality and to analyse the effects and even the potential impact of total or targeted free medical care on the well-being of target populations.

3.4.1. Immediate effects of the program on mortality and morbidity
During Phase II, the DFID program implemented activities related to improving the accessibility of health services, strengthening the health system and improving water and hygiene. and sanitation.
Overall, the number of consultations in the FOSAs supported by the DFID program in Ouham, Ouham Pende have risen and the Basse Kotto experienced an average quarterly growth of 8.2%.
The increase in the use of health services in the program's intervention area has enabled the treatment and prevention of diseases (malaria, diarrhoea, IRA, etc.) as mentioned by women in focus group discussions in Bemal,

"Since our health centre was rebuilt, we have the opportunity to give medical care to our children and no longer fall sick"
Women FGD in Bemal

Similarly, the Nzélété chief of health centre shows that through CHWs / RECOs and UMMs or mobile clinics, populations on the axes that previously had very low access to health care can now benefit from health care (malaria screening and treatment, treatment of acute diarrhoea, health and nutrition counselling, etc.). It is in this sense that he affirmed the following:

"With Cordaid's activities, mortality has dropped because people now have access to quality health care for free"
Chief of Nzélété health center

From the economic perspective, the DFID program has enabled communities to provide the least amount of effort to access health care, saving time and increasing the time needed for agricultural and economic activities. The DFID program relies on local community actors (CHW, RECO, matrons or FPF, supervisors, etc.) and thus offers jobs to the population. Program activities also enabled communities and women specifically to gain new knowledge about managing the health of their children.

3.4.2. Effects of financing systems: targeted and total free access
The DFID program has increased access to primary and secondary health care (with an average quarterly growth of 2.7% as mentioned above). This attendance is on average much higher than the target value (cf. section on effectiveness).
The effectiveness of targeted free or total free is correlated to the security situation. In a stable security situation, the targeted free service empowers the population and strengthens CAR's health care system, while total free degrades the health system due to the lack of recovery of funds and the operation of the COGES and CONGES. In crisis and post crisis: the targeted free helps reduce access and use of health services by vulnerable people while the total free of charge tends to improve the use of health services. The free system should be adopted differently depending on the security situation.
3.4.3. Other effects of the DFID program
Besides reducing morbidity and mortality, the DFID program activities have had other positive effects:
The drop in mortality due to malnutrition among children under 5 years, whose rate was 1%, lower than the mid-term rate (2%) and the target value (15%). However, a "sawtooth" evolution of the number of deaths recorded in the FOSA is to be noted, as shown in the figure below. The observed peaks in mortality are partly related to the insecurity that prevails at times and which weaken activities such as mobile clinics, or which prevents access to FOSA. The peaks are related to the fact that the populations die mainly in the hospitals where they arrive in very difficult conditions, as mentioned the Chief doctor of Alindao District.

Graph 3 : Evolution of the number of monthly deaths in the FOSA

 Source: Midterm Evaluation DFID supported Emergency Assistance to Crisis-affected Communities of C.A.R. Phase II
- The project allowed communities to have at least one trained person on primary health care. The consortium works with local actors (CHW, RECO, FPF, matrons, etc.) who are trained on basic health concepts. Thus, populations have close to them at least one health resource person;
- The project has created jobs for local people: they are field supervisors and CHWs, RECOs, FPFs, matrons, taxi-bikes, etc. to whom the DFID program has been an opportunity for a paid employment. In addition, companies contracted for infrastructure construction are required to use local labour;
- The proximity of CHW / RECOs and UMMs to populations allows time savings: populations living 30 to 45 km from the nearest FOSA now have on-site screening and treatment of diseases through CHWs and consequently save time that would allow them to carry out their economic activities

"[...] the women who live in the axes have the care on the spot and this gives them time to attend to other occupations like the farms and the market"
Chief of Manda village (Markounda)

The program has had a social impact on community life in that the decline in mortality and morbidity has reduced the opportunities for witchcraft charges in a context where people see the disease as the result of occult practices. It is in this sense that the CHWs of Paoua emphasized that:

"The number of cases of witchcraft charges has dropped in the village because children are falling less sick [...]"
CHW FGD in Paoua

On the other hand, the free care practiced in certain areas such as Alindao has been a threat to social cohesion: the support of the internally displaced people hosted in the Christian sites in Alindao has given Muslims living in communities a feeling that they are put aside.

3.5 Sustainability
The activities carried out under DFID Phase II are largely implemented in the context of a humanitarian emergency. This does not preclude questioning the sustainability of the installations put in place, the knowledge acquired and the recording of the effects of the program over time.

3.5.1. Sustainability of effects at community level and on the national health system and gaps
In the very short term, it is clear that the DFID program has many effects (improving access to health care, reducing malnutrition, broadening immunization coverage, improving knowledge of hygiene rules, increasing attendance rate of CPN services, etc.). Several facts demonstrate a high probability of continuity and sustainability of the effects of the DFID program.
The transfer of competence at the local level:
- The project relies on CHWs / RECOs, matrons / FPFs recruited from the villages and trained on malaria and diarrhoea screening and sensitization of the populations;
- Women in the communities claim to have gained new knowledge since the consortium partners started interventions in their respective areas: hand washing, cleaning around houses, feeding children, etc.;
- Possibility of transferring knowledge of qualified Cordaid health personnel to other local staff of the FOSA.

Continuity and infrastructure maintenance
- The establishment by Cordaid of the management committees of the water point made up of residents; the training of repair men equipped with toolboxes for pumps for example 1 in Paoua and 1 in Taley by Cordaid are all positive points to ensure the sustainability of WASH infrastructures;
- The water point management committees are equipped with maintenance kits, which allows the water point to be maintained even in the absence of the program.

The high involvement of local actors
A memorandum of understanding is signed between the consortium, chiefs of FOSAs and local leaders in the choice of the site and the realization of WASH infrastructures;
In addition, it is worth noting that:
- Qualified Cordaid health personnel could transfer knowledge to other FOSA staff who can continue. Similarly, the transmission of knowledge through supervision by qualified personnel and training done by IMC and MENTOR is likely to have lasting effects;
- The program's strategy aligned with health promotion benchmarks in CAR, namely the HRP and the Ministry of Health's strategy; the program is implemented in HRP clusters and emergency areas. It is aligned with the national health system through the use of ministry tools and adaptation of indicators to the SNIS.
Sustainability also materializes through outreach and training on the one hand, and the collection and sharing of program data with the ministry and partners in the field. Indeed, RECOs, CHWs, FOSA staff trained, CONGES and COGES must ensure the sustainability of the program's actions. The data collected under the program will serve as a database for the state to feed the health information system. During the interviews, it was noted that some COGES and CONGES are already developing their action plans and producing reports, while others do not because of their low level of education.

3.5.2. The gaps to be filled:
Shortcomings that hinder the sustainability of the effects of the DFID program were identified:
- Cordaid in its approach assigns qualified and well-motivated staff in the FOSA, which is interesting for the delivery of quality care to communities. However, it is still left to see whether after the program, the ministry will be able to take over and continue to paying these staff as Cordaid, or simply, are they ready to stay there even if conditions change?
- The risks of destruction of infrastructures due to the volatility of the security situation;
- The low number of health personnel assigned to the communities by the Ministry of Health and the recruitment of health staff from Bangui.
- The absence of a well-designed exit strategy is an obstacle to sustainability as the free practice risks plunging people into a situation of eternal assistance. However, without being included in an exit plan, the choice of CHWs, RECOs and women focal point among the communities suggests that the project's achievements will be long beneficial to the communities even if the program ends. Nonetheless, the program will have to design an exit plan that contains:
- Promoting community resilience measures to natural shocks such as drought through the development of Income Generating Activities (IGAs);
- Promoting good practices in health, hygiene and sanitation in schools for schools.

3.5.3. The advantages and disadvantages of the PBF approach
Advantages
The PBF approach has many advantages in the context of humanitarian crisis in the program areas. Overall, it makes health care more accessible to people living in precarious socio-economic conditions. The main advantages are:
- The DFID program contributes to increase the PBF subsidies of the supported health facilities;
- Strong involvement of caregivers
- The actors are solidarising and pooling their efforts for the accomplishment of their respective missions.
- The PBF approach is conducive to infrastructure development
- The focus is on overall performance. The allowances of the staff of the FOSA are used to support the vulnerable.
Disadvantages
Currently, the socio-economic levels of the crisis-affected areas do not allow the implementation of the PBF alone; the PBF should be supplemented with targeted free access. The population is extremely poor. A policy that would require drug cost recovery would result in people not going to health care workers in the event of illness, which would reduce access to health care. The populations would thus recover drugs of dubious origins bought on the street and relatively cheaper. Mortality and morbidity rates may increase. Drugs in the PBF system are not controlled and serious health consequences can follow.

3.5.4. Readaptations to be done under the PBF
Given the shortcomings of the PBF approach in some of the areas of intervention of the Consortium, adaptations are useful for optimizing the strategy. An evaluation of the funding system commissioned by the Consortium is underway, which will lead to more effective corrective actions.
However, it should be noted that the consortium will have to take ownership of the tools and acquire the qualified personnel needed for the funding system, not to mention the security situation.
The field observations also make it clear that the adoption of the financing plan will have to take into account the situation of poverty of the beneficiaries and the difficulties of the CHW / RECO whose equipment and working materials are not always sufficient.

"If we depended solely on the recoveries that patients should make and the PASS no staff should still be at the FOSA today. Imagine when there is a shortage in drugs, we make prescriptions to patients who go to the market to get drugs even though they are not controlled and come from BOKOLOBO, but most patients do not manage to buy drugs prescribed that cost less than 300 FCA. We understand them because there is insecurity, they do nothing for the moment and even if security is restored, it takes a little time for the population to acquire a minimum of financial autonomy. For the subsidies of the PASS it is even more serious, we have the arrears of 6 months. As usual, the day the subsidy arrives would be at most the equivalent of a month. But for us who are supported by DFID, our monthly subsidy is better than the non-supported FOSAs. Our PASS grants enable us to strengthen our infrastructure and motivate staff. For example, the maternity that we have just completed is largely due to the total gratuity we apply. Thanks to CORDAID, we receive our monthly salaries without delay and the staff is motivated to be constant at the FOSA "
Un staff de FOSA à Basse Kotto

In addition, the program should also draw on the EU's Bekou Fund approach, which requires the purchase of good quality approved drugs.
3.6 Accountability
Accountability is the criterion of a program that provides reassurance that this program consults and reports to the various stakeholders in the context of its activities.

3.6.1. Accountability to beneficiaries and to national and local authorities
During the field visits, satisfaction was noted with the tools and means used by the consortium's NGOs to ensure the visibility of the program. The evaluation team observed the FOSA and interviewed the beneficiaries and stakeholders about the accountability of the DFID program as shown in the figure below.
Graph 4 : Percentage of beneficiaries who feel that consortium NGOs are communicating with them and are open to receiving complaints and grievances

Source: Final Evaluation DFID supported Emergency Assistance to Crisis-affected Communities of C.A.R. Phase II

This shows that most beneficiaries surveyed (95%), which is an improvement over the mid-term evaluation (84%), believe that the consortium's NGOs communicate with them and are open to receiving complaints and claims.
Several means are used in the program to ensure accountability to beneficiaries, national and local authorities and donors. Among others, the following channels are used:
- Suggestion boxes are installed in some FOSAs supported by the program;
- The toll-free number 4022 managed from the IMC headquarters in Bangui;
- Community contacts through meetings in the community and in the FOSA;
- Community radio spots;
- Banners indicating total free and information on the project are made and posted all-over in the FOSA and NGO bases;
- Communities are involved in the selection of the members of the CGPEs. Similarly, the perspective of the beneficiaries is taken into account through meetings in the community and in the FOSA;
- CSA and RECO reports validated in the presence of community leaders.

The big innovation at Mentor is the posting in all offices and FOSA of Mentor of a toll-free number (4077) by which people can contact the Mentor team for free for cases denunciations and other concerns.

The DFID guidelines in terms of visibility are respected: the UK / DFID logo is visible on the sites where the program operates, on all printed documents and at public events such as trainings and workshops. The activity reports of the CHW / RECO in the villages are validated after consultation and signature of the local leaders. The management of FOSA facilities and medicines integrates local populations through the COGES. In addition, joint supervision with health staff gives the program greater credibility vis-à-vis the public authorities.
The consortium involves the local administrative, communal and traditional authorities in the community activities, as was the case with the MoU of water points that bear the signature of these local actors. In addition, it was observed in the field that the distribution of bicycles to the ASCs of Markounda was made in the presence of the prefect, the mayor and traditional leaders, as shown in the image to the left.

3.6.2. Value for Money Considerations in Program Management
As mentioned above (confers efficiency section), although the Consortium has optimization assets (presence of a full-time Financial Manager, procurement and recruitment of staff according to documented procedures, etc.), the optimization of resources suffers from the weak application of the VFM due to the low control of the DALY metrics by the members of the Consortium. It should be noted that meetings have been organized by the Consortium to discuss the VFM.
The last meeting that took place during the month of February in the IMC offices made it possible to reflect on these metrics, as shown by the image of the workshop flipchart below beside.
The presence of a full-time Consortium Financial Manager and the strong engagement of partners for the VFM are signs of a good prospect for value for money and better accountability to DFID in the next phase

3.6.3. Importance of remote management tools
Due to the chronic insecurity in some areas of intervention, remote management is necessary to ensure the continuity of the activities of the program.
IMC has implemented a remote management tool that can be improved: the back stock. It consists of verifying drugs through COGES that move and keep them after cross-checking by the community. These measures help to ensure that populations have received the drugs given that they often have minutes. The risks of theft and diversion can be envisaged.
For Cordaid, when insecurity becomes severe, Cordaid informally asks for support from the District and MSF to deliver drugs to the localities when field staff cannot move because of insecurity. However, the leaders of the different armed groups are consulted either directly or through intermediaries to solicit health interventions when security is problematic.

3.6.4. Weaknesses of program accountability
Some weaknesses and threats to the accountability of the program have been identified. It should be noted that:
- MENTOR's remote management practices have not been observed;
- The toll-free numbers are always displayed inside the FOSA not outside.

3.7 Accessibility
The DFID program places special emphasis on community accessibility to health care. MENTOR and IMC's extensive network of CHWs, Cordaid RECOs, UMMs or mobile clinics, and matrons or FPFs are the elements adopted to improve accessibility to health care.

3.7.1. Accessibility and well-being of the populations
Overall, the project has allowed some people to receive health services that they could not access before. In the 2016-2018 period, this resulted in an overall increase in consultation rates in the Mentor, Cordaid and IMC facilities, and specifically for women and children under 5 (see Graph 1). This high accessibility has resulted in a high demand for medicines, particularly in the FOSA of Alindao where Cordaid has had to cope with an influx of internally displaced people who forced them to move to total free care. Thanks to the endowments of WASH infrastructure, people now have access to well-equipped toilets, drinking water points, although defective for some and insufficient overall. The accessibility of health services can be shown by the following facts:
Breaking of geographical barriers: Thanks to the network of CHWs and RECOs, populations furthest from FOSA now have the possibility of accessing primary and secondary health care. This results in people gaining time that they can allocate to other activities (economic activities, education, childcare, etc.). The presence of these agents in communities can be seen as bringing health care closer to the people, which is a clear advantage for people with disabilities;
"We stayed here a long time and no one helped us. But Mentor arrived and told us that we could go to the health centre for treatment even without money. [...] God sent them / FGD with men in Kadjama Kota

Breaking Financial Barriers: The DFID program benefits all people regardless of income level. Excluding some specific services such as vaccines for children, CPN services for women, activities under the DFID program benefit everyone regardless of income level, ethnicity, etc. A beneficiary in Kadjama Kota during FGD affirms as opposite;
"Since Mentor gives drugs to the village, women no longer think about witchcraft when the child is sick. " / FGD with women in Bemal

Breaking cultural barriers: the sensitization of the populations made it possible to break with certain cultural habits which consist in seeing in the disease witchcraft rather than a dysfunction in the organism. They have reduced their propensity to use traditional medicine to the benefit of the FOSA.
Breaking down security barriers: People fearing kidnapping and violence can now benefit from counselling and health care in their communities through mobile clinics and CHWs, RECOs, Matrons and FPFs.

3.7.2. Factors preventing or restricting access to health care services
Several factors may weaken the accessibility of populations, including minorities and the most vulnerable.
- Poverty linked to poor livelihoods that prevents people from obtaining drugs at the market in the event of a breakdown in the FOSA;
- The insecurity preventing from time to time the different Christian and Muslim religious groups to cross the respectively Christian Muslim areas to benefit from health care. Areas at risk include North Paoua, Kongbo and Pavica (Alindao), Ouin and Kakouda (Batangafo), the southern axis of Bria;
- The long-distance displacement to cover the FOSA combined with the poor road conditions (to go to Poudjio by vehicle located 55 km from Alindao it takes 3 hours or 18.3 km / h when without stop). The population and the field staff are concerned about the distance to go to get treatment for certain diseases that could be done in their villages;
- The low coverage of the Alindao-Mingala program area consisting of 27 FOSA of which only 6 are covered;
- Infrastructure drilling, ambulance (HDA), and breakdown of other equipment in the communities;
- Absence of water points in several villages for example in TAMBIA where there is no drilling.

Some factors, however, have contributed to improving the accessibility of DFID program services:
- UMMs / Mobile clinics, CHW / RECO networks and other community agents enable partner NGOs to reach populations furthest from FOSA;
- The free practice practiced by the NGOs of the consortium contributed to the elimination of the financial barriers, thus increasing the attendance of the FOSAs in Paoua, Bria and Alindao.

Strategies can be jointly developed to address barriers to accessibility:
- Recruiting more competent personnel to work in the FOSA;
- Develop the infrastructures (FOSA, products, materials) in the FOSA and in the communities;
- Continue with total free care;
- Coordinate the various interventions of the NGOs in the FOSA to optimize the use of the resources (this is the case of MENTOR which must coordinate with the PASS in the Ouham-Pendé);
- Equip ASCs and RECOs with equipment and working materials (means of transport, work dress during rainy seasons and dry seasons…).

3.8 Quality
In terms of services offered, quality is a characteristic for the satisfaction of the beneficiaries. The DFID program places special emphasis on the quality of services and the quality of the intervention, with a view to improving the health status of the population and reducing mortality. During this evaluation, issues related to the quality and acceptability of the services offered were addressed.

3.8.1. Quality of the intervention
The quality of the intervention can be analysed in terms of selected and reported indicators, methodology, staff competence, team building and gender.
Indicators and methodology: the program indicators are organised into four outcomes and effectively measure the scope of activities in the logical framework. Rehabilitation of the target values ​​and calculation methods of some key indicators (number of inhabitants for 01 CHW which has been reduced from 3700 to 1000, the utilization rate which has been reduced to 0.6 consultation / staff / year) in the Central African context was made. However, the logical framework of Phase II is deficient due to lack of specific WASH objectives. This implies a low consideration of WASH indicators in the logical framework of the program.
Staff competence: the coordination of the consortium is made up of qualified personnel with proven expertise (Coordinator of the Consortium, Medical Coordinator, etc.). The consortium has a Senior Financial Manager who works full-time in Bangui, which is likely to contribute to the quality of financial reporting. At the operational level, the NGO bases (Alindao, Bria, Paoua) are managed by qualified expatriate staff. Partners work with community workers who have been trained on the tasks they have. The capacities of these agents are strengthened through joint supervision and workshops organised for this purpose. Unlike CORDAID, IMC and Mentor use community health workers, who have limited capacity, but benefit from regular formative supervision
Constitution of teams and gender: the NGOs in the consortium demonstrated their ability and willingness to involve the community in its approach; ASC / RECO, FPF / matrons are recruited from the community after validation of good morals by the people and village leaders. The constitution of the field teams facilitates the transmission of the messages in the sense that the community agents express themselves perfectly in "Sangho" and in other local languages. In addition, even in a situation of insecurity, people move to the same localities as the CHWs, which helps to maintain the continuity of the CHWs' services to the beneficiaries. With regard to gender, it should be noted that although CHWs and RECOs are male and female, and program beneficiaries are not treated by gender. In addition, consortium NGOs have established a network of FPFs and matrons who work with women in the communities.

3.8.2. Quality of services
The quality of the services offered by the program can be analysed in terms of ethics (beneficence, respect for the individual, justice) and from the point of view of the acceptance of services at the community level.
Beneficiary: surveys and key informants helped to address issues related to ethics.
Benefit: the care and services provided to the populations by the DFID program, given the evidence on the ground, has not only improved the health well-being of the populations, this is manifested by the satisfaction expressed by the patients surveyed vis-à-vis - services of the DFID program. The following graph shows overall satisfaction of the beneficiaries of the quality of care, latrines and water in the FOSA and sensitization sessions. This overall satisfaction is increased compared to the mid-term situation. This can be attributed to the efforts made by the consortium to implement WASH infrastructures in FOSAs supported by the program.
Graph 5 : Percentage of beneficiaries satisfied with the services offered by the DFID program
Source: Final Evaluation DFID supported Emergency Assistance to Crisis-affected Communities of C.A.R. Phase II
Respect for the person: as part of the DFID program, all activities are implemented taking into account community leaders and local leaders who, in one way or another, are guarantors of the protection of populations. All reports and results related to the program are shared, discussed and validated with local leaders.
Justice: the field surveys have revealed that, apart from the context of targeted free access, the populations benefit equally from the services and care of the DFID program. However, interviews with people in Alindao reported discrimination between Christians and Muslims in the provision of care. This information was cross-referenced with other sources (Cordaid staff, COGES members, FOSA staff) and it turned out that there is no problem of discrimination, but rather a problem of communication with the beneficiaries. Thus, it is important for Cordaid and its partners to put an emphasis on communication with communities.
DFID program activities have been accepted by local populations. Indeed, the NGOs of the consortium have previously presented the activities of the DFID program to leaders and community leaders who have given their no objection. This reinforces the idea that program activities respect local customs. Interviews with village leaders revealed that, overall, the activities carried out in their communities are socially acceptable, and they hoped that the program would continue for future years. The head of Manda village in Markounda had this to say;

"Everything Mentor has done in our health centres is good for our people. [...] they respect our customs well "
Chief of Manda village in Markounda

In terms of the field work and the analyses, it appears that several factors positively or negatively influence the quality of the program's activities and the services offered to the population.
- Factors improving the quality of program activities and services offered:
  - The use of the image boxes of the ministry and national medical protocol;
  - Linking program activities with the HRP of CAR;
  - Indicators adapted to CAR's SNIS;
  - Purchase of drugs from accredited vendors
  - Supervision and capacity building of CHWs.

The main obstacle to the quality of care is the low level of qualification of the nursing staff in some FOSA (the heads of the FOSA of Bemal, Dokabi, Kadjama, etc. are only first-aiders or carers).

3.10 Level of taking into account the mid-term recommendations
The mid-term evaluation clarified weaknesses and proposed corrective or adaptive actions for Phase II. It is therefore important to know if these recommendations have been taken into account so far.
Mid-term recommendation	Taken into account	Comments
Reduced delays in the payment of motorcycle taxis for referrals	Yes	The transportation costs for referrals are paid to motorcycle taxis every Tuesday and not once a month
Sensitization of the heads of FOSA on the need to make the counter-referrals	Yes	Heads of FOSAs say they have already been sensitized
Recruitment of a full-time senior Financial Manager for the consortium to be based in Bangui	Yes	The Senior Financial Manager of the consortium is currently in Mentor
Capacity building of CHW / RECO on referral procedures and reporting	On going	//
Capacity building of the coordination team and partners on VFM	On going	At the level VFM, efforts are made by the partners especially in terms of added value of the program. However, there is need to make available a VFM methodology document with useful metrics ideas for comparisons (a practical guide and application guide).
Creation of a framework for collaboration with the Ministry of Energy through its Department of Water with regards to water points	Not yet	//
Improved budget structure so that the level of detail is the same for all partners	Not yet	This is one of the projects of the Senior Financial Manager of the consortium
Develop a VFM methodology document with useful metrics ideas for comparisons (a practical guide and application guide)	Not yet	//

4. Conclusions
The objectives initially set were achieved overall despite the existence of endogenous and exogenous factors that affected in one way or another the performance of the program as a whole as analysed by the evaluation criteria.
The DFID program in terms of its activities and targeted areas is consistent with the PRH 2017 of Central Africa. Useful tools and performance measurement indicators fit well with the national strategy of the Central African health system.
The activities carried out have made it possible to achieve the assigned objectives despite some shortcomings that are inherent not only in the Consortium's strategy, but also to other exogenous factors that the partners cannot control. The way in which consortium NGOs deploy in the field allows for good collaboration with other humanitarian actors and avoids duplication. The DFID program has limited value-for-money limits, but it should be noted that the Consortium is aware of these limitations and laid the groundwork for greater efficiency with the hiring of a time full Financial Manager and programming workshops on the VFM.
The effects of the program are perceptible at the social (reduction of accusations of witchcraft), and economic levels (the level of income is no longer a constraint to access to health care). In addition, people who are afraid of the security situation can benefit from health care and sensitisation without necessarily having to travel long distances. The free care practice could create social tensions if it is not well explained to communities.
The involvement of locally recruited community actors and local authorities are facts that contribute to the sustainability of the program results. It is the same with the training of management committees of water points, repairmen and the equipment of these actors with repair kits for water points.
The program has developed communication channels with beneficiaries through toll-free numbers, banners, visibility of the donor, and validation meetings of monthly reports held with local stakeholders. In addition, joint supervision with health staff increases the credibility of the program vis-à-vis public authorities.
The services that are offered to the population comply with humanitarian standards and respect local customs. The good quality of services is also perceived through the respect of ethics. However, health personnel do not always have the required qualification in view of the level of the FOSA.
5. Recommendations
Based on the results of the study, recommendations can be made to the key stakeholders of the DFID program and can be used to formulate the third phase of the program:
Recipient of the recommendation	Details on recommendations
Consortium ONGs	To improve on the effectiveness and efficiency of the program: / Implement Mentor's ASC approach in Lower Kotto to fill the gap at the community level; / Implement the Cordaid health system strengthening approach in MENTOR and IMC FOSA; / Make an evaluation of all the modalities related to the realization of the WASH works and budget it for the phase III by capitalizing on the realization of the works WASH in progress; / Define within the consortium a common methodology for recording expenditures; / Inform all target values ​​of Phase III logical framework indicators that were poorly documented in Phase II; / To improve on the impact of the program: / To equip pharmacy managers with inventory management; / Define a stock of drug alert to avoid / reduce stockouts; / Adopt a free system taking into account the security situation / To improve on the accountability of the program: / Discuss with the Ministry of Health to identify within it a focal point for the DFID program / To improve on the quality of the program: / Set up an early warning system for the rapid detection of urgent cases of disease in the axes and refer them quickly. / To improve on the sustainability of the program: / Develop an exit strategy / Advocate with the Ministry of Health for the assignment of public health staff in the program's FOSAs; / Advocate with the Ministry of Health, the Global Fund and Humanitarian Coordination actors to set up a supply system for drugs and vaccines in the CAR; / Promote community resilience measures to natural shocks such as drought through the development of Income Generating Activities and strengthen coordination with other partners working in this area. / To improve on the accessibility of the program: / Develop social cohesion activities (contests, sports, cultural days, etc.).
Mentor and IMC	To improve on the effectiveness and efficiency of the program: / To sensitize the heads of FOSA on the necessity to make the counter-referral; / Provide community relays with mobile and work equipment (cycling, work wear in rainy seasons and dry seasons…); / To improve on the accountability of the program: / Post the toll-free numbers outside of the FOSA (Mentor). / To improve on the accessibility of the program: / Mentor will need to learn from IMC remote management tools to manage the cases where the FOSA are inaccessible
Cordaid	To improve on the effectiveness and efficiency of the program: / Learn from IMC remote management tools (Pavica/Kongbo). / To improve on the impact of the program: / Reinforce the sensitisation of the population on the free system practiced. / To improve on the sustainability of the program: / Reflect on the transfer of knowledge of qualified health personnel to first aid workers and RECOs.
Mentor (consortium lead)	To improve on the relevance of the program: / Share with the ministry the project proposal to decide on the activities to be carried out by the consortium and the targeted areas / Create a framework for collaboration with the Ministry of Energy through its Department for Water as part of WASH activities. / To improve on the effectiveness and efficiency of the program: / Improve the budget structure so that the level of details is the same for all partners; / Include expenses for supervision missions for authorities of the Ministry of Health in the budget of phase III travel; / Create a framework of collaboration with the Ministry of Energy, Mines and Hydraulics through its Department for Water. (repeated recommendation) / Put in place stabilisation mechanisms for the position of Coordinator of the Consortium over a long period
Bailleur	Strengthen the capacity of the coordination team and partners on VFM / Providing the Consortium with vehicles dedicated to the DFID program

6. Appendices
Annex 1 : ToR
See attached

Annex 2 : List of persons interviewed
Annex 3 : Tools
See attached
Annex 4 : Documents Consulted
Rapport de la visite de l'équipe de renforcement
Rapport d’évaluation finale Phase 1
Rapport Enquête de Satisfaction
Rapports de suivi trimestriels
Documents des ateliers sur le Value for Money
Base des données sur le Value for Money
Documents sur le DALYs
DFID Consortium Full Proposal
Logical Framework-Final
DFID Consortium Realigned Budget
Updated Log frame data