## Annual Review

Title: Financial Sector Deepening Zambia (FSDZ)
Programme Value £ (full life): 22,950,000		Review Date: June 2019 (for review period March 2018 – April 2019)
Programme Code: 203000	Start Date: May 2013	End Date: March 2021

Summary of Programme Performance
Year	02/2014	11/2014	11/2015	11/2016	07/2017	12/2018	06/2019
Programme Score	B	A	A	A	A	A	A
Risk Rating	Medium	Low	Medium	Minor	Minor	Moderate	Moderate

DevTracker Link to Business Case:	https://ec.vault.dfid.gov.uk/OTCS/cs.exe?func=ll&objaction=overview&objid=4320471 / https://ec.vault.dfid.gov.uk/OTCS/cs.exe?func=ll&objaction=overview&objid=30266711
DevTracker Link to Log frame:	https://ec.vault.dfid.gov.uk/otcs/cs.exe/open/14778608

# A. Summary and Overview

This annual review covers the 12-month period April 2018 – March 2019. The Annual Reviews for this programme have historically taken place annually in November, eight months after the end of the FSDZ financial and reporting year. This year the review date was brought forward to better align with the FSDZ reporting cycle (which runs from April to March) and reduce time lag between results and DFID review.

## Description of programme

The £22.9 million Financial Sector Deepening Zambia (FSDZ) programme aims to expand financial inclusion in Zambia. This means increasing the number of poor Zambians who have access to financial services to enable them to save, borrow, receive insurance coverage, make payments, or use mobile money. To achieve this, the programme takes a ‘whole system’ approach and seeks to tackle constraints at different levels, from advising policymakers on financial sector reforms, to partnering with local insurance firms to provide weather index-based insurance for smallholder farmers.

Financial exclusion in Zambia remains high. Nationally, it has reduced from 62% in 2009 to 41% in 2016. However, in rural areas 50% of adults still have no access to any financial service, whether formal or informal. Financial exclusion is higher for women (43%) than men (39%), and for those working in the informal sector than formal wage earners.

The Government of Zambia has shown commitment to expanding financial inclusion and with extensive support from FSDZ launched the National Financial Inclusion Strategy in 2018 and established a new Financial Inclusion Unit in the Ministry of Finance to deliver on this strategy. The aim is to have an overall increase in financial inclusion from 59% to 80%.

As well as partnering with government, FSDZ works with a wide array of financial service providers, regulators, civil society organizations, market infrastructure actors, consumers and other stakeholders to spur their engagement in inclusive finance.

FSDZ was established by DFID and run as a consultant-led model until April 2016, where the status was changed to a local non-profit company led by an independent board made up of mostly Zambian financial sector specialists, policymakers and private sector entrepreneurs. During the reporting year a new indicator was added to the log frame to capture the institutional development of FSDZ.

The target impact of the programme is ‘expansion in income opportunities and reduced vulnerability by poor men and women in Zambia’ as a result of improved financial inclusion.

FSDZ developed a new 5-year strategy in November 2018 (covering the period 2019 – 2024). This was a positive development as it demonstrates FSDZ’s increasing independence as an independent body beyond a DFID programme.

The strategy identifies three ‘framework themes’. These are areas of focus that are pan-market and span all FSDZ efforts to support financial inclusion. The three themes are: digital financial services, policy and infrastructure, and financial education and consumer protection.

Underneath the framework themes are five ‘field themes’. These address special products or unserved groups. The themes are:
- Informal finance, especially savings groups, for entry points into financial inclusion,
- Inclusive insurance for risk management, particularly for low-income households,
- Inclusive enterprise finance for medium and small enterprises, particularly for microenterprises,
- Rural and agricultural finance for rural people, and
- Financial inclusion for women and young people.

FSDZ has integrated gender and social inclusion throughout its programme activities and disaggregates results data by gender where possible.

In March 2018 ‘gender and disability integration’ was added to the programme workplan as an activity in its own right. During the reporting period, the M&E team reviewed the policies, procedures and manuals of FSD Zambia and incorporated gender and disability and made recommendations for how gender and disability could be integrated. FSD Zambia also co-financed and co-led the first ever Southern African Development Community (SADC) gender workshop on financial inclusion for women in Johannesburg South Africa

There is also a suite of bespoke programme initiatives that seek to enhance equity in financial inclusion. These are:

- Increasing financial inclusion for women and youth;
- Financial education for youth; and
- Digital financial inclusion for female smallholder farmers

Summary supporting narrative for the overall score in this review

In line with the 5-year strategy, FSDZ delivers activities against the five thematic areas above. The Annual Review in 2018 recommended that the programme log frame be restructured around these themes to better capture the breadth of work underway by FSDZ.

Unfortunately, the log frame refresh was not completed in time for this review and so some activities underway by FSDZ have not been counted towards the score, whereas some have been counted more than once. It is vital that this is now completed in the near-term to ensure performance metrics and targets are in place to guide interventions and capture the full value of the programme.

Table 1 summarises the output scoring for this annual review. Overall the expectations were met, and the programme scores an A in this review. The programme is broadly on track at the outcome level and targets set out in the original Business Case have already been exceeded.

Table 1. Summary of output scores
	Weight	Score	Summary
Output 1	10	C	Outputs substantially did not meet expectations / The targets for both the number of financial sector stakeholders using new data (1.1) and the target number of beneficiaries receiving financial information (1.2) were substantially missed.
Output 2	20	A	Outputs met expectations / The target for number of institutions with improved capacity was moderately exceeded (2.1). The target for number of government bodies with improved policy and regulation (2.2) was poorly defined, but a range of activities were implemented.
Output 3	20	A	Outputs met expectations / The targets for both 3.1 and 3.2 were both exceeded. However, the target for 3.2 was poorly defined as it was not clear how many ‘infrastructure functions’ were targeted.
Output 4	20	B	Outputs moderately did not meet expectation / Whilst three financial service providers were supported to build capacity under 4.1, the target for the year was zero and so FSDZ was not given a stretching objective. / Under 4.2 the target number of community-based financial institutions providing financial services to poor women and men (i.e. savings groups) was missed by 50%.
Output 5	20	A	Outputs met expectations / Output indicator 5.1 substantially did not meet expectations (by 50%) but output indicator 5.2 exceeded expectations
Output 6	10	A	Outputs met expectations / The target for innovations and pilots (6.1) was exceeded, but some activities have also been counted towards other output areas. The targets for institutional development (6.2) and new funding (6.3) were met.
Total	100	A

Recommendations for the year ahead

- The log frame refresh recommended in the 2018 annual review was not completed on time for this review. A light touch refresh was conducted (adding output 6 for example), but it was not far-reaching enough to capture all of the programme activities. Several of the indicators used for this review were poorly defined and lacked proper targets (e.g. 3.2 and 4.1). A full review of the log frame is required to align programme reporting with the 5-year strategy and ensure resources are being allocated in line with the strategy. (FSDZ, by December 2019)
- FSDZ should continue to lobby the Government of Zambia to meet its legal obligation to make the premium payment owed to the insurance provider for weather index insurance. FDSZ should continue to monitor this and keep DFID fully informed. (FSDZ, by December 2019)
- FDSZ should convene a donors’ group, bringing together DFID with the other funding partners on a regular basis. This will improve collaboration between donors and aim to reduce the need for separate donor requests. (FSDZ, by December 2019)
- DFID should continue to monitor the performance metrics set out in the Special Conditions of the FSDZ Accountable Grant. (DFID, on quarterly basis)
- Following completion of the independent governance review, the FSDZ Board should clarify their role in securing external funding for FSDZ, drawing on their extensive expertise and professional networks. (FSDZ Board, December 2019).
- The FSDZ Board and Programme Investment Committee should conduct an annual self-assessment to appraise their performance. (FSDZ to commission first self-assessments by March 2020)
- FSDZ should continue to improve its financial management, particularly forecasting, in order to reduce variances. (FSDZ, March 2020)
- FSDZ should integrate safeguarding into the overall risk management process, including the delivery risk chain mapping. FSDZ should also include safeguarding capacity assessment in the due diligence process and grant manual for their delivery partners. (FSDZ, December 2020)
# B: DETAILED OUTPUT SCORING

## OUTPUT 1
Output Title	More and better industry data and public information on the financial sector is available and used by stakeholders
Output number per LF		Output 1	Output Score	C
Impact weighting (%):		10%	Impact weighting % revised since last AR?	No

Indicators	Milestones for this review	Progress
1.1 Number of financial sector stakeholders using new industry data and public information products	238 (100 for year)	Outputs substantially did not meet expectation / 160 (22 for year) (22%)
1.2 Number of target beneficiaries receiving financial education	Total: 251,023 (56,000 for year) / Women: 152,372 (28,000 for year)	Outputs substantially did not meet expectation / 225,938 (30,915) (55%) / 163,278 (26,540) (94%)

### Supporting narrative for the score

Overall the output has scored a C. The targets for both the number of financial sector stakeholders using new data and the target number of beneficiaries receiving financial information were substantially missed.

FSDZ note that some interventions contributing to this output had a late start (for example the Zazu financial education intervention) or did not start during the reporting period as planned (particularly FIT in Luapula, due to substantial delays with Innovations for Poverty Action in setting up the baseline for the randomized control trial).

Indicator 1.1

This indicator measures the extent to which financial sector stakeholders are using new industry data and public information as a result of FSDZ activities. Despite a wide range of activities and partnerships, only a quarter of the log frame target number of stakeholders for the year was achieved.

Activities that contributed to the results included:
- Support to the Bank of Zambia to conduct a diagnostic study of SMES (not yet published).
- Support to the Bank of Zambia to conduct sex-disaggregated data analysis for financial institutions. FSD Zambia assisted the Bank of Zambia in the first gender assessment of regulated financial institutions including staff, management, and clients, which provided important results affecting product services. A key set of findings were that female clients save more despite earning less, are more loyal as clients, and are better at repaying loans on time, by up to 17% more than males.
- Support to Zambia Information, Communication and Technology Authority (ZICTA) to plan and implement the National ICT study. FSD Zambia will support ZICTA to disseminate the findings from the ICT study in 2019.
- Partnership with the University of Cape Town to host research data and information on the ‘DataFirst’ website. Through this website, research data from FSDZ supported FinScope, Geospatial and Financial Diaries studies have been shared enabling access and use by researchers, NGOs and private sector companies.
- A series of dissemination events for key research findings and lessons learnt from pilots to deliver financial sector information and data to the financial sector stakeholders. For example, during the period under review, FSD Zambia hosted a dissemination event on the results from the Zazu Africa pilot with 42 attendees (see indicator 1.2).

Indicator 1.2

Indicator 1.2 measures the number of beneficiaries receiving financial education. Overall 30,915 beneficiaries were supported during the reporting year, against the target of 56,000.

FSDZ responds to financial education needs of people through a number of initiatives including financial education of members of saving groups, education to farmers about insurance products, working with educational institutes on incorporating financial education in curricula, and large-scale campaigns such as ‘Insurance Week’ and ‘Financial Literacy Week’.

Key activities that contributed to the results in the reporting year were:
- Increased outreach of savings groups, who receive financial education as part of their training to become a group member. Support to savings groups is discussed in more detail under output 4.
- Partnership with “Zazu Africa” to pilot mobile phone-based financial education. Zazu and FSD Zambia developed a series of five simple courses which could be accessed in English and Bemba on feature phones. The courses were provided as trial content for savings, borrowing, basic money management, insurance, and mobile money. The initial trial in a poor area of the Copperbelt was highly successful, with the most popular course being insurance. The programme has since expanded nationwide with a new course on consumer protection and deepened to all seven national languages.
- Support to events with Zambia Information Communications Technology Authority (ZICTA) on ICT for girls to encourage learning for girls about digital financial services. This included funding, mentoring, and educational work with over 200 girls nationwide.
- Developing a learning drama series to be broadcast on community radio. The programme aims to educate Zambia’s rural population on digital financial issues, to encourage savings and responsible borrowing while also promoting sustainable business. The project is at pre-testing for airing stage in Eastern Province, where the first pilot intervention is planned. Should the radio drama prove successful, it will be rolled out to all 10 provinces.

### Lessons identified this year, and recommendations for the year ahead linked to this output

The financial education delivery team found that most target beneficiaries do have access to the smart phone technology required to run the Zazu programmes. However, many face difficulties in charging mobile phones due to unreliable electricity. Future phases of implementation could look at how initiatives link and collaborate with renewable energy programmes. (FSDZ by March 2020)

The biggest engagement on the Zazu platform happens between 4pm and 6:30pm daily and understanding when people are ready to learn, is key for any programme that wants to increase engagement and actually reach people when they are receptive.

## OUTPUT 2
Output Title	Improved policy and regulatory environment for the delivery of financial services
Output number per LF		Output 2	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of organisations demonstrating improved effectiveness in advocating for financial sector reform	8 (4 for year)	Outputs moderately exceeded expectations / 10 (6 for year) (150%)
2.2 Number of policy-making bodies recording progress to formulate and implement effective financial sector policies and regulations during the year	Minimum 1 to 2 step Progression levels/policy making body	Outputs met expectations – but target poorly defined. / Full assessment was not made but in-house assessment identified progress of four bodies (ZICTA, MoF, BoZ and Smart Zambia)

### Supporting narrative for the score

Overall the output has scored an A. Under this output FSDZ works with regulators and policy makers to improve the policy and regulatory environment in the financial sector. The activities aim to strengthen the capacity of regulators and policy makers to advocate, formulate and effectively implement regulations and policies that create an enabling environment for the delivery of financial services and products.

The target for organisations demonstrating improved effectiveness (2.1) was exceeded – with two additional institutions (the Pensions and Insurance Association and the Digital Financial Services working group) supported beyond the target of four.

The target for output indicator 2.2 was poorly defined and no targets set and so it is difficult to assess whether expectations were met. Overall good progress was made.

Indicator 2.1

The six organisations supported in the reporting year were: The Pensions and Insurance Authority (PIA); the Insurance Association of Zambia (IAZ); the Microinsurance Technical Advisory Group (TAG); the Bankers Association of Zambia (BAZ); the Digital Financial Services Working Group (DFS); and the National Financial Inclusion Strategy (NFIS) Working Group.

Activities that contributed to the output in the reporting year included:
- Supporting and building an industry-led coordination function for the insurance sector with the PIA and the IAZ. In addition, FSDZ facilitated the two organisations to work with the MOF and MoA on improving the claims payment system under the FISP weather index insurance product, and to support PIA with the gender audit of insurance firm and pension organization clients, staff and management. The two initiatives have been adopted and there is significant progress.
- Support to a new Technical Advisory Group (TAG) for microinsurance. FSDZ helped the group to set up, register and provided technical support to help draft 10 microinsurance principles which are aimed at creating an enabling environment for the microinsurance industry. FSDZ supported the development of the TAG’s strategy, work plan, financial sustainability plan, and website which describes the association, its activities, achievements and upcoming events.
- Provision of technical advice and financial support to the five working groups under the Government’s National Financial Inclusion Strategy. FSDZ rendered specific support to both the financial literacy/consumer protection and the digital payments working groups. Some of the support to the latter included expanded outreach and quality of agent-based delivery channels, expanded use of mobile-based delivery channels, and strengthened pathways to formal financial inclusion for users of informal financial services.

Indicator 2.2

FSDZ has developed a methodological framework to measure progress against this indicator, which will be assessed by an independent third party. The relatively short period between annual reviews meant that the full assessment was not conducted during the reporting period. A light touch assessment was conducted by the FSDZ M&E team.

FSDZ supported four policy making bodies in the reporting year: the Zambia Information, Communication and Technology Authority (ZICTA), the Ministry of Finance, the Bank of Zambia and Smart Zambia (part of the Cabinet office). While progress has been made, the assessment does not include an analysis of the policy and regulatory impact of the activities.

The annual review team met with Bank of Zambia and ZICTA as part of this review. Both reported that FSDZ were a trusted partner and expressed strong desire to continue collaboration in the future.

Activities that contributed towards the aims of this output area included:
- Support to ZICTA to plan, implement and disseminate findings from a national ICT survey. FSDZ also helped to facilitate increased collaboration between Bank of Zambia and ZICTA on regulation of ICT. As a result, the two institutions are working more closely to improve the regulation of ICT and DFS.
- Support the Ministry of Finance to design an M&E framework and Communications Strategy for the National Financial Inclusion Strategy.
- Support to the Bank of Zambia for the first gender survey to assess management and staff of regulated financial institutions, as well as clients.
- Support to the Smart Zambia Institute in the Cabinet Office for the process of digitising a wide range of Government services and payments. FSDZ supported a Digital Readiness Assessment. The assessment has contributed to high-level Government consultations and decision-making to roll out of a number of government functions, such as the national biometric identity system, FISP weather index insurance, and social security payments.

### Lessons identified this year, and recommendations for the year ahead linked to this output
Indicator 2.2 needs to be properly defined, targets set, and an independent assessment made. The assessment should include analysis of the policy and regulatory impacts of the programme activities. (FSDZ, by December 2019)

        OUTPUT 3

Output Title	Adequate infrastructure and support services in place to support financial sector development
Output number per LF		Output 3	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of new or improved support service offerings to stakeholders/policy working groups/partners	15 (5 for year)	Outputs substantially exceeded expectations / 28 (18 for year) (360%)
3.2 Number of financial infrastructure functions recording progress during the year	Minimum 1 to 2 step progression levels using FSDZ ‘infrastructure incremental improvement scoring system’	Outputs met expectations – but target poorly defined / 8 (6) / 6 elements of financial infrastructure were supported and increased by at 1 level on the scale

### Supporting narrative for the score

Overall the output scores an A. The target for 3.1 was substantially exceeded. It is not possible to objectively assess 3.2 as the target was poorly defined (it was not clear how many ‘infrastructure functions’ were targeted).

The output captures technical support and “support services” provided by FSDZ to sector players with the aim of improving the effectiveness of financial sector ecosystem. (“Support services” are defined as business advisory services, staff training and human resource development which lead to cost reductions, improved revenues and/or facilitate the development of new financial services).

Indicator 3.1
The target was exceeded with 18 support services provided to partners through the FSDZ programme. Activities that contributed to the output in the reporting year included, for example:
- Providing training and support to providers to help them replicate the “master trainer programme” for savings groups that has been developed and implemented by FSDZ. Under this system, the programme provides training to ‘master trainers’ who then develop their own savings groups on a commercial basis.
- Support to providers of rural agricultural finance (such as Alliance Ginneries, Mayfair Insurance, Agora Microfinance Zambia and Investrust Bank Plc). Support to partners included capacity needs assessments to broaden the understanding of their operations and plans for growth, support to scale-up pilots, and support to design and effectively deliver rural agriculture financial products.
- Support to the Microinsurance Technical Advisory Group on formulation of microinsurance principles, consumer education, registration of the group and development of a strategy.

Indicator 3.2

To measure this indicator FSDZ has developed a scoring system, with levels that range from 0 (nothing in place) to 8 (infrastructure is in use by more than 50% of relevant financial service providers). A clear target was not set for the number of ‘infrastructure’ components to be supported.

Six elements of financial sector infrastructure were supported in the financial year:
- The Collateral Registry (moved from level 4 to 8). FSDZ worked with the International Finance Corporation to develop the registry.
- The National Financial Switch (moved from 3 to 6). FSDZ worked with a range of stakeholders to support an integrated system that will facilitation coordination between ATMs and Points of Sale providers.
- The Zambia National Data Centre (part of Government) (moved from unrated to 5). FSDZ helped the organisation to develop a cloud for safe data storage.
- The biometrics identity system remained at level 0. FSDZ has been in early conversations with Government about how such a system might work in Zambia. The system is will aim to improve payment efficiencies and security for ‘government to person’ payment processes.
- The Payment Association of Zambia (moved from unrated to 5). FSDZ facilitated the formation of the association and is helping to develop the organisational structure.
- Credit Market Analysis (moved from unrated to 6) FSDZ conducted awareness campaigns on the roll out of credit reference bureau and credit market monitoring system.

### Lessons identified this year, and recommendations for the year ahead linked to this output
As no targets have been set under 3.2 it is difficult to assess whether a strategic approach has been taken to capacity building, and how FSDZ is making decisions about how and where to allocate resources. A clearly defined target for output 3.2 needs to be set out in the new version of the programme log frame to ensure that FSDZ is taking a strategic approach. (FSDZ, by December 2019)

OUTPUT 4

Output Title	Increased capacity of financial service providers to deliver products that are accessible, affordable and appropriate to poor women and men
Output number per LF		Output 4	Output Score	B
Impact weighting (%):		20%	Impact weighting % revised since last AR?	Yes, down from 30%

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of financial service providers with increased capacity to reach poor women and men/microenterprises with financial services	20 (0 for year)	Outputs moderately exceeded expectations / 23 (3 for year)
4.2 Increased number of sustainable community-based financial institutions providing financial services to poor women and men	7,737 (2,000 for year)	Outputs substantially did not meet expectations / 6,721 (984 for year) (49%)

### Supporting narrative for the score

Overall the output has scored a B. The output relates to FSDZ support to financial service providers to enhance their capacity to deliver a range of financial services (such as microfinance, insurance, and agri-finance) to poor people and support to informal saving groups to enhance culture of savings and credit amongst poor women and men.

Whilst three financial service providers were supported to build capacity under 4.1, the target for the year was zero and so FSDZ was not given a stretching objective.

Under 4.2 the target number of community-based financial institutions providing financial services to poor women and men (i.e. savings groups) was missed by 50%. A new project on ‘financial inclusion through traditional leadership’ was expected to be the main contributor to this output, but the project experienced implementation delays due to extended timelines for implementation of the RCT baseline under IPA and did not deliver results in the reporting year as anticipated.

Indicator 4.1

During the reporting year FSDZ provided capacity building and innovation stimulation activities for inclusive insurance. FSD Zambia supported three institutions: Sanlam Life, Madison Life and Barclays Life to roll out their life insurance products to low-income individuals and households. Technical and financial support was provided. During the year, 12,390 (8,673M, 3,717F) lives were covered under the funeral and hospitalization product (Sanlam), 1,244 (871M, 373F) under domestic travel (Madison) and 1,506 (602M, 904F) under the funeral policy (Barclays).

Indicator 4.2

The informal saving groups continued to be instrumental in supporting the culture of savings, access to informal loans and earning interest income. The size and influence of groups as a vehicle for women’s empowerment and expansion of microenterprises, particularly in rural areas, is increasingly being recognised, given that group members are over 80% female. The annual review team visited one savings group in Lusaka for this annual review and received positive feedback from beneficiaries. Families are now able to easily meet household expenses including school fees and creating small business. For example, a widow who sells second hand clothes has expanded her business after accessing loans from this investment. She is now able to trade outside Lusaka to nearby towns increasing her profits. She shared with joy how her children who were out of school for a year are now back in school due to this initiative.

During the reporting year FSDZ collaborated with a series of partners to contribute to the increase in the number and quality of savings groups in the informal financial sector. Support to savings groups included:
- Facilitation of the final phase of a grant agreement with the Catholic Diocese of Ndola (CDN) targeting 600 savings groups. At the close of the year, CDN had facilitated 783 groups (with 14,019 members) with a cumulative total of 3,841 groups and 93,154 members (87.7% of whom are women).
- Provision of training to the Ministry of Community Development and Social Services, resulting in their decision to adopt the savings group approach more broadly. FSD Zambia will be engaging with the World Bank and Government in the next year to improve savings groups generation. There is also discussion about national rollout of savings groups under additional World Bank project funding.
- FSD Zambia signed a new agreement with Plan International for expanded savings group coverage in Eastern Province. Plan International will facilitate 25,000 individuals into savings groups in the next 3 years using the master trainer programme methodology that has been demonstrated by FSDZ.
- FSD Zambia continued to monitor the progress of the master trainers and their community-based trainers in the formation of savings groups. Supervision, training and monitoring of master trainers was done to support the master trainer programme pilot. Monitoring reports indicate a membership growth rate of 28.9% with a cumulative total of 4,177 members (93.2% women) mobilised in 196 savings groups.
- FSD Zambia continued engaging with an NGO called SaveNet on the master trainers programme model and provided ongoing technical assistance on the methodology and potential steps for master trainers programme to be conducted across the country.

### Lessons identified this year, and recommendations for the year ahead linked to this output
- No target was set for the year under 4.1, so it is difficult to assess whether a strategic approach was taken to identify private sector partners. A clear target needs to be set in the new version of the log frame to ensure that resources are being allocated according to a strategic approach. (FSDZ, by December 2019)
- Savings groups continue to use physical cash, which is stored in a safety deposit box by one of the members. FSDZ should continue to look at how savings groups can use digital systems (for example mobile phone banking) and promote this for new savings groups. (FSDZ, by March 2020)

.

OUTPUT 5

Output Title	Increased capacity of financial service providers to deliver accessible, affordable and appropriate products and services to MSMEs and smallholder farmers
Output number per LF		Output 5	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1 Number of financial service providers with increased capacity to reach MSMEs with financial services	17 (4 for year)	Outputs substantially did not meet expectations / 13 (2 for year) (50%)
5.2 Number of financial service providers with increased capacity to reach smallholder farmers with agricultural financial services	10 (4 for year)	Outputs substantially exceeded expectations / 18 (12 for year) (300%)

### Supporting narrative for the score

Overall the output scores an A. Output indicator 5.1 substantially did not meet expectations (by 50%) but output indicator 5.2 exceeded expectations.

The indicator captures FSDZ’s capacity building support for financial service providers, aimed at helping them to reach small businesses and smallholder farmers. Activities aim to help providers enhance their institutional and human resource capacity, develop strategies for increased outreach, and strengthen governance and internal control functions. Macroeconomic pressures have resulted in financial service providers slowing innovation/delivery of products for MSMEs.

Indicator 5.1

The milestone for this year of four new financial service providers was not met. Two new partners were added in the reporting year – Sanlam Life Insurance and Investrust Bank.

FSDZ continued providing technical support to the same 13 organizations supported in previous years. However, there are only a limited number of organisations in Zambia (18 banks for example) and not all will have the capability and desire to participate with FSDZ. Also, the indicator does not capture progress made within the organisations.

Activities that contributed towards this output indicator were:
- Sanlam Life Insurance were supported to roll out their life insurance product (funeral and hospitalisation) to low-income individuals and households including smallholder farmers and MSMEs.
- FSD Zambia launched a pilot project called the “Working Capital Access project” in Southern Province. The initiative was visited by the annual review team. The objective of the project is for rural-based MSMEs, particularly village shops, to increase access to affordable savings and working capital facilities. FSDZ facilitated the identification and mobilisation of traders, who formed themselves into five savings groups benefiting103 MSMEs. Each group member was enabled to save and borrow at an affordable interest rate from the pool of savings for working capital purposes only. The group funds are placed into an Investrust Bank account and members can borrow from the group for wholesale purchases. Funds are then digitally transferred in to a wholesaler account at no cost. Both businesses and savings are growing, increasing the number of transactions e.g. one trader had K4,000 worth of goods in 2013, grew slowly but has expanded rapidly to K35,000 in 2019 after accessing SG loans through the project. This also supports banks to observe the repayment and cashflow systems of these shops for future direct lending.

FSDZ also launched a new funding window for financial service providers called the ‘FinClient Centric Cycle’ (F3C). Through this mechanism businesses are able to apply for support to develop new data-driven products using client centric technology, and to install this approach into their firms. A call for applications took place in mid-April 2018 and was heavily over-subscribed with 25 applicants. The process began implementation with five firms at the end of the reporting year. Results will be captured in the next annual review.

Indicator 5.2

This indicator measures number of financial service providers with improved capacity to reach smallholder farmers as a result of the programme. The target of 4 providers was exceeded in the reporting year, with 12 organisations reporting improved capacity.

Activities that contributed towards this output include:
- Insurance add-on to the Government’s Farmer Input Support Programme, which enables farmers to access weather index insurance. This continues the support from last year, in partnership with Mayfair Insurance. During the reporting year FDSZ lobbied the Government to make payments owed from the previous season and worked with government to design an automated system whereby premiums and pay-puts are digitized.
- Partnership with Alliance Ginneries (an agriculture inputs company) to provide small loans at zero interest to poor farmers during the hungry season. This helps them meet their daily consumption needs and mitigates the risks of short selling of crops or engaging in other jobs and ignoring their own fields. In the repotting year the pilot was scaled up to reach 3,414 (1,434M 1,980F) farming households benefitting 20,484 (7,652M 12,832F) individuals.
- Continued support to Agora Microfinance Bank to digitise their loan processes. The bank teams working in the field are now equipped with digital tablets which allow them to issue loans and receive payments in the field with biometric verification and issuance of receipt. The pilot project reached 22,199 clients (63% female) in the reporting year.

### Lessons identified this year, and recommendations for the year ahead linked to this output
- DFID visited farmers who had paid for weather index insurance through the Farmer Input Support Programme. Despite repeated engagements by FSDZ, the claims for the prior season 2017-18, which the Government required that it pay to eligible smallholder farmers directly rather than by the insurance firm, only began to be paid in early February 2019 and continue to be slowly paid.
- In addition, through farmers have paid premiums to the Government for the 2018/19 season, the Government has not yet paid the premiums to Mayfair Insurance. Claims are already due in significant numbers because of the drought conditions in some areas of the country. As a result, claims cannot be paid to customers or reinsured until this season’s premiums are paid in full to Mayfair and its re-insurers.
- FSDZ should continue to lobby the Government of Zambia to meet its legal obligation to make the premium payment to the insurance provider. FDSZ should continue to monitor this and keep DFID fully informed. (FSDZ, by December 2019)

## OUTPUT 6

Output Title	Effective governance of Special Purpose Vehicle, and support for financial sector innovation
Output number per LF		Output 6	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	Yes – new indicator

Indicator(s)	Milestone(s) for this review	Progress
6.1 Number of financial sector pilots/innovations supported by FSD Zambia	4 financial sector innovations supported	Outputs significantly exceeded expectations / 9 financial sector innovations supported
6.2 Effective SPV corporate governance, as demonstrated by: / 1) Compliance with conditions in Accountable Grant / 2) Unqualified external audit / 3) Governance Charter updated and signed off by Board and PIC / 4) Accurate forecasting and budgeting (< 5% under or over spend) / 5) Strategic Plan, budget and annual workplan approved by Board and PIC and implemented	All 5 areas successfully met	Outputs met expectations / Progress was made against all target areas.
6.3 Amount (£) of funding provided to FSD Zambia by other donors	£2 million	Outputs moderately met expectations / £3.89 million / Cumulative from previous FY. / (Other donors include Sida, Comic Relief and RUFEP)

### Supporting narrative for the score

This output was added to the log frame during the reporting year with a weighting of 10%. The output measures the number of financial sector pilots and innovations supported by FSD Zambia and captures progress towards institutional development of FSDZ as a SPV.

Overall outputs met expectations. The target for 6.1 was exceeded, but these activities have also been counted towards other output areas. The targets for institutional development (6.2) and new funding (6.3) were met.

Indicator 6.1

This indicator captures the extent to which FSDZ has supported innovations and pilots that have the potential to be scaled up by the private sector. The target of 4 innovations/pilots for the reporting year was exceeded, with 9 innovations supported. However, the activities contributing towards this indicator are already captured under other output areas.

Activities that contributed towards this output indicator included:
- The ‘master trainer’ programme pilot for savings groups and other innovations in relation to savings groups (captured under outputs 3.1 and 4.2)
- Roll of out of the ‘working capital access’ pilot programme (captured under output 5.1)
- Mobile phone based financial information through Zazu and financial education radio show pilot (both captured under 1.2)
- Support to Agora Microfinance Zambia to digitise loan payments and small loans with Alliance Ginneries (both captured under 5.2)
- The new ‘FinClient Centric Cycle’ (F3C) finding window (captured under 5.1)

Indicator 6.2

This was the third year of operations for FSD Zambia as a company limited by guarantee and progress was made during the reporting year against all of the 5 areas set out in the indicator. The indicator measured progress against five areas of organisational development. Good progress was made against all of the five areas:
- Compliance with conditions in Accountable Grant. The special conditions set out in the accountable grant were met (discussed further in section F).
- Unqualified external audit. An external audit was conducted by KPMG at the end of the financial year and no issues were identified.
- Governance Charter updated and signed off by Board and PIC. This was completed.
- Accurate forecasting and budgeting (< 5% under or over spend). Variances for the year were 5% (agreed budget versus actual spend).
- Strategic Plan, budget and annual workplan approved by Board and PIC and implemented. A new Strategic Plan was designed and is in use. The annual workplan, budget, and performance contracts approved by Board, reviewed and reported quarterly.
Indicator 6.3

The addendum to the FSDZ Business Case from 2017 identified the need for FSDZ to put in place a sustainable and responsible transition of FSDZ from DFID funding by 2021. Indicator 6.3 was added to the log frame in order to capture progress towards this aim.

FSDZ has attracted £3.8 million in non-DFID funding since 2017. Contributions have been made by the Swedish International Development Agency (SIDA) (£2.5m), the Rural Finance Expansion Programme (RUFEP) (£0.34m) and Comic Relief (£1.01m).

# C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summary of the theory of change and any major changes in the past year

The theory of change of the programme was broadly set out in the Business Case from 2012 and remains valid. The impacts and outcomes in the Business Case are set out in box 1. The key assumptions from in the original theory of change still stand. Progress against impact and outcomes are assessed in the next section - overall progress has been strong and results substantially exceed those envisioned during programme design.

Box 1: Impacts and outcomes in the FSDZ Business Case, May 2012 / The impact of the programme is to make sustainable improvements in the livelihoods of poor people in rural areas. / It will contribute to: / 25% increase in the real median average incomes of 200,000 poor households in rural areas. / an increase in the percentage of people able to access to financial services to 50% of the adult population by 2017 / The outcome of the programme will be a financial sector delivering a wide range of financial services to more people and businesses in rural Zambia. / It will provide: / 300,000 additional people with access to finance (of which 65% will be women) / 50,000 smallholder farmers with access to agricultural finance (of which 50% will be women) / 12,000 additional SMEs with finance from banks and MFIs. / Key theory of change assumptions were: / Government finalises its national financial literacy plan / Government remains supportive of the access to finance agenda and puts in place a supportive policy agenda / There is a continued expansion of the mobile phone network in rural areas. / Stability in the macro-economy and political environment / Absence of severe external environmental factors (e.g. drought) / Government refrains from sudden and arbitrary policy interventions in the market

The Business Case specified that the programme would tackle constraints to financial inclusion in Zambia, including policy level issues, weaknesses in financial infrastructure, as well as work with financial service providers themselves. This has continued to be the focus of the programme.

The programme design stated that the programme would “take a holistic view of the financial market and its impact on the poor and follow the principles of ‘making markets work better for the poor’ (M4P). The M4P approach seeks to change the way that markets function to be in the interest of a range of poor stakeholders. It does this through directly considering how the poor are involved or excluded from markets, what stops them benefiting more and how this can be changed in a way that will be sustainable and lasting.”

A new 5-year Strategy for FSDZ was approved in November 2018. The strategy confirms the commitment to the M4P methodology, stating, “this means we aim for market system change, moving the underlying dynamics within the market rules, support systems, and players and changing the way of thinking. FSD Zambia is already known as a market facilitator and we will continue in this role, bringing players together and suggesting new methods of engagement”.

An update of the theory of change took place by the FSDZ M&E team during the reporting year. The theory of change maps the impact, outcomes, outputs and project activities on to the FSDZ 5-year strategy. A simplified version of the theory of change is set out in the figure below.

Overall it is in line with the original programme theory of change and demonstrates how strategy and delivery has become increasingly sophisticated as the programme has evolved.

Figure 1: Simplified version of FSDZ theory of change
Impact	Expansion in income opportunities and reduced vulnerability by poor men and women in Zambia.
Outcomes	Expanded usage of financial services / Expanded access to financial services / Increased knowledge and understanding of financial products and services
Outputs	Widely available high quality and secure savings groups / Increased financial service offering to smallholder farmers / Increased supply of inclusive services in the insurance market / Increased supply and types of MSME financial services / Enhanced enabling environment for financial inclusion / Increased financial capabilities by youth, women and their households on the usage of financial services
Projects (activities)	Project 1: Informal finance (savings groups) / Project 2: Financial inclusion and traditional leaders / Project 3: Rural and agricultural finance / Project 4: Inclusive insurance / Project 5: Inclusive enterprise finance / Project 7: Digital financial services / Project 8: Policy and infrastructure / Project 9: Increasing financial inclusion for women and youth in Zambia

Assessment of whether the programme is on track to contribute to the expected outcomes and impact, and planned actions

Impact

The programme target impact is ‘expansion in income opportunities and reduced vulnerability by poor men and women in Zambia’.

This is defined as “sustainable improvements in the livelihoods of poor people” in the current log frame and measured as “% of adults financially included in Zambia”. The metric is measured using a bespoke survey called FinScope, which is carried out approximately every 2 years. The next measurement will be in 2019/20.

The most recent FinScope data is from 2017/18, which found that 59% of adults were financially included, compared to the 2018 milestone of 50%. This exceeded the target set out in the log frame and Business Case.

Outcomes

The programme outcomes are measured through one higher outcome (‘number of poor people experiencing an expansion in income opportunities or a reduction in vulnerability’) and two intermediate outcomes (‘number of poor people, microenterprises and smallholder farmers with new access to financial services’ and ‘number of SMEs accessing a new financial service’)

Outcome level achievements are summarised in table 2. Progress was fairly good overall – the targets for the higher outcome and intermediate outcome 1 were substantially exceeded. The target for intermediate outcome 2 (SMEs accessing a new service) as not met, with only 69% of target achieved.

The achievements are significantly higher than envisioned in the Business Case during programme design – more than four times the target number of beneficiaries have experienced an expansion in income. Almost 1.5 million poor people or microenterprises have new access to financial services (compared to just 50,000 in the business case) and over 20,000 SMEs have accessed a new financial service (compared to 12,000 in the business case).

Table 2. Outcome level achievements
	Milestone (for year in brackets)	Achievement
Higher outcome: Number of poor people experiencing an expansion in income opportunities or a reduction in vulnerability	1,284,555 (45,016) / Women - 642,278 (22,508)	Target substantially exceeded / 1,329,850 (90,311) (200%) / Women – 437,223 (53,192) (236%)
Intermediate outcome 1: / Number of poor people/microenterprises and smallholder farmers with new access to financial services due to FSDZ	1,470,802 (65,000) / Women - 956,021 (42,250)	Target substantially exceeded / 1,496,113 (105,250) (161%) / Women – 489,828 (63,179) (149%)
Intermediate outcome 2: / Number of SMEs accessing a new financial service	20,770 (400)	Target moderately not met / 20,647 (277) (69%)

Major changes to the logframe in the past year

The 2018 Annual Review recommended that the log frame undergoes a major restructure, in line with the FSDZ Strategy. This was not completed in the reporting year, as the strategy was still being finalised.

Though a full restructure did not take place, a series of changes were made in the reporting year. These were:
- The impact indicator was refined to measure national level trends in financial inclusion (% of adults financially included in Zambia) to be consistent with the approach of other FSD programmes and the Government’s National Financial Inclusion Strategy.
- Outcome 1 was shifted up to become a ‘higher level’ outcome (combining the old outcome 1 and 2, and including direct results such as insurance pilots as well as indirect results such as farmers with weather insurance);
- Outcome 2 methodology was refined to capture those experiencing an increase in income or a reduction in vulnerability (similar to the current impact indicator, but without farmers who receive weather insurance);
- Addition of Output 6 and output indicators 6.1, 6.2 and 6.3: number of financial sector pilots/innovations supported by FSDZ; performance and sustainability of the Special Purpose Vehicle; and funding provided to FSDZ by other donors.

Planned changes to the logframe as a result of this review

Following this annual review, the logframe should undergo a full revision in line with the FDSZ 5-year strategy and theory of change (summarised in figure 1 above). It is imperative that this is now done as soon as possible.

# D: VALUE FOR MONEY

## Assessment of VFM compared to the proposition in the Business Case, based on the past year

FSDZ’s value for money approach is aligned with DFID’s ‘4Es’ VFM framework. Whilst the programme reports against a suite of useful VFM indicators, not all of these have targets or success ratings, so it is difficult to evaluate performance using the current framework.

A new VFM framework has been developed, with a refreshed set of indicators and ratings system to enable performance assessment against the indicators. The new framework will also enable VFM comparisons with other FSD programmes elsewhere in Africa.

### Effectiveness

The FSDZ Business Case (drafted in 2012) did not include a full cost benefit analysis to assess VFM of programme options as insufficient data was available. However, the business case did provide a cost effectiveness analysis of programme options and estimate potential returns.

The Business Case estimated that the costs of the programme would be £20.2 million over 5 years (2012/13 – 2015/16). The estimated benefits were growth in formal banking services, at around 5% a year, and continued growth in access to non-bank services. Overall access to financial services were projected to grow at an average of 6.5% per year and reach 54.9% of the adult population by 2019.

Table 3 compares the Business Case assumptions to the costs and benefits achieved to date. Overall the programme has delivered the higher expected benefits that set out in the Business Case.

Table 3: Costs and benefits of FSDZ relative to Business Case projections
	Costs	Benefits
Expected	£20.2m / (5 years, 2013/13 – 2015/16)	By 2019: / 1,021,300 additional people with access to finance as a result of programme / 54.9%, of people with access to finance, relative to expected baseline of 42.3%
Actual	DFID expenditure = ~£18 million since 2011/12 / Other donors = / ~£2.7 million	Target met / 1,496,113 poor people/microenterprises and smallholder farmers with new access to financial services due to FSDZ / 59.3% (March 2018)

FSDZ currently monitors progress against two indicators of effectiveness:

- Number of actual people utilising financial services vs. planned
- Estimated economic returns on specific project activities

Progress against these is summarised in table 4. Overall progress was good – the number of people utilising financial services exceeded the target number. No target was set for ‘economic returns’ to the project, but analysis of savings groups interventions indicates a positive return on investment.

Table 4: Effectiveness performance
Indicator	Target	Achievement	Comment
Number of actual people utilising financial services vs. planned	1,470,802 (cumulative to March 2019)	1,496,113 / (102% of the annual milestone)	Target met / Results under log frame outcome 1 and 2 contribute towards this outcome. The metric includes poor people, microenterprises and smallholder farmers accessing a new financial service.
Estimated economic returns on specific project activities	No target set	£1.70 value returned for every £1 invested in savings groups interventions.	No target set – but positive return observed / This was a new VFM indicator added during the reporting year. FSDZ estimated the economic returns from savings groups interventions. The results are calculated by estimating the benefits (share out per member * number of members) / costs (cost of supporting savings groups + amount saved).

### Efficiency

FSDZ currently monitors progress against three indicators of efficiency:

- Average cost per client
- Partner leverage ratio
- Crowding-in ratio

Progress against these is summarised in table 5. Whilst the analysis provides a useful summary of programme performance on efficiency, targets have not really been set, so it is difficult to assess performance. Under the new VFM framework clear targets need to be set (and ideally benchmarked against other FSD programmes).

Table 5: Efficiency performance
Indicator	Target	Achievement	Comment
Average cost per client (ACPC)	No target set	CDN reached a total of 93,154 members with an ACPC of £6.03, (compared to £10.4 in FY2017/2018) / Through Zazu 12,098 users accessed weather index insurance information with an ACPC of £26.	No target set so not possible to evaluate / Average cost per client measures the average costs of selected cost line items across similar grantees / FSD Zambia considered an ACPC ratio for interventions with the Catholic Diocese of Ndola (CDN) and Zazu mobile phone financial education: / FSDZ provided a grant to CDN to enable facilitation of 600 savings groups / Zazu scaled up the digital financial education intervention, in which cell phones are used to access financial education content for free via SMS and voice
Partner leverage ratio	Target achieve a ratio of not more than 50% contribution by FSD Zambia, with FSD Zambia contributing less over time	14 interventions analysed, of these the leverage ratio ranges from 29% (Zazu) to 89% (Bankers Association). / Of these, 10 have a leverage ratio of 50% or higher	Target not met, but target poorly defined / Partner leverage ratio = Partner contribution as a percentage of the total cost. / Between March 2017 and March 2018, the percentage of partners that achieved a leverage ratio of 50% or more increased to 73%. This year the proportion was 71% (10 of 14). This suggests that performance has been relatively stable but hides the fact that more partners have been added.
Crowding-in ratio	No target set	Master Training Programme Pilot support under savings group crowed in two new partners / Ratio: 1:2	No target set so not possible to evaluate / Crowding-in ratio measures the influence FSD Zambia is actualising in the market system because of its efforts in working with partners. If FSD Zambia supports 4 banks to sustain new SME products, and 8 others crowd-in, then the crowding-in ratio is 1:2.

### Economy

Figure 2 describes the key cost drivers in FSDZ during the reporting year. These figures cover all FSDZ spending (some of which is financed by donors other than DFID). Figure 2 describes the expenditure om 2018/19 of just DFID funding, disaggregated by programme and admin budget. Within the DFID funding, 81% was spent on programme budget and 19% was spent on administration.

Figure 2

Figure 3

In total FSDZ spent £4 million in 2018/19, £3.3 million of which was DFID funded. Figures 2 and 3 suggest that the main cost drivers in FSDZ are:

- Payments to partners (i.e. programme costs). In 2018/19 these totalled £1.58 million;
- Costs of permanent employees;
- Consultancy costs (tracked in the economy indicator below);
- Board expenses;
- Travel.

Not all the key cost drivers are tracked through the current VFM measurement framework – this could be improved as part of the VFM strategy refresh planned for next reporting year.

FSDZ currently monitors progress against three indicators of economy:

- Ratio of national to international consultants for programme activities technical assistance
- Cost savings
- Ratio of programme management costs to total costs

Progress against these is summarised in table 6. Indicators 1 and 2 (use of national consultants and cost savings) demonstrate a positive trend and commitment to reduce costs, however as no targets were set it is not possible to evaluate performance.

The target of 18% ratio of programme management costs to total costs was marginally not met. However, progress was made in relation to the previous reporting year, with the ratio coming down from 24% to 19%.

Table 6: Economy performance
Indicator	Target	Achievement	Comment
Ratio of national to international consultants for programme activities technical assistance	The higher the numerator, the more value for money.	22 national and 7 internationals / (ratio 3.1/1) / Improvement on 1.7/1.1 in 2018	No target set so not possible to evaluate / From March 2017 there has been more use of national consultants, with the trend continuing in that direction. For example, between April 2018 and March 2019, the use of international consultants reduced by 36%. / With the increase in the use of national consultants, FSD Zambia reports savings accrued with lower fee costs, consultant accommodation/allowances and flight costs.
Cost savings	No targets set, but general target to reduce costs	Savings from use of FSD Zambia office training space in lieu of hotel facility = £3354 / savings from a cost share of the office space with CIG = £37,536	No target set so not possible to evaluate / FSD Zambia continued to obtain VFM savings from the use of office conference facilities for meetings, workshops and trainings as opposed to venue hiring. / Beginning 1 October 2018, FSD Zambia started sharing office space with CIGZ. These cost savings are observed in reductions arising from shared utilities such as electricity, security, gardening, generator operations and office cleaning services
Ratio of programme management costs to total costs	18% ratio; / (the target was 20% for 2016 and 2017, but DFID is requiring now 18% for this reporting year and 16% thereafter.)	19%, down from 24% in 2017/18	Target not met / Programme Management costs as a % of total costs is a ratio of the total cost of administration expenses to the total organisational running cost. / The total administration cost includes employees, IT cost, accommodation costs, supplies/consumables outsourcing, recruitment, learning and development costs and other related expenses.

### Equity
FSDZ has integrated gender and social inclusion throughout its programme activities and disaggregates results data by gender where possible.

In March 2018 ‘gender and disability integration’ was added to the programme workplan as an activity in its own right. During the reporting period, the M&E team reviewed the policies, procedures and manuals of FSD Zambia; incorporated gender and disability and made recommendations for how gender and disability could be integrated. FSD Zambia also cofinanced and co-led the first ever Southern African Development Community (SADC) gender workshop on financial inclusion for women in Johannesburg South Africa

There are also a set of programme initiatives that seek to enhance equity in financial inclusion. These are:

- Increasing financial inclusion for women and youth;
- Financial education for youth; and
- Digital financial inclusion for female smallholder farmers

As well as disaggregating results in the logframe, FSDZ monitors progress against three indicators of equity:
- Percentage of beneficiaries that are female
- Percentage of beneficiaries that are below $2.5/day as measured by PPI

The results from indicator 1 are set out in table 7. Overall the target of at least 50% of beneficiaries was not met. The reason why the target was not met was due to the large numbers of persons who are smallholder farmers under the FISP weather index insurance, where the lists of farmers are 75% male and targeted by the government without FSD Zambia ability to influence.

Table 7: Equity performance
Indicator	Target	Achievement	Comment
Percentage of beneficiaries that are female	50%	489,828 women were reached and accessed various financial services (33% of the total clients reached)	Target not met / The indicator measures the percentage of women beneficiaries accessing FSD Zambia supported services in each period.

The second indicator measures the proportion of beneficiaries that live at incomes below US $2.5/person/day as measured by the PPI (Progress out of Poverty Index). No target was set so it is not possible to assess performance. However, sampled savings groups were 81% under the poverty line in 2016, and the same groups were 65% under the poverty line in late 2018, showing both a poverty impact and a majority of current clients under the PPI poverty line.

FSDZ carried out research in the reporting year to assess the poverty and vulnerability impacts of FSDZ interventions:
- During October/November 2018, FSD Zambia conducted a longitudinal study on members of 50 savings groups supported through the programme, as well as those from control groups. Preliminary results from this study show that 65% of the respondents were poor (extremely poor 17%, poor 27%, and near poor 21%). The rest of these savings group members are nonpoor (35%) but are clustered close to the poverty line. In these groups there was a 16% reduction in members (households) that are either extremely poor, poor or near poor. This reduction provides a plausible business case that savings groups do have the potential to reduce vulnerability and improve the livelihood status of poor and low-income households
- In July 2018, FSD Zambia conducted a verification exercise on the Chilala Weather Index Insurance intervention. A total of 126 smallholder farmers were purposively sampled from four districts. Preliminary results from this study showed that 49% of the farmers interviewed live below the PPI poverty line.

Assessment as to whether and why the programme should continue from a VFM perspective, based on its own merits and in the context of the wider portfolio

Overall it is quite difficult to make an objective assessment of VFM of FSDZ because most of the VFM indicators do not have targets or use benchmarks for comparison. That said, a positive trajectory was observed across the 4 E’s and from a VFM perspective it is recommended that the programme should continue.

In summary:
- On effectiveness the programme is performing well. The benefits of the programme at impact and outcome level exceed those anticipated during programme design (and costs have been lower than forecast). A focus should be placed on ensuring continued “stretch” of targets.
- Targets and benchmarks need to be more clearly defined in order to assess efficiency. As the analysis in section B shows, FSDZ is delivering a suite of strong results at the output level; but measurement against targets can help.
- Good progress is being made on economy, with a reduction in administrative costs and a number of cost savings. Again, benchmarks should be used to determine how the programme is performing (for example relative to other FSD programmes).
- On equity, the programme has demonstrated a strong commitment to integrate gender and inclusion in programme activities and delivers a number of inclusion-specific activities. Despite this, targets for female beneficiaries were missed for the year. Thus, targeting should be considered in terms of client engagement with partners over time, so as they engage more with women this can translate into FSD Zambia improving on these targets.

# E: RISK
## Overview of programme risk and mitigation

The overall risk rating for the programme is ‘moderate’. Table 8 sets out the risk appetite for the programme against the DFID risk categories. The DFID programme team regularly discuss risks against these categories and assess whether the current level is within the agreed appetite.

Overall none of the risks exceeded their risk appetite during the reporting year. Contextual risk associated with the worsening economic climate continued to climb throughout the year and should be monitored closely in 2019/20.

FSDZ continued to monitor the risk associated with weather index insurance closely (see output indicator 5.2). Under this activity, FSDZ have piloted an initiative that Government then took on but then have not delivered as agreed (government did not make payments to farmers or premium payments to the insurer).  FSDZ have continued to actively lobby Government at increasingly high levels to ensure payments were made to farmers and had some success in getting them to pay out before they might otherwise have done.

Table 8: Risk appetite for FSDZ
Category	Appetite	Rationale
Contextual	Major	Uncertainty of the regulatory environment. The programme has fairly high appetite for contextual risk due to its engagement with markets which are strongly influenced by rapidly changing government policy. It is also affected by the changing of government or responsible government officials, as it collaborates closely with government officials to influence financial inclusion in Zambia.
Delivery	Major	The nature of the programme is to allow innovation and piloting new policies, rules, approaches, products and services, of which some may be successful in taking financial inclusion forward and some of which may fail. The risk appetite for delivery is high to allow piloting new products and enable continual learning.
Fiduciary	Minor	Low appetite for fiduciary risk.
Reputational	Minor	Low appetite for reputational risk.
Safeguarding	Minor	Low appetite for safeguarding risk.
Operational	Moderate	Unresponsive market demand due to failure by clients to respond to FSDZ's initiatives. This is mainly because of lack of trust in the financial sector and lack of consumer education (mindsets makes it difficult for clients/beneficiaries to fully understand FSDZ product/initiative). But it is also affected by very low willingness for spend on innovation by the market in the uncertain macroeconomic circumstances.

Key programme risks that emerged and were mitigated during the reporting year were:

#### Delivery risk – sustainability of funding

The grant agreement signed in April 2018 required FSDZ to secure up to £1 million from other sources in order to receive match funding from DFID. The amount provided by DFID Zambia therefore depended on the amount of new funds FSDZ secures from other sources.

This was identified as a delivery risk, as failure to raise the required £1 million would delay implementation of planned activities and would affect the projects results.

FSDZ managed to secure new funding of £1 million from Comic Relief and as a result DFID disbursed a match contribution in April 2019.
#### Delivery risk – adhering to special conditions

The new grant agreement signed in April 2018 included a break clause after six months to review a series of special provisions included in the accountable grant which FSDZ was required to adhere to. These related to financial management, VFM assessment, reputational risk management and procurement.

There was a risk of DFID reducing or ending its funding if FSDZ failed to meet the conditions. During the period FSDZ and DFID worked closely to ensure compliance with the conditions and strengthening of FSDZ processes where necessary.

Progress during the first six months of the new Accountable Grant was reviewed at the end of 2018 and overall, FSDZ performed well against the special provisions and DFID allowed the formal break clause to lapse. However, there was need for further improvement in accelerating spend.

DFID will continue to engage on these through presence at the FSDZ Board, through chairing the Programme and Investment Committee and bilateral quarterly review meetings, and through DFID assurance processes.

Safeguarding risks

FSD Zambia has a good safeguarding policy in place. The policy establishes the methods for maintaining safeguards to ensure a positive work environment for all FSD Zambia employees, consultants, contractors and clients. The policies are incorporated in the FSD Zambia human resources manual and code of conduct. The CEO is responsible for any safeguarding issues and the head of operations is the designated safeguarding officer. Safeguards awareness workshops are conducted, however, safeguarding related risks are not included in the risk and feasibility section of the Project plans.

DFID recently carried out an enhanced due diligence assessment on FSDZ and below were the findings;
- Safeguarding risks are not included in the delivery risk chain mapping
- Due diligence assessments carried out on downstream partners do not have a safeguarding component.
- FSDZ to put in place a grievance redress/reporting process for its projects especially for those that have higher risks of safeguarding concerns

To mitigate the above risks, FSDZ will consider incorporating safeguarding risks in their project plans and will review all their downstream partners assessment processes to include safeguarding. DFID will continue to support FSDZ on safeguards related issues.

## Key upcoming risks for next year

#### Delivery risk – sustainability of funding

The delivery risk related to sustainable funding sources beyond the DFID programme will persist in to the next reporting year. DFID Zambia’s support is gradually declining – with £3 million allocated in 2019/20 and £2 million in 2020/21 (down from £3.5 million in 2018/19).

There is a risk that FSDZ will not be able to secure long term finding and as a result will need to scale back operations.

To mitigate this risk DFID will continue to be an active supporter of FSDZ, using our role on the Board to help FSDZ grow in to an increasingly competent organisation. During the year, the Board and DFID agreed to strengthen CEO incentives around attracting additional funding.

#### Contextual risk – economic context

The macroeconomic situation in Zambia continues to worsen, with rising levels of government debt and constrained public spending. Uncertainty around the implementation of a new ‘sales tax’ to replace VAT is depressing private sector investment.

During the next reporting year an economic downturn could limit the appetite for FDSZ’s partners (such as financial institutions) to engage with new customers and markets. For example, they may be less likely to test innovative products that work with rural communities or women.

To mitigate this risk, it is recommended that FSDZ include contextual risk in their risk register and regularly report on how it is impacting on programme delivery.

# F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

## Performance of DFID
The programme is overseen by the DFID Senior Responsible Officer (SRO), who is also the Team Leader for the Economic Development Team in DFID Zambia. He is supported by a Lead Adviser and Programme Manager, who manage day-to-day operations of the programme.

In early 2019 DFID Zambia faced staffing gaps which limited the amount of advisory time available for the programme for around three months. DFID Zambia is going through a restructure process and a new adviser has been allocated to the programme as the lead adviser.

Internally DFID managed programme performance through Programme Board meetings, which took place on a monthly basis. These are chaired by the SRO and cover progress updates, review of the delivery plan, financial performance and review of the risk matrix. DFID Zambia also holds quarterly scrutiny meetings with the Head of Office.

DFID had strategic oversight of FSDZ performance through its role on as an observer on the FSDZ Board and chair of the FSDZ Programme Investment Committee (a sub-committee of the Board). This enables DFID to have good insight, where desired, into the workings of FSDZ and through the PIC, together with other funders, strong engagement in the technical delivery of the programme.

On occasions, certain decisions have been referred by FSDZ to DFID for decision, particularly in relation to funding matters.  In some cases, DFID responses have not been as timely as desired.  Aside from committing to shorter turnaround of decisions, DFID and the Board can also work together to seek to have all decisions resolved as part of formal Board meetings.

The Swedish International Development Agency (SIDA) is co-funding FSDZ. Their support is for a discrete component to improve financial capabilities for women, youths and children. The 2018 Annual Review (conducted in November 2018) recommended that DFID and SIDA set up a donors’ working group to improve coordination and collaboration between funding partners. This action was not completed in the reporting period.

Engagement with other funding partners (now including Comic Relief and Jersey Aid as well as RUFEP) therefore remains a potential weakness, and from time to time has created a more challenging governance environment for FSDZ.  This is particularly true with each donor requiring reporting under different timelines and with different formats and approaches. Stronger funder relationships and coordination of reporting and other requests would likely help further strengthen FSDZ performance.

## Performance of FSDZ

#### Institutional development

FSDZ was originally conceived as a supplier led programme, delivered by development consultancy DAI. In 2016, DFID registered FSDZ as a Zambian not-for-profit company, to create a local entity that is able to secure funding from other sources and a first step to a transition from DFID funding. This is in line with the development of other FSD programmes in Africa.

In December 2017, approval was given by the DFID Minister of State to proceed with a £8.5 million 3-year contract extension for FSDZ. The objectives of the proposed cost extension were to:
- Expand financial inclusion in Zambia and drive policy change and innovation in the financial sector so that more Zambians have access to financial services; and
- Put in place a sustainable and responsible transition of FSDZ from DFID funding by 2021, contributing funds while incentivising the programme to attract funds from other sources.

DFID support to FSDZ between 2018 and 2021 is on a sliding scale, to incentivise FSDZ to put in place a responsible exit strategy from DFID funding. DFID also committed to provide match funding for new finance secured by FSDZ. This transition period included the recruitment of a new CEO brought into the grow the organisation and so that it could evolve as a sustainable company with the support of other funding partners after DFID funding ends.

During the reporting year development of the SPV and access to new funding sources were measured using two new output indicators (6.2 and 6.3). Overall good progress has been made on professionalisation of the organisation and new funders have been identified.

Following the Business Case addendum in 2017, an Accountable Grant agreement was signed in April 2018 with break clause of ‘special conditions’ to be reviewed after 6 months. These were designed to assess FSDZ’s progress towards improvements in financial management, VFM measurement, procurement, and safeguarding.

The DFID Lead Adviser for the programme assessed performance of FSDZ against the special conditions in January 2019 and found that good progress had been made. As a result, DFID funding to FSDZ will continue until 2021. DFID will continue to monitor progress against the special conditions.

Human resource management

During the year, FSDZ brought in an independent HR specialist to sit on the HR Committee which has helped strengthen HR practices.

An exhaustive HR review was conducted during the reporting year by FSDZ with the aim of strengthening the organisational capacity of the company.

The HR review found that staff contracts were not sufficiently performance based, and staff did not have standard key performance indicators against which to measure performance. It found that the performance appraisal tools needed further development, with no standard framework for assessing competencies, meaning that performance appraisals were too subjective. The review also found that more junior staff were needed to perform routine administrative functions in the organisation and to develop a pool for staff advancement.

Following the HR review, FSDZ took the following actions:
- A new organisational structure was implemented in April 2019, with refreshed policies and strategies on remuneration, workload balancing and expectations, and cost structures.
- The staff restructure aims to enable more effective use of technical skills and an improved CEO focus away from direct technical work into direct leadership and fundraising. A significantly expanded financial team provided enhanced financial projections and oversight. More junior technical staff have been recruited to fill administrative roles.
- A new Performance Management System was put in place and all staff took part in a training programme on the new system in March 2019. The first staff appraisals were conducted in March 2019 using the new tools and procedures, with participation from all staff.
- All staff took place in rating and ranking capabilities, and in setting up both detailed work plans with clear independent targets and performance contracts. Succession plans will be developed this year for each position.
- Two distinct Directorates were created within the organisation (Policy and Digital Financial Services and Gender and Financial Education).
- A capacity building workshop took place, aimed at building team cohesion and strengthening inter-personal traits that contribute to high performance, efficiency and impact for all staff and managers.

A new employment law was enacted by the Government of Zambia in the reporting year. FSDZ anticipated the changes and was able to plan and budget for the increased staff costs.

#### Safeguarding

FSDZ have been a responsive partner on safeguarding. During the reporting year safeguarding policies were refreshed, and the Code of Conduct was refreshed to include new safeguards. Safeguarding training has been integrated in to the induction process for new staff.

A revised delivery chain map was developed in collaboration with DFID Zambia to include more in-depth analysis of risks. This was shared with other delivery partners as an example of good practice at a workshop held by DFID Zambia.

However, FSDZ and DFID have both acknowledged the need to further strengthen practices and develop better understanding of the costs and trade-offs of different mitigation measures.

Governance

FSDZ is governed by an Independent Board, on which DFID sits as an observer. During the reporting year progress was made on governance systems, with the adoption of new Articles of Association and governance Charter, and the addition of two sub committees – on Human Resources and Audit and Risk.

Both of these new committees have undoubtedly strengthened the overall governance structure, relieving the Board of some activity, and dealing with important issues around HR restructuring, CEO contract renewal and audit reporting.

DFID commissioned an independent review of the governance mechanisms in FSDZ in 2019. The key findings from the review are:
- The FSDZ governance structure is largely satisfactory. They are governed by appropriate Articles of Association and related documentation that meet Zambian legal requirements and are a strong foundation for the sustainability of the company.
- The FSDZ board has a strong common understanding of its objectives and vision for the organisation, with directors outlining their objectives as providing a check on management, ensuring they are operating within their set-out regulations and budgets, and ultimately ensuring FSDZ is an impactful organisation.

More needs to be done to clarify roles and responsibilities of DFID, the Board, Programme Investment Committee and Management. For example, the governance review finds that in some respects the Board acts like an advisory council to DFID, who has real decision-making power as the major donor. Resolving this will require full engagement of the Board and DFID to evolve governance arrangements effectively.

FSDZ’s Board meetings tend to be long, and the Board and Programme Investment Committee often have to review large information packs at short notice rather than being presented with short summaries of the materials with adequate notice.

Neither the FSDZ Board nor Programme Investment Committee have had a performance review or appraisal.

FSDZ has strong financial systems backed up by a knowledgeable Finance Sub-Committee. The Board has spent limited time, however, thinking about institutional sustainability and can play a larger role in supporting the CEO to bring in additional funding.

Quality and timeliness of narrative reporting and audited financial statements

FSDZ prepares monthly quarterly progress and finance reports, which were submitted on time. The quarterly reports are shared with DFID and the Board for approval. The quarterly finance report provides an analysis of   FSDZ’s performance during the quarter as compared to the cash flow forecast and budgets. The DFID programme team report that at times good warning was provided where variances were expected, but this was not consistently the case.

FSDZ is audited on an annual basis by a firm appointed by the Audit Committee. KPMG were appointed to audit the accounts in the reporting year and raised no issues of concern.

Quality of financial management

At the close of the reporting year (2018/19), the FSDZ programme had spent £17.47 million, or 76% of the total programme budget. A further £3.07 million is forecast for 2019/20 and £2.0 million for 2020/21. Table 9 sets out the forecast and actual spend for FSDZ in the 2018/19 reporting year.

Table 9: Forecast and actual spend for FSDZ 2018/19
Disbursement	Forecast	Actual	Variance	Variance %
Q1	£1.08	£0.86	£0.22	20
Q2	£0.74	£0.84	£-0.1	-1
Q3	£1.13	£1.15	£-0.02	-2
Q4	£0.49	£0.48	£0.01	2
Total	£3.44	£3.33	£0.11	3

*Note: Variances are carried over to the next quarter

Financial management improved somewhat during the reporting year but spending still varied from the approved budget by 5% (down from 18% in 2017/18).

In the reporting year:
- FSDZ forecast spend of £3.44 against the budget of £3.5m;
- Variance between forecast and actual spend was 3% (£3.33m spent against forecast of £3.44m);
- Variance between the budget and actual spend was 5% (£3.33m against £3.5m).

Despite the continued existence of variances, which at these levels is common across the nine member FSD Network, improvements were made to financial management systems and processes during the reporting year.

The contract with Deloitte and Touché (the external financial manager that had provided financial management services to FSDZ in previous reporting years) was terminated, and a new internal Finance Manager and Operations Manager were appointed. This has given FSDZ more internal oversight over its financial performance and improved communication with DFID. A new in-house internal auditor was appointed early in the 2019-20 FY to address risk management and internal audit functions.

A monthly meeting between the DFID Programme Manager and FSDZ Finance Manager was put in place. This gave DFID more notice of variances from forecast, as well as better understanding of the causes of underspend and emerging risks.

Procurement

FSDZ has a Procurement Manual which promotes openness, transparency and value for money in the procurement process.

The Special Conditions set out in the FSDZ Accountable Grant identified two areas for potential improvement: use of single sourcing and ceilings on consultants’ day rates.

The review of the Special Conditions in January 2019 found that there have been a number of instances where FSDZ has requested single sourcing, (e.g. an RCT in Luapula and a savings groups project in Eastern Province). These were discussed with DFID and more competitive routes adopted.

DFID and FSDZ continue to discuss ways of more effectively delivering competition in procurements going forward and ensuring approval processes are clear. FSD Zambia has also raised the role that an FSD Network could play in driving common standards across the network and creating pooled procurement mechanisms that could help FSDZ deliver consultancy support more quickly and cheaply without resorting to single sourcing. This should be a primary area for ongoing focus in terms of ensuring VFM and adherence to the highest standards of procurement activity.

Monitoring of assets

FSDZ maintains a register of all its fixed assets, periodically updated (normally on a monthly basis) to reflect any additions. All the company’s assets are tagged. Computers and other valuable items are allocated to specific staffs that are personally responsible for these assets. An asset spot check was conducted in June 2018 during which the disposal of guest house furniture was flagged as an issue. This has since been rectified.

Recommendations
- FDSZ should convene a donors’ group, bringing together DFID with the other funding partners on a regular basis. This will improve collaboration between donors and aim to reduce the need for separate donor requests. (FSDZ, by January 2020)
- DFID should continue to monitor the performance metrics set out in the Special Conditions of the FSDZ Accountable Grant. (DFID, on quarterly basis)
- Following completion of the independent governance review, the FSDZ Board should clarify their role in securing external funding for FSDZ, drawing on their extensive expertise and professional networks. The Board should set out a strategy for taking this forward (FSDZ Board, December 2019).
- The FSDZ Board and Programme Investment Committee should conduct an annual self-assessment to appraise their performance. (FSDZ to commission first self-assessments by April 2020)
- Continue to improve on financial management, particularly forecasting and continuous improvement in procurement practices, in order to reduce variances. (FSDZ, March 2020)

Date of last narrative financial report(s)	11 January 2019
Date of last audited annual statement (s)	03 September 2019

# G: MONITORING, EVIDENCE & LEARNING

FSDZ has a new Analytics Department. The department has 5 full-time employees, with a focus on monitoring, results management, learning, research and knowledge management. A new Director of Analytics was recruited towards the end of the reporting year in an effort to further professionalise FSDZ’s work on research, results and learning.

FSDZ spent ~£600,000 on research, knowledge management, monitoring and communications in the reporting year. This comprised 23% of the DFID funded intervention budget and 19% of the total DFID funding (i.e. inclusive of admin/staff costs). Analytics is one key area where strengthened relationships across FSD partners in Africa could help reduce country-level cost and strengthen practice.

During the reporting year the team took forward a refresh of the theory of change, aligning it to the FSDZ 5-year strategy. The log frame underwent a minor refresh, but it still fails to capture the breadth of activities underway by FSDZ, or to reflect strategic themes that the programme works on.

The log frame will be revised in 2019 to reflect the new strategy and theory of change. This will be a significant piece of work given the complexity of the FSDZ programme and will need to be taken forward in collaboration with DFID.

## Monitoring

The analytics department took forward a series of activities in relation to results measurement and monitoring. These included:
- Monitoring systems development. the team developed ‘results chains’ for new interventions and updated results chains for existing interventions. These enable the programme to develop expected results estimates and measure performance at the activity level.
- Verification. The team conducted verification assessments for a number of pilot activities under implementation across the programme (for example the Zazu financial education pilot).
- Reporting. Under this theme the team collated results against programme activities and updated progress against the log frame on a quarterly basis. A dashboard comparing annual results with targets and the FSD Zambia logframe were updated quarterly, indicating cumulative results. Logframe indicators were improved and upgraded to reflect agreements with DFID Annual Review recommendations.

The team also commissioned a VFM expert to design a new VFM framework for FSDZ. This will allow better assessment of VFM and benchmarking against other FSD programmes. The new framework will be used in 2019/20 for quarterly and annual VFM reporting.

## Evidence

The analytics department designed and commissioned a number of social research projects to generate evidence on programme performance. These included:
- Planning for a randomised control trial (RCT) to look at the impacts of involving traditional leaders in savings groups
- Planning a new study in collaboration with Oxford Policy Management to look at the extent to which savings group participation encourages participation in formal financial services
- Research in how gender and social norms affect financial inclusion with the University of Nottingham.
- An ‘end line study’ on savings groups, following up from baseline longitudinal data set collected 2 years ago.
- Providing technical assistance to Bank of Zambia to collect gender disaggregated data on banking management, staff, and customers and analyse for lessons learned.
- Support to the Zambia Information, Communication and Technology Authority (ZICTA) to design the survey tools for the National Information and Communications Technology (ICT) household survey.

## Learning and communications

During the reporting year the Analytics Department convened a series of monthly and quarterly review meetings with technical programme leads. These are a new initiative and are used to review progress of interventions, and to identify risks and opportunities. The meetings also aim to promote learning across thematic areas, as staff from different departments can join.

FSDZ has a knowledge strategy in place and in the reporting year a knowledge management ‘matrix’ was developed in the reporting year to record the progress of different learning products under way. The matrix is shared with technical leads to promote collaboration between programme staff and the analytics department.

The knowledge management strategy needs to be refreshed in light of the new 5-year strategy for FSDZ, and in particular key learning questions need to be identified. This is planned for 2019.

Currently the knowledge management strategy does not sufficiently identify the audiences that FSDZ is trying to target, and there are limited links made with the communications strategy. FSDZ also plans to develop a revised communications strategy in 2019 and will link it more closely with the knowledge management strategy.

Some good progress was made on communications in the reporting year. For example:
- A digital and print version of the 2017/18 Public Annual Report was designed and published online, with physical copies distributed widely to stakeholders and shared online.
- The team developed the branding guidelines and oriented the rest of FSD Zambia staff on their application. These were used to redesign publications (for example on Age, Gender and Financial Inclusion and the Insurance Landscape Survey). These publications have also been converted to digital versions and are available on the website.
- FSDZ engaged in several country-wide financial inclusion events. These included the 2018 Financial Literacy Week, Financial Literacy Governor’s Awards and World Savings Day.
- The team finalised website revamping and development to make it easily accessible, including on any device, and launched it to the public. The team also developed and began implementing a digital strategy to increase engagement on social media and drive traffic, awareness and usage of the new website.
## Recommendations
- The logframe needs a radical overhaul to align it to the new theory of change and FSDZ strategy. This should be done with technical support from DFID. Ideally, all donors should start to use the same results framework. (FSDZ, March 2020)
- The new Knowledge Management and Communications Strategies should be developed in parallel, to ensure that FSDZ has identified key audiences and is developing learning products for those audiences. (FSDZ, January 2020)

## Progress on recommendations from previous reviews

Table 10 summarises the progress made on recommendations made in the 2018 annual review. Overall 7 of the 12 recommendations have been completed.

Table 10: Progress on recommendations from 2018 annual review
Recommendation	Progress
For the period to March 2018, the logframe for the programme is outdated and requires review for future activity. Outputs are not always clear, and milestones are not current. In many cases, quality aspects of change due to FSDZ interventions are not captured. / (DFID & FSDZ by January 2019)	Not completed. A minor update was completed, adding two new outputs. However, a major refresh is still needed in order to better reflect the breadth of work undertaken by FSDZ to align with the FSDZ 5-year Strategy. Effective DFID engagement has been slowed by frequent staff changes.
An additional output should be added to the logframe to measure the strength of FSDZ as an independent entity. The output indicators may include strength of corporate governance (Board’s role/oversight) annual board performance evaluation, management structures/compliance (internal/external audits), financial management (% of forecasts being met), adopting a cost centre approach, and Value for Money. / (DFID & FSDZ by January 2019)	Completed.
FSDZ should engage with the government to ensure the Farmer Input Support Programme (FISP) claims are disbursed to the beneficiaries. In addition, we found that not all FISP beneficiaries under the Government-led programme are yet aware of their insurance claims and the amounts they are entitled to. FSDZ should engage the relevant department to encourage clearer communication to farmers and grievance redressal mechanisms are in place. / (FSDZ January 2019)	Partly completed. FSDZ continued to engage with Government on the FISP programme. Payments for the previous season were eventually disbursed. / However, issues with the FISP insurance programme persisted during the reporting year (See output 5.2) and appear to be above one single institution to resolve. FSDZ could work with groups like Kivu to bring about meaningful traction.
Reporting formats should be updated to have clear read across to the logframe outputs (some activities feed into multiple outputs/milestones in the current logframe) / (FSDZ and DFID January 2019)	Not completed. Though a minor review of the log frame was conducted, a full review was not finalised. The FSDZ annual report does include a table where programme activities are mapped to log frame indicators but this still does not give sufficient read across.
Independent third-party arrangements should be built into the programme monitoring regime to validate/ quality assure the results. / (FSDZ March 2019)	Completed. A sample of programme activity results were verified by external third party.
An independent assessment should be prioritised to assess the learning outcomes of the saving groups. Findings from the review should be used to improve the quality of groups / (FSDZ June 2019)	Not completed. Procurement is underway for this assessment, to be taken forward in 2019.
FSDZ should build on the success of the Zazu financial education pilot and consider how it could be scaled up on a commercially sustainable basis. (FSDZ March 2019)	Completed. The Zazu pilot was scaled up.
FSDZ should strengthen the means by which lessons from its technical support to market players are made available to other Financial Service Providers in the market / (FSDZ June 2019).	Completed. Additional knowledge management materials and events took place in the reporting year. New website was launched to increase outreach ready.
DFID should put in place a risk-based field monitoring strategy to monitor the activities in the field and obtain first hand beneficiary feedback. (DFID January 2019)	Completed. A field visit monitoring schedule for 2019 is in place
Quarterly Reporting should be provided on Value for Money indicators and risks, in addition to results. / (FSDZ January 2019 – i.e. for reporting on 2018-19 Quarter 3)	Completed. VFM reports were submitted for quarter 3 and for the annual report. A new VFM framework has been developed to improve reporting in 2019/20.
Regular donor Coordination arrangements should put in place for DFID and other funders to review progress of FSDZ, discuss challenges and financial performance together / (DFID & SIDA; March 2019)	Not completed. This was not taken forward this year.
DFID should carry out the next Annual Review (for 2018-19) at an earlier point in the year to ensure that findings are timely, and recommendations are in place for the remaining year – this should be done after the FSDZ Annual Report is received (DFID June 2019)	Completed. Annual review date brought forward.