## Annual Review Template

Title: Financial Sector Deepening Zambia (FSDZ)
Programme Value £ (full life): 22,950,000		Review date: Dec 2020
Programme Code: 203000	AMP start date: March 2013	AMP end date: March 2021

Summary of Programme Performance
Year	02/2014	11/2014	11/2015	11/2016	07/2017	12/2018	06/2019	2020
Overall Output Score	B	A	A	A	A	A	A	A
Risk Rating	Medium	Low	Medium	Minor	Minor	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-1-203000/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-1-203000/documents

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]
The UK government allocated a total of £22.9m to Financial Sector Deepening Zambia (FSDZ) over the period 2013 - 2021 to expand financial inclusion in Zambia. This programme's intended outcome is to increase access, usage and knowledge of financial services to enable Zambians to save, borrow, receive insurance coverage, make payments, or use mobile money. The programme's target impact is ”expansion in income opportunities and reduced vulnerability by poor men and women in Zambia as a result of improved financial inclusion”. FSDZ is a company limited by guarantee, formally established by DFID in 2013. FSDZ is accountable to a Board of Directors, who provide scrutiny and strategic oversight.

FSDZ’s work is guided by the ‘Making Markets Work for the Poor’ (M4P) approach, which aims to develop market systems that benefit poor people, offering them capacities and opportunities to improve their lives. FSD Zambia has built a reputation as a respected advisor, researcher, and innovation stimulator for the financial market using a wide variety of tools – including grants and cost-share agreements, research, consultancy, training, convening market players and advocacy.

This annual review covers the period April 2019 to March 2020 and therefore does not reflect disruptions due to the COVID19 pandemic. During this financial year, FSDZ invested significant work in developing the FSD Network model, which includes 9 FSD entities around Africa working together with common aims and a shared approach to financial sector development in Africa. The CEO of FSDZ was elected the Chair of the FSD Network in September 2019. At the Africa Investment Summit in January 2020, the UK Government committed £320m to FSD Africa over 5 years. The FSD Zambia Strategy for 2020-2024 was passed by the Board and is almost fully funded for five years. The structure of FSD was adjusted and approved to increase the number of technical staff implementing the new strategy (titled FSD 2.0).

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

The project has scored an A (met expectation). The FSDZ portfolio includes some strategic interventions which are contributing to transformational change in the financial system in Zambia. These include work to introduce national identification of citizens, national switch (to provide interbank clearing and payments services, and interoperable digital payments) and weather index insurance for smallholder farmers. FSD has also facilitated Savings Groups expansion nationwide, wide scale digitisation and digital finance growth in several sectors, and financial education introduction in the national curriculum grades 1-12. FSDZ staff have shown themselves to be adept at market facilitation to initiate systemic change, making full use of the different tools available – including grants and cost-share, research, consultancy training and convening, and advocacy – evidence considered in this review suggests that, when finance is deployed, it has been done carefully and proportionately. FSDZ has had a capable core team who have a high level of technical credibility with both public and private sector actors. FSD substantially exceeded its targets related to increased supply of insurance products and financial services for MSMEs (e.g. small shops), which have significant impact on poverty reduction, income generation and job creation in Zambia.

Output number	Output description	Impact Weight / (%)	Performance
1	More and better industry data and public information on the financial sector is available and used by stakeholders	5	A met expectations
2	Improved support service offering to regulators, policy making bodies and other key market actors for enhanced enabling environment to support financial inclusion (enhanced financial inclusion rules, regulations, principles and infrastructure	15	A met expectations
3	Increased financial service offering to smallholder farmers	15	B moderately did not meet expectations
4	Increased supply of inclusive insurance products and services in the insurance market	20	A++ substantially exceeded expectations
5	Widely available high quality and secure Savings Groups that are appropriate, affordable and accessible to the target clients	20	B moderately did not meet expectations
6	Increased supply and types of MSME financial services	10	A met expectations
7	Support for financial sector innovation/pilots provided	5	A++ substantially exceeded expectations
8	Corporate governance processes followed, compliance with funding partner requirements, unqualified audit, Governance charter updated, forecasting and budgeting accuracy, strategic plan, budget and workplan followed.	10	A met expectations

Major lessons
It is useful to reflect lessons from the Finscope report in 2020, which lays out where progress has been made in financial inclusion in Zambia over the past 5 years, and indicates where a focus could be in coming years. It shows digital finance has been growing fast (14% of Zambian adults using mobile money in 2015, compared to 58.5% in 2020), though banking continues not to grow substantially, with key barriers being outreach and relevance of products and services offered. Insurance take up has been slow, with only 5% of adults using it (up from 2.8% in 2015). A gender gap exists, with men having higher levels of financial inclusion, and the gap is larger in digital finance. Older, less well educated and more rural-based citizens use fewer financial services.

FSDZ performed well against all output indicators but did not meet its targets related to increasing financial inclusion of smallholder farmers and savings groups. This is consistent with the Finscope analysis that financial education uptake in Zambia has been slow, despite growing investment, and the design and delivery of financial education may need to be adjusted to reach different segments of target beneficiaries. For example, Finscope analysis of barriers to people using insurance shows 40.9% of Zambians have never heard of insurance, 10.8% don’t know the benefits of insurance and 16.5% don’t know how it works or where to get it. This is compared to only 24.9% of respondents saying they do not have insurance because they cannot afford it. This makes FSD’s performance in terms of supporting a massive growth in inclusive insurance particularly impressive.

Lack of financial education affects financial health- people’s ability to use financial services to manage daily needs, protect themselves from shocks, and achieve their goals- with only 13.6% of adults being financially healthy.

Significantly more attention is needed to financial education, and client-centric product development continues to be essential for improved financial inclusion.

Recommendations for the year ahead
1. Rolling out financial services to farmers has proven slower than anticipated, considering constraints to uptake, and FSD could consider adjusting down over-ambitious targets as well as an increase in differentiated and segmented financial education.
2. For the coming year, FSDZ should measure progress against the programme’s outcome indicators. Until now, tracking performance of outcomes is dependent on the Finscope study, which will not run again for a number of years.
3. FSDZ should revise the logframe to ensure it is in line with other logframes for FSD 2.0. Changes should include removing Output 8 on governance of FSD as well as merging outputs 3 (increased financial service offerings to smallholder farmers) and 7 (support for financial sector innovation/pilots) as both measure financial products for smallholder farmers.
4. Since this reporting period, FSDZ progress has been negatively impacted by the COVID 19 pandemic. FCDO Zambia should agree a 6-month no-cost extension with FSDZ to enable completion of disrupted activities, and to enable smooth transition to the new FCDO centrally funded FSD Africa programme. This would extend FSDZ to September 2021, at which time FCDO would conduct a project completion review.
5. As FCDO funding for FSD Zambia transitions to a new centrally-managed FSDA programme, FCDO should agree clear governance arrangements between FCDO Zambia, the team in London, and the new FSD Network adviser to be seconded by FCDO to Zambia, working 80% for the FSD Network and 20% to support the FCDO Zambia office with FSD management and oversight.
6. Donors (FCDO, SIDA, Irish Aid) should come together on a regular basis, as recommended in the previous annual review. FCDO should call a meeting early in 2021 to start this process.
7. In early 2021, FCDO to conduct a spot check to verify the FSDZ asset register is accurate.
8. FSDZ should report spend against specific outputs to facilitate more in-depth analysis of the relative value for money of its different activities.
9. In assessing the equity measure of value for money, FSD Zambia should disaggregate and quantify the targets for its core target beneficiaries (women, youth, the disabled, rural people and the poor) identified in the strategic plan. The disaggregation should be done at both thematic and project levels.
10. Logframe targets for income increases should be tracked in both kwacha and pounds sterling, and adjusted according to exchange rate fluctuations to make it easier to track income increases as a result of project interventions.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

FSD Zambia’s Theory of Change (ToC) was laid out in the 2012 business case and the theory of change and key assumptions remain valid. The theory of change is that addressing market systems challenges that hinder sustainable access and usage of financial products and services will expand financial inclusion. The ToC identifies important market functions required to facilitate sustainable change that have the potential to trigger financial market development. It specifies that the programme will tackle constraints to financial inclusion in Zambia, including policy level issues, weaknesses in financial infrastructure, and work with financial service providers themselves. It assumes that increased knowledge, access and usage of financial products and services will improve the livelihoods and/or reduce the vulnerability of poor Zambian women and men. The intended programme impact is expansion in income opportunities/reduced vulnerability by poor men and women in Zambia, as measured by average household income. The metric is informed by the Living Conditions Monitoring Survey, Finscope monitoring and FSDZ’s Impact Assessment. According to the available data, average household income in Zambia rose to £75 as estimated from the FSD Zambia Impact Assessment Survey against a 2019/20 logframe milestone of £147. This was affected by the depreciation of the Kwacha (from roughly 16 kwacha at end March 2019 to 22 at end March 2020), but still represents a significant dip in household income in real terms . Average household income has been impacted by the poor macro-economic context.

The intended outcomes are shown in the table below. Data on outcome indicators is produced by the FinScope studies which are produced every 5 years, with the most recent one reporting at the time of writing this review in late 2020. The exception is the data to track outcome indicator 2.1 on the number of access points per 10,00 adults, which is not yet available and is being worked on by FSD.

Intended Outcomes	Indicators	Status in 2015	Milestone / (March 2020)	Achieved
1 Expanded use of financial products by Zambian adults	1.1 % of adults financially included in Zambia	59%	65% (of which 50% women)	69.4%
2. Expanded access to financial services	2.1 Number of access points per 10,000 adults	7	10	***there are 92.6 access points per 10,000 adults
	2.2 % of adults with at least one type of financial product	11.5%	18.7%	69.4%*
3. Increased financial knowledge and understanding of financial products and services	3.1 % of adults with high financial knowledge	29% (in 2016)	45%	23.6%**

*This relates to the % of adults with access to formal financial services.
** This tracks financial literacy levels, but the criteria were adjusted, which has resulted in the decline in % terms.
*** UNCDF state of the DFS industry 2019 page 13,

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

FSD Zambia’s mandate is to contribute the improvement in financial inclusion. Based on the targets set for the attainment of outcome indicators, there is a clear demonstration that the programme is on track in contributing to improvements in financial inclusion benchmarks as set out in the National Financial Inclusion Strategy. There was particularly impressive performance on two indicators; adults who are financially included and adults with at least one type of financial product. Going forward, FSD Zambia will need to pay more attention to programmes that are targeted toward improvement in financial knowledge such as financial literacy programs.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

FSD fits with the UK Government priorities for international development to promote global prosperity through building the financial sector in developing countries, both to encourage and enable investment, and to make financial systems more inclusive; to support economic transformation, growth and job creation. Further increased support to FSD Africa was announced by the Prime Minister at the Africa Investment Summit in January 2020 in London. FSD Zambia also fits with the HMG priority to strengthen resilience and response to crisis, by expanding access to weather index-based insurance for small scale farmers and savings products to build individual economic resilience, allowing households to withstand shocks such as poor rainfall or ill health. Financial sector reform and inclusion are important priorities for the Government of Zambia (GRZ), demonstrated by the strong interest from the Ministry of Finance and FSD partnership with the Bank of Zambia. The programme is performing well, represents good value for money, and should continue.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	More and better industry data and public information on the financial sector is available and used by stakeholders
Output number:		1	Output Score:	A- met expectations
Impact weighting (%):		5	Weighting revised since last AR?	Yes, from 10% to 5% as additional outputs were added.

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of financial sector stakeholders accessing industry data and public information products (disaggregated by local and International)	50	69 / (Local: 40 / International: 29)
1.2 Number of financial sector focused knowledge products (research papers, blogs, infographics, focus notes, etc) produced and disseminated to the stakeholders	35	45
1.3 Number of targeted clients receiving financial education; / a) Planned / b) Women	a) 155,500 / b) 77,750	a) 89,238 / b) 54,119
1.4 Number of target beneficiaries receiving financial awareness / a) Planned / b) Women	31,259 / 15,625	897,717 / 394,943

Briefly describe the output’s activities and provide supporting narrative for the score.

This output has scored A- met expectations, a significant improvement from the previous annual review where this output scored C (output substantially not met expectations). All targets were significantly exceeded apart from the number of clients receiving financial education, where only 60% of the target was achieved. This included financial education offered though saving groups; education on insurance products; working with education institutes; incorporating financial literacy into the curriculums and radio programmes. The target was not met as FSDZ does not recognise work of some of its implementers who did not meet set criteria.

The number of beneficiaries with increased financial awareness was 897,717 massively exceeding the target of 31,259. This is largely attributed to a successful partnership with Mayfair Insurance who in turn partnered with the Zambian government to include weather index insurance to the national Farmer Input Support Programme (FISP). Zazu developed a mobile phone-based application that was used to sensitise farmers under the FISP about weather index insurance. The product sensitisation content was developed in English and translated into 7 local languages. Mayfair Insurance with support from FSD Zambia, bought airtime on TV and radio to inform farmers about the free learning on topics related to weather index insurance. Further outreach activities were organised at community level in conjunction with the local extension officers. The annual review team visited some beneficiaries of the weather index insurance in Chongwe and Mumbwa district and received positive feedback. Farmers are enthusiastic about the product which has been introduced at a time when weather patterns are becoming more erratic due to climate change. However, the team noted a gap in consumer awareness: despite the training, some the farmers were unfamiliar about many product features and how they work.

69 financial sector stakeholders accessed industry data and products, exceeding the target of 50. The main stakeholders include universities, commercial companies and consultancy firms. Notably, the number of financial sector focused knowledge products produced and disseminated to stakeholders significantly exceeded the target and comprised 12 blogs, 3 briefs, 3 research papers, 8 articles and 19 podcasts. Although the target was achieved, impact could be enhanced by interrogating data further to determine how the information was used.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

As FSDZ report on budget expenditure according to thematic areas, a direct mapping of spend to each output is not possible this year. Direct mapping of expenditure to outputs should be done in future years.

FSDZ’s collaboration with other financial stakeholders to benefit from pre-existing means of communication with beneficiaries, within pre-established structures, demonstrates good use of resources and a drive to make efficiencies. For example, the extremely high over-achievement in beneficiaries receiving financial awareness demonstrates effectiveness. Addressing those issues that led to certain implementers not meeting the requisite criteria on financial education will be crucial to achieve efficiency and effectiveness on output 1.3 in coming years.

FSDZ demonstrated good economy in its research activities by establishing a 50:50 cost -share partnership with international universities (Leiden and Nottingham Universities) to undertake research on “Social and Gender norms focusing on financial decision making between couples” that will inform FSDZ programming. Targets around research were met, even though expenditure on research and knowledge management was just 43% of the amount budgeted.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Two more indicators were added - indicator 1.2 to capture the knowledge products produced and disseminated to the public and indicator 1.4 to capture and measure activities under financial awareness campaigns being implemented by FSD Zambia and its partners.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

In response to the AR recommendation that FSD link with renewable energy programmes to make is easier for beneficiaries to charge phones when mains electricity is unreliable, FSD has supplied solar mini-chargers in the Cash Shake-Off initiative. Cash Shake-off is an FSD initiative to facilitate public awareness and education of financial services and products, and to expand usage of digital financial services to low-income rural women and other groups from vulnerable households. This is being done through distribution of up to 44,000 low cost cell phones and up to 12,000 solar phone chargers in areas with cell tower coverage. FSD is also looking at engaging Savings Groups to purchase these items.

Recommendations:
- FSDZ should introduce a future indicator that measures information rather than just dissemination (as per indicator 1.2).
- FSD could work with implementers to help them meet set criteria regarding standards of financial education in future, and to segment and target financial education for increased uptake and impact.

Output Title	Improved support service offering to regulators, policy making bodies and other key market actors for enhanced enabling environment to support financial inclusion (enhanced financial inclusion rules, regulations, principles and infrastructure)
Output number:		2	Output Score:	A met expectations
Impact weighting (%):		15	Weighting revised since last AR.	Y- new output

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of policy/regulatory bodies and other market actors receiving FSD Zambia support (technical assistance (TA), Human Resources (HR) development, Training, financial, strategy formulation, monitoring)	9	12
2.2 Number of targeted support services offered to policy and regulatory bodies and other market actors during the year	11	8
2.3 Number of financial inclusion rules, regulations, initiatives, principles, strategies developed/revised with FSD Zambia support during the year	3	4
2.4 Number of financial infrastructure functions recording progress during the year	8	6

Over the year, FSD supported 12 key government and private sector institutions to improve the policy and regulatory environment necessary for improving the effectiveness of the financial sector ecosystem. These organisations including the Pensions and Insurance Authority, Technical Advisory Group, Insurers Association of Zambia, Bank of Zambia, Zambia Information Communications Technology Authority, Ministry of Finance and Smart Zambia Institute, a division under the Office of the President, mandated to coordinate and implement e-government for improved service delivery. FSDZ provided targeted support services to 8 of these organisations, below the target of 11, with requests being relatively low due to limited capacity, especially within government institutions to deliver the intended objectives of service uptake. However, a range of impressive support services were delivered.

During the year, FSD Zambia conducted a detailed assessment to determine the significance of FSD Zambia support to partners. Average partner and end client responses showed that FSD Zambia support meets the expectations of the partners and target beneficiaries, and the support provided is significant in helping them pursue their individual financial inclusion agendas into their lives. Interviews held by the review team confirmed FSDZ has built a constructive relationship with the Government of Zambia (GRZ). FSDZ support to the Bank of Zambia included FSDZ-facilitated workshops to support BoZ implementation of the National Payment Systems (NPS) Act. Commercial banks, fintechs and mobile network operators were also brought together to discuss views. FSD Zambia has continued to engage the BoZ to ensure the NPS Bill is presented to the National Assembly for consideration during the 2020 legislative period. FSD also provided high-level project management training for practitioners with participants from BoZ, commercial banks, non-bank financial institutions, mobile network operators and others. Bank of Zambia particularly noted support from FSD to ensure Government reach rural areas with digital financial services and financial products.

Smart Zambia noted the quality technical support on the Biometric ID programme and the efforts FSDZ had put in to assist with donor engagement plans, which has been particularly helpful for quality control of the system. At the Smart Zambia Institute (SZI), FSD Zambia took a strategic role to lead some components of change management in the biometrics identity project, extended project management training to 4 SZI staff; and facilitated stakeholder discussion on the best course of action for digitising government. FSDZ also supported a stakeholders’ workshop with The Zambia Electronic Clearing House (ZECHL), banks and Mobile Money Operators (MMOs) a to discuss the interchange and associated fees of the National Financial Switch (NFS).

FSDZ exceeded the target of 3, achieving 4 financial related rules, regulations, initiatives, principles, strategies developed/revised with FSD Zambia support. This included revisions to the Bank of Zambia strategy, National Payment Systems Act and operationalisation of the Payments Association of Zambia (PAYZ). PAYZ is widely respected by financial service providers for providing sector players with a self-regulating system of checks and balances and FSDZ has committed finances to support the Secretariat‘s start-up and initial maintenance.

Progress in terms of the number of financial infrastructure functions recording progress during the year was slightly off target. FSDZ developed a scoring system to assess the level of infrastructure development with a scale of 0 (nothing in place) to 8 (infrastructure is in use by more than 50% of relevant financial institutions). During the review period, FSDZ supported the creation of a fully functional Collateral Register hosted by the Patent and Company Registration Agency; work towards the National Financial Switch (NFS) which went live across automatic teller machines (ATMs), points of sale (POS) machines mobile payments across the country Zambia National Data Centre; supported discussions on the ideal type of biometric identity system; support to the Payment Association Zambia (PAYZ); and awareness campaigns on the roll out of a credit reference bureau and credit monitoring as part of a credit market analysis.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

The FSD Zambia commissioned report notes good efficiency scores for output 2, reflecting that the policy and regulatory bodies referred to in output 2.1 have been responsive, which has helped with efficient implementation by FSD Zambia. This was supported by stakeholder interviews. By operating effectively at the policy level and liaising with key Zambian institutions, FSD Zambia is building the foundation for sustainable improvements in the operating environment.

The effectiveness of these outputs in achieving the desired outcomes and impact will depend upon the implementation of the various initiatives and strategies devised and this should be tracked in the coming year.
Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

This new output was developed as a combination between old Outputs 2 and 3, which measured improvements in the policy and regulatory environment, infrastructure and support services for financial sector development. Indicators were added to specifically measure the contributions of FSD Zambia to these improvements.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The output and indicators were adjusted as recommended in the previous annual review.
FSDZ is a valued partner to financial institutions in terms of its support to improve the enabling environment for inclusive financial sector development, and this work should continue to be prioritised and developed.

FSDZ to consider the developing a financial sustainability plan for all infrastructure that has attained level 6 of development.

Output Title	Increased financial service offering to smallholder farmers
Output number:		3	Output Score:	B moderately did not meet expectations
Impact weighting (%):		15	Weighting revised since last AR?	New output

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of Rural Agricultural Finance (RAF) FSPs receiving FSD Zambia support (TA, Business development support, etc) to design/deliver financial services to smallholder farmers	9	8
3.2 Number of targeted clients accessing RAF financial products and services due to FSD Zambia support / a) Planned / b) Women	66,000 / 33,000	56,193 / 25,158

FSD Zambia works to increase rural financial inclusion by building the capacity of smallholder farmers and rural communities to engage in financial services, particularly agriculture. It also supports Financial Service Providers (FSPs) to offer a wider and more relevant range of financial services to rural people. This year, FSDZ did not meet expectations in terms of the number of financial products developed and utilised by smallholder farmers. This is a new output and most interventions were in their pilot phase. FSDZ did significant work on crop insurance expansion as well as digitisation and cell phone access of farmer market and cultivation data.  All this work was experimental pilot work and expansion was not as expected due to the slow processes of farmer innovation. FSDZ now predicts a 3-5 year period to uptake rather than the initially expected 2-3 years.

FSD Zambia supported 8 (against a target of 9) RAFs to design/deliver financial services to smallholder farmers. The organisations supported include Investrust, Agora Microfinance, Alliance Ginnery, Mayfair, ATS, Mushili Corporation, Vision Fund Zambia, and Rent to Own. Key achievements include:
- Launch of the micro-leasing facility bundled with input credit pilot project. The project is jointly funded by Rent-To-Own (RTO) and FSD Zambia and is using a two-pronged approach of offering small holder farmers solar irrigation pumps jointly with K5,000 or K10,000 worth of inputs, with the repayment period of between 12-20 months. During the reporting period eleven 11 smallholder farms accessed the package with a total value of ZMW 209,000.
- FSD Zambia supported 16 small aggregators to access finance from Investrust Bank Plc Under the invoice discounting bundled with credit guarantee. This support directly benefitted 278 SHFs who supplied horticultural produce to the aggregators.
- The pilot project with Alliance Ginneries to advance cash payment for contract cotton with small holder farmer pilot project was scaled up. The expansion involved increase in the number of small holder farmer clients SHFs from 3,414 to 15,000 and bundling payments with crop insurance

Indicator 3.2 measures the number of targeted clients accessing rural access finance financial products and services due to FSD Zambia support. The metric did not meet targeted expectations, largely attributed to most activities being in their pilot phase and not being fully rolled out through partners such as Alliance Ginnery, Agora, Rent to Own and Investrust.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

While this output has good potential, the relative infancy of the activities makes it difficult to yet judge overall VfM. For example, in considering the efficiency measure, the FSD Zambia commissioned VFM report notes that the slight under achievement in output 3.1 (design and delivery of financial services to SHF) could be attributed to the requirement for financial service providers to contribute to intervention costs, and nudging toward this may take more time than initially anticipated.

Frequent, thorough and honest appraisal of the interventions being piloted will be required to ensure that those interventions that provide the best value for money are pursued at scale and this should be reflected in future logframes accordingly.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

This is new output, which brings together indicators from several outputs from the old logframe to clearly track financial inclusion of smallholder farmers. This is better aligned to the theory of change in terms of improved livelihoods and reduced vulnerability of poor men and women as a result of access to rural agricultural finance, inclusive insurance and informal finance.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

This output was added and indicators refined in line with recommendations in the last annual review.

Recommendations are:
- Rolling out financial services to farmers is slower than expected, considering constraints to uptake, and FSD could consider a stronger j-curve on targets.
- FSD should work with farmer associations to extend product options, building on learning and interest to date.

Output Title	Increased supply of inclusive insurance products and services in the insurance market
Output number:		4	Output Score:	A++ substantially exceeded expectations
Impact weighting (%):		20	Weighting revised since last AR?	Yes- this is a new output

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of FSPs receiving FSD Zambia support (Technical Assistance, Business devpt support etc) to design/deliver inclusive insurance products and services to target clients during the year.	7	10
4.2 Number of targeted clients accessing insurance products due to FSD Zambia support. / a) Planned / b) Women	a) 132,000 / b) 66,000	a) 234,421 / b) 119,930
[note] Financial Service Provider

FSD Zambia provided excellent support to market actors to develop and deliver tailor-made and appropriate insurance products and services to the low-income individuals and households, and to expand market information and understanding. During the reporting year, FSDZ worked with Madison General Insurance, Barclays Bank, Sanlam, ZSIC Life, Hollard Zambia, Pula Advisors, Innovate Insurance, General Alliance, Mayfair, and Professional insurance Zambia. Key activities that contributed to the results included support to:
- Technical Advisory Group on microinsurance (TAG) to organise a microinsurance industry capacity building workshop for insurance industry stakeholders to develop products that meet specific needs of intended beneficiaries;
- Celsius Pro20 to develop digitised insurance training in Kaonde, Luvale, Bemba, Nyanja, Lozi, Tonga and Lunda to trigger the course, farmers were sending the word ‘FISP” to 619.
- Sanlam Life, Madison Life and Barclays Life for the Inclusive Insurance Upscaling Challenge Fund (IIUCF). Under the IIUCF facility, Barclays Life’s Twafwane funeral insurance product covered a total of 587 lives while Madison Life domestic travel insurance product covered a total of 1,581 lives while Sanlam Life under their funeral and hospitalisation product covered 2,285 lives.
- General Alliance (GA) and Hollard Life for pilots of GA’s fire microinsurance product bundled with life insurance cover for microentrepreneurs; and Hollard Life’s life insurance product through chain stores for easy access by low-income individuals and/or store customers. This is expected to commence in the next FY.
- The Government Weather Index Insurance Project under FISP, signing a partnership agreement with the Smart Zambia Institute (SZI). The aim was to enhance the Zambia Integrated Agriculture Management Information System (ZIAMIS) for the development of a comprehensive and dedicated solution to manage the weather index insurance product.
Over 234,000 clients have accessed insurance due to FSD Zambia support for new insurance products, with just over half being women. These impressive results are over double the target. FSD supported the design, implementation, and client and insurance firm sensitisation of the weather index insurance offered by Mayfair and Pula Advisors These 234,000 new clients contributed to the total of 1,085,721 farmers covered during the 2019/2020 farming season (with the rest being existing clients). Mayfair alone provided cover to 940,207 smallholder farmers through its partnership with the Ministry of Agriculture (MoA), Alliance Ginneries, World Food Programme, NWK, Afri-Seed, Agora Micro-finance, and Vision Fund. Pula Advisors provided cover to 145,514 SHF under FISP. Farmers interviewed by the review team in Mumbwa and Chongwe testified to the benefits of insurance pay-outs which they used to purchase farming tools, pesticides and vegetable seeds which they grow during off maize season to sustain their livelihoods. They are willing to increase their own premium contributions to increase the pay-out which they feel is not enough. Minimum pay-out for the year under review was Kwacha 85.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]
In substantially exceeding expectations and performing above target on the two indicators of relevance, this output is deemed to be very effective and good value for money. The partnerships with several existing FSPs increase the likelihood that a competitive market for insurance products can be sustained. This output has very high potential for both likelihood of success and potential impact.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

This output was introduced to adequately capture FSDZ’s work in the insurance sector.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

- The impressive progress to supply inclusive insurance products and services should be capitalised on in coming years with further attention and expansion.
- FSD should work with insurance providers to help ensure clients understand all relevant features of insurance products, as some beneficiaries seemed to have limited understanding of how, e.g. micro insurance works.

Output Title	Widely available high quality and secure Savings Groups that are appropriate, affordable and accessible to the target clients
Output number:		5	Output Score:	B- moderately did not meet expectations.
Impact weighting (%):		20	Weighting revised since last AR?	Yes- new output

Indicator(s)	Milestone(s) for this review	Progress
5.1 Number of savings groups providing SG products and services to the targeted clients	4,600	2,360
5.2 Number of targeted clients accessing SG financial products and services due to FSD Zambia support / a) Planned / b) Women	a) 62,542 / b) 40,654	a) 48,798 / b) 42,942
5.3 Number of Master Trainer/private sector providers/community-based trainers providing SG training, supervision services to targeted SG members. / a) Planned / b) Women	a) 643 / b) 322	a) 412 / b)187
5.4 Total number of SGs per 10,000 people	735	480
5.5 Number of stakeholders receiving FSD Zambia support in SG service delivery	7	7

Significant achievements were made related to this output. FSD works with a range of partners to support savings groups products and services, including the Catholic Dioceses of Ndola; Financial Inclusion through Traditional Leadership (FIT); Caritas; Mansa Diocese; and Girls Education and Women`s Empowerment and Livelihoods (GEWEL). During the period under review, there was engagement in savings groups expansion from the World Bank and Ministry of Community Development and Social Services (MCDSS), and Provincial Chiefs from Eastern Province visited Luapula to learn from FIT savings groups there. The number of women in savings groups remains much higher than the number of men, and GEWEL and Master Trainer are reported to be making some progress in encouraging men to join. The review team found that MCDSS (GEWEL project) staff appreciate the support of FSD to provide financial and technical support to build the capacity of MCDSS staff to implement the Master Training Plan (MYP) model. The Ministry confirmed the FSDZ model will be implemented in 51 districts of Zambia.

Due to COVID-19 restrictions, the review team was unable to meet savings groups. However, the MTs attested to impressive results in terms of women’s empowerment, expansion of small businesses, paying school fees, purchasing of land, buildings, etc. Both businesses and savings are growing, increasing the number of transactions through savings groups. For example, the review team heard that one trader had K4,000 worth of goods in 2013,and after steady growth through accessing SG loans, K35,000 in 2019.

Progress against this output was slower than intended due to Innovations for Poverty Action (IPA) delaying the baseline study for the randomised controlled trial (RCT) necessitating delays to implementation of Financial Inclusion through Traditional Leadership (FIT) savings group development until IPA had finalised their village selection methods across Luapula Province, which only happened half way through the financial year. This was problematic and was outside the control of FSD.

FSD partnered with the Savings at the Frontier (SatF) programme (led by Mastercard Foundation and Oxford Policy Management) to conduct a qualitative study of Informal Savings Mechanisms (ISMs), particularly Savings Groups in three provinces (Copperbelt, Luapula and Lusaka). The aim of the study was to gain new insights regarding ISM users, how they perceive their groups and formal FSPs, and what drives their decisions to use one service rather than another.
[note] https://www.opml.co.uk/files/Publications/a0600-savings-at-the-frontier/19-12-11-zooming-in-on-isms-in-zambia-sv2.pdf?noredirect=1

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]
While performance against this output this year was behind target, this was attributable to delays in implementation that should be overcome in the medium term. In that respect, this output demonstrates promise.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

This is new output to better align the logframe with the theory of change in terms of supporting inclusive and informal enterprise finance.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The previous AR recommended that FSDZ continue to look at how savings groups can use digital systems (for example mobile phone banking) and promote this for new savings groups. FSD has been looking at this, but many SG members do not have cell phones, and until this year signal in several areas was poor. FSD expects to do a Finscope challenge to try to progress this.

Output Title	Increased supply and types of MSME financial services.
Output number:		6	Output Score:	A - met expectations
Impact weighting (%):		10	Weighting revised since last AR?	Yes, from 20% to 10%

Indicator(s)	Milestone(s) for this review	Progress
6.1 Number of financial service providers (FSPs) receiving FSD Zambia support to design/deliver appropriate and affordable MSME financial products and services	1	2
6.2 Number of MSMEs accessing financial products and services due to FSD Zambia support / a) Planned / b) Women	a) 400 / b) 200	a) 501 / b) 185

During the reporting time FSD Zambia completed the second-round call for Finclient Centric Cycle (F3C) applications, targeting rural enterprises, women and youth and digitisation of savings groups operations. Out of the ten applicants, four were selected and FSD started working with United Bank for Africa (UBA) to develop a product for rural enterprises. UBA has since undergone the first design sprint and is expected to design a prototype after field activities are completed. FSD also worked with Investrust Bank on inclusive enterprise finance.

501 MSMEs accessed financial products and services (against a target of 400) due to FSD Zambia support to FSDPs to design and deliver financial services to MSMEs. Most MSMEs supported were in wholesale and trade as well as horticulture who are predominantly from rural parts of the country. MSMEs supported under FSD’s Inclusive Enterprise Finance workstream include:
- Working Capital Access (WCA): Choma (103) Maamba (110), Chipata (51), Solwezi (80), WCA-Wholesalers (10)
- Rural Enterprise Growth (REG)- Agro-dealers (4),
- Rural Agricultural Finance-Investrust (19)
- Microinsurance Acceleration Facility – Chilala (124).
The impressive performance in terms of the number of MSMEs accessing financial products and services was due to the scaling up of the Working Capital Access intervention and the launch of the Rural Enterprise Growth intervention, which attracted significant demand from MSMEs. The WCA project aims to address challenges of growth by increasing the cash flows or working capital of traders using a blend of informal and formal finance mechanisms, including partnerships between wholesalers, banks and groups of rural traders organised in savings groups. Feedback from WCA project shop-owners visited in Choma was positive- all had used the scheme to invest in expanding or diversifying their businesses. In general, they appeared to be borrowing for stock that was equivalent to 1-2 months of business income.  Interest rates were said to be 20% over 3 months – but shop owners seemed to welcome this as a good deal and had no other apparent finance options other than money lenders who would be much higher. The savings element meant they also had a cash share-out at end of the year.  In one case, a shop-owner had received 30,000 kwacha and had used it to buy a new house. Others had used it to buy their own shop premises instead of renting and investing in new shops.  Another had used the combination of borrowing and share-outs to install solar electricity in their shop, diversify into other business lines, such as mobile money and cash management, and expand the range of items they had for sale (e.g. moving into school uniforms).

Despite the over-achievement of the target of MSMEs accessing financial products and services, the number of women owned MSMEs accessing financial products and services was 185, slightly below the target of 200. This is a concern because FSD analysis shows that 55% of Zambian MSMEs (e.g. rural shops) are operated by women whereas women only represent 7% of the beneficiaries.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]
In facilitating greater access to well-targeted financial services and products for MSMEs, of which 37% of the beneficiaries were women, this output delivered effectively and performed well on measures of equity. Interviews conducted as part of the review process provided anecdotal evidence of step-change improvements in the ability of MSME owner to access capital and expand their businesses. In this way, the activities undertaken by FSD Zambia under this output had a beneficial multiplier effect for local economies, effectively facilitating business expansion and investment. Given the very high interest rates faced by Zambian MSMEs through existing commercial facilities, largely as a result of wider macroeconomic factors, activities under this output at relatively low cost to FSDZ, have delivered an effective mechanism for firms to access capital.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
The weighting of this output was reduced in the logframe refresh.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs
- In relation to our separate off-grid energy objectives, it was interesting that candles were one of the most popular/regular sales items in the WCA shops the team visited in Choma.  The likely savings that could be made through purchases of pico-solar lamps are somewhat stymied by the wholesaler and small shops welcoming the volume and regularity of trade in candles.  FSDZ could investigate whether these types of shop-owners could agree a suitable incentive structure with a company like SolarAid/SunnyMoney to stock high quality solar lamps which save customers money, reduce fire hazards and air pollution, rather than candles.
- FSD should consider how to promote sustainability of the WCA model, noting the complexity of different actors involved. FSD and FCDO should consider the need for a broader role for BHC or Prospero to help communicate or encourage certain players to take this up as a model.
- FSD should research why there is more uptake by men than women for financial products and services aimed at MSMEs and address the bias.

Output Title	Support for financial sector innovation/pilots provided
Output number:		7	Output Score:	A++ substantially exceeded target
Impact weighting (%):		5	Weighting revised since last AR?	Yes- new output

Indicator(s)	Milestone(s) for this review	Progress
7.1 Number of financial sector pilots/innovations supported by FSD Zambia	5	10
7.2 Number of financial products/services developed/revised due to FSD Zambia support	3	7

This is an important output; FSD supported-pilots and innovations are significant because financial service providers have often struggled to design their products to fit client needs.

The number of financial sector pilots/innovations supported by FSD Zambia was double the set target. This included:
- Mobile Phone Financial Education by Zazu,
- Digitizing Loan processes -Agora Microfinance Zambia;
- Developing and launching a Comic Relief/JOA project to digitise payments and provide value added services to farmers;
- Micro-leasing bundled with input credit. This pilot was jointly funded with Rent–To–own was implemented in Chongwe and Chibombo farming areas.
- Rent to own micro-leasing bundled with input credit, with Informal Finance;
- A working capital access for MSMEs pilot; and
- Bank Yako Yako- a digital financial services (DFS) radio soap opera to train families on DFS processes and benefits implemented through various radio stations in Easter Province.
Feedback to the review team from Zazu (Zambia’s first digital only bank) on FSD’s technical support was very positive. FSD support included loading the Financial Education courses on the App. This intervention by FSD piloted financial education through a mobile phone-based platform in Bemba and English and sought to scale up to include consumer protection, with translation into more local languages (Nyanja, Tonga, Lozi and Kaonde) planned. The course contents included income and budgeting, savings, loans, micro-insurance, mobile money and consumer protection. However, Zazu terminated the partnership agreement with FSDZ in May 2020. The main reason for the termination was the high cost of maintaining the platform and not breaking even given lack of sufficient demand (pull) from learners. This situation has resulted in suspension of delivery of financial education activities to low income groups such as SHFs. FSDZ has engaged Kwantum Innovations to set up a new FE digital platform with costs related to the number of learners.

The number of financial products/services developed/revised due to FSD Zambia support also exceeded the target by more than double. These products and services included invoice discounting for horticultural farmers, Inclusive Crop Insurance Scheme Pilot, Funeral and health microinsurance.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

While FSDZ performed very strongly against its targets in this output, thereby demonstrating good efficiency, the extent to which these pilots have demonstrated a marketable concept and lead to longer term uptake by FSPs will determine their effectiveness. This should be monitored by FSDZ going forward.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

This new Output and the indicators were added in response to a recommendation from the 2018 AR, to align the logframe with FSDZ’s 5-year strategy and the theory of change.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs

- FSD to consider merging outputs 3 (increased financial service offerings to smallholder farmers) and 7 (support for financial sector innovation/pilots) as both largely measure financial products for smallholder farmers.
- FSD Zambia will consider working through other partners such as Viamo to improve financial education for SHFs.

Output Title	Corporate governance processes followed, compliance with funding partner requirements, unqualified audit, Governance charter updated, forecasting and budgeting accuracy, strategic plan, budget and workplan followed.
Output number:		8	Output Score:	A met expectations
Impact weighting (%):		10	Weighting revised since last AR?	Yes- this output was added

Indicator(s)	Milestone(s) for this review	Progress
8.1 Corporate governance processes followed, compliance with funding partner requirements, unqualified audit, Governance charter updated, forecasting and budgeting accuracy, strategic plan, budget and workplan followed.	All processes followed.	Achieved
8.2 Amount (£) of funding provided to FSD Zambia by donors other than DFID (FCDO).	1.2m	957,885

Strong progress was made on corporate governance, with the Board and 3 Committees (HR, Audit and Risk) meeting regularly. Governance was fully aligned with legal and good practice requirements per the Company Secretary’s annual report. Compliance with funding partner requirements was good over the period, reflected in the annual audit, tracking in quarterly reviews and reporting. The audit was unqualified for the fourth consecutive year with a few minor items complete or presently being completed. The governance charter was updated, and the new five-year strategy aligned to the FSD Network and FSD 2.0 was approved on 23 March. Budgeting and forecasting improved after a problematic first two quarters (more detail in Section E).

Other donors almost matched DFID funding for the year. In addition, the UK Government committed £22.4m over 5 years to FSD Zambia as part of the FSDA total commitment announced by the Prime Minister at the 20 January Africa Investment Summit in London. FSD also secured a £403,000 cost extension from the Swedish International Development Agency; £400,000 from Comic Relief and Jersey Overseas Aid; £50,000 from the University of Nottingham or work on social norms and gender; and £3.2m committed to be signed next year with SIDA for Women and Youth in Financial Inclusion. Together with the performance on following corporate governance processes, this warrants a score of A.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]
The improvement of corporate governance processes, budgeting and audit has led to more efficient delivery of central administrative functions. Ongoing openness to strategic challenge and learning from thorough monitoring and evaluation procedures will enable FSD Zambia to revise, refine and adapt its portfolio to hone in on the highest value interventions. By expanding its sources of funding throughout the year, FSD Zambia has diversified its risk and improved long-term sustainability.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

This is new Output added following the 2018 AR recommendation to monitor required improvements in corporate governance.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

- FSD should continue to focus on accurate and timely budgeting and forecasting, and quick communication of any changes to FCDO.
- The previous AR recommended FSD bring donors together more frequently and this remains to be done. This is particularly important during the transition to FSD2.0 and because of the different requirements of donors. FCDO should take on this recommendation and bring donors together.

D: RISK [½ to 1 page]

Overall risk rating: Moderate

Overview of programme risk
The overall risk assessment for the programme is moderate, which is aligned with FCDO Zambia appetite and the DFID programme team and advisers reviewed the risk register for the programme each quarter, in consultation with FSD Zambia Team. In addition, the delivery chain risk map was reviewed and updated every six months. During the period under review, the main risks included:

1. Contextual risk; Macro-economy - significant deterioration in the global environment or the Zambian macroeconomy could limit the appetite for FDSZ’s partners (such as financial institutions) to engage with new customers and markets. Climatic variability, particularly affecting agricultural livelihoods and causing load shedding.
2. Delivery risk; Policy environment and partner support - Deterioration in the Zambian policy/regulatory environment (e.g. reserve requirements further crowd out lending to MSMEs; Financial Inclusion Policy not finalised). Key policy partners such as Bank of Zambia, Ministry of Finance, and the Pensions and Insurance Authority cease to be supportive of financial inclusion.
3. Operational Risk; Diversions of expectations, requirements and ways of working between donors, including joint funding, logframe, workplans etc
4. Reputational risk; Misuse of funds - funds not being used as intended e.g. fraud and corruption (a proportion of the programme funds were subcontracted and granted to downstream organisations).
5. Safeguarding risk; Safeguarding violations may be going unnoticed or unaddressed due to socio-economic and cultural contexts which negatively affect identification and of reporting. Participants of saving groups may be at risk of gender-based violence (at home or in the community) as a result of shifting household dynamics linked to new livelihood
streams or increased income.

Key risks that emerged during the reporting period:
The contextual risk environment showing an increasing trend and further deterioration during the period under review, particularly due to the devaluation of the Kwacha and high lending interest rate caps affecting livelihoods and private sector access to finances. Another emerging risk was possible disruption to DFID programme funding and oversight due to planned DFID internal transition from oversight by the Zambia office to FSDA managed by a team in London., This risk was managed through communications such as transition meetings and written guidance between DFID Zambia, the London team and FSDZ, to manage emerging risks around complementary logframes, workplans and funding.

DFID staff turnover became an operational risk during the period. Both the Senior Responsible Owner and lead adviser were leaving FCDO Zambia almost at the same time and a risk of maintaining oversight and continuity was identified. Handover plans were put in place with comprehensive notes. Key documents were saved on the internal DFID filing system (VAULT), and the programme manager continued to hold long-term institutional knowledge.

#### A further risk emerged during the period: as DFID Zambia funding was ending in 2021, the accountable grant agreement required FSDZ to secure funding from other sources in order to receive funding from DFID. In the year under review, FSDZ was to secure £1 million in order to receive matched funding from DFID. This was identified as a risk as failure to raise the £1m would affect implementation of activities.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Governance
FSD Zambia is accountable to a Board of Directors who provide scrutiny and strategic oversight. FCDO is a Member, has a veto over key decisions, and chairs the AGM. The Board is supported by three committees: HR; Audit and Risk; and the Programme Investment Committee (PIC). The PIC provides expert technical advice and guidance on investment decisions, FCDO is a member of the PIC.

During the year under review, the PIC and the Board met four times and had a strategy retreat. The Audit and Risk Committee and the Human Resources Committee of the Board had their first full financial year, and met three and four times, respectively. The Board and its committees finalised the FSD Zambia Charter, which is the working document for all governance, and determined the process for selecting, orienting, and replacement of governance body members. It finalised the revised human resource approach, confirmed levels of compensation for staff, reviewed the performance of the CEO and renewed her contract. The Board responded to and acted on the DFID Governance Review recommendations, approved a new Five-Year Strategy and a fundraising strategy, established/revised policies for Internal Audit and Risk Management and Communications and moved the Internal Audit function in-house with a full-time Director. It reviewed FSD Zambia contributions to the FSD Network strategy and decided to join the FSD Network. The annual budget, workplans, and various revisions of funding were reviewed and approved. The prior year annual report with unqualified external audit was presented to the Members and financing partners in the AGM. The Board considered and made revisions in the PIC roles and responsibilities and the financing partner roles in governance bodies, by the Members’ request.

Monitoring
Monitoring of actual results against set targets is done through monthly review meetings with FSD monitoring and results measurement (MRM) and quarterly progress meetings (QPM) with MRM and project leads, as well as a review of quarterly reports from FSD. QPMs and monthly review meetings assess project progress, review challenges and determine actions to be taken. FSDZ submits quarterly reports detailing progress made in terms of targets and actual achievements, risks and challenges faced and mitigation measures as well as the status of financial spend. Quarterly report from FSD partners are integrated into reports to donors.

During the period under review, DFID oversight was done by the Senior Responsibility Officer (SRO) with support from Lead Adviser and Programme Manager who manage day-to-day activities. During the reporting period, programme performance was monitored through monthly internal DFID programme board meetings where risks, finances, delivery chain risk mapping, AR recommendations and delivery plans were standing agendas items. Field visits were carried out to visit stakeholders and beneficiaries such as Zazu (financial education), PLAN (savings group and Master Trainers) in 4 districts of Eastern Province, and Mayfair (Insurance for Farmers). All these visits provided the opportunity to learn from beneficiary feedback and inform programming decisions. The overall feedback from partners and project beneficiaries continues to be very positive and complimentary.

This Annual Review was led by the SRO for FSD Tanzania, alongside the SRO, Lead Adviser and Programme Manager for FSD Zambia. It involved virtual meetings as well as a week of fieldwork in and around Lusaka where meetings were held with Government of Zambia representatives, Financial Service Providers, Saving Groups members and insurance beneficiaries. During physical meetings, all necessary precautions were taken to protect the review team and interviewees from spreading/contracting COVID 19. Measures taken include social distancing, mask wearing and conducting meetings in open spaces where possible.

In the year under review, this programme faced a staffing gap of advisory role and was allocated an interim SRO for a period of one year. This was after the DFID Zambia office restructuring that took place in 2018 and was finalised in 2019. Since the period under review, a new SRO has been allocated to this programme and a new adviser has been employed.

Asset Management
Regarding asset monitoring and control, FSDZ maintains an asset register which is reviewed quarterly, whenever major assets are procured, and at year-end in advance of the external audit. It was most recently updated in October 2020, and an asset spot check is due in early 2021.

Procurement
FSD Zambia implements a transparent and segregated procurement process. It has clearly stipulated thresholds which determine the procurement route. A procurement manual is in place which offers guidance to procurement processes.

Financial performance
The original planned budget at the beginning of the year was £3,076,748, however, FSDZ spend was slow in the first two quarters due to a delay in some programme activities, which is common across all FSDs. A decision was made and discussed with FSDZ to reduce the budget by 12% in order to mitigate a risk of underspending at the end of the year. The budget was revised to £2,706,351. There was great improvement to both forecasting and spend in the last two quarters which led to a 7% overspend of the revised budget. The main cost drivers were programme fees and operational costs as per audited financial statements. FSDZ utilised 85% on programme activities and 15% on commitment to the innovations which, in turn, is provides an indication of the sustainability of these interventions.

FSD Zambia was deemed by the commissioned report to have met the criteria for excellent economy during the assessment period. It found “verifiable evidence that demonstrates good resource management and compliance with the set benchmarks and operating standards”.
FSD Zambia achieved some increased efficiencies through the internalization of some functions that were previously outsourced. For example:
- The internal audit function has significantly reduced the turnaround time on assignment as compared to when FSD Zambia was outsourcing this function;
- In the communications section, website management, graphic design and social media tracking led to approximately £40,000 in savings in the short run and 80% reduced turnaround time on assignments;
- The hiring of the Programme Assistant under the Analytics department h led to reduced outsourcing of research assistants on some research activities, especially on verification.
The VfM report deems that Zambia “meets the criteria for adequate cost effectiveness. To achieve cost-effectiveness, long term impacts, sustainable markets systems change, and increased utilisation of financial products and services need to be observed beyond initial projects. Considering that all projects are still under implementation, FSD Zambia ascertains that it is too early to see these high-level impacts.” In this respect, while there is strong evidence that FSDZ is delivering economy and efficiency, strong evidence of effectiveness will likely take longer to fully demonstrate.

An important element in establishing the effectiveness of the various interventions across the programme and the extent to which they contribute to desired outcomes and impacts will be consideration of the operating environment within which the programme is delivering. The ongoing deterioration in Zambia’s macroeconomic environment, described above as ‘contextual risk’, should be considered when agreeing feasible targets and in assessing the overall effectiveness of the programme going forward.

“Technical assistance to support financial sector development, such as increasing financial inclusion (access to credit and savings) and strengthening capital markets” is a ‘high potential’ buy within the FCDO ‘best buy’ framework, meaning that, although evidence is weaker than for some other interventions, it is a promising area of research. With this in mind, FSDZ’s portfolio of activities show promise for development impact. Continued rigorous monitoring and evaluation will help to build an evidence base to further support assessment of the relative value for money of its activities.

Date of last narrative financial report	5 May 2020 (FSD Zambia Annual Report)	Date of last audited annual statement	14 July 2020