Programme Completion Review

Title: Better Jobs in Bangladesh
Final Programme Spend £ (full life): £5.1million	Review Date:	22 February 2021
Programme Code: [AMP ID#] 205275	Start Date: / 01 July 2017	End Date: / 22 November 2021

Summary of Programme Performance
Year	2018	2019	2020	2021
Programme Score	A	A	A	A
Residual Risk Exposure Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case (and any addendum):	http://iati.dfid.gov.uk/iati_documents/9085375.odt
DevTracker Links to all logframes used during programme lifetime:	http://iati.dfid.gov.uk/iati_documents/49271484.xlsx

GLOSSARY

BFSCD	Bangladesh Fire Service and Civil Defence
BGMEA	Bangladesh Garments Manufacturers and Exporters Association
BIDA	Bangladesh Investment Development Authority
BJB	Better Jobs in Bangladesh
BWB	Better Work Bangladesh
BLA	Bangladesh Labour Act
DIFE	Department of Inspection for Factories and Establishments
EPZ	Export Processing Zone
GEAR	Gender, Equality and Returns
GoB	Government of Bangladesh
IFC	International Finance Corporation
ILO	International Labour Organisation
ISU	Industrial Safety Unit
LIMA	Labour Inspection Management System
MoLE	Ministry of Labour and Employment
MoU	Memorandum of Understanding
NI	National Initiative
OSH	Occupational Health and Safety
OSS	One-Stop-Shop
PDP	Programme Delivery Plan
RAJUK	Dhaka/ Capital Development Authority
RCC	Remediation Coordination Cell
RMG	Ready-Made Garments
RSC	RMG Sustainability Council
SRO	Senior Responsible Owner
ToC	Theory of Change
ToR	Terms of Reference
VfM	Value for Money

A. Summary and Overview

Description of the programme and what it has achieved
1. Better Jobs in Bangladesh (BJB) is a (US dollar) $24.5 million programme, jointly funded by the UK, The Netherlands and Canada, to improve the working conditions and safety standards in the Ready-Made Garments (RMG) sector of Bangladesh over the period 2017-2023. As part of the UK Official Development Assistance (ODA) reprioritisation in July 2020, it was decided to bring forward the closure of the UK’s approved contribution of £6.6 million by three years to November 2020 from its original planned end date of December 2023. This PCR has been undertaken as a part of closure of the UK’s programme funding whilst BJB will continue with the UK’s policy engagement and funding from the other two donors.
2. BJB provided knowledge and capacity building support to the Government of Bangladesh (GoB) to improve industry inspections and compliance by factories with the GoB’s building and fire safety standards. BJB also helped strengthening occupational health and safety (OSH) in the workplace. BJB had a total budget of $24.5 million originally shared equally by the three partners and implemented by the International Labour Organisation (ILO). The UK’s decision to close funding earlier than originally scheduled reduced the budget to $22.5 million. The ILO and the other two donors are committed to deliver the programme till the planned closure in December 2023 with the funds available.

3. BJB was part of the international community’s response to enhance industrial safety in one of Bangladesh’s leading manufacturing and export sectors, following a major industrial accident in 2013 at the Rana Plaza. In addition to structural and fire safety of industrial and commercial buildings in the RMG sector, the programme helped the GoB develop and enforce health and safety standards, now more important than before because of health risks to factory workers posed by the ongoing COVID-19 pandemic.
[note] Globally one of the largest industrial disasters that took about 1100 lives, mostly workers at lower end RMG factories. https://en.wikipedia.org/wiki/2013_Dhaka_garment_factory_collapse

4. The programme has a special focus on relatively smaller RMG factories which were not covered by industrial safety initiatives, namely Alliance and Accord, supported by European and American apparel retailers. Both initiatives are now closed, following a directive from the Bangladesh High Court in favour of the RMG sector’s desire to replace them with a local initiative called the RMG Sustainability Council (RSC). The bottom tier factories, called National Initiative (NI) factories, although not directly contracted by international retailers, exist in large numbers (at last count nearly 700) and employ about 250,000 men and women in total across the country. The NI factories, with about 300 workers at each factory, work on low profit margins and have few incentives for industrial safety, posing significant risk to the lives of their workers and reputational risk for the sector.

5. The primary objective of the programme was to protect businesses and jobs by strengthening workplace safety in the RMG sector, a major contributor to economic growth, jobs, and poverty reduction in Bangladesh over the past two decades. The sector grew from a mere £480m export business to a £26bn business over the period 1990 to 2019, creating 4.5 million new jobs; including economic opportunities for 2.5 million women. It is estimated that another 20 million people indirectly depend on the sector which has contributed to the socio-economic development of Bangladesh by improving standards of living and access to various services, including children’s education. The programme had strategic significance for the UK’s national interest by helping to secure apparel supply chains for British retailers. Bangladesh is the second largest supplier of garments to the UK, after China. The programme also strengthened the ILO’s ability to advocate for appropriate action by government, the private sector (especially, RMG factories and international brands), and development partners to strengthen workplace safety, workers’ rights, and working conditions.

6. The programme is delivered through four outputs:
1. Inspection and enforcement of safety standards by government authorities
2. Developing a one-stop service for all licensing related to factory registrations
3. Improving OSH in policy and practice by the GoB
4. Supporting factories directly supplying international retailers to become role models for compliance through an ILO and International Finance Corporation (IFC) initiative called Better Work Bangladesh (BWB)
7. From 2017 to 2020 the programme delivered the following headline results despite the plethora of vested interest groups within the RMG sector:
1. Supported inspection at 1,549 NI factories, the closure of 510 structurally at risk factories and regular follow up with the 747 NI factories.
2. Facilitated the move of 171 factories to Accord/ Alliance or the newly set up RSC and 12 factories to the Export Processing Zone (EPZ) Authority; and relocation of 109 factories.
3. Completed training of 311 engineers from the Department of Inspections for Factories and Establishments (DIFE) and other GoB departments on safety aspects of inspection.
4. All 23 of the Deputy Inspector General’s (DIG Safety) offices across Bangladesh are now using the Labour Inspection Management Application (LIMA). This app was developed by the programme to record information on an online platform for improving transparency and accountability in inspection reporting.
5. DIFE’s Gender Road Map was approved by the GoB in July 2020 and outlines eight strategic areas that will help DIFE in improving women’s retention in the inspection jobs and sensitise the inspectors/engineers to the gender aspects of their respective jobs.
6. Four Standard Operating Procedures (SOPs) were developed for DIFE. One on labour inspection was approved by DIFE, and another three on licensing; complaints management; and accident injury reporting and investigation were awaiting approval at the time of this review.
7. Supported the GoB in the introduction of OSH Good Practice Awards for recognising companies maintaining high safety and workers’ health standards in factories. In 2018 and 2019 the GoB awared 34 companies across multiple sectors for OSH excellence.
8. In BWB factories, compliance with minimum wage payment doubled from 2017 to 2020. Compliance with rules on overtime payments, wage information, and record-keeping also increased. The average working day decreased from 9 hours 8 minutes to 8 hours 50 minutes.
9. Supported the development of the COVID-19 OSH Guidance for workers’ safety at the BWB factories which was later adopted by the Ministry of Labour and Employment (MoLE) as national guidance.

Major lessons learned, evidence generated and recommendations
8. This programme started as an emergency response and later on was able to deliver some longlasting benefits like mainstreaming OSH and prioritising workers’ safety for the GoB, the industry associations, and factory owners. This proved that aligning development interest with the government and private sector stakeholders can help in gaining traction and multiply the benefits of reforms. Since the Rana Plaza collapse in 2013, the sector was able to avoid further large-scale disaster and also manage and respond to the ones that had already occurred.

9. A single, unified institutional architecture is important for the sustainability of industrial safety initiatives. The RMG sector has benefitted from initiatives like Accord, Alliance, and The National Plan of Action; but a multisector safety standard is a necessary next step in streamlining the success of these initiatives. Accord has now folded its operations into RSC with representation from the brands, labour unions and local manufacturers on its board. Setting up the RSC by the private sector and developing the concept of an Industrial Safety Unit (ISU) within MoLE were necessary first steps in the right direction by the GoB and the private sector. But it still requires some strong hand-holding from the international community (including buyers and donors) to ensure the benefits that have been gained over the past years are not lost while the sector recovers from the economic shock of the ongoing pandemic. The ILO will have a strong role to play in brokering the governance model that works for both MoLE and RSC to ensure the sustainable exit of the programme.

10. The ongoing pandemic has highlighted the fact that workers’ safety is one of the major requirements to keep running the RMG manufacturing business. The DIFE and the MoLE were able to quickly mobilise resources to support COVID inspection at factories. This was possible due to the increased capacity of this GoB department supported by the programme. This also corroborated the business case assumption that a strong government agency is absolutely necessary for stepping up in emergency situations.

11. The programme generated evidence through its Baseline Report published in 2020 to establish a repository of data on working conditions in the RMG sector in Bangladesh. The study analyses the demographic profile, health status, and perceptions of workers and employers on working conditions in the industry. It highlights existing issues with a focus on their compliance with the Bangladesh Labour Act (BLA) as well as the International Labour Standards of the ILO ratified by Bangladesh. The baseline recognises areas that require the attention of the government, workers, employers and other relevant stakeholders. While the ILO will continue to use it in the programme, it is also an important repository of information for any stakeholder working in the sector.

12. As the programme will continue even after the UK exits, the ILO will be focusing its work on intensifying its relationship with the GoB and the private sector. This will aim to develop a long-term institutional architecture of the industrial safety regulation and enforcement mechanism which is independent, efficient, and credible to protect factories and their workers. It will help to achieve the intended impact results of the programme. The other two donors will be following up through the regular reporting of the ILO. The UK will continue its policy level influence and engagement through the 3+5+1 platform. This provides the opportunity for three GoB Secretaries (Commerce, Labour and Foreign Affairs) along with five Ambassadors/High Commissioners (UK, EU, USA, Canada and another European country on rotating basis) and the ILO to have periodic structured dialogues on Bangladesh’s progress in labour rights conditions, workplace safety and responsible business practices.

How this report was conducted
13. This report was compiled based on the various reports (quarterly and annual progress reports) and documented evidence of programme implementation provided by the ILO. This report also consolidates information from FCDO’s previous annual reviews (2018-2020) and the 2020 mid-term cluster evaluation commissioned by the programme. Supplementary interviews were held with the programme’s implementing partners/beneficiaries i.e. Remediation Coordination Cell (RCC) and RSC to assess the impact and sustainability of results. This review was led by the Senior Responsible Owner and Programme Manager of BJB and supplemented by Social Development, Governance and Economic Advisers of FCDO and colleagues from the UK Department for International Trade based in Dhaka.

Actions following approval of this report
14. FCDO will receive an audited financial report from the ILO for the period January to December 2020 in June 2021. FCDO made the last payment in August 2019. The payment has gone into a multi-donor trust fund and the total disbursed amount was committed before the closure on 22 November 2020. FCDO is not expecting any return of funds from the ILO, neither is due to make any further payments. No assets were procured as part of the programme, hence there is no requirement for asset disposal.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	Original programme budget at BC sign-off was £6.6 million	The final spend was £5.1 million
Timeframe	The anticipated programme timeframe at BC sign-off was 2017-2023	The programme timeframe from BC sign-off to closure was 2017-2020
Outcomes	Outcome 1: By the end of 2020, all active factories of the target 1,500 National Initiative (NI) factories are remediated. / Outcome 2: Government effectively regulates industrial safety. / Outcome 3: OSH improved in policy and practice in a gender inclusive manner / Outcome 4: Better Work factories serve as models for compliance.	The indicators did not change between 2017 and 2020. There has been substantial progress towards achieving those which have been included in paragraphs 15-18 and Section C of this document.

Overall assessment of programme outcomes, sustainability and VfM
15. Outcome 1: This outcome was focused on completing the remediation at all of the 1549 NI factories which were structurally at risk at the business case stage of this programme. At the end of 2020, 19% of these factories were in safer conditions than at the beginning of the programme and about 33% had closed down business operations. The programme is now responsible for 747 factories of which about 30% have shown a higher degree of commitment in completing the structural improvements to make the factories safe. The challenge remains with the bottom 525 factories or about one third of what the programme started with. This also represents the bottom 11% of RMG factories. These factories have very limited incentives or access to adequate financing to sustain their ongoing business, let alone make structural improvements in rented or shared properties. So, the Outcome 1 target of completing remediation at all NI factories will not be achieved even by 2023. But one noticeable improvement has been DIFE’s knowledge about these factories’ condition and the follow-up mechanism that was developed through the use of LIMA. So, these bottom 11% factories are not completely safe for workers, but the GoB is aware of the degree of risk and has the capacity to prevent any large disaster from happening at these factories.

16. Outcome 2: This outcome focused on improving the GoB’s capacity to independently regulate industrial safety. Besides the RMG sector, DIFE is responsible for the safety of all types of factories and commercial establishments across Bangladesh. With the programme support, the GoB has gradually increased its numbers and capacity of engineers and inspectors but this is still quite low compared to what it needs to effectively regulate all sectors. The governance architecture that the GoB has designed for the ISU will help to regulate the RSC, which is responsible for the higher-end RMG factories. This will also free up some DIFE resources and allow it to concentrate on the lower-end factories. The programme is supporting the design and implementation of the ISU model which will contribute towards a reliable and accountable industrial safety governance architecture by 2023.

17. Outcome 3: This outcome was for improving OSH both in policy and practice. National OSH Profile was approved by the National OSH Council in September 2019. This profile now provides a national standard for OSH best practice in line with international standards. The National Plan of Action on OSH was developed and shared with all stakeholders. The action plan will work as a guiding document for both government and private sector stakeholders to define responsibilities and improve OSH standards across all sectors. Besides these, the GoB has developed a master plan for setting up OSH training centres across Bangladesh which will help to train the workers, managers and owners of factories in OSH good practice. All these steps will help embed OSH good practice in the strategies and operations of stakeholders and contribute to achieving Outcome 3 by 2023.
18. Outcome 4: This outcome involved working with factories to improve workers’ rights so that they become role models of compliance across the sector. BWB works with factories which supply to the large global brands and their supplier factories in Bangladesh. BWB is helping to improve workers’ participation in the safety improvement process. The standards are internationally compliant and some of are also used in the brands’ supplier factories in other countries. So this is helping to maintain consistent safety standards across countries. BWB has been able to introduce and scale up some of its flagship interventions such as Mothers@Work and Gender, Equality and Returns (GEAR) in Bangladesh. These have helped to promote 89 female sewing operators to supervisory roles; and help 890 pregnant women, 773 lactating mothers, and 719 management staff to improve their knowledge of maternity rights and breastfeeding protection. Women’s participation in higher grade jobs and the rights of women workers are two very important aspects for any factory to become a role model for compliance. BWB has gained traction between 2017 and 2020 which indicates it will be able to achieve its outcome target by 2023.
19. The programme has embedded the following to ensure the sustainability of its interventions:
1. Establishing the RCC within DIFE to oversee the remediation of 1,549 NI factories. This will be folded into the ISU to oversee the safety aspect of factories across all sectors in Bangladesh.
2. The development of the LIMA, the management of which will be gradually handed over to the GoB. The DIFE staff are now capable of providing refresher training on LIMA with limited input from the ILO. This is helping to embed the practice of ongoing training using DIFE’s resources.
3. The development of various checklists and SOPs to guide the effective implementation of labour inspections. These checklists are prepared with the support of the ILO maintaining international standards and will help the GoB to continue to maintain it.
4. The development of Road Maps to ensure a systemic approach to labour inspection and gender mainstreaming within DIFE. Understanding that recruitment in public service is a competitive process, the programme developed a gender road map that will help to retain the women inspectors in the pool and sensitise all staff to conducting gender sensitive inspections and reporting.
5. At the time of drafting this PCR, advances had been made to improve factory safety through licensing under the One Stop Service Window which will integrate the licensing systems of DIFE, RAJUK (the capital development authority) and the Bangladesh Fire Service and Civil Defence (BFSCD). This will be a milestone in bringing all factory licensing onto one platform.

20. Value for Money:
1. The business case stated that economy will be achieved through the use of best practice, especially via large procurements and savings generated through negotiations. The ILO has used competitve bidding processes for all of its contracts and from 2017 to 2020 was able to reduce the contract value by 5-10% in each procurement through such negotiations.
2. The VfM indicators of BJB suggests that efficiency will be achieved by creating impacts that encourage the sector to replicate them. The RMG factories and labour bodies have supported setting up Participatory Committees and Safety Committees at factories, replicating the model the programme developed. 1,929 Safety Committees were set up in factories, where only 162 were set up with the direct support of the programme. This provides a good example of how the programme is efficiently embedding the practice of improving workplace safety through a bottom-up approach.
3. Effectiveness will be achieved by embedding measures of sustainability so that the impact will last beyond the programme. The programme has supported the development of the National OSH Profile. This was taken a step further by the GoB with the plan to set up a National OSH Institute to centralise all OSH learning in one place so that all stakeholders have equal access. This provides a good example of how the GoB is taking ahead the OSH agenda and embedding its own sustainability measures.
4. Equity will be achieved by ensuring the workplace improvements benefit women and people with disabilities to continue to do their jobs in the sector. The benefits of the Mothers@Work and GEAR components have helped female workers to continue to do their jobs after giving birth and helped them upgrade their jobs from operators to supervisory roles. Thus far 890 pregnant workers have benefitted from the information on their rights during pregnancy and maternity leave, and 89 female sewing operators have been supported with guidance through their promotion process and capacity improvement to deliver and maintain their position in supervisory roles.
Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.
21. The theory of change (ToC) did not change between 2017 and 2020 and remained relevant to the context and programme’s objectives. It is premised on the need for enabling policies and organisational capacity to secure workplace safety. Safe workplaces and decent working conditions need well-defined standards and protocols, and robust and independent surveillance and enforcement mechanisms. Improved workplace safety and working conditions will help international retailers protect the reputation of their supply chains which, in turn, will help protect businesses and jobs in the RMG sector in Bangladesh. This in turn will contribute to poverty reduction through economic growth and jobs for the poorer segments of society, including many women.

22. Whilst the ToC remained relevant and the underlying assumptions largely did not change over the last year, COVID-19 has affected how RMG supply chains operate globally. The decline in clothing sales in EU, UK and USA at the beginning of the pandemic translated into reduced demand for Bangladeshi RMG products. Given the sector’s importance to job creation and economic growth, and the economic empowerment of the 2.5 million women directly employed in the sector in Bangladesh, the programme has been significant in making the supply chains more secure for their workers.

## C: Detailed Output Assessment

Output Number and Title		A Remediation Coordination Cell (RCC) is established / 1.2 Employers, workers and buyers are better equipped to support and sustain remediation efforts
Output Score		A
Impact weighting (%)		35%	Impact weighting revised since last AR?	No

Output Indicator	Starting Target		Final Logframe Target ( Dec 2023)	Final Result Achieved
1.1.1. A compliance and escalation protocol in place	Baseline (June 2017): Compliance Protocol introduced. / Milestone (Dec 2020): No additional milestone for 2020		Compliance Protocol is fully adopted by end 2018.	Met expectation. / The Compliance and Escalation Protocol was developed in 2018 and endorsed in July 2019 by the GoB and now used by DIFE.
1.1.2. Proportion of relevant cases examined by the Review Panel for immediate action / (meaning- complains received by DIFE on structural safety are examined/ assessed)	Baseline (June 2017): / 0 (the Review Panel was set up in 2018) / Milestone (Dec 2020): 100% of the relevant cases examined by the Review Panel for immediate action		100% by end of 2021	Met Expectation. / The review panel received two cases in 2020. Both were reviewed and actions were taken.
1.1.3. Frequency of visits to factories by RCC representatives	Baseline (June 2017): 0 (NI factories were not even visited once in a year by DIFE inspectors) / Milestone (Dec 2020): / a) 100% of the NI factories that are under remediation visited at least once by RCC engineers; / (b) 35% of them will be visited at least three times.		a) 100% of the NI factories that are under remediation visited at least once by RCC engineers; / (b) 35% of them will be visited at least three times.	Substantially exceeded expectations / a) By October 2020, 100 % factories had been visited once / b) by October 2020, 81% factories were visited at least three times
1.2.1. Percentage of NI factories who receive information on remediation and access to finance by the RCC (per factory, based on priority)	Baseline (June 2017): 0 / Milestone (Dec 2020): 60% of the active NI factories		100% of the active NI factories receive information on remediation and access to finance	Met expectation / 100% of the active NI factories received Remediation / Financing fact sheet. and only five factories have accessed the finance between January 2019- March 2020 (right before the pandemic)

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.
23. The output scores an A in this review. Of the four indicators, one substantially exceeded expectations at the end of 2020, and the remaining three indicators met expectations. These indicators are related to the follow up with the factories to drive up the remediation completion rate.

24. The programme helped set up the RCC, a separate unit within DIFE, to inspect the NI factories. The inspections continued from 2017 to early 2020, though implementation of corrective measures recommended by inspection had been slow. Out of the 747 active factories only one was fully remediated; about 14% of the factories completed more than 80% of the remediation; and about 15% of the factories are between 50-80%. The majority of the factories (about 70% of the active NI factories) are, however, below 50% remediation completion. Accelerated remediation will be critical for the programme to move outputs to outcomes. This review assesses that the challenge will remain in completing the remediation activities. Smaller factories were hard hit by the pandemic and the incentives for remediation became even more constrained. DIFE continues to inspect these factories, which are at higher structural risk, to avoid any imminent danger.

25. By October 2020, BJB had supported the training of 311 engineers from multiple GoB departments who are important stakeholders in improving the safety standards across all types of factories and establishments. The departments include DIFE, Chittagong Development Authority, City Corporations, RCC staff, representatives from employers’ associations, and BFSCD. This will help maintain the same inspection standards across all GoB departments. This improved capacity has helped DIFE in rapidly organising the COVID Inspection Teams with staff from cross-governmental departments.

26. The programme, in collaboration with DIFE, Bangladesh Garments Manufacturers and Exporters Association (BGMEA) and Bangladesh Bank (the central bank of Bangladesh), reached 738 RMG factories (including all currently active NI factories) with information on the available remediation financing. This information was also shared by the RCC engineers while conducting remediation follow up at factories.

27. The programme supported DIFE to develop the strategic plan for setting up the ISU, which will be the umbrella body within DIFE for industrial safety across all sectors. Setting up this ISU took a back-seat during the pandemic, but this review found that there is now increased interest from the private sector stakehoders. The ILO will continue to work with DIFE to set up the role and functions of ISU to make it an effective and functioning body.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
28. The programme invested in setting up the RCC, training up the engineers, and improving the existing sytems and processes of the inspection authority. While these systems and processes were already in place, it lacked transparency and accountability. The programme intervention has been able to deliver some success through developing the LIMA and making the inspection reports available online. The number of engineers/inspectors and their lack of capacity were an issue as well. Now the inspectors/engineers have fewer factories in their portfolio compared to numbers before 2017. This is allowing them to invest more time in each inspection and resulting in improved inspection quality. This has been an effective use of FCDO money in improving the quality of inspection and increasing the transparency and accountability.

Lessons learned through this output, and recommendations for future programming
29. Remediation of the NI factories struggled to progress for a number of reasons. Either there is a lack of financing available to them; or factory owners do not want to invest in rented/shared properties; or there is no pressure to maintain standards from the small buyers that they supply. These are the same factories which were badly affected by the loss of orders from the beginning of the pandemic and later on by the loss of payments. The risk of deprioritising workers’ safety is higher at these factories. On top of that the incentives to complete remediation at bottom-tier factories vary widely from one factory to the other where the GoB has a very limited role to play. So, any programme that works with these bottom-tier factories needs to design the incentive model from the outset so that it helps to deliver results more quickly and effectively.

Output Number and Title	Framework for one-stop-shop for industrial safety and compliance conceptualised / 2.2 Labour inspection capacity of DIFE is developed, which is fair, effective and gender sensitive
Output Score	A
Impact weighting (%)	25%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target	Final Logframe Target (Dec 2023)	Final Result Achieved
2.1.1 One-stop-shop (Single Window Service) proposal and business processes recognised and agreed by all relevant ministries		Baseline (June 2017): Single Window Service concept agreed in principle by stakeholders / Milestone (Dec 2020): One-stop-shop (OSS) conceptualized based on a common understanding amongst various regulatory bodies.	Recommendations arising from the piloting of the one-stop-shop about its efficacy provided to the government by Dec 2022	Did not meet expectation / Discussion has started with IFC, Bangladesh Investment Development Authority (BIDA), and Bangladesh Economic Zone Authority (BEZA). / DIFE is awaiting to sign MoU with BIDA and ILO initiated development of a OSS Roadmap by identifying all relevant stakeholders.
2.2.1 Proportion of labour inspectors who report increased knowledge and skills acquired through practical training (disaggregated by sex)		Baseline (June 2017): 72% / Milestone (Dec 2020): / 80%	100% at June 2023	Exceeded Expectation / 99% of trainees reported in a post-training evaluation of increased understanding of the LIMA
2.2.2 Proportion of trained staff within DIFE who report increased knowledge on gender issues (disaggregated by sex)		Baseline (Jun 2017): / Nil / Milestone (Dec 2020): / 10% percentage point increase from the previous year	10% percentage point increase from the previous year	Did not meet expectation / The training was postponed from Q3 2019 to 2020 and has not yet taken place.
2.2.3 DIFE’s information and knowledge management capacity strengthened		Baseline (Jun 2017): DIFE's Information and Knowledge Management System LIMA developed in June 2017. / Milestone (Dec 2020): All 24 Offices use LIMA	a) All 24 DIFE Offices use LIMA. / b) Analytical reports published based on LIMA data. / c)LIMA process and system improved.	Met Expectation / a) All 24 DIFE offices use LIMA / b) Analytical reports are published through LIMA website / c) LIMA system has been once improved since introduction.
2.2.4 DIFE gender roadmap developed and implemented		Baseline (Jun 2017): 'No gender roadmap available at the beginning of the project / Milestone (Dec 2020): The Gender Roadmap is adopted by DIFE	DIFE starts implementing the Gender Roadmap.	Met Expectation / DIFE adopted the Gender Roadmap in July 2020 and started implementation of it.
2.2.5 Labour Inspection Reform Roadmap reviewed, and progress reported annually		Baseline (Jun 2017): Nil / Milestone (Dec 2020): Labour Inspection Reform Roadmap progress report developed and published.	Labour Inspection Reform Roadmap reviewed annually, progress report developed and published	Met Expectation / The Labour Inspection Reform Roadmap was reviewed in September 2020 and awaiting to be published.
2.2.6 DIFE Labour Inspection report published annually		Baseline (Jun 2017): Last report published for 2016-17 / Milestone (Dec 2020): Report published by July 2019	Labour Inspection Report of DIFE is published annually	Met Expectation / Labour Inpsection Report for 2018-2019 was published in March 2020
2.2.7 All labour inspectors are trained systematically following the comprehensive training plan of DIFE		Baseline (Jun 2017): Nil / Milestone (Dec 2020): Comprehensive training plan developed for DIFE	a) A comprehensive training plan developed for DIFE; / b) 100% newly recruited labour inspectors receive foundational training	Did not meet expectation / The comprehensive training plan for DIFE that was supposed to be developed in Q3 of 2019 has been postponed to Q1 2021.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.
30. This output scored an A in this review. Of the seven indicators, four met expectations and three did not. The objective of the output is to ensure that the GoB has the right capacity and governance structures to effectively regulate industrial safety with staff that are credible and accountable. To do that the programme is supporting the set-up of a one-stop-shop (OSS) for industrial safety and developing a robust and accountable labour inspection system. The programme started engaging with other relevant government agencies for setting up the OSS from early 2020 and is in the process of signing agreements to implement the plan in 2021.

31. The programme funded the development of the Labour Inspection Management Application (LIMA) which was rolled out in all 23 DIFE DIG offices across the country. About 70% of the inspections are now reported through this online system which is helping provide real-time data on the status of the factories, segregated by sectors and geographical locations. DIFE conducted training of 280 officials on the use of LIMA with gradually less support from the programme which helped embed the capacity development programme within DIFE.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
32. The business case identified that the effectiveness of the programme will be in building capacity of government to deliver services and ensure sustainability. This includes tracking the number of in-house training sessions provided to the newly recruited inspectors and the number of inspections completed by the inspectors. The programme has been effective in conducting inspections, using LIMA for inspections, and reporting issues in the system. To put it into context, DIFE did not have any central database to report the outcome of the inspections other than keeping records manually. Now DIFE inspectors collect data through an on-line system which can help to collate and generate information for further use. This information is also available online which has increased the transparency of the inspections.

Lessons learned through this output, and recommendations for future programming
33. Developing an OSS requires long-term planning and it cannot happen in silos when there are national-level initiatives underway to streamline government services. The OSS of DIFE gained lower traction as it was running on a separate stream from the national one. Any future programme having an OSS component should take into consideration other similar larger initiatives that are gaining traction with the government and try to align with those. This will help achieve results more quickly.

Output Number and Title	Framework for national OSH programme initiated in line with national OSH policies of the government / 3.2 Stakeholders' capacity and awareness on OSH built in a gender inclusive manner
Output Score	B
Impact weighting (%)	20%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target	Final Logframe Target (Dec 2023)	Final Result Achieved
3.1.1 National OSH profile is ready for adoption by the government		Baseline (Jun 2017): Existing OSH policy and profile / Milestone (Dec 2020): No additional target for 2020	National OSH profile drafted and submitted to the government for adoption by Dec 2019.	Met Expectation / National OSH Profile approved in the National OSH Council in Sept 2019. In August 2020, DIFE was in the process of publishing the OSH profile.
3.2.1 DIFE's capacity to monitor the operations of the Safety Committees is strengthened		Baseline (Jun 2017): Nil / Milestone (Dec 2020): All members of the DIFE OSH Unit received training on the Safety Committee	DIFE produces Safety committee monitoring report through LIMA by Dec 2021	Did not meet expectation / One training took place in 2019 where 20 DIFE staff were trained on the Safety Committe. / Checklist for the monitoring report has been prepared but the delay in training in safety committees will result in a delay in the monitoring of the committees as well.
3.2.2 Number of Trade Union member and Safety Committee members equipped to support OSH management, Risk Identification and correction (disaggregated by sex)		Baseline (Jun 2017): Nil / Milestone (Dec 2020): 1800	1800 Trade Union members and Safety Committee members equipped to support OSH management, Risk Identification and correction by Dec 2020	Did not meet expectation / The training was planned for Q3 2019. It was delayed to combine it with trainings of Workers’ Resource Centre and was further delayed due to the ongoing pandemic.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.
34. This output scores a B in this review. The objective of this output is to improve OSH both in policy and in practice; and also, to assess whether OSH committees in factories are working in accordance with the BLA. This became an even higher priority for workers’ protection during the pandemic. The target for this component is to develop a National Plan of Action on OSH that can be implemented and carried forward by both the public and private sector. While that is progressing well, the indicators related to training of the OSH committees at factories are struggling.

35. Achievements of the output:
1. The National OSH Profile was approved by the National OSH Council in September 2019.The programme supported the revision of the National OSH Profile in order to create a regulatory environment in line with international standards and best practice.
2. The first draft for the National Plan of Action on OSH was produced by DIFE in February 2020. The action plan will work as a guiding document for both government and private sector stakeholders to define responsibilities and improve OSH standards across all sectors.
3. The programme drafted and shared with DIFE an OSH guidance for Prevention and Mitigation of COVID–19 at Workplace, a checklist and SOPs for COVID inspection. All three documents, especially the OSH guidance, have been developed with due emphasis on the gender specific OSH needs of women workers. This was then adopted and rolled out as national guidance by the MoLE.

36. This output has been instrumental in mainstreaming OSH in policy and practice in Bangladesh. But to strengthen the institutionalisation of OSH, it requires active participation of the trade unions and workers’ participatory committees. These are factory-based committees and the programme has developed alliances with organisations that can help get traction with these committees. Building up alliances took time and was then further affected by the pandemic. The programme will continue to work through the alliances to ensure the output delivers the intended results.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
37. The business case identified that the effectiveness of the programme will derive from building the capacity and incentives of stakeholders to ensure sustainability. This will be calculated based on the number of safety committees established by trade unions and sector associations. 1929 Safety Committees were set up by the industry associations between July 2018 and March 2020, of which only 162 were directly set up with the programme’s support. This means BJB has created the incentives for trade unions and factories to support the establishment of Safety Committees that largely benefit workers.

Lessons learned through this output, and recommendations for future programming [
38. Setting up safety committees at factories is the responsibility of the factories (both workers and owners). But through the programme support the DIFE inspectors have been sensitised to the benefits of such committees. This resulted in inspectors encouraging the factory management to set these up. This has been a positive shift in the mindset of the stakeholders that the safety of workers is a multi-dimensional issue and needs to be prioritised by all for it to be mainstreamed. Any future programme working in mainstreaming a policy also needs to use the similar ‘push and pull’ factor by working with both the beneficiaries and the policymakers to make it effective.

Output Number and Title	Core service delivery model applied / 4.2 Engaging stakeholders to contribute to responsible business practices
Output Score	A
Impact weighting (%)	20%		Impact weighting revised since last AR?	No

Output Indicator		Starting Target	Final Logframe Target (Dec 2023)	Final Result Achieved
4.1.1 Number of compliance assessment reports completed in the reporting period		Baseline (Jun 2017): Nil / Milestone (Dec 2020): 570	650 at the end of Dec 2021	Exceeded expectation / 587 Compliance assessment reports have been completed to end December 2020.
4.1.2 Percentage of PC worker representatives that are women		Baseline (Dec 2018): 35% / Milestone (Dec 2020): 45%	50% at the end of Dec 2021	Met expectation / 45% of the Participatory Committee (PC) members are women.
4.1.3 Percentage of supervisory training participants that are women		Baseline (Dec 2018): 15% / Milestone (Dec 2020): 70%	50% at the end of Dec 2021	Met expectation / 70% participants were women in the supervisory trainings provided in factories.
4.2.1 Number of assessment reports produced that are being accessed via subscription by Brand partners		Baseline (Jun 2017): Nil / Milestone (Dec 2020): 350	400 assessment reports accessed by the end of Dec 2021	Substantially exceeded expectation / 950 assessment reports were used by brand partners.
4.2 .2 Number of buyer partners affiliated with BWB		Baseline (Jun 2017): 17 / Milestone (Dec 2020): 28	30 by the end of Dec 2021	Moderately did not meet expectation / 27 buyer partner are now affiliated with BWB. The progress was impacted by COVID.
4.2.3 Percentage of cost recovery viz. total expenditures		Baseline (Jun 2017): Nil / Milestone (Dec 2020): 40%	42% by the end of Dec 2021	Met expectation / 40% of the cost of the programme was recovered.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.
39. This output scores an A in this review. The output focuses on improving compliance standards in factories in line with the Bangladesh Labour Act (BLA) and contributes to reducing the number of social/compliance audits required by brands and buyers. Better Work Bangladesh (BWB), works with factories to improve performance in social compliance to reduce the number of social/compliance audits that brands need to undertake. BWB is the Bangladesh chapter of an ILO and IFC programme called Better Work (BW). COVID has affected how the brands work with the factories, and this component has the unique opportunity to work directly with brands to ensure workers’ safety and that their voice remains a priority for all.

40. Achievements of the output:
1. Since the last review in August 2020, 18 more factories (total 272) were enrolled by the brand partners into the programme.The number of active brands also increased from 25 to 27 during the same period. This indicates the brands are finding the social audits of BWB to be useful, even more important during an ongoing pandemic.
2. In BWB factories’ compliance with minimum wage payment doubled from 2017 to 2020. There were also higher rates of compliance with rules on overtime payments, wage information, and record-keeping. The average working day decreased from 9 hour 8 minutes to 8 hours 50 minutes. Factories enrolled on the programme improved inventory keeping practices and the storing of chemical and hazardous substances. 90% of them now have acceptable temperatures and ventilation systems in place.
3. BWB’s on-the-ground core service delivery has been affected by the restriction of movement since mid-March 2020. However, BWB continued to deliver training and advisory services virtually to address the changing needs of factory management and workers. 684 advisory visits were conducted virtually between March and December 2020. These sessions aimed to influence compliance with national legislation and international labour standards; and also provided COVID-19 response specific support.
41. While the brands and factories have benefitted from improvement in workers’ satisfaction, it has not necessarily translated into efficiency gains for factories. BWB’s ultimate objective of making the factories ‘role models for compliance’ will be affected if it is unable to create its value proposition that helps in reducing the number of audits in a factory.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme
42. The business case stated that the efficiency of the programme will be achieved through maximising the value of partnerships with sector associations and trade unions which will reflect in the number of safety committees established. The programme has been able to set up 70 safety committees at factories out of the 254 it works with. This is a 30% year on year increase between 2019 and 2020.

43. In terms of equity, this component works at the factories with women workers using two projects: GEAR and Mothers@Work. These projects/initiatives are providing training to female workers to take up supervisory roles, providing support for career progression, creating an enabling environment for mothers, and improving their understanding of their rights related to maternity protection. Thus far, 89 female sewing operators have been promoted to supervisory roles; and 890 pregnant women, 773 lactating mothers, and 719 management staff gained improved knowledge on maternity rights and breastfeeding protection.

Lessons learned through this output, and recommendations for future programming
44. The factories perceive BWB to be a high cost programme led by the brands. Brands and factories started to benefit only from the beginning of 2020 from the social compliance improvements as it added Mothers@Work and GEAR to its offer. It is now important that BWB improves its offer by partnering with other compliance projects related to environmental impacts and the improvement of labour rights. This will help brands receive a one-stop service for all of its audit requirements and factories to become role models of compliance.

D: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.
45. The programme retained a moderate risk rating throughout its lifetime. Risks were identified, discussed, and recorded consistently under the Risk Register on FCDO’s Aid Management Platform (AMP). The ILO updated the risk matrix guided by their 2009 Policy on Risk Management and was updated by the Risk Management Framework in 2020. The Framework details the objectives and governance arrangements for the management of risk within the ILO. The risk assessment tool included all contextual, delivery, financial and operational parameters. These were also discussed within FCDO through structured bi-monthly Programme Delivery Plan (PDP) meetings and escalated as per the risk categorisation. The programme’s risk register was adjusted according to the context with the most pressing being the COVID-19 pandemic and changes were further prompted by the 2020 Mid-Term Evaluation and FCDO Annual Review findings and recommendations, as well as through numerous donor/programme discussions.

46. The programme’s overall risk appetite remained the same, with increased appetite adjusted after the 2020 review period (August 2020). Major risks were escalated and action plans were discussed accordingly with ILO. ILO maintained open dialogue and engagement with FCDO on anticipated risks, risk appetite, and mitigation measures in a problem-solving approach. All risks were updated on AMP and in the PDP.

47. A safeguarding due diligence assessment of the ILO’s approach to safeguarding its employees and beneficiaries was conducted as part of 2019 annual review. The assessment was carried out based on the FCDO’s central enhanced safeguarding assessment guidance and no major risk was identified.

Overview of programme risk
48. The programme faced staffing challenges at the beginning of the programme which continued until mid-2018. This had a prolonged impact on the programme in developing an influencing relationship with stakeholders and a thorough workplan that helps to translate the outputs into outcomes. This was managed through discussion with the donors and change in both personnel and workplans.

49. Another notable risk that the programme encountered was the RCC under DIFE not fully accepting the technical and training support that the private sector firm Bureau Veritas (BV) was contracted to provide. To mitigate the risk, the ILO and the donors, especially FCDO, engaged with the GoB/RCC proactively to discuss the significance/benefit of the BV/RCC relationship in early 2020. This risk was also flagged by the ILO early on and proactively mitigated with FCDO and other donor support.

50. The main risks in 2020 were largely prompted by the COVID-19 pandemic which threatened delivery of the programme’s results with a negative impact on the timeline of delivery. However, this was mitigated through immediate action, including a repurposing effort by the programme that resulted in the development of National OSH COVID-19 guidelines that were later on adopted as national guidance. BWB provided technical guidance for enterprise-level mitigation of risks related to hygiene and safety, social dialogue, human resources management, and retrenchment and lay-off.

51. In general, the programme maintained Risk and Fraud Registers over the course of implementation and undertook regular risk management meetings. Mitigation measures related to fraud and corruption were managed by thoroughly reviewing all invoices and reports submitted by the RCC and DIFE within the established implementation agreements. In November 2019, the programme and the ILO Bangladesh benefitted from a high-level mission led by the ILO’s Global Risk Officer that included discussions with the programme staff and donors, during which training on risk was delivered and the programme’s risk register benefitted from comprehensive feedback.

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.
Programme Management:
52. The ILO has responded to FCDO’s request for information promptly and professionally. The criticism of previous reviews was also taken positively and translated into workplans and activities to improve the programme deliverables. Meetings were arranged as required and reports were shared with FCDO at regular agreed intervals. Communication materials were also shared with FCDO when developed. Overall, the ILO Bangladesh has been constructive and professional in delivering BJB and managing the early closure requirements of FCDO.

53. FCDO discussed the early closure with donor partners and the ILO separately, prior to issuing the offical notice to complete any unfinished tasks and financial commitments with the FCDO funding.The MoU termination letter related to the closure of BJB was issued by FCDO on 23 August 2020 with the agreed two months’ notice and with an end date of 22 November 2020. Prior to the announcement of the closure, FCDO and the other two donors were working with the ILO on the additional COVID-19 deliverables and the impact of the ongoing pandemic on the programme. FCDO’s early closure will affect the ILO’s ability to execute the proposed plan, but as stated below in paragraph 58, the ILO generated savings during the initial lockdown in 2020 and that has provided some flexibility in realigning its priorities and in allocating funds for the remaining activities.

54. In the course of implementation, the programme refined its performance management framework in consultation with the three donors, the ILO’s tripartite constituents (government, employer and worker representatives) as well as members of the Programme Steering Committee (PSC). In particular, the programme set up a robust Monitoring and Evaluation (M&E) system informed by the programme’s logframe indicators. 2020 Annual Review led to revisions to the programme’s logframe as the pandemic initially adversely threatened the RMG sector and the deliverables. The ILO will be working with the other two donors to revise the logframe based on the MTE findings and recommendations, FCDO Annual Reviews, and feedback from stakeholders.

Commercial and Financial Performance:
55. A Due Diligence Assessment (DDA) was carried out in August 2017 before the funding commitment was signed. The programme has a standard financial management system that conforms to the ILO’s financial regulations and procedures. The system uses a results-based framework in order to improve accountability, transparency and enhance the ILO’s reporting processes.
56. The total budget was $24.5million (£19.8million) with the UK, The Netherlands and Canada contributing one third each. As of November 2020, $17.78 million (about 72.47% of total commitment) was disbursed to the ILO, including FCDO’s £5.1 million (about $6.6 million). All contributions went to a multi-donor trust fund. Thus far, no payment has been made to the ILO in advance of need and payments from all three donors are scheduled in a way that prevents the ILO holding large amount of idle cash. By November 2020, the programme had spent and committed to spend $15.78 million, which represents about 88.71% of the total disbursed funds.
57. The last instalment of £1.5 million from FCDO was due in August 2020 but due to the ODA Review decision to close the programme for the UK, FCDO discontinued its funding to the ILO and did not release its final instalment. The other two donors are committed to continue their financial support to the programme till its natural closure.
VfM measures:
58. The programme has used the ILO as it has expertise in delivering programmes to improve workers’ rights. In Bangladesh it has strong networks and relationships with the GoB across the Labour, Foreign and Commerce ministries. This was important for the programme to deliver its objectives and also to influence relevant reforms. MoLE was the most important counterpart in delivering the programme targets, and the ILO, based on its existing relationships, could easily identify the challenges of working through the bureaucratic process and provided the best solutions. Improving workers’ safety is also a central pillar discussed at the ILO Conventions that take place annually in Geneva where the Foreign and Commerce ministries of Bangladesh are usually present. Influencing through the ILO Convention helped to reform the BLA in 2018 and this has improved workers’ participation in collective bargaining and in improving safety standards. The ILO has used all its relationships, including the ones with BGMEA and factories, to deliver the programme targets as described in the business case, which was an efficient use of FCDO resources. Any other multilateral, NGO or private sector partner would have needed time to build up these relationships first, and then to deliver the results. Using the ILO as a partner has saved time and was effective from the outset.
59. BJB’s business case stated that the programme support cost will be 11%, which will be used to cover the costs of administration incurred by the programme. An additional 5% was allocated for technical monitoring and evaluation and 2% for security of the project operations. This has not changed over the period 2017 to 2020; rather the ILO made savings where possible by recruiting local personnel and firms. During the initial lockdown due to the pandemic, the ILO did not enter into any new agreements to minimise the recurring costs to the programme. This has been an efficient use of FCDO resources.
Monitoring and Evaluation
60. As per the M&E plan of the programme, the ILO continued to undertake routine internal programme monitoring, to assess the extent to which the programme has achieved the results set out in the logframe and the activities committed to in the workplan. These were reported through quarterly reports and discussed at the monthly meetings; and necessary actions were taken based on the workplan. All three donors took part in these meetings. Besides these, the donor partners met on specific issues, as and when required.
61. As part of regular monitoring FCDO programme team had periodic consversations with DIFE, Department of Labour, RCC, RSC, BGMEA, Bangladesh Employers’ Federation, IndustryAll Bangladesh Council (labour union), Accord, Nirapon, IFC, SNV (international NGO working on workers’ rights), Fakir Apparels (BWB factory) and H&M (brand partner of Accord and RSC). FCDO programme team visited NI and BWB factories from 2017 to 2020. These visits and meetings validated the information found in reports produced by the programme.
62. The ILO commissioned a mid-term cluster evaluation in 2020 based on the ILO’s evaluation standards and OECD Development Assistance Committee (DAC) guidelines which assessed relevance, design validity, and coherence; and drew out lessons learned, gaps, impact, and sustainability across the programme’s four strategic objectives. The final report was shared with donors and stakeholders in November 2020. The recommendations provided by the three donors will be used for the logframe revision and the final activities of the programme. The other two donors will be monitoring these until the closure in 2023.
Date of last narrative financial report	15 March 2020	Date of last audited annual statement	02 March 2020