## BRACE II Logframe WFP-FAO
OVERARCHING LOGFRAME - WFP-FAO (2018) - updated March 2020 | [9 empty] | 2020-03-01
PROJECT TITLE: Building Resilience through Asset Creation and Enhancement - Phase Two (BRACE II)
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20) | Assumptions
Increased resilience to food insecurity and climate variability and extremes in target areas | Reduced prevalence of moderately and severely food insecure households (in counties where BRACE II is implemented) | Planned | 92% | 10% reduction | 20% reduction | 20% reduction | 30% reduction | 35% reduction | 40% reduction
|  | Achieved |  | 83% (=12% reduction) | N/A | 78.3% | 50.2% | 59% (=63% reduction over the baseline).
Source: FSNMS survey
| Impact Indicator 2 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20)
| Resilience Index Measurement and analysis (RIMA II) (in counties where BRACE II is implemented) | Planned |  |  |  |  | n/a | 10% increase | 10% increase
|  | Achieved |  |  |  | N/A | n/a | RCI = 31.0
Source: FSNMS survey, data analysed by M&E team
FINAL OUTCOME | Outcome Indicator 1 |  | Baseline (July 2016) | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20) | Assumptions
Improved food security and better community relationships | Prevalence of poor and borderline food consumption, disaggregated by sex of household head (Food Consumption Group) | Planned | 93% all 95% male-head 92% female-head | 30% reduction | 45% reduction | 25% reduction | 25% reduction | 30% reduction | 35% reduction
|  | Achieved |  | 83.9% all (10% reduct) 79.2% male (17% reduct) 92.5% female (1% increase) | 60% all (28% reduction) 49% male (38% reduction) 72% female (22% reduct) | 71% all 64% male 79% female | 55% all 51% male 60% female | 32.6% all 35.7% male 26.7% female
Source: WFP Outcome Post-Distribution Monitoring Surveys
| Outcome Indicator 2 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20)
| Diet diversity score of targeted households, disaggregated by sex of households head (HDDS) | Planned | 2.51 all 2.56 male-head 2.48 female-head | 5% increase | 10% increase | 15% increase | 15% increase | 18% increase | 18% increase
|  | Achieved |  | 2.73 all (9% increase) 2.87 male (13% increase) 2.47 female (0% increase) | 4.3 (58% increase) 4.3 male (74% increase) 4.4 female (53% increase) | 3.34 all 3.30 female 3.39 male | 1.54 all 1.61 male 1.45 female | 4.84 all 4.64 male 5.20 female
Source: WFP Outcome Post-Distribution Monitoring Surveys
| Outcome Indicator 3 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20)
| Proportion of targeted households implementing crisis and emergency strategies, disaggregated by sex of household head (Livelihoods CSI) | Planned | 71% all 85% male-head 63% female-head | 25% reduction | 38% reduction | 50% reduction | 50% reduction | 55% reduction | 60% reduction
|  | Achieved |  | 66.3% all (7% reduct) 76.4% male (10% reduc) 50% female (21% reduc) | 23% all (65% reduction) 10% female (80% reduction) 42% male (45% reduction) | 42% all 48% female 38% male | not available in 2nd PDM | 69.8% all 78.6% male 53.3% female
Source: IPs Outcome Post-Distribution Monitoring Surveys
| Outcome Indicator 4 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20)
| Reduced vulnerability to climate risks and shocks | Planned | N/A | N/A | N/A |  |  | TBD | TBD
|  | Achieved |  | N/A | N/A | N/A | N/A | N/A
Source: M&E Service provider (Mid-Term Evaluation and Final Evaluation)
| Outcome Indicator 5 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20)
| Reduced vulnerability to communal conflict | Planned | N/A | N/A | N/A |  |  | TBD | TBD
|  | Achieved |  | N/A | N/A | N/A | N/A | N/A
Source: M&E Service provider (Mid-Term Evaluation and Final Evaluation)
INTERMEDIARY OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20) | Assumptions
Increased capacity to absorb, anticipate and adapt to shocks and stresses (including climate variability and extremes) | Number of people with improved resilience [ICF indicator] | Planned | 0 | N/A | N/A |  |  | TBD | TBD | 0
|  | Achieved |  | N/A | N/A | N/A | N/A | N/A
Source: M&E Service provider (Mid-Term Evaluation and Final Evaluation)
| Outcome Indicator 2 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20)
| Proportion of targeted households using good nutrition practices |  | 0 | N/A | N/A |  |  | TBD | 7000
|  |  |  | N/A | N/A | N/A | N/A | N/A
Source: M&E Service provider (Mid-Term Evaluation and Final Evaluation)
| Outcome Indicator 3 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20)
| Proportion of targeted households using improved and climate-sensitive agricultural practices |  | 0 | N/A | N/A |  |  | TBD | 7000
|  |  |  | N/A | N/A | N/A | N/A | N/A
Source: M&E Service provider (Mid-Term Evaluation and Final Evaluation)
| Outcome Indicator 4 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20)
| Proportion of households giving or receiving support from other households (Social cohesion) |  | 0 | N/A | N/A |  |  | TBD | TBD
|  |  |  | N/A | N/A | N/A | N/A | N/A
Source: M&E Service provider (Mid-Term Evaluation and Final Evaluation)
| Outcome Indicator 5 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20)
| Proportion of targeted communities where there is evidence of functional structures for conflict resolution |  | 0 | N/A | N/A |  |  | TBD | TBD
|  |  |  | N/A | N/A | N/A | N/A | N/A
Source: M&E Service provider (Mid-Term Evaluation and Final Evaluation)
| Outcome Indicator 6 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20)
| Increase in incomes at households level |  | 0 | N/A | N/A |  | not set | TBD | TBD
|  |  |  | N/A | N/A | N/A | N/A | N/A
Source: M&E Service provider (Mid-Term Evaluation and Final Evaluation)
| Outcome Indicator 7 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20)
| Increase in cereal production at household level, disaggregated by increase in production and cultivated area (MT) | Planned | TBD | (a, production) 30% (b, area) 20% | (a, production) 40% (b, area) 20% | (a, production) 50% (b, area) 20% | not set | (a, production) 55% (b, area) 20% | (a, production) 60% (b, area) 20%
|  | Achieved |  | a. 55% b. 80% (2.58 feddan/hh) | a. % (0.865 tonnes/hh) b. 54% (2.2 feddan/hh) | Post Harvest Assessment ongoing | 47% | a. 54% (0.379 tonnes/hh) b. 84% (4.435 feddan)
| Outcome Indicator 8 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20)
| Increase in number of food / incomes sources at households level | Planned | 0 | N/A | N/A | N/A | not set | (+2) additional sources at household level | (+3) additional sources at household level
|  | Achieved |  | N/A | N/A | N/A | N/A | 1. sorghum production (Wahamed variety) 2. casava production 3. fishing in flood affected areas
Source: M&E Service provider (Mid-Term Evaluation and Final Evaluation)
OUTPUT 1 (35%) | Output Indicator 1.1 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20) | Assumptions
Food insecure targeted households access to labour based safety nets (cash/food-based transfer) | Number of women, men, boys and girls receiving cash/food transfers, disaggregated by sex and types of transfer [Accepted variance of 10%] | Planned | 0 | 77808 | 98304 | 99842 | 99842 | 113250 | 113250 | • Financial institutions, economic stability of the country and market access enable continued cash tranfers • Qualified partners are available to support and complement BRACE II interventions
|  | Achieved |  | 77772 | 98304 | 99842 | 99842 | 113250
Source: IPs quarterly reports (cash transfer tracker)
| Output Indicator 1.2 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20)
| Total amount of cash transferred to targeted beneficiaries (USD) [Accepted variance of 10%] | Planned | 0 | 2871214 | 3538944 | 2021760 | 4043520 | 4586625 | 4,586,625 (2,3331,305 DFID funds)
|  | Achieved |  | 1778175 | 3534677 | 2478309 | 4043520 | 4586625
|  | Source: IPs quarterly reports (cash transfer tracker) | [7 empty] | RISK RATING
OUTPUT 2 (30%) | Output Indicator 2.1 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20) | Assumptions
Community assets that enhance resilience to food insecurity and climate variability and extremes are improved or created | % of achievement in assets built, restored and maintained [Accepted variance of 10%] | Planned |  | 100% | 100% | 50% | 100% | 100% | 100% | • Community participation in activity and site selection and management starts at project inception and remains ongoing • Value of assets creation entitlement is attractive against work norms • Entitlements and complementary resources are sufficient to prevent negative coping strategies • Entitlements are supplemented by complementary foods, provided by partners or otherwise available • Households have access to local functioning markets • Limited price/currency inflation or fluctuation
|  | Achieved |  | 77% | 95% | 50% | 103% | 94
Source: IPs quarterly reports (cash transfer tracker)
| Output Indicator 2.2 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20)
| % of asset that are still used and/or maintained +12 months after their construction, disaggregated by types of assets | Planned | N/A | N/A | N/A | N/A | N/A | not set in 2019 | 85%
|  | Achieved |  | N/A | N/A | N/A | N/A | 80%
Source: IPs post-project assessment + Third Party Monitoring
| Output Indicator 2.3 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20)
| # of households having access to improved seeds, tools, equipment [Accepted variance of 10%] | Planned | 0 | 12968 | 16384 | 16640.3333 | 16640.3333 | 15485 | 19541 (MSR) 7,000 (DSR)
|  | Achieved |  | N/A | 16384 | 18, 544 | 18544 | 15485
|  | Source: IPs quarterly reports | [7 empty] | RISK RATING
OUTPUT 3 (25%) | Output Indicator 3.1 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20) | Assumptions
Skills and knowledge for resilience are improved | # of people trained on improved and climate-sensitive agricultural practices [Accepted variance of 10%] | Planned |  | 8800 | 16384 | 6820 | 6820 | 15485 | 9725 (MSR) 7,000 (DSR) | • Trainees are willing to be trained • Extension departments participate in backstopping • Inputs (seeds and tools) are locally available for the ITFs
|  | Achieved |  | 5,062 overall 2,231 male 2,831 female | 16,384 overall 5,837 male 10,547 female | 5903 | 5,903 (86%) | 15485
Source: IPs quarterly reports
| Output Indicator 3.2 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20)
| # of people trained for improved nutrition practices (disaggregated by sex) [Accepted variance of 10%] | Planned | N/A | N/A | N/A | 8320 | 16640 | 15485 | 9725 (MSR) 7,000 (DSR)
|  | Achieved |  | N/A | N/A | 4019 | 16,203 (97%) | 20208
Source: IPs quarterly reports
| Output Indicator 3.3 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20)
| # of people trained on conflict mitigation in targeted communities [Accepted variance of 10%] | Planned |  |  |  | 120 | 1210 | 1050 | 1050
|  | Achieved |  |  |  | 69 | 1159 (96%) | 1050
Source: IPs quarterly reports
| Output Indicator 3.4 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20)
| Number of dispute resolution / resource management structures set up (or improved) | Planned | N/A | N/A | N/A | 2 | 2 | 105 | 105
|  | Achieved |  | N/A | N/A | 2 | 2 | 105
|  | Source: IPs quarterly reports | [7 empty] | RISK RATING
OUTPUT 4 (10%) | Output Indicator 4.1 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20) | Assumptions
BRACE II management is adaptive and informed by the M&E and feedback mechanism | Partners' community feedback mechanisms established at the distribution sites | Planned |  | N/A | 40% | 80% | 80% | 100% | 100% | • Beneficiaries are willing to use the available complaints and response mechanisms
|  | Achieved |  | N/A | Data not routinely collected in 2017 | 100% | 100% | 100%
Source: IPs quaterly reports
| Output Indicator 4.2 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20)
| Proportion of people who know where to complain/provide feedback | Planned | 35% | N/A | 7.5% increase | 15% increase | 15% increase | 15% increase | 15% increase
|  | Achieved |  | N/A | 77% all 72% male 83% female | 76% all 75% male 77% female | 82% all 83% male 80% female | 80%
Source: IPs quaterly reports
| Output Indicator 4.3 |  | Baseline | Milestone 1 (Oct 16) | Milestone 2 (Oct 17) | June 2018 update | Milestone 3 (Oct 18) | Milestone 4 (Oct 19) | Milestone 5 (Oct 20)
| # of Monitoring & Evaluation & Learning products produced by the M&E component | Planned
Achieved
|  | Source: M&E service provider quaterly reports | [7 empty] | RISK RATING

## BRACE II Logframe World Vision
Update: April 2020
PROJECT TITLE: Building Resilience through Asset Creation and Enhancement - Phase Two (BRACE II)- WORLD VISION, SAADO, SPEDP
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Update June 20 | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of Project Target | Comments | Assumptions
Strengthened food and nutrition security and resilience among food insecure households and communities in Greater Bahr-el-Ghazal and Equatoria Regions in South Sudan | Reduced prevalence of moderately and severely food insecure households (in counties where BRACE II is implemented) Adopted as is from WFP | Planned | 92% | 70% | 60% | 50% | 50% | 40% | 40% | Extracted from May 2018 FSNMS, Average for Warrap, EEQ and NBG | World Vision, SAADO and SPEDP will use competent human resources to implement and monitor food security and resilience activities
|  | Achieved |  | 58% | [6 empty] | An enabling environment which is politically stable, accessible and secure for activity implementation
|  | Source: FSNMS | [8 empty] | Adequate financial resources over the project implementation period
| Impact Indicator 2 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Update June 20 | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of Project Target | To be discussed with DFID | Beneficiaries are retained throughout the respective phases they are selected to participate in
| Resilience Index Measurement and analysis (RIMA II) (in counties where BRACE II is implemented) Pending finalization | Planned | N/A | TBD | TBD | TBD | TBD | TBD | TBD
Achieved
Source: FSNMS survey, data analysed by M&E team
FINAL OUTCOME | Outcome Indicator 1 |  | Baseline (July 2018 | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone | WVSS Post Distribution monitoring report | Assumptions
Improved food security and better community relationships | Prevalence of poor and borderline food consumption, disaggregated by sex of household head (Food Consumption Group) | Planned | 82% ( Male 78%; Female 86% | 70% | 60% | 50% | 45% | 35% | 30%
|  | Achieved |  | 69.3% (Male 67.8%; Female 71.1%) | 57.2% ( Male 55%; Female 59.4%
Source: WVSS Outcome Post-Distribution Monitoring Surveys
| Outcome Indicator 2 |  | Baseline (July 2018 | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone
| Diet diversity score of targeted households, disaggregated by sex of households head (HDDS) | Planned | 28% ( Male 31%; Female 25%) | 35% | 45% | 55% | 65% | 75% | 75%
|  | Achieved |  |  | 48.71% (Male 46.9%; Female 51.6%)
Source: WVSS Outcome Post-Distribution Monitoring Surveys
| Outcome Indicator 3 |  | Baseline ( July 2018) | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone
| Proportion of targeted households implementing crisis and emergency strategies, disaggregated by sex of household head (Livelihoods CSI) | Planned | 61% ( Male 61.2%; Female 60.4%) | 55% | 45% | 40% | 35% | 30% | 30%
|  | Achieved |  |  | 47.42% (Male 44.6%; Female 51.6%)
Source: IPs Outcome Post-Distribution Monitoring Surveys
| Outcome Indicator 4 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone
| Reduced vulnerability to climate risks and shocks | Planned | 0 | TBD | TBD | TBD | TBD | TBD | TBD | This is extracted from Mid term evaluation
|  | Achieved |  | 43% *
Source: M&E Service provider (Mid-Term Evaluation and Final Evaluation)
| Outcome Indicator 5 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone (cumul.)
| Reduced vulnerability to communal conflict | Planned | 0% | 50% | 60% | 70% | 80% | 80% | 80%
|  | Achieved |  |  | 62.8% ( Male 69.5%; Female 58.3%)
Source: M&E Service provider (Mid-Term Evaluation and Final Evaluation)
INTERMEDIARY OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone |  | Assumptions
Increased capacity to absorb, anticipate and adapt to shocks and stresses (including climate variability and extremes) | Number of people with improved resilience [ICF indicator] | Planned | 0 | TBD | TBD | TBD | TBD | TBD | TBD
Achieved
Source: M&E Service provider (Mid-Term Evaluation and Final Evaluation)
| Outcome Indicator 2 |  | Baseline ( July 2018) | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone
| Proportion of targeted households using good nutrition practices |  | 55% | N/A | N/A | 60% | 65% | 65% | 70% | To be tracked next PDM. Initally dropped since WFP was not tracking | Initially dropped however since we have baseline we can start tracking on PDMs
Source: M&E Service provider (Mid-Term Evaluation and Final Evaluation)
| Outcome Indicator 3 |  | Baseline ( July 2018) | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone
| Proportion of targeted households using improved and climate-sensitive agricultural practices |  | 19.2% | 20% | 25% | 30% | 35% | 40% | 40%
28.9%
Source: M&E Service provider (Mid-Term Evaluation and Final Evaluation) Partner PDM
| Outcome Indicator 4 |  | Baseline ( July 2018) | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone
| Proportion of households giving or receiving support from other households (Social cohesion) |  | 38.9% | 60% | 70% | 80% | 80% | 90% | 90%
|  |  |  | 74% | 74%
Source: M&E Service provider (Mid-Term Evaluation and Final Evaluation) PDM
| Outcome Indicator 5 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone | 92% is from WVSS PDM Oct 2019
| Proportion of targeted communities where there is evidence of functional structures for conflict resolution |  | 79.4% | 85% | 90% | 95% | 95% |  | 95%
|  |  |  | 91% | 92%
Source: M&E Service provider (Mid-Term Evaluation and Final Evaluation) Partner PDM
| Outcome Indicator 6 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone (cumul.)
| Increase in incomes at households level |  |  | TBD | TBD | TBD
Source: M&E Service provider (Mid-Term Evaluation and Final Evaluation)
| Outcome Indicator 7 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone
| Increase in agricultural production at household level, disaggregated by increase in production (MT), cultivated area (ha) and total value of production (MT) | Planned | TBD | TBD | TBD | TBD | TBD | TBD
Achieved
Source: FAO Post-Harvest Assessment / M&E Service provider (Mid-Term Evaluation and Final Evaluation)
| Outcome Indicator 8 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone
| Increase in number of food / incomes sources at households level |  | 1.69 | N/A | 1.8 |  | 1.9 | 2 | 2
1.82
Source: M&E Service provider (Mid-Term Evaluation and Final Evaluation)
OUTPUT 1 (35%) | Output Indicator 1.1 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone (cumul.) |  | Assumptions
Food insecure targeted households access to labour based safety nets (cash/food-based transfer) | Number of women, men, boys and girls receiving cash/food transfers, disaggregated by sex and types of transfer [Accepted variance of 10%] | Planned | 0 | 54900 | 75900 | 57000 | 36000 | 36000 | 111900 |  | World Vision, SAADO and SPEDP will use competent human resources to implement and monitor food security and resilience activities
|  | Achieved |  | 54040 | 75450 M- 37606 F- 37844 | [5 empty] | An enabling environment which is politically stable, accessible and secure for activity implementation
|  | Source: IPs quarterly reports (cash transfer tracker) | [8 empty] | Adequate financial resources over the project implementation period
| Output Indicator 1.2 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone (cumul). |  | Beneficiaries are retained throughout the respective phases they are selected to participate
| Total amount of cash transferred to targeted beneficiaries (USD) [Accepted variance of 10%] | Planned | 0 | 2223450 | 2156025 | 1396500 | 882000 | 882000 | 7539975
|  | Achieved |  | 2217942 | 2156025
|  | Source: IPs quarterly reports (cash transfer tracker) | [8 empty] | RISK RATING
OUTPUT 2 (30%) | Output Indicator 2.1 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone |  | Notes
Community assets that enhance resilience to food insecurity and climate variability and extremes are improved or created | % of achievement in assets built, restored and maintained [Accepted variance of 10%] | Planned | 0 | 100% | 100% | 100% | 100% | 100% | 100%
|  | Achieved |  | 112% | 108%
Source: IPs quarterly reports (cash transfer tracker)
| Output Indicator 2.2 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone
| % of asset that are still used and/or maintained +12 months after their construction, disaggregated by types of assets | Planned | 0 | 100% | 100% | 100% | 100% | 100% | 100%
|  | Achieved |  | 83% | 98%
Source: IPs post-project assessment + Third Party Monitoring
| Output Indicator 2.3 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone
| # of households having access to improved seeds, tools, equipment [Accepted variance of 10%] | Planned | 0 | 9150 | 12650 | 9500 | 9500 | 6000 | 17150
|  | Achieved |  | 9150 | 12650
|  | Source: IPs quarterly reports | [8 empty] | RISK RATING
OUTPUT 3 (25%) | Output Indicator 3.1 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone |  | Notes
Skills and knowledge for resilience are improved | # of people trained on improved and climate-sensitive agricultural practices [Accepted variance of 10%] | Planned | 0 | 9150 | 12650 | 9500 | 9500 | 6000 | 17150
|  | Achieved |  | 9150 | 12650
Source: IPs quarterly reports
| Output Indicator 3.2 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone
| # of people trained for improved nutrition practices (disaggregated by sex) [Accepted variance of 10%] | Planned | 0 | 4575 | 1750 | 0 | 1560 | 1560 | 9445
|  | Achieved |  | *7,092 | 7092
Source: IPs quarterly reports
| Output Indicator 3.3 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone
| # of people trained on conflict mitigation in targeted communities [Accepted variance of 10%] | Planned | 0 | 322 | 249 | 0 | 384 | 192 | 1147
|  | Achieved |  | 327 | 249
Source: IPs quarterly reports
| Output Indicator 3.4 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone
| Number of dispute resolution / resource management structures set up (or improved) | Planned | 0 | 23 | 9 | 0 | 24 | 12 | 68
|  | Achieved |  | 23 | 9
|  | Source: IPs quarterly reports | [8 empty] | RISK RATING
OUTPUT 4 (10%) | Output Indicator 4.1 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone |  | Notes
BRACE II management is adaptive and informed by the M&E and feedback mechanism | Partners' community feedback mechanisms established at the distribution sites | Planned | 0 | 100% | 100% | 100% | 100% | 100% | 100%
|  | Achieved |  | 100% | 100%
Source: IPs quaterly reports, PDM
| Output Indicator 4.2 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone
| Proportion of people who know where to complain/provide feedback | Planned | 78% | 95% | 95% | 95% | 95% | 95% | 95%
|  | Achieved |  | 78% | 81.3%
Source: IPs quaterly reports, PDM
| Output Indicator 4.3 |  | Baseline | Milestone 1 (Oct 18) | Milestone 2 (Oct 19) | Milestone 3 (Jun 20) | Milestone 3 (Oct 20) | Milestone 4 (Oct 21) | End of project milestone
| # of Monitoring & Evaluation & Learning products produced by the M&E component | Planned | 0 | 5 | 3 | 1 | 2 | 2 | 13
|  | Achieved |  | 3 | 3
Source: M&E baseline report, PDM, Market Survey, Evaluations, TPM etc