## PFM Log Frame
PROJECT NAME | Improving the management of public funds for the benefit of the people of Burma
|  |  |  | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
Effective, efficient, accountable and responsive delivery of public services for the people of Myanmar | Improvement of scores in two of four areas measured by the World Bank's Public Expenditure and Financial Accountability (PEFA) framework: Credibility of the Budget; Comprehensiveness and Transparency of the Budget; Budget cycle; and Donor Practices | Planned | PEFA (March 2012) | n/a | n/a | n/a | n/a | n/a |  | Improvement in 2 areas (2019)
|  | Achieved |  | n/a | n/a | n/a | n/a | PEFA to be conducted in 2019H1 | PEFA to be published in 2020
Source
Current PEFA scores are available at http://www.pefa.org/en/assessment/mm-mar12-pfmpr-public-en PEFA published in 2015 and 2019
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7 | Assumptions
Strengthened PFM systems and institutions, and improved policy formulation and implementation | Increase in Tax collection from Large Taxpayers | Planned | Baseline: Taxes collected by LTO in FY 2015-2016 was 1,105,670 million MMK. | Baseline+5% (in real terms)(2015) | Baseline+10% (in real terms) (2016) | Baseline+15% (in real terms) (2017) | Baseline+20% (in real terms) (2018) | Baseline+20% (in real terms) (2019) | +20 percent in real terms | +40 percent in real terms. Taxes collected by for FY 2020/21 is estimated at 3,250,000 million MMK | o Benefits of improvements in PFM systems to service delivery will be more pronounced if development partner funds are progressively moved on to the budget o PFM systems are currently a binding constraint on public service delivery and as such addressing weaknesses will lead to improvements
|  | Achieved |  | >7% | 8.1% | 8.71%, Taxes collected by LTO in FY 2016/17 stood at 2,390,434 million MMK | 7.9%, Taxes collected by LTO in FY 2017/18 stood at 2,878,057 million MMK | 8.49% (2018 mini budget) | 7.1%, Taxes collected by LTO in FY 2018/19 stood at 3,705,921 million MMK
Source
Fiscal Reports produced by Internal Revenue Department
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
| Budget preparation process including (i) issuance of ceilings (ii) preparation of medium-term fiscal framework | Planned | (i) N and (ii) N | (i) N and (ii) N | (i) N and (ii) Y | (i) Y and (ii) Y | (i) Y and (ii) Y | (i) Y and (ii) Y | (i) Y and (ii) Y | (i) Y and (ii) Y
|  | Achieved |  | (i) Y and (ii) Y | (i) Y and (ii) Y | (i) Y and (ii) Y | (i) Y and (ii) Y | (i) Y and (ii) Y | (i) Y and (ii) Y
Source
Budget circular and Budget Documents produced by the Budget Department
| Outcome Indicator 3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
| Composition of expenditure out-turn compared to original approved | Planned | 24% 2012/13 | 22% (2015) | 20% (2016) | 18% (2017) | 16% (2018) | 14% (2019) | 14% (2020) | 14%
|  | Achieved |  | 20% | 10% | 6% | 4.87% | 3.84% | 10.1% (2018/19)
Source
Financial Statements produced by the budget department
| Outcome Indicator 4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
| Number of beneficiaries of (i) training courses | Planned | None, as PFM Academy not operational as yet | 0 | 50, 0 | 100, 20 | 200, 40 | 300, 60 | 300 (60% female) | 300 (60% female)
|  | Achieved |  | 0 | 1000, 0 | 1450, 0 | 1822, 0 | 7900, 0 | 8513, 0
Source
MoPF PFM Academy
| Outcome Indicator 5 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
| Government commitment to fiscal transparency in line with global good practice (i), including report on revenues from natural resources(ii) | Planned | 1 (enacted budget); no report on revenues from natural resources | (i) 1 (2015) | (i) 2(2016) | (i) 3; (ii) report on revenues from natural resources published (2017) | i) 3; (ii) report on revenues from natural resources published(2018) | (i) 4; (ii) report on revenues from natural resources published (2019) | (i) 4; (ii) report on revenues from natural resources published (2020) | (i) 8; (ii) report on revenues from natural resources published (2020)
|  | Achieved |  | 1 | 2 | 4 | 4 | 7 documents + 1 EITI Report | 7 documents + 1 EITI Report
Source
Availability of documents on Ministry of Finance website produced by Budget Department
| Outcome Indicator 6 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
| Increased citizen engagement in budget processes measured by improvement to Myanmar's score in Open Budget Index. |  | 0 (2012 data from 2010) | no data will be available | >0 (2014 data available in 2016) | no data will be available | >5 (2016 data available in 2018) | no data will be available | no data will be available | >/= 15 (Cambodia's current score)
|  |  |  | n/a | 2 |  | 7 | n/a | To be published in 2020
|  |  | Source | [7 empty] | RISK RATING
|  |  | Open Budget Index produced every two years | [7 empty] | Moderate
INPUTS (£) | DFID (£) |  | Govt (£) | World Bank |  | Total (£) |  | DFID SHARE (%)
| 24 million |  | No Monetary Resources | $30 million |  | £38 million |  | 52%
INPUTS (HR) | DFID (FTEs)
0.7
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7 | Assumption
Increased tax revenue for delivery of public services | Number of large tax-payers completing self-assessment. Delivery of an integrated tax information system for testing in IRD headquarters, LTO and MTO by March 2021. | Planned | 0 (2012/13) | 0 (2015) | 20 (2016) | 50 (2017) | 150 (2018) | 250 (2019) | 250 (2020) | Delivery of an integrated tax information system for testing in IRD headquarters, LTO and MTO. 2300 taxpayers completeing self-assessment | o An allocation of resources aligned to priorities will depend upon a clear politically determined expenditure strategy o Trust in revenue generation and the use of public funds will depend on civil society issues being heard and addressed.
|  | Achieved |  |  |  | 512 | 537 | 861 | 850
Source
Internal Revenue Department records
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6
20% | Quarterly revenue forecasting bulletin issued | Planned | No |  |  |  |  | Yes | Yes | Yes
|  | Achieved | [5 empty] | Yes | Yes
|  | Source | [8 empty] | RISK RATING
|  | Annual budget documentation produced by Internal Revenue Department | [8 empty] | Major
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  | DFID SHARE (%)
| Component 1 contribution of $11 million (USD) | [6 empty] | 40%
INPUTS (HR) | DFID (FTEs)
0.1
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7 | Assumptions
Improved budgeting and planning | Improving information base for linking budgets to plans( Number of departments submitting (i) recurrent budget and (ii) capital budget forms electronically ) | Planned | 0 (2012/13) | (i) 5 and (ii) 5 (2015) | (i) 20 and (ii) 20 (2016) | (i) 30 and (ii) 30 (2017) | (i) 35 and (ii) 35 (2018) | (i) 40 and (ii) 40 (2019) | (i) 40 and (ii) 40 (2020) | (i) 40 and (ii) 40 (2020) | o An allocation of resources aligned to priorities will depend upon a clear politically determined expenditure strategy o Trust in revenue generation and the use of public funds will depend on civil society issues being heard and addressed.
|  | Achieved |  | (i) 0 and (ii) 0 | (i) 0 and (ii) 0 | (i) 0 and (ii) 0 (2017) | (i) 0 and (ii) 35 | (i) 1 and (ii) 40 | All 169 agencies submit recurrent and capital budget forms.
Source
Electronic Budget submissions and Electronic Planning submissions
IMPACT WEIGHTING (%) | Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
10% | Budget rebalancing through increased budgetary share of resources to health and education ministries relative to baseline. | Planned | 11.2% of total spending in education and health ministries in 2013/14. |  |  |  |  | +2.5% from baseline (2019) | +3% from baseline (2020) | n/a
|  | Achieved | [5 empty] | Target met in budget allocations. 14.3% of budget allocated to education and health. | Not met. 13.4% of budget allocated to education and health.
|  | Source | [8 empty] | RISK RATING
|  | MoPF Budget Department | [8 empty] | Moderate
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  | DFID SHARE (%)
| Component 1 contribution of $14 million (USD) | [6 empty] | 40%
INPUTS (HR) | DFID (FTEs)
0.1
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7 | Assumptions
Improved budget execution | Timeliness of reconciled budget execution reports (Number of months after end of period) | Planned | >6(2012/13) | </=5(2015) | <5 (2016) | </=4 (2017) | <4 (2018) | </=3 (2019) | </=3 (2020) | </=3 (2021) | o An allocation of resources aligned to priorities will depend upon a clear politically determined expenditure strategy o Trust in revenue generation and the use of public funds will depend on civil society issues being heard and addressed.
|  | Achieved |  | >6 | 4 | 3 | 2 | 2 | 3
Source
Budget Execution Reports, MOPF
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
| Information on procurement opportunities and contract awards (above USD 100 000) are publicly available for 5 Union ministries. (Percentage) | Planned | 55 | Information on 20% of large contracts(2015) | 35% (2016) | 45%(2017) | 55%(2018) | 70% (2019) | 70% | 70
|  | Achieved |  | 0% (No standardized information provided in Baseline) | 0% (No standardized information provided in Baseline) | 0% (No standardized information provided in Baseline) | 0% (No standardized information provided in Baseline) | 0% (No standardized information provided in Baseline) | 66%
Source
Consolidated Central Bank statement
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
10% | New Financial Rules and Regulations are enacted and published | Planned | Financial rules and regulations outdated and not widely available | Updated financial rules and regulations approved by MOF | Rules and regulation put on website | Financial rules and regulations revisited and further refined | Updated rules and regulation published. | Updated rules and regulation published | Appropriate financial rules and regulations in line with practice | Updated financial rules and regulations published and adopted
|  | Achieved |  | Not yet achieved | Approved but not published |  | The Financial Rules and Regulations were updated by the MOPF during FY 16-17 and approved by the Government in April 2017. They have since been put on the MOPF website. | New Financial Rules and Regulations enacted on 1st April, 2017 and posted on the web site www.mof.gov.mm. Official English version of the financial rules and regulations (FRR) approved and posted on MOPF website in October 2018. | MOPF has developed the Financial Information and Reporting System for Treasury (FIRST) and expected to complete and ready for usage by July 2020.
|  | Source | [8 empty] | RISK RATING
|  | Consolidated Central Bank statement | [8 empty] | Major
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  | DFID SHARE (%)
| Component 1 contribution of $15 million (USD) | [6 empty] | 40%
INPUTS (HR) | DFID (FTEs)
0.1
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7 | Assumptions
Improvement in institutional PFM capacity for implementation | Number of beneficiaries of training courses (by gender) | Planned | 0 | 50, 0 | 100, 20 | 200, 40 | 300, 60 | 300, >40% women (2019) | 300, >60% women (2020) | 300, >60% women (2020) | o An allocation of resources aligned to priorities will depend upon a clear politically determined expenditure strategy o Trust in revenue generation and the use of public funds will depend on civil society issues being heard and addressed.
|  | Achieved |  | 1000, 0 |  | 1450,0 | 1822,0 | 7900, 77% women | 8513
Source
PFM Academy Records
IMPACT WEIGHTING (%) | Output Indicator 4.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
10% | Establishment of PFM Academy Includes: curriculum development and engaging training provider | Planned | [5 empty] | Curriculum developed | Training provider engaged | PFM academy is established and carrying out initial training. A gender disaggregated training monitoring and evaluation framework is operational.
|  | Achieved | [5 empty] | Y | Y
|  | Source | [8 empty] | RISK RATING
|  | World Bank | [8 empty] | Moderate
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  | DFID SHARE (%)
| Component 1 contribution of $6 million (USD) | [6 empty] | 40%
INPUTS (HR) | DFID (FTEs)
0.1
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7 | Assumptions
Improved transparency in the mobilisation and use of public funds in line with global good practiceshowing improvements in competency-based assessments | Time liness of submission of audit reports to parliament by the Office of the Auditor General | Planned | Over 1 year | <14 months | <13 months | <12 months | <11 months | <10 months | <10 months | <10 months | o An allocation of resources aligned to priorities will depend upon a clear politically determined expenditure strategy o Trust in revenue generation and the use of public funds will depend on civil society issues being heard and addressed.
|  | Achieved |  | 14 months | 11 months | 9 months | 12 months | 13 months | 1 1 months
Source
Audit reports produced by the Office of the Auditor General
IMPACT WEIGHTING (%) | Output Indicator 5.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
10% | JPAC publish a report on their website based on their review of the OAG’s report on the accounts of the Union. | Planned | [5 empty] | Y | Y | Y
|  | Achieved | [5 empty] | Y. Published in Aug 2018 | Y
|  | Source | [8 empty] | RISK RATING
|  | JPAC Website | [8 empty] | Major
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  | DFID SHARE (%)
| Component 1 contribution of $9 million (USD) | [6 empty] | 40%
INPUTS (HR) | DFID (FTEs)
0.1
OUTPUT 6 | Output Indicator 6.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7 | Assumptions
Improved citizen and civil society engagement | Consultations with public as part of determining budget priorities (OBI Q70) | Planned | c. Yes, the executive has established some mechanisms to identify the public’s perspective on budget priorities, but these mechanisms are not effective or practical or are not accessible in practice to a majority of the public. |  |  |  | Progress in at least one output indicator. |  |  |  | o An allocation of resources aligned to priorities will depend upon a clear politically determined expenditure strategy o Trust in revenue generation and the use of public funds will depend on civil society issues being heard and addressed.
|  | Achieved |  |  | D. No, the executive has not established any mechanisms to identify the public’s perspective on budget priorities |  | D - Participation mechanisms do not exist with respect to the national annual budget process. | No longer used 6.4-6.6 | No longer used 6.4-6.6 | No longer used 6.4-6.6
Source
Open Budget Survey
| Output Indicator 6.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
| Public hearings on fiscal framework with citizen views heard (OBI Q76) | Planned | d. No, public hearings are not held on the macroeconomic and fiscal framework in which testimony from the executive branch and the public is heard. |  |  |  | Progress in at least one output indicator. | No longer used pls see 6.4-6.6 | No longer used pls see 6.4-6.6 | No longer used pls see 6.4-6.6
|  | Achieved |  |  | D. No, public hearings are not held on the macroeconomic and fiscal framework in which testimony from the executive branch and the public is heard. |  | D - Participation mechanisms do not exist with respect to the national annual budget process. | No longer used 6.4-6.6 | No longer used 6.4-6.6 | No longer used 6.4-6.6
Source
Open Budget Survey
| Output Indicator 6.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
| Access to budget information (OBI Q63) | Planned | d. The executive does not consult with the citizens before publishing a Citizens Budget, or a Citizens Budget is not published. |  |  |  | Progress in at least one output indicator. | No longer used pls see 6.4-6.6 | No longer used pls see 6.4-6.6 | No longer used pls see 6.4-6.6
|  | Achieved |  |  | D. No, the executive has not established any mechanisms to identify the public’s requirements for budget information in the Citizen’s Budget. |  | D - The Citizens Budget is published late and therefore considered not publicly available. | No longer used 6.4-6.6 | No longer used 6.4-6.6 | No longer used 6.4-6.6
Source
Open Budget Survey
| Output Indicator 6.4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
| Publication of the eight key Union budget documents identified by IBP | Planned | Two not produced Five published late, or not published online, or produced for internal use only. One available to the public. |  |  |  |  | Improvement over milestone 4 | Four budget documents published on the MoPF website on time. | Eight budget documents published on the MoPF website on time.
|  | Achieved |  |  | One not produced Six published late, or not published online, or produced for internal use only. One available to the public. |  | Zero not produced Six published late, or not published online, or produced for internal use only. Two available to the public. | Achieved - Four budget documents were published on the MoPF website on time. | Exceeded - Seven budget documents were published on the MoPF website on time.
Source
MoPF Website
| Output Indicator 6.5 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
| Number of States & Regions producing the following fiscal documents in the previous fiscal year: i) Citizen's Budgets ii) Reform Priority Documents iii) Regional Economic Development Plan iv) Budget Briefs v) Pre-Budget Statement | Planned | [5 empty] | i) 8 ii) 4 iii) 2 iv) 3 | i) 7 ii) n/a iii) n/a iv) 5 v) 2 | i) 7 ii) n/a iii) 1 iv) n/a v) 3 vi) 2 vii) 5
|  | Achieved |  |  |  |  | i) 4 ii) 4 iii) 0 iv) 3 | i) 9 ii) 6 iii) 2 iv) 4 | i) 14 (7 directly supported by TAF) ii) n/a iii) 2 iv) 4 v) 3
Source
Asia Foundation
IMPACT WEIGHTING (%) | Output Indicator 6.6 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
10% | Number of States & Regions conducting events in the previous fiscal year: i) Citizen Budget launch events ii) Budget Transparency Regional Forums iii) Budget Literacy Trainings iv) Dialogue Sessions v) Citizen Budget CSO feedback Events | Planned | [5 empty] | i) 8 ii) 6 iii) 6 iv) 5 | i) 7 ii) 1 iii) 4 iv) 4 v) 5 | i) 7 ii) n/a iii) 1 iv) n/a v) 7 vi) 1
|  | Achieved |  |  |  |  | i) 3 ii) 0 iii) 1 iv) 0 | i) 6 ii) 6 iii) 6 iv) 0 | i) 8 (6 directly supported by TAF) ii) n/a (funded by US OBI project) iii) 0 iv) n/a (funded by US OBI project) v) 5
|  | Source | [8 empty] | RISK RATING
|  | Asia Foundation | [8 empty] | Moderate
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  | DFID SHARE (%)
| 2 million |  | 0 | 0 |  | £2 million |  | 100%
INPUTS (HR) | DFID (FTEs)
0.1
OUTPUT 7 | Output Indicator 7.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7 | Assumptions
Increase transparency and accountability in Myanmar’s management of extractive industry data, revenue, and impacts | An established well functioning Multi Stakeholder Group | Planned | No MSG | MSG established (2015) | MSG meets regularly with effective participation by civil society and companies (2016) | MSG meets regularly with effective participation by civil society and companies (2017) | MSG meets regularly with effective participation by civil society and companies (2018) | MSG meets regularly with effective participation by civil society and companies (2019) |  |  | o An allocation of resources aligned to priorities will depend upon a clear politically determined expenditure strategy o Trust in revenue generation and the use of public funds will depend on civil society issues being heard and addressed.
|  | Achieved |  | Completed | Achieved | No longer used - 7.3 to 7.5 | No longer used - 7.3 to 7.5 | No longer used - 7.3 to 7.5 | No longer used - 7.3 to 7.5 | No longer used - 7.3 to 7.5
Source
EITI application
| Output Indicator 7.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
| Validation of EITI country reports and process b y EITI board | Planned | None | EITI application produced and published (2015) | EITI application produced and published (2016) | EITI application reviewed and accepted (2017) | EITI reports produced, published and validated (2018) | EITI reports produced, published and validated (2019)
|  | Achieved |  | Completed | First EITI report | No longer used - 7.3 to 7.5 | No longer used - 7.3 to 7.5 | No longer used - 7.3 to 7.5 | No longer used - 7.3 to 7.5 | No longer used - 7.3 to 7.5
Source
EITI reporting
| Output Indicator 7.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
| Successful publication of annual EITI Reconciliation Reports and EITI Validation results that indicate 'meaningful progress' against the EITI standard | Planned | EITI Scoping Study completed | N/A See 7.1 and 7.2 | Publication of First EITI Reconciliation Report | Publication of Second EITI Reconciliation Report | Publication of Third EITI Reconciliation Report | Publication of Fourth EITI Reconciliation Report | Publication of Fifth EITI Reconciliation Report and validation of making 'meaningful progress' against the EITI standard | Publication of Sixth EITI Reconciliation Report
|  | Achieved |  | N/A See 7.1 and 7.2 | Achieved | Not achieved | The Second and Third EITI Reconcilliation Reports was published in March 2018 | The Fourth EITI Reconcilliation Reports was published in March 2019 | The Fourth EITI Reconcilliation Reports will be published in March 2020. Myanmar was validated as making 'meaningful progress' against the EITI standard
Source
EITI Reconciliation Document
| Output Indicator 7.4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
| Media, CSO, and citizen engagement in governance and accountability of the extractive industries | Planned | Limited understanding of and access to information on resource governance and EITI | N/A See 7.1 and 7.2 | 15% of respondents report improved understanding of the EITI compared to previous year | 25% of respondents report improved understanding of the EITI compared to previous year | 30% of respondents report improved understanding of the EITI compared to previous year | 35% of respondents report improved understanding of the EITI compared to previous year
|  | Achieved |  | N/A See 7.1 and 7.2 | N/A See 7.1 and 7.2 | n/a | No longer used | No longer used | No longer used | No longer used - 7.3 to 7.5
Source
World Bank Group Survey
| Output Indicator 7.5 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
| Improved management of the extractive industries through systematic registration and monitoring of gemstones, oil, gas and mining licenses | Planned | No publicly available mineral or hydrocarbons license registry | N/A See 7.1 and 7.2 | Computerized databases of hydrocarbons and mineral licenses | Digitization of license information and re-verification of data-sets and geographic coordinates | Design and installation of a computerized mineral cadastre | Public access to mineral cadaster system and hydrocarbons registry | Registry for mineral and gemstone licenses (Mineral Cadastre System) is publicly accessible | Registry for mineral and gemstone licenses (Mineral Cadastre System) is publicly accessible
|  | Achieved |  | N/A See 7.1 and 7.2 | N/A See 7.1 and 7.2 |  | Digital registration of licenses has commenced. Design study of license database has started | Conceptual design completed and recruitment of main consultant under way | Not achieved – the final phase of the mining cadastre procurement was finalised in January 2020. The system is expected to be operational by March 2021
Source
Cadastre on Mining
IMPACT WEIGHTING (%) | Output Indicator 7.6 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
20% | Number of outreach activities | Planned |  |  |  |  | Three outreach events implemented Male participants:150 Female participants: 90 | Three outreach events implemented Male participants:150 Female participants: 90 | Completion of at least 15 training and outreach events 650 male participants 400 female participants | Completion of at least 15 training and outreach events 650 male participants 400 female participants
|  | Achieved | [5 empty] | Eight outreach events 589 Male paticipants 238 female participants | 4 trainings, 5 workshops & 5 outreaches , 650 male, 550 Female
|  | Source | [8 empty] | RISK RATING
|  | National co-ordination secretariat | [8 empty] | Major
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  | DFID SHARE (%)
| 3 million |  | 0 | 0 |  | £3 million
INPUTS (HR) | DFID (FTEs)
0.1
OUTPUT 8 | Output Indicator 8.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7 | Assumptions
Improved planning, budgeting and revenue raising in targeted subnational government | Qualitative assessment of overall progress against programme outcomes and the AISR results framework. Progress is assessed according to the extent to which the programme has contributed to improvements in the following areas: Subnational public financial management: more inclusive and responsive subnational public finance Effective policy making: more effective policy implementation and reform Social accountability: stronger social accountability through improved civic engagement Institutional Collaboration: support to broader DFID objectives and discovery of new opportunities to strengthen programme goals. | Planned | NA | NA | A | A | A | A | A | A | 1) NLD government in the States and Regions has built up sufficient understanding of the structures of subnational government, and its role within these, that it is able to articulate visions for their state and regions. (2) There remains a consensus amongst elites that Myanmar should continue on a path towards federalism and fiscal decentralization.
|  | Achieved |  |  |  | A | A | A+ | A
Source
Scoring A+ = programme exceeded expectations A = programme met expectations B = programme is below expectations C = programme is considerably below expectations
IMPACT WEIGHTING (%) | Output Indicator 8.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Milestone 7
10% | Qualitative assessment of the extent to which the programme demonstrates strong evidence of: (a) collaborating with, and influencing, other development actors (b) learning and adapting to new evidence and changes in the political context. | Planned |  |  | A | A | A | A | A | A
|  | Achieved |  |  |  | A | A+ | A | A
|  | Source | [8 empty] | RISK RATING
|  | Scoring A+ = programme exceeded expectations A = programme met expectations B = programme is below expectations C = programme is considerably below expectations | [8 empty] | Moderate
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  | DFID SHARE (%)
| 4.1 million |  | 0 |  |  | £4.1 million
INPUTS (HR) | DFID (FTEs)
0.2

## Log of Change Frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE | Reason of making changes
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2018-01-01
1 | Output indicator 6.1 | Added Achieved target date - No longer used 6.4-6.6, Added Source - Open Budget Survey | N | 2018-10-09
2 | Output indicator 6.2 | Added Achieved target date - No longer used 6.4-6.6, Added Source - Open Budget Survey | N | 2018-10-09
3 | Output indicator 6.3 | Added Achieved target date - No longer used 6.4-6.6, Added Source - Open Budget Survey | N | 2018-10-09
4 | Output indicator 6.4 | Indicator 6.4 is newly added in the logframe | N | 2018-10-09
5 | Output indicator 6.5 | Indicator 6.5 is newly added in the logframe | N | 2018-10-09
6 | Output indicator 6.6 | Indicator 6.6 is newly added in the logframe | N | 2018-10-09
7 | Output 6 | Input (£) amended from DFID £ 5 million to £2 million, Risk Rating amended from high risk to Moderate | N | 2018-10-09
8 | Output indicator 8.1 | Output indicator amended from '' Qualitative assessment of overall progress against programme outcomes. Progress with State and Region governments (component 1.1) and Development Affairs Organisations (component 1.2) is assessed according to the extent to which the programme has contributed to improvements in the following: Efficiency: revenue mobilization and budget management executed more efficiently and subnational government delivers better key social services in programme target areas Accountability: improved transparency of budget process and PFM and space for public monitoring of policy management and public finances in programme target areas Responsiveness: implementation of inclusive and evidence-based reforms in program target areas. Progress against component 1.3 (Subnational Governance Discussion Paper Series and public awareness raising) will be assessed according to the extent to which subnational governance policy discourses are strengthened and catalyzed through the dissemination and uptake of high quality research on subnational governance processes, structures and dynamics.'' To ''Qualitative assessment of overall progress against programme outcomes and the MSSP results framework. Progress with State and Region governments (component 1.1) and Development Affairs Organisations (component 1.2) is assessed according to the extent to which the programme has contributed to improvements in the following: Efficiency: revenue mobilization and budget management executed more efficiently and subnational government delivers better key social services in programme target areas Accountability: improved transparency of budget process and PFM and space for public monitoring of policy management and public finances in programme target areas Responsiveness: implementation of inclusive and evidence-based reforms in program target areas. Progress against component 1.3 (Subnational Governance Discussion Paper Series and public awareness raising) will be assessed according to the extent to which subnational governance policy discourses are strengthened and catalyzed through the dissemination and uptake of high quality research on subnational governance processes, structures and dynamics. Progress against component 1.4 (CSO Engagement in Subnational Governance) will be assessed according to the capability of CSOs to hold subnational governments to account on budget issues.'' | N | 2018-10-09
9 | Output 8 | Inputs (HR) amended from DFID (FTEs) 0.1 to 0.2 | N | 2018-10-09
10 | Output 7 | Output Indicator 7.3 amended from ''Successful publication of annual EITI report and improvement in the validation process to become an EITI compliance country.'' To Successful publication of annual EITI Reconciliation Reports and EITI Validation results that indicate steady progress towards to achievement 'Successful Progress'. | Y | 2018-12-18 | A slight edit to better match the terminology of the 2016 standard.
11 | Output indicator 7.4 | Make changes on Achieved 1) For Milestone 4 from n/a to No longer used 2) for Target Date - adding No longer used | Y | 2018-12-18
12 | Output indicator 7.5 | Added additional words 'Gemstones' in the Ouput indicator 7.5 | Y | 2018-12-18
13 | Output indicator 7.6 | Newly added output indicator | Y | 2018-12-18
14 | Added Milestone 6 | Accommodate project extension by adding additional year of WB and TAF results | NW | 2019-06-10
15 | Output Indicator 1.2 | Add new WB MDTF IS Window results indicators | NW | 2019-06-10
16 | Output Indicator 2.2 | Add new WB MDTF IS Window results indicators | NW | 2019-06-10
17 | Output Indicator 4.3, 4.2 | Add new WB MDTF IS Window results indicators | NW | 2019-06-10
18 | Output Indicator 5.2 | Add new WB MDTF IS Window results indicators | NW | 2019-06-10
19 | Extended Mileston 7 | Added one column for Milestone 7 | NW | 2019-11-19 | BC extened to end of March 2021
20 | Outcome Indicator 1 | Revised Baseline Changed Baseline from '' Baseline established'' To '' Baseline: Taxes collected by LTO in FY 2015-2016 was 1,105,670 million MMK''. Added information in the Achieved Row for Milestone 3 (Taxes collected by LTO in FY 2016/17 stood at 2,390,434 million MMK) and 4 (Taxes collected by LTO in FY 2017/18 stood at 2,878,057 million MMK) and added more information in the Planned Column for Milestone 7 " Taxes collected by for FY 2020/21 is estimated at 3,250,000 million MMK" | NW | 2019-11-19 | Due to the approved Restructiuring Document in September 2019
21 | Outcome Indicator 4 | Added Source | NW | 2019-11-19 | There is no sources for this indicator.
22 | Outcome Indicator 5 | Added Core budget documents: i) pre-budget statement; (ii) annual Executive budget proposal documentation, (iii) enacted budget, (iv) in-year and year end budget execution reports, (v) audited annual financial statements, (vi) external audit reports, (vii) summary of the Executive budget proposal; (viii) medium term budget proposal, and (xi) summary of enacted budget. | NW | 2019-11-19 | Added comments for Core budget documents to get better understanding on the this indicator
23 | Risk Rating for Outcome | Reduced Risk rating: High from Moderate | NW | 2019-11-19 | After doing the risk exercise in Oct 2019 the PFM programme risk has chenged to Moderate
24 | Outcome Indicator 6 | Move Milestone 5 to Milestone 6, | NW | 2019-11-19 | Due to the Open Budget Index produced every two years, no data will be available in Milestone 6
25 | Output Indicator 1.1 | Added additional words 'Delivery of an integrated tax information system for testing in IRD headquarters, LTO and MTO by March 2021' | NW | 2019-11-19 | Added more info to get more specific
26 | Output 1 | Changed Risk Rating Hight to Major | NW | 2019-11-19 | To get consistence using wording for Risk
27 | Output Indicator 2.2 | Added information for 'Source' | NW | 2019-11-19 | No information added in the Source for this indicator before
28 | Output 3 | Risk Rating from Medium/ High to Major | NW | 2019-11-19 | To get consistence using wording for Risk
29 | Output Indicator 3.1 | Added Source | NW | 2019-11-19 | No information added in the Source for this indicator before
30 | Output indicator 3.2 | Changed Output indicator from "Availability of information on public procurement outcomes" to "Information on procurement opportunities and contract awards (above USD 100 000) are publicly available for 5 Union ministries. (Percentage)". Changed Baseline from " No standardized information provided" to "55". Added notes for Achieved column for Milestone 1, 2, 3, 4, 5) | NW | 2019-11-19 | More details has been added
31 | Output indicator 3.3 | Changed from "Budget holders are empowered to execute budget within clearly defined procedures and regulations that are consistently enforced" to "New Financial Rules and Regulations are enacted and published" | NW | 2019-11-19 | To get more appropriate measurement on this indicator
32 | Output 4 | Risk Rating from Medium to Moderate | NW | 2019-11-19 | To get consistence using wording for Risk
33 | Output 5 | Risk Rating High to Major | NW | 2019-11-19 | To get consistence using wording for Risk
34 | Output Indicator 6.4 | Changed Source from ''Open Budget Survey/ SPECTRUM'' To ''MoPF'' | NW | 2019-11-19 | The previous one is no loger providing the information.
35 | Output Indicator 6.5 | Changed Milestone 6 from (i) 9 to (i) 7 | NW | 2019-11-19 | Updated inforamtion provided by partner. Althought the previous milestone is 9, it is combining of summary data which is 2.
36 | Outpur Indicator 6.6 | Added one more indicator which is v) Citizen Budget CSO feedback Events and its milestone | NW | 2019-11-19 | Added one indicator
37 | Output Indicator 7.3 | Changed from ''EITI Validation results that indicate steady progress towards to achievement Progress'' ''To EITI Validation results that indicate 'meaningful progress' against the EITI stand'' | NW | 2019-11-19 | To get more clear in this indicator
38 | Output Indicator 7.5 | Added information for Milestone 6 | NW | 2019-11-19 | There were no information avaliable for Mileston 6
39 | Output Indicator 7.6 | Added information for Milestone 6 and Added information for Source | NW | 2019-11-19 | There were no information avaliable for Mileston 6 and Source
40 | Output 7 | Risk Rating High to Major | NW | 2019-11-19 | To get consistence using wording for Risk
41 | Output 8 | Added information for Risk rating | NW | 2019-11-19 | No information has been added in the risk rating table before
42 | Output indicator 8.1 | Change from "Qualitative assessment of overall progress against programme outcomes and the MSSP results framework. Progress with State and Region governments (component 1.1) and Development Affairs Organisations (component 1.2) is assessed according to the extent to which the programme has contributed to improvements in the following: Efficiency: revenue mobilization and budget management executed more efficiently and subnational government delivers better key social services in programme target areas Accountability: improved transparency of budget process and PFM and space for public monitoring of policy management and public finances in programme target areas Responsiveness: implementation of inclusive and evidence-based reforms in program target areas. Progress against component 1.3 (Subnational Governance Discussion Paper Series and public awareness raising) will be assessed according to the extent to which subnational governance policy discourses are strengthened and catalyzed through the dissemination and uptake of high quality research on subnational governance processes, structures and dynamics. Progress against component 1.4 (CSO Engagement in Subnational Governance) will be assessed according to the capability of CSOs to hold subnational governments to account on budget issues." To " Qualitative assessment of overall progress against programme outcomes and the AISR results framework. Progress is assessed according to the extent to which the programme has contributed to improvements in the following areas: Subnational public financial management: more inclusive and responsive subnational public finance Effective policy making: more effective policy implementation and reform Social accountability: stronger social accountability through improved civic engagement Institutional Collaboration: support to broader DFID objectives and discovery of new opportunities to strengthen programme goals." | NW | 2019-11-19 | MSSP ending and started the AISR programme
43 | Impact Milestone 6 | Planned Milestone 6 moved to Milestone 7 & Added the achieved milestone 6 | NW | 2020-02-01 | Updated after AR
44 | Achieved Milestone 6 for 2020 | Added achieved outcome & Output milestone 6 | NW | 2020-02-01 | Updated after AR
45 | Output indicator 6.5 & 6.5 | Added planned indicators for milestone 7 | NW | 2020-02-01 | completed information
46 | Outcome indicator 4 | The sub-indicator ‘(ii) training module on revenue and expenditure incidence analysis (including by gender, income group and region)’ removed from the DFID Log Frame | NW | 2020-06-05 | Removed it according to AR recommendation

## Guidance Notes
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.