## Template
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | CSSF Economic Stabilisation Project 2
IMPACT | Impact Indicator 1 |  | Baseline (2018) | Milestone 2 | Target (March 2021)
UK contribution to creating the conditions for a sustainable, inclusive, nationwide ceasefire and peace process, and economic stability which lays the foundations for a durable peaceful stable Yemen in the future; and which contributes to regional security and stability. | Economic stability a. stable exchange rate b. import levels are mainitained | Planned | 700 YER/$ |  | a. less than 50% variance b. meeting the UN benchmark average
Achieved
Source
YETI
| Impact Indicator 2 |  | Baseline (2018) | Milestone 2 | Target (date)
| Reduced humanitarian need | Planned | 80% |  | Humanitarian caseload < 75%
Achieved
Source
HRP
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 2 | Target (March 2021) | Assumptions
Integrity of key Yemen economic institutions maintained; with more economic opportunities for women/youth | Budget prepared for 2021 | Planned | No budget |  | Yes | Conflict does not escalate to the extent the project activities are no longer possible
Achieved
Source
| Outcome Indicator 2 |  | Baseline | Milestone 2 | Target (June 2021)
| Updated national accounts inform interventions | Planned | Current data has been extrapolated since 2014 |  | Updated data used for in World Bank and IMF briefs
Achieved
Source
| Outcome Indicator 3 |  | Baseline | Milestone 2 | Target (May 2021)
| High quality data on the economy available and utilised | Planned |  |  | Dashboard has 40 visits per month 300-400 dowlaods per ACAPS analysis product
Achieved
Source
ACAPS reports
| Outcome Indicator 4 |  | Baseline | Milestone 2 | Target (March 2021)
| Process of engaging economy in peace process is designed and presented to OSE | Planned |  |  | Complete
Achieved
Source
IGC report
| Outcome Indicator 5 |  | Baseline | Milestone 2 | Target (June 2021)
| GoY action plan includes recommendations on: a. electircity, b. private sector | Planned |  |  | a. yes, b. yes
Achieved
Source
GoY Action Plan
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 2 | Target (March 2021) | Assumptions
Capacity building of the Central Bank of Yemen and Ministry of Finance | Assistance provided to CBT to facilitate implementation of Phase 1 action plan recommendations in banking supervision. | Planned |  |  | Complete
Achieved
Source
| Output Indicator 1.2 |  | Baseline | Milestone 2 | Target (March 2021)
| Assistance provided to CBY to facilitate implementation of Phase 1 action plan recommendations in anti-money laundering / counter-terrorism financing | Planned |  |  | Complete
Achieved
Source
| Output Indicator 1.3 |  | Baseline | Milestone 2 | Target (March 2021)
| Assistance provided to CBY to respond to the contractionary macroeconomic impacts associated with the COVID-19 crisis | Planned |  |  | Complete
Achieved
Source
| Output Indicator 1.4 |  | Baseline | Milestone 2 | Target (March 2021)
| Assistance provided to establish a monthly CBY report which presents and analyzes information related to major macro-financial performance parameters; including the CBY and commercial banking sector balance sheets, foreign reserve balances, debt indicators, and other relevant macro-financial data. | Planned |  |  | Complete
Achieved
Source
| Output Indicator 1.5 |  | Baseline | Milestone 2 | Target (March 2021)
| Assistance provided to the Ministry of Finance in budget preparation and execution. | Planned |  |  | Complete
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 1.6 |  | Baseline | Milestone 2 | Target (March 2021)
| Assistance provided on foreign exchange management to the CBY | Planned |  |  | Complete
50% |  | Achieved
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) | DFID SHARE (%)
1000000
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 2 | Target (Sept 2021) | Assumptions
Restoring capacity of the Central Statistical Organisation | New base year of the national accounts of Yemen completed following the main concepts and definitions of the 2008 System of National Accounts | Planned | Works to update the base year from 2000 to 2010 have been initiated but not completed due to the conflict situation in the country. Details included in 2013 transition plan to 2008 SNA. Training in this regard was provided by IMF/METAC in 2013. No more missions have been conducted since then. |  | New base year of the national accounts of Yemen completed following the main concepts and definitions of the 2008 System of National Accounts | Source data for national accounts compilation is made available in a timely manner and of good quality. Conflict situation does not deteriorate. Relations between CSO and source data profiders do not deteriorate. CSO allocate sufficient finance and human resourced to implement the recommendations.
Achieved
Source
WB report
| Output Indicator 2.2 |  | Baseline | Milestone 2 | Target (Sept 2021)
| Supply-use table (SUT) for the new base year to derive GDP estimates from the production, expenditure and income approaches completed | Planned | The latest SUT dates refers to year 2000 (the current base year) |  | SUT for the new base year to derive GDP estimates from the production, expenditure and income approaches completed
Achieved
Source
WB report
| Output Indicator 2.3 |  | Baseline | Milestone 2 | Target (Sept 2021)
15% | National accounts series for GDP completed from the base year onwards | Planned | The lack of appropriate data for extrapolating from 2014 onwards, as major surveys have not been conducted due to the conflict situation, makes it difficult to evaluate the correctness of the overall GDP level for later years. Existing GDP series covers the period 2000-2018 |  | National accounts series for GDP completed from the base year onwards
Achieved
Source
WB report
IMPACT WEIGHTING (%) | Output Indicator 2.4 |  | Baseline | Milestone 2 | Target (Sept 2021)
| Quarterly national accounts series consistent with annual national accounts are completed and disseminated (including seasonal and calendar adjusted series) | Planned | Quarterly national accounts are not available |  | Quarterly national accounts series consistent with annual national accounts are completed and disseminated (including seasonal and calendar adjusted series)
Achieved
Source
WB report
INPUTS (£) | FCDO (£) |  | Govt (£) | Total (£) | DFID SHARE (%)
138728
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 2 | Target (March 2021) | Assumptions
Analysis of key economic trends and risks and economic data made available | Number of quality and timely thematic products delivered | Planned | N/A |  | 2 | thematic and rapid analysis products to be dtermined in consultation with FCDO
|  | Achieved |  |  | 2
Source
| Output Indicator 3.2 |  | Baseline | Milestone 2 | Target (March 2021)
| Number of quality and timely rapid analysis support products delivered | Planned | N/A |  | 2
|  | Achieved |  |  | 2
Source
| Output Indicator 3.3 |  | Baseline | Milestone 2 | Target (March 2021)
| Number of joint analysis meetings to disseminate findings from the research | Planned | N/A |  | 1
|  | Achieved |  |  | 1
Source
| Output Indicator 3.4 |  | Baseline | Milestone 2 | Target (March 2021)
| Number for reports translated to Arabic | Planned | N/A |  | 6
Achieved
Source
| Output Indicator 3.5 |  | Baseline | Milestone 2 | Target (March 2021)
| Web-based economic database and interactive dashboard developed | Planned | N/A |  | Complete
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 3.6 |  | Baseline | Milestone 2 | Target (March 2021)
15% | Daily monitoring and tracking of economic trends and risks based on the analysis framework developed in phase I | Planned | N/A |  | Complete
Achieved
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) | DFID SHARE (%)
208317
INPUTS (HR) | DFID (FTEs)
SRO 0.3, PM 0.4
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 2 | Target (March 2021) | Assumptions
Online convening of Yemeni economic stakeholders | a. Number of topics addressed in series of 1.5 hour online consultations b. Number of participants per topic | Planned | N/A |  | a. 3 b. 12 | Consultations are not hampered by logistical issues
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 4.2 |  | Baseline | Milestone 2 | Target (March 2021)
| Number of consultation findings reports presented to the OSE | Planned | N/A |  | 3
5% |  | Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Total (£) | DFID SHARE (%)
| 15853 |  | 0 | 15853 | 100%
INPUTS (HR) | DFID (FTEs)
SRO 0.3, PM 0.4
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | Milestone 2 | Target (March 2021) | Assumptions
Assistance provided to the Executive Bureau to support the development of key policy reform priorities for the Government of Yemen. | Electricity sector reforms: a. identification of interventions that could improve service and reduce costs b. number of policy papers developed (1) c. number of workshops held with key stakeholders | Planned | N/A |  | a. complete b. 1 c. 2
Achieved
Source
| Output Indicator 5.2 |  | Baseline | Milestone 2 | Target (March 2021)
| Macroeconomic stabilisation: a. identification of interventions to control inflation, stabilise the currency, and coordinate monetary, fiscal and trade policies b. number of policy papers developed (1) c. number of workshops held with key stakeholders | Planned | N/A |  | a. complete b. 1 c. 2
Achieved
Source
| Output Indicator 5.3 |  | Baseline | Milestone 2 | Target (March 2021)
| Private sector support: a. identification of urgent priorities including the feasibility of and best approaches to implement PPP projects, potential tools and approaches to de-risk private sector investments, and identifying priority sectors for investments b. number of policy papers developed (1) c. number of workshops held with key stakeholders | Planned | N/A |  | a. complete b. 1 c. 2
Achieved
Source
| Output Indicator 5.4 |  | Baseline | Milestone 2 | Target (March 2021)
| Support to prioritsation of key policy reforms: a. advice on best approach to prioritise refroms identifed by the government b. number of policy papers developed (1) c. number of workshops held with key stakeholders | Planned | N/A |  | a. complete b. 1 c. 2
Achieved
Source
| Output Indicator 5.5 |  | Baseline | Milestone 2 | Target (March 2021)
| Number of strategic conversations between senior GoY leaders and relevatn IGC experts, including under 1.4c | Planned | N/A |  | 5
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 5.6 |  | Baseline | Milestone 2 | Target (March 2021)
15% | Number of embedded technical specilaists | Planned | N/A |  | 3
Achieved
Source
INPUTS (£) | FCDO (£) |  | Govt (£) | Total (£) | DFID SHARE (%)
|  |  | 0 |  | 100%
INPUTS (HR) | DFID (FTEs)
SRO 0.3, PM 0.4

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2018-01-01
1 | output 2 | Target date changed from June 2021 to Sept 2021 to reflect project extension | MB | 2021-02-01
2 | output 4 | 4.2 ("a. Number of background notes prepared and circulated to meeting participants in Arabic and English ahead of the consultations b. Number of summary notes prepared with key findings and recommendations") deleted and 4.1 changed from " a. Number of topics addressed in series of 1.5 hour online consultations b. Number of participants per topic " to "Number of consultations and accompanying reports on topics agreed with FCDO Yemen" (target: 3). Target for 4.3 (not 4.2) changed from 4 to 3 | MB | 2021-02-01
3 | output 3.3 | Target for number of workshops reduced from 2 to 1 | MB | 2021-07-03
4
5
6
7
8
9
10
11

## Guidance Notes
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.