## Template
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
Health Transitions - To strengthen the health system in Mozambique for improved delivery of reproductive and maternal health services (September 2016-March 2020)
PROJECT TITLE
IMPACT | Impact Indicator 1 |  | Baseline | 2017-09-01 | 2018-03-01 | 2019-03-01 | 2020-09-01
Reduction in maternal and neonatal mortality | (i) Maternal mortality ratio (ii) neonatal mortality ratio in Mozambique | Planned | (i) 489/100,000 (ii) 30/1,000 live births |  | Tbc | Tbc | (i) 350/100,000 (ii) 23/1,000 live births
|  | Achieved |  |  |  | (i) 451/100,000
Source: Baseline: MMEIG – UN Inter-agency expert group on Maternal Mortality Trends, 1990-2015; Target - Health Sector Strategic Plan (PESS 2015-2020) and 2017 CENSUS
| Impact Indicator 2 |  | Baseline | 2017-09-01 | 2018-03-01 | 2019-03-01 | 2020-09-01
| Contraceptive prevalence rate (CPR) (i) for adolescents 15-19 years (ii) general population | Planned | (i)19% (ii) 25% |  | Tbc | Tbc | (i) 25% (ii) 34%
Achieved
Source: Baseline: Mozambique survey on Immunisation, malaria and HIV& AIDS (IMASIDA) (2015) and SARA 2019 (Service Availability and Readness Assessment)
OUTCOME | Outcome Indicator 1 |  | Baseline | 2017-09-01 | 2018-03-01 | 2019-03-01 | 2020-09-01 | Assumptions
People equitably access and use quality health services | Additional users of modern methods of family planning (i) with DFID contribution (ii) through the State budget | Planned | (i) 0 (ii) 15,000 |  | Tbc | Tbc | (i) 100,000 (ii) 173,155 | The programme will improve the coverage of reproductive and maternal health services in the country Coverage of WASH in health centres can be scaled up within the project timeframe
Achieved
Source: Baseline for Mozambique 2016 Health Annual Review report and 2018 Health Sector Annual Report
| Outcome Indicator 2 |  | Baseline | 2017-09-01 | 2018-03-01 | 2019-03-01 | 2020-09-01
| Health facilities accredited as being able to deliver comprehensive emergency obstetric and newborn care (CEmoNC) | Planned | 33% |  | Tbc | Tbc | 70%
Achieved
Source: Baseline: 2012 National EmoNC study and 2018 Health Sector Annual Report
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
COMPONENT 1: UN JOINT PROGRAMME
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone Sept 2017 | 2018-03-01 | 2019-03-01 | 2020-09-01 | Assumptions
Enhanced availability and quality of trained midwifery workforce and improved facility readiness at national level by 2020 | Number of maternal and child health (MCH) nurses available in health facilities Number of health facilities equipped with (i) ambulances and (ii) emergency obstetric and neonatal care (EmONC) Kits, includind safe abortion care and life saving commodities | Planned | 5,159 MCH nurses | Agreement signed with UN to start implementation that includes (i) Governance Structure (ii) Results Framework (iii) Official endorsement of the project by the Ministry of Health | 200 MCH nurses enrolled into pre-service training | Tbc | 6400 MCH nurses in total and additional 1,329 MCH nurses (DFID will be responsible for 320 additoinal nurses) | - Operational costs and salaries will continue to be paid by Government - Training institutions will continue to have sufficient funds for operating costs -MoH will need to increase their absorption capacity
|  | Achieved |  | (i)Progress but not finalised. (ii)Included in proposal submitted to DFID in July 2017 (iii) Achieved in August 2017. | 246 nurses enrolled by October 2018 | 298 nurses enrolled by March 2019 (168 in initial MCH course and 130 enrolled in MCH promotional course) | Tbc
| Output Indicator 1.2 |  | Baseline | Milestone Sept 2017 | 2018-03-01 | 2019-03-01 | 2020-09-01 | Assumptions
| Number of health facilities equipped with (i) ambulances and (ii) emergency obstetric and neonatal care (EmONC) Kits, includind safe abortion care and life saving commodities | Planned | Tbc | Minimum condition for interventions to be successfully implemented agreed with Government and UN | (i) 26 ambulances (II) 3 out of 7 EmONC kits procured | (i) 51 ambulances | ((i) 51 (ii) 37 | Minimum standards of health will translate into improved quality services MoH will cover maintenance and distribution costs
|  | Achieved |  | Minimum conditions agreed with the UN and the MoH. They will be discussed on quarterly basis as risks to the delivery of the programme. | (i) 32 ambulances (ii) 3/7 kits arrived in May 2018- now being distributed | (i) 32 ambulances and (ii) 41 HR EmONC kits |  | Distribution will not take longer
|  | Source: 2017 Annual Report , 2018 Mid-year report (submitted November 2018) and 2018 Annual Report (submitted April 2019) | [5 empty] | RISK RATING
Moderate
IMPACT WEIGHTING (40%) | DFID (FTEs)
INPUTS (£) |  |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone Sept 2017 | 2018-03-01 | 2019-03-01 | 2020-03-01 | Assumptions
Platforms for community engagement focused on lowest performing districts strengthened by 2020 including through improved National health management information sistem (HMIS) | Proportion of CHW (i) working in target districts (over total needed) (ii) receiving at least 1 supervision visit per quarter | Planned | (i) 48% (ii)40% | Minimum conditions for | (i) Train an additonal 700 CHW at national level (ii) 2 supervision visits to CHW carried out this year | (i) 850 by March and 900 by December 2019 | (i) 75% (ii) 70% | DFID will be training an additional 1650 CHW in five provinces; Current numbers of CHW will be sustained
|  | Achieved |  |  | (i) 650 CHW trained (ii) Only 1 supervision visit carried out in the last year | (i) 850 new APEs trained by March 2019 (ii) guidelines for supervision under revision
|  | Source: 2017 Annual Report, 2018 Mid-year report (submitted November 2018) and 2018 Annual Report (submitted April 2019) | [5 empty] | RISK RATING
Moderate
|  |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
DFID (FTEs)
| Output Indicator 2.2 |  | Baseline | 2017-09-01 | 2018-03-01 | 2019-03-01 | 2020-09-01 | Assumptions
| Proportion of CHW equipped and using UPSCALE mobile platform in (i) Cabo Delgado province (ii) Nampula province | Planned | 40% (ii) 0% |  | (i) 70% coverage in Cabo Delgado province (ii) 10% in Zambezia province | Tbc | (i) 80%(ii) 60% | The mobile platform will be seen as a job-aid by health authorities and CHW in the different provinces
|  | Achieved |  |  | (i) 50% in Cabo Delgaodo (ii) Not started yet and switched to Zambezia province. | (i) 70% coverage in Cabo Dealgado and (ii) 70% in Inhambane (switched to Inhambane province)
IMPACT WEIGHTING (25%) |  | Source: 2017 Annual Report, 2018 Mid-year report (submitted November 2018) and 2018 Annual Report (submitted April 2019) | [5 empty] | RISK RATING
Moderate
INPUTS for outputs 1-4 (£) 23,000,000 |  |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
DEMAND SIDE COMPONENT
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | 2017-09-01 | 2018-03-01 | 2019-03-01 | 2020-09-01 | Assumptions
Generating demand for family planning among adolescents | Additional family planning users in the target areas as a result of DFID interventions | Planned | No additional FP users | OJEU tender for service provider completed and supplier selected OR Plan B for family planning update approved | OJEU tender for service provider and supplier selected by January 2018 | 500 users of FP <20 years | Actions taken by key influencers to improve access to FP for adolescents and young women | PCD will expedite tender process to make up for delay caused by the supplier review
|  | Achieved |  | ToR finalised but scope changed in November 2017 | Service provider awarded contract in August 2018 | 732 users of FP< 20 years (529 in Maputo and 203 in Nampula)
IMPACT WEIGHTING (20%) |  | Source: 2017 Annual Report and 2018 Mid-year report (submitted November 2018), 2019 Annual Report and 2020 Mid-year report. | [5 empty] | RISK RATING
Moderate
| DFID (£) 5,500,000 |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS for 3.1 & 3.2 (£) 8,000,000 | Output Indicator 3.2 |  | Baseline | 2017-09-01 | 2018-03-01 | 2019-03-01 | 2020-03-01 | Assumptions
| Improved knowledge, capacities and agency for SRHR | Planned |  |  |  |  | 5,799 girls and young women trained as mentors by December 2019 in 20 target districts in Nampula and Zambezia
|  | Achieved |  |  |  |  | 5, 609 young women trained as mentors
Source: 2019 Rapariga Biz Report, 2020 Evaluation Report
DFID (£) 3,000,000
EMERGENCY PREPAREDNESS COMPONENT (WHO Emergency Prepredness project) and COVID-19 support through the UN Joint Programme
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | 2017-09-01 | 2018-03-01 | 2019-03-01 | 2020-03-01 | Assumptions
Strengthen the sector's capacity to respond to emergencies | MoH's ability to prevent and respond to outbreaks is strengthened (through WHO's Emergency Preparedness project). | Planned | Outbreaks distrupt service delivery and catch MoH by surprise. |  | MoH responds to the cholera outbreak in Northern Mozambique | MoH responds to the cholera outbreak in 4 affected districts by Cyclone IDAI (Beira, Buzi, Dondo and Nhamatanda) through EWAR system | MoH preparedness and response to any disease outbreak in target areas
IMPACT WEIGHTING for Output 4 (10%)
INPUTS for 4.1 (£) 2,000,000
|  | Achieved |  |  | Achieved with DFID support. | 59 HFs received EWARS handset to detect and report Cholera and other disease outbreaks
| Output Indicator 4.2 |  | Baseline | 2017-09-01 | 2018-03-01 | 2019-03-01 | 2020-09-01 | Assumptions
INPUT for 4.2 (£) 1,000,000 | Institutional support to the MoH to advance the pandemic response to reduce the risk of mothers, newborn and children as well as health workers through the UN Joint Programme. | Planned |  |  |  |  | Instituional support to the health COVID-19 response plan
Achieved
INPUTS Total (£) |  | Source: 2017 Annual Report, 2018, 2019 and 2020 Mid-year report (submitted by October of each year) | [5 empty] | RISK RATING
Major
VILLAGE REACH COMPONENT
OUTPUT 5 | Output Indicator 5 |  | Baseline | 2017-09-01 | 2018-03-01 | 2019-03-01 | 2020-06-01
Strengthen our central support towards innovation through drones for health by September 2020 | Number of test flights conducted for TB samples transportaion | Planned |  |  | VR conduct community sensitization and engage stakeholders at all levels | MoH starts testing the use of drones for TB sample transporation | In-country UAS (drone)study flights conducted
IMPACT WIGHTINING (5%) |  | Achieved |  |  | Achieved with DFID support. | Not achieved
RISK RATING
COMPONENT 2 - DEMAND GENERATION FOR FAMILY PLANNING
OUTPUT 6 | Output Indicator 6.1 |  | Baseline | Milestone Sept 2017 | 2018-03-01 | 2019-03-01 | 2020-03-01 | Assumptions
Generating demand for family planning among adolescents (in process of procurement of service provider - outputs and indicators to be agreed in inception period ) | Additional family planning users in target areas as a result of DFID interventions | Planned | No additional family planning users | OJEU tender for service provider completed and supplier selected OR Plan B for family planning uptake approved. | 1100 | 10000 | 16,800 cumulatively | The OJEU tender will be approved in September 2017; Plan B will be implemented for two years alongside the winning bid.
Achieved
|  | Source : Project report | [5 empty] | RISK RATING
Major
| DFID (£) 5,500,000 |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
DFID (FTEs)
| Output Indicator 6.2 |  | Baseline | 2017-09-01 | 2018-03-01 | 2019-03-01 | 2020-03-01 | Assumptions
| Young women and men with improved knowledge and more positive attitudes towards family planning | Planned |  | ToR for the youth media platform finalised with a decision on the scope and focus of the work | Tbc | Tbc |  | The youth media platform will compliment the project in output 6.1
Achieved
IMPACT WEIGHTING (25%) |  | Source: ToR submitted to PCD | [5 empty] | RISK RATING
Moderate
INPUTS (£) 7,500,000 | DFID (£) 2,000,000 |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) Social Development DESA (20%), Health Advisor (10%) | DFID (FTEs)
COMPONENT 3- COORDINATION AND COHERENCE OF UK INVESTMENTS
OUTPUT 7 | Output Indicator 7.1 |  | Baseline | 2017-09-01 | 2018-03-01 | 2019-03-01 | 2020-03-01 | Assumptions
To improve the coordination and coherence of all UK investments in the health sector in Mozambique | To get leverage with the MoH by funding discreet interventions in health | Planned | Tbc | Progress on the human resources retention and attraction strategy consultancy | Global Funds PFM Specialist follows up on risk audit recommendations | Tbc |  | DFID support to these pieces of work will get us a lot of support; DFID will get additional capacity to coordinate UK investments in Mozambique
Achieved
IMPACT WEIGHTING (5%) |  | Source: Progress - consultancy reports. | [5 empty] | RISK RATING
Major
INPUTS (£) | DFID (£) 460,000 |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)

## Explanatory notes
Explanatory Note for Logical Framework
| Milestones | Milestones for outputs relate to 2018 and 2019 as indicated
Result Level | Indicator | Usefulness of indicator | Indicator methodology | Milestone Description | Importance of Milestone | Data Source for Baseline | Data Source for Milestones | Data Source for Targets | Reporting Year | Frequencey of Reporting | DFID pro-rata share used? | Calculation of DFID pro-rata share | Indicator comments
Impact | Reduction in maternal and neonatal mortality
1 | (i) Maternal mortality ratio (per 100,000) live births (ii) Neontatal mortality ratio (per 1,000) live births | Important to track maternal at high level and as proxy indicators of the strength of health system because a functional system is needed for these indicators to improve(ii) Neonatal mortality is an indicator of the quality of health services before and after birth. | (i) Numerator-# of maternal deaths in a population while pregnant or within 42 days of termination of pregnancy. (ii) Death within the first 28 days of life. |  |  | MMEIG – UN Inter-agency expert group on Maternal Mortality Trends, 1990-2015 |  | Health National Strategic Plan |  | Every 3 years from National Survey or UN estimates |  |  | Estimate is calculated assuming that it is getting harder to reduce maternal deaths.
2 | Contraceptive prevalence rate (CPR) (i) for adolescents 15-19 years (ii) general population | CPR is important to prevent deaths in adolescents which contributes to 20% of maternal deaths. Also prevents deaths as a result of abortions. | CPR is the % of women currently using, at least one modern method of contraception. (i)Adolescent rate has been increasing and is the DFID focus. (ii) 15-49 years is usually reported for women. |  |  | Mozambique survey on Immunisation, malaria and HIV& AIDS (IMASIDA) (2015) |  |  |  | Every 3 years from National Survey
Outcome | People equitably access and use quality health services
1 | Health facilities accredited as being able to deliver comprehensive emergency obstetric and newborn care (CEmONC) | Women with direct obstetric complications need comprehensive obstetric care facilities. Referrals where these are not available lead to delays in accessing these services contributing to the death of mothers and newborns before, during or soon after birth. | Health facilities have to be accredited as having the adequate environment, skilled staff, equipment and infrastructure to be deliver CEmONC services. |  |  | 2012 National EmoNC study | [6 empty] | DFID will be paying for equipment of health facilities and training of nurses as well as the accreditation process for selected primary health care facilities.
2 | Additional users of modern methods of family planning (ii) with DFID contribution (ii) through the State budget | Calculates the additional number of people who are using modern methods of contraceptives as a result of (i) all DFID interventions (ii) the State budget | The difference in total number of contraceptive users in a population between two points in time:- the baseline and a point in time after it. |  |  | 2016 Annual Health Review report |  | Perfomance Assessment Framwork ( (Government Target;DFID target calculations in 2017) | UK financial | Annual - to verify with the National Survey or a Demographic Health Survey (DHS) |  |  | The UN Joint Programme and Demand Generation components will contribute to this indicator
3 | Targeted children receiving Vitamin A | Tracks child health and child nutriton. Will also capture the transition from delivering Vitamin A through national health compaigns which are expensive and disruptive to the health system to delivery through routine health systems including through the community health workers (CHW) | Vitamin A is needed for good eyesight, supporting the immune system and producing red blood cells. It prevents illness and blindness in children under 5 years of age. |  |  | Performance Assessment Framework (PAF) | Government target | PAF (DFID assumes will increase by average of 1% from 2007-2010.) | UK financial | Annual - to verify with DHS |  |  | DFID will be supporting the expansion of the community health worker programme through which Vitamin A is being delivered to children under 5 years.
COMPONENT 1 - UN JOINT PROGRAMME
Output 1 | Enhanced availability and quality of trained midwifery workforce at national level by 2020
1.1 | Number of maternal and child health (MCH) nurses available in health facilities | The country has a chronic shortage of medical professionals that are essential for quality delivery of maternal, newborn and child health services. | The ratio of doctor, nurses and miwifes per 100,000 people was 71/100,000 inhabitants which is far below the WHO threshold of 230/100,000 needed for essential maternal, newborn and child health services. | Agreement signed with UN to start implementation that includes (i) Governance Structure (ii) Results Framework (iii) Official endorsement of the project by the Ministry of Health | Ensures that agreement is signed, there is ownership from the MoH for the project and that a Governance arrangement is agreed between all stakeholders. | 2015 MoH HR Statistics report |  | UN Joint Programme Proposal(June 2017) | UK financial | Annual |  |  | DFID will be paying or an additonal 200 nurses to be trained and 120 nurses to be upgraded.
2 | Improved facility readiness to provide essential and emergency obstetric and neonatal care (EMoNC), including safe abortion care and life saving commodities by 2020
2.1 | Number of health facilities equipped with (i) ambulances and (ii) emergency obstetric and neonatal care (EmONC) Kits | This will address the main causes of maternal deaths - delays getting emergency care because of a lack of transportation and having more health centres equipped to deliver basic emergency care. | Basic emergency obstetric and newborn care is critical to reducing maternal and neonatal death. This care, which can be provided with skilled staff includes the capabilities for: administering antibiotics, uterotonic drugs (oxytocin) and anticonvulsants (magnesium sulphate); | Minimum condition for interventions to be successfully implemented agreed with Government and UN | Economic crisis means that Government are not always able to ensure value for money of DFID support. An agreement between DFID, UN and Government will ensure that minimum conditions are in place to make the most of the these interventions. | Supply reports/ programme reports |  | UN Joint Programme Proposal(June 2017) |  | Annual |  |  | DFID will be providing 51 ambulances and equipping 41 health centres to provide EmONC services
2.3 | Proportion of target health facilities with no stockout of life-saving commodities | Maintains the pressure on the Government and partners to ensure that life-saving commodities are available in health centres | Assesses the stock levels of the MoH's essential medicines list annually in a representational sample of health facilities throughout the country. |  |  | UN Commodities Survey |  | UN Joint Programme Proposal(June 2017) | Calendar | Annual
Output 3 | Improve health infrastructure, focused on closing water and sanitation (WASH) gaps in primary health care (PHC) facilities with maternities by 2020 |  |  | Target health facilities for WASH construction /rehabilitation identified | DFID would prefer if the majority of health facilities are in Nampula and Zambezia provinces where our WASH programme has a strong presence.
3.1 | Number of primary health facilities provided with adequate water and sanitation services in priority districts | WASH in health facilities prevents infections and contributes to a hygienic environment. | Health facilities which will have WASH services constructed where these do not exist (eg. borehole) or rebilitation where these services have deteriorated over time. |  |  | Programme Implementation reports |  |  | Calendar | Annual |  |  | 100 Health facilities will be targeted by the project. This will require collaboration between the MoH and the Ministry of Public Works at Provincial level.
Output 4 | Availability of family planning services and information in communities and health facilities (UNFPA) |  |  | Compliance tools in place including (i) Risk matrix (ii) Delivery risk mapping and (iii) Value for money indicators | Ensure that the project meets DFID compliance rules and that these are regularly discussed with the UN
4.1 | Proportion of CHW (i) working in target districts (over total needed) (ii) receiving at least 1 supervision visit per quarter | Coverage of CHW needs to increase from for them to effectively deliver services in rural and remote areas. Regular supervision improves the quality of services delivered by CHW. | Total coverage of CHW varies according to population but is an average of 48% to 85%. A process is underway to train 1,362 and DFID will be fund for an additional 1,200 to be trained. |  |  | CHW programme reports |  | UN Joint Programme Proposal to DFID (June 2017) | UK Financial
4.2 | Proportion of CHW equipped and using UPSCALE mobile platform in (i) Cabo Delgado province (ii) Nampula province | UPSCALE mobile platform is a job-aid for CHW and improves their data collection. This is being piloted in Cabo Delgado province with plans to roll it out in Nampula province from 2018. | The CHW mobile Health system is integrated into the District Health Information Software. This allows Government officials to access real-time data from CHW. The mobile system also guides CHW through diagnostic process sand provides treatment recommendations. |  |  | CHW programme reports |  | UN Joint Programme Proposal(June 2017) | UK Financial | Annual
Output 5 | Institutional reform agenda advanced for the sector for a better policy enabling environment by 2020 | [12 empty] | The CHW mobile Health system is integrated into the District Health Information Software. This allows Government officials to access real-time data from CHW. The mobile system also guides CHW through diagnostic process sand provides treatment recommendations.
5.1 | National health policy updated to respond to a number of emerging priorities | A framework is needed to define the role of the MoH and guide their response to emerging trends such as emergency preparedness, decision-making at decentralised level and health financing from sources other than the Government. The last health policy from 1995 is now outdated. | To consult and develop a nationa health policy that focuses on the MoH's stewardship role rather than their implementation role and provides guidance on emerging trends such as emergency preparedness, decentralisation and health financing. |  |  | Reform Unit Report |  | UN Joint Programme Proposal(June 2017) |  | Annual |  |  | Political will is needed for this process to be effective and conclude within the established timeline. The Reform Unit at the MoH will be leading the process. | To build the APE mHealth system, APE level indicators will be integrated into Mozambique’s electronic District Health Information Software 2 (DHIS2) platform, known as Sistema de Informação de Saúde de Moçambique para Monitorização e Avaliação (SIS-MA). The APE-level indicators in SIS-MA will be populated in real-time from data collected by APEs and submitted directly to SIS-MA. Government health officials will be able to view this data on the APE dashboard in a user-friendly format. This system will help to assist data driven decision-making around APE programme investments, surveillance and responses to infectious diseases including malaria, and early detection of disease outbreaks. APEs will submit data directly to SIS-MA using the ‘APE app’, an interactive mobile phone application that guides community health workers through the diagnostic process, provides treatment recommendations, issues targeted behaviour change messages for patients, and collates inputted data.
COMPONENT 2- DEMAND GENERATION FOR FAMILY PLANNING
Output 6 | Generating demand for family planning among adolescents (in process of procurement of service provider - outputs and indicators to be agreed in inception period )
6.1 | Additional family planning users in target areas as a result of DFID interventions | Calculates the additional number of people who are using modern methods of contraceptives as a result of the project |  | OJEU tender for service provider completed and supplier selected OR Plan B for family planning uptake approved. | Approval of tender by Ministers is delayed until September due to recess. DFID exploring Plan B of having a delegated cooperation agreement with the Netherlands to deliver family planning targets by 2020. |  |  | ToR for OJEU process
6.2 | Young women and men with improved knowledge and more positive attitudes towards family planning | Improve knowledge of family planning methods for young people to select what is best for them |  | ToR for the youth media platform finalised with a decision on the scope and focus of the work | DFD Mozambique to decide scope of the work and what it will focus on. It should not duplicate 6.1 but compliment it. |  |  | ToR submitted to PCD |  |  |  |  | Two different interventions on family planning can add value
Output 7 | To improve the coordination and coherence of all UK investments in the health sector in Mozambique
7.1 | To get leverage with the MoH by funding discreet interventions in health | Funding for discreet interventions (consultancies) or for a programme funded post to support coordination of all UK support in health in Mozambique. | Changes as a result of consultancies or intervention funded with DFID support. | Progress on the human resources retention and attraction strategy consultancy |  |  | Consultancy reports |  |  | Every six months at least.

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.