Annual Review

Title: / Partnership for Learning for All in Nigerian Education (PLANE)
Programme Value £ (full life): £ 170 million		Review Date: 28 February 2020
Programme Code: / 300 416	Start Date: / 26/03/2019	End Date: / 31/08/2027

Summary of Programme Performance
Year	2019
Programme Score	A
Risk Rating	Major

DevTracker Link to Business Case:	PLANE BC
DevTracker Link to Log frame:	PLANE Logframe - Year 1

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

Nigeria faces a learning crisis. Literacy rates are low, and lower still for marginalised children. It has the largest number of primary-aged children out of school in the world. Public investment in education is insufficient, and millions of children are failing to learn the basics. Improving participation of marginalised children in schooling, and ensuring children learn when in school, is critical to averting a demographic crisis and meeting SDG commitments.

PLANE is DFID Nigeria’s flagship multi-window basic education programme, seeking to invest £170 million over eight years (approximately £21.25m per year) to improve foundational skills (reading, writing and mathematics) for children. The programme will use these funds to enable a more inclusive and effective basic education system through three windows and a DFID managed component:

- Window One (£100m): Getting the Foundations right - a systems approach. More focused teaching and learning, improved governance (for state and non-state education delivery) and increased use of data and evidence – a large technical assistance programme to support schools and improve systems, delivered through a contracted consortium.
- Window Two (£38m): Education in Emergencies. Support to help marginalised children affected by conflict learn foundational skills and support for recovery of systems, including through a bilateral agreement with USAID and non-governmental organisations.
- Window Three (£20m): Community support to learning. Improving inclusion and learning for marginalised children – an accountable grant to a partnership of non-governmental organisations.
- DFID Managed component (£12m) – multilateral agreement with World Bank, programme funded adviser, third party monitoring, independent research, evaluation, reviews, audits.

PLANE balances evidence-based classroom and child-level interventions with higher risk/higher return system-level interventions. The programme is aligned to wider donor support and seeks to influence additional reform through others, which is vital given the large need in Nigeria.

The programme aims to address current educational underachievement for the poorest and most vulnerable in Nigeria acknowledging that these education indicators reflect both cause and effect within the poverty cycle. PLANE interventions will support improved state provision of basic education in DFID’s partner states in the North West of Nigeria – Kano, Kaduna, Jigawa (KKJ); and address Education in Emergencies in the two North East states of Borno and Yobe (BY). In addition, PLANE will support standards and regulation of non-state schools in the South of Nigeria. We will work strategically at federal level to influence policy making.

PLANE will directly support an estimated 1.5 million children in KKJ, allow 600,000 children in BY to access schooling, and potentially reach up to 8 million children nationally. Exact numbers will be agreed during the inception phase. The PLANE portfolio also has two cross-cutting elements delivering on monitoring, evaluation and learning, and ability to respond flexibly to arising crises.

These various elements will work together to deliver the programme’s outcomes and ultimate impact. The outputs are delivered through multiple components that combine in a comprehensive approach; components include:

- OJEU contract (to be announced) working at federal level and in targeted states
- Accountable grant, MOU and a Delegated Corporation Agreement (DCA) with International Rescue Committee (IRC), United Nations Children’s Fund (UNICEF) and United States Agency for International Development (USAID) – to support essential educational services for crisis affected populations - working in Borno and Yobe
- Trust Fund with World Bank – to support the Research on education financing and school supply
- DFID Nigeria Human Development Evaluation, Learning and Verification Service (DELVe) Contract for monitoring, evaluation and learning (to be procured - also supporting LAFIYA and SUNMAP2 programmes).

The programme is still in its early stages so agreements with some implementing partners are yet to be completed. Implementers already identified include the World Bank, USAID, UNICEF and IRC, all of which have historical presence and active engagement in the education sector in Nigeria.

Summary supporting narrative for the overall score in this review (1/2 page)

The current review is based on the first-year transitional log-frame that focusses on initial, approved process indicators. The first year of this programme incorporates the period from Business Case approval to date. The review covers the initial preparation, agreement, consultation and procurement processes required to get the various components up and running. The logframe for this period includes these initial processes and limited outputs and timeframes. The log-frame will need to be updated for the next annual review to take account of the next inception and delivery phase of the portfolio.

The programme has been managed to date as a portfolio programme with an overall SRO and three lead advisers (including the SRO) for individual components, together with a programme management team. Coordination of the design, approval and mobilisation processes had been achieved through weekly team meetings by the education team. The team members have liaised extensively with Procurement and Commercial Department (PCD) to take forward the procurement processes for Window 1 and DELVe.

Coordination meetings and close dialogue across components will continue as the processes move into the next phases to ensure the required alignment of components and development of the programmatic log-frame and other documentation to be finalised in the next phase.

The management and oversight of components and governance arrangements for the programme are outlined in the Business Case. These will be confirmed during the inception period of the programme (planned for April-September 2020).

Recommendations for the year ahead (1/2 page)

1. The PLANE portfolio log-frame will need to be re-written in the next six months to move from a transitional log-frame to a programmatic log-frame, with agreed indicators and milestones for all outputs. Whilst separate indicators and milestones will be agreed with respective organisations for each separate component of the portfolio, this should come together in an overarching log-frame in line with the six outputs in the business case. ACTION – DFID by September 2020
2. The process to evaluate a large programme/portfolio with complex service delivery and TA elements provided procurement lessons which will be reviewed with PCD once the contract is signed and fed into future processes.
3. DFID should push for agreement with the World Bank on the type of Trust Fund to be used to fund the research on education financing and school supply as soon as possible – ACTION - DFID by JUNE 2020.
4. DFID Nigeria may need to conduct a review of Window 3 under the PLANE portfolio to ensure that the proposed activities under this project will align with new UK Manifesto and Ministerial commitments on Education. ACTION - DFID by end July 2020.
5. DFID Nigeria will also need to recruit a Lead Adviser for Window 3 of the programme to oversee the selection of partner(s) and the implementation of the project. ACTION - DFID by end July2020.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Evidence based teaching and learning approaches and materials in use, in better managed schools & colleges
Output number per LF		1	Output Score	B
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Progress towards contracting main supplier	OJEU tendering process established, bids evaluated, and preferred bidder identified	The tender process has been completed with bids evaluated through a two- stage process. A preferred bidder is in the process of being identified by the end of March 2020.
Number of primary teachers (P4-6) in formal schools of the targeted Local Government Associations (LGAs) who have received training on Teaching at the Right Level, in Output 1 Bridging Intervention (the Kano Mathematics and Literacy Accelerator)	Male: 580 and Female: 90	Male: 564 and Female: 110
Number of children reached through the Output 1 Bridging Intervention (KaLMA)	Male: 26,000 and Female: 25,000	Male: 14,392 and Female: 14,122

Provide supporting narrative for the score

The overall success of the programme is predicated on a high-quality contractor being appointed to undertake the work on the OJEU contract. Ensuring an appropriate and robust process to identify the preferred contractor has been the critical activity in the period under review.

The process to assess the preferred bidder is underway and due to be completed by end April 2020. The process of assessment has followed a two-stage process with bids assessed on a range of factors including: (i) the structure and quality of the consortium and the extent to which technical merits of each consortium partner were utilised to deliver on the outputs and outcomes; (ii) the structure and quality of the core team and the leads at various levels of the programme, and the approach to coordination and management within the consortium; and, (iii) collaboration, and payment by results risk share set against delivery milestones.

Following this process, a suitable contractor will be identified to deliver on the outputs. It is anticipated that confirmation of the contract will be by end April 2020. Once this stage is completed and signed off, it will pave the way for discussions on the inception period of programme implementation.

To prepare for the work by the contractor on Window 1, an Accelerated Learning bridging intervention is being carried out in the 2019/2020 school year. British Council have been awarded an Accountable Grant to test and adapt the Teaching at the Right Level (TaRL) approach in Kano State to improve foundational literacy and numeracy skills. After a three-month inception period (September – December 2019) including training of master trainers, mentors, and teachers, the programme was rolled out in schools in January 2020. Teaching is taking place in all of the government primary schools in two LGAs in Kano: Wudil, where the pilot includes testing the use of student teachers in TaRL delivery, and Dawakin Tofa, where English is included in the approach alongside Hausa and Mathematics.

In total, the project aimed to train 670 teachers (580 male and 90 female), but has overachieved, training 674 teachers (564 male, 110 female). The proportion of female teachers in the target was low due to a shortage of female teachers in the targeted schools, so it is positive that the proportion of female teachers trained was (very slightly) higher than the aim. These figures do not include the 96 student teachers trained (92 male and 4 female) who will be able to carry the TaRL methodology forward into their professional practice, or the 50 additional mentors (head teachers, deputy head teachers, local government officials and others) who will act as champions for the approach.

In comparison, the number of students reached is currently lower than expected. The project aimed to reach 51,000 children (25,000 females and 26,000 males) and has in fact only reached 28,505 (14,392 males and 14,122 females). The reason for this shortfall is that the original target was based on the number of schools and students in the Kano Annual School Census (ASC) report. However, on beginning training and implementation, it became clear that there were inaccuracies in the data (it included schools without upper primary as well as adult literacy centres). In addition, the baseline data was collected at the beginning of the school term when some children had not yet resumed school. Therefore, it is expected that the number of pupils reached through the TaRL intervention will be higher than that reported above, but lower than the log frame targets from the ASC data. British Council have been asked to take action to ensure that the total number of students reached is as close as possible to the log-frame number by the end of March.

Lessons identified this year, and recommendations for the year ahead linked to this output

The process to evaluate a large programme with complex service delivery and TA elements provided procurement lessons which will be reviewed with PCD once the contract is signed and fed into future processes.

Baselines for future log-frame indicators should be verified carefully and work needs to be done to encourage better student attendance at school – ACTION DFID TO INCLUDE IN CONTRACT BY SEPTEMBER 2020

Output Title	Improved planning, personnel management, public financial management practices, to deliver foundational skills
Output number per LF		2	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
2.1 Research on education financing and school supply with World Bank	Concept Note Agreed	Concept note has been agreed, and a signed agreement will enable research to start in mid-2020.
2.2 Progress towards contracting main supplier	OJEU tendering process established, bids evaluated, and preferred bidder identified	The tender process has been completed with bids evaluated through a two- stage process. A preferred bidder is in the process of being identified by the end of March 2020.

Briefly describe the output and provide supporting narrative for the score

This output covers the processes to initiate support to the World Bank for Research on education financing and school supply with World Bank. This is an important aspect of the programme addressing a key challenge in Nigeria and will complement work within the OJEU contact. There has been good progress on this output and the technical concept note for the research has been agreed between DFID Nigeria and the World Bank. There has been a delay in starting the research due to an internal World Bank process to streamline the number of projects in Nigeria. Discussions are on-going with the World Bank about the form of funding that will be used for this research, which could be a separate Externally Funded Output (EFO) or part of a broader multi-donor trust fund. The final agreement will be negotiated and agreed with the World Bank before end June 2020 and the finances transferred soon afterwards. The concept note should be re-reviewed before this time to include any changes to need or existing information, especially considering the upcoming (Global Partnership for Education (GPE) funded Education Sector Analysis (ESA). These changes have not yet been agreed with the World Bank, but possible changes will include a more focussed financial analysis given the work done through the ESA.

As stated in the narrative for Output 1, the OJEU contract process is on track to select a preferred supplier before end March 2020. The process to sign the agreement is expected to be completed by 30th April 2020.

Lessons identified this year, and recommendations for the year ahead linked to this output

DFID should push for agreement on the type of Trust Fund to be used to fund this research as soon as possible – ACTION - DFID by JUNE 2020.

Output Title	Improved management and performance of non-state sector in delivering foundational skills
Output number per LF		3	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
3.1 Progress towards contracting main supplier.	OJEU tendering process established, bids evaluated, and preferred bidder identified.	The tender process has been completed with bids evaluated through a two- stage process. A preferred bidder is in the process of being identified by end March 2020.

Provide supporting narrative for the score

This objective covers the identification of the preferred bidder for contract of the programme. This element of the programme is buying the expertise to deliver improved management & performance of non-state sector in delivering foundational skills. As stated in output 1, the OJEU contract process is on track to select a preferred supplier before the end of March 2020. The process to sign the agreement is expected to be completed by 30th April 2020.

n/a

Output Title	Effective generation, communication and use of evidence informs citizen engagement and service delivery
Output number per LF		4	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
4.1 Progress towards contracting supplier for Monitoring, Evaluation and Learning - HD DeLVE.	GEFA tendering process established, bids evaluated, and preferred bidder identified.	DELVe contract supplier has been identified and selected and we are in final stages of negotiating contract terms. The contract should be signed before end March 2020.

Provide supporting narrative for the score

This objective refers to the development of baselines at impact and outcome levels. At this time, the Monitoring, Evaluation and Learning (MEL) supplier has not been identified due to delays in the DELVe contract that covers this element. It is anticipated that the DELVe contract will be up and running so that the evaluation design will be ready during the inception period.

Lessons identified this year, and recommendations for the year ahead linked to this output

Further details on this procurement are covered in section F.

Output Title	Effective approaches to teaching and learning and more resilient systems for children affected by conflict
Output number per LF		5	Output Score	A
Impact weighting (%):		15%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
5.1 Education Authorities Increased Capacity to Plan, Manage and Oversee Education Services in Borno and Yobe State, through USAID Delegated Corporation Agreement (DCA).	Proposal agreed, funds disbursed, and first quarterly meeting held to review progress and results	Current DFID support on Education in Emergencies is delivered through a DCA agreement with USAID. The DCA was finalised at end November of 2019 and funds disbursed at end-December 2019. / An initial introduction meeting was held with the implementing partner for the Addressing Education in North-east Nigeria (AENN) end-January 2020; a formal quarterly meeting is planned for end-March 2020.

Provide supporting narrative for the score
Output 5.1 focuses on supporting USAID’s Addressing Education in the Northeast (AENN) programme to address urgent education needs of 302,500 children in 225 communities in Borno and Yobe States from October 2019 to September 2021. DFID support will go towards AENN Results Area One which focuses on increasing the capacity of education authorities to plan, manage, and oversee education services through the:
- Establishment of data hubs.
- Expansion of data hub data collection to the LGA level.
- Digitisation of the education management information system (EMIS).
- Incorporation EMIS data into data hub information products.
- Mapping of non-formal education data and inclusion in data hub information products.
At the time of this annual review, scant data on the impact on results area one was available. This was primarily the result of delays in the release of DFID funding to USAID. FHI 360, USAID’s implementing partner, intends to engage in regular monitoring of government (by SAME – State Agency for Mass Education and SUBEB – State Universal Basic Education Board staff) use of data for decision making, (including for annual budgeting and planning, response to issues raised in schools for planning and safeguarding, and for developing annual education plans), but to date FHI 360 has not yet captured the value added of data collection for decision making.

Lessons identified this year, and recommendations for the year ahead linked to this output
Regular meetings with and monitoring of results one data collection and use will need to be a key focus for FY 2020/21. Given delays in programming combined with shrinking access to education LGAs particularly for the collection of data on out of school children means that tight monitoring of the programme will be vital to ensuring the added value of DFID support. Quarterly meetings held with USAID AENN staff and FHI 360 will be a basic requirement along with visits with SUBEB and SAME staff during field visits to the NE to gather direct feedback on how data is being used for informed decision making.

Recommendations for the year ahead
Education in Emergencies work is currently under NENTAD support and with results on EiE attributable to NENTAD through FY 2019/2020. In November 2019, the UNICEF led consortium received a second phase of funding (as a cost extension from initial NENTAD funding) totalling £4.8 million approved until 31st March 2021 which came from the PLANE budget. In June 2019, a second phase of the IRC-led EiE consortium was approved until 31st March 2021 for £3.8 million, with funding until 31st March 2020 being provided through NENTAD and subsequent funding then to come from PLANE.
1. Phase two IRC consortium interventions are targeting 45,000 educationally marginalised and vulnerable children: 15,000 of whom are out of school; and 30,000 who are in school but struggling academically and are at risk of dropping out.
2. The UNICEF consortium (with Plan International and StreetChild as downstream partners) is targeting 78,000 children aged 6-17, with an emphasis on girls and children with disabilities, in the most underserved conflict-affected IDP and host communities in 95 public schools and 15 IQSs (Integrated Qur’anic Schools). Additional beneficiaries include 1,700 teachers and facilitators (formal primary schools and non-formal education centres/IQSs), School/Centre-based Management Committees.
Findings from the 2018/19 NENTAD Annual Review indicated that combined EiE programming created access to formal and non-formal education for over 130,000 children (130% achievement against the target) with an evidenced 90% retention in school. Achievement against the 2019/2020 NENTAD Annual Review anticipates that another 100,000 children will be reached through EiE programming. However, data from implementing partners IRC and UNICEF suggest that that total will be higher with estimates closer to 45,000 children reached through non-formal interventions and 78,000 children through formal interventions.

Output Title	Communities support children’s participation and learning, including for marginalised groups
Output number per LF		6	Output Score	B
Impact weighting (%):		15%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
6.1 Progress towards selecting an implementing partner for community support component.	Call for proposal process to select implementer(s) launched.	The process to select an Implementer for this output was scheduled to begin in February 2020. However, the gap in technical support on the education technical advisers has meant a delay in the process. New timeline will be developed as soon as there is clear direction on how and when the technical capacity gap will be filled.

Provide supporting narrative for the score
The start-up of this project delivering on output 6 was delayed following the brief illness and unexpected demise of the Lead Adviser and DFID Nigeria education adviser. This slowed down the process of selecting a partner to manage the implementation of this output under the PLANE programme. The team started the process of selecting a partner(s) for this window. On 2nd December 2019, the team held an external consultation event with potential partners (civil society and multilateral organisations) highlighting the concept, and the objectives of the project, while also informing the audience of specific requirements which is expected is of the delivery partner who will implement the project.

The project under this output will play a vital role in ensuring that DFID Nigeria contributes significantly to DFID efforts to achieve its targets and objectives in the focal area of Girls’ Education.

Lessons identified this year, and recommendations for the year ahead linked to this output

DFID Nigeria may need to conduct a review of this Window under the PLANE portfolio to ensure that the proposed activities under this project will align with new UK Manifesto and Ministerial commitments on Education. ACTION - DFID by end July 2020.

DFID Nigeria will also need to recruit a Lead Adviser for this component of the programme to oversee the selection of partner(s) and the implementation of the project. ACTION - DFID by end July 2020.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

The Theory of Change (ToC) is outlined in the business case and remains unchanged. The PLANE ToC argues that IF state and non-state basic education providers are better enabled to deliver foundational skills (Outcome) THEN there will be more children and young people (who) can transition to more productive life opportunities (Impact). The ToC further argues that the outcome will be achieved IF there is more focus on quality teaching and learning; better managed resources and a focus on measurable results; children in conflict environments are supported to continue to learn; and communities are better able to support learning. Each intermediate outcome is expected to be achieved if the outputs within the windows are achieved.

The ToC is informed by the evidence of what works to improve education systems and help children to learn foundational basic skills in low resource contexts. It is also informed by research and independent evaluations in DFID Nigeria over the last ten years.

At this early stage in the process it is too soon to assess whether any changes will be required.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

Not applicable at this stage given the early timing of this review.

Explain major changes to the log-frame in the past year (1/2 page)

This initial process log-frame covers the processes required to put in place the contract/ grants to deliver the programme. The log-frame will be reviewed and updated to cover the next stage. In addition, work on the log-frames to reflect individual programme elements will be developed in the next period and will be aligned to the overall programme log-frame.

The current log-frame includes impact and outcome indicators. Milestones for these indicators include the development of respective baselines in 2019. At this time these baselines have not been developed due to delays in the DELVe contract that covers this element. It is anticipated that the DELVe contract will be up and running in time to ensure that the indicators can be developed in the next period with the PLANE.

Describe any planned changes to the log-frame as a result of this review (1/2 page)

As stated earlier the log-frame will need to be re-written in the next six months, to move from a transitional log-frame to a programmatic log-frame, with agreed indicators and milestones for all outputs. Whilst separate indicators and milestones will be agreed with respective organisations for each separate component of the portfolio, this should come together in an overarching log-frame in line with the six outputs within the business case. ACTION – DFID by September 2020

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

There is no change in the value for money proposition as outlined in the Business Case.

A Value for Money Action Plan forms part of the deliverables for the inception phase of the programme.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

As above there is no change at this time.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

The overall risk rating for the programme is major and is operating within its risk appetite. All risks (as outlined in the business case) continue to be relevant. The mitigation measures outlined in the business case continue to be relevant. An Initial risk matrix with mitigation measures forms part of the deliverables for the inception phase of the programme

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

There have been some delays in the planned procurement of the DELVe contract. which has impacted on the establishment of baselines for the outcome and impact indicators as outlined in the log-frame. At this time, it is anticipated that the baselines will be established during the implementation phase of the programme.

The TORs were initially developed to fit with this time-frame. The advice has subsequently been updated allowing for new TORs to be developed that will allow for the period to be extended to cover the length of PLANE and other programmes covered by the DELVe contact.

The majority of the other procurement activities – bid evaluation and identification of preferred bidders are on course to be delivered during (or close to) the end of the review period with contracts in place soon after. The award of the OJEU contract is running a little later than planned with the expectation that confirmation of the contractor will be finalised by the end of April 2020.

Date of last narrative financial report(s)	25 February 2020
Date of last audited annual statement (s)	Annual Audited Statements will be due in 2020/21.

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

The PLANE partners will be responsible for monitoring their projects closely at output and outcome level, using specific and measurable indicators against demonstrable, realistic and timebound milestones. A detailed Results Framework (log frame), setting out indicators and targets for each Place at output, outcome and impact level will form the foundation of programme monitoring, and will include value for money indicators.

DELVe will provide a range of independent evaluation, learning and verification services needed to manage the DFID Nigeria Human Development Portfolio. These services will achieve both learning and accountability purposes. The DELVe contract will support the PLANE programme with an independent performance evaluation as well as verification of the accuracy of reporting and quality of delivery of results.

Actions to take forward the tender for DELVe are progressing with the expectation that a supplier will be engaged by end of the year.

Evidence (1/2 page)

The evaluation design (detailed design) is expected to be finalised in the next period.

Learning (1/2 page)

It is too early to include learning at this time.

Progress on recommendations from previous reviews (1/2 page)

Not applicable as this is the initial review of the programme.