## Revised Logframe October 2020
OUTCOME | Outcome Indicator 1 |  | Baseline (September 2020) |  |  | Target (March 2021) | Assumptions
Pitcairn’s public services are managed and delivered efficiently. | Percentage of people with diabetes with an acceptable fasting blood glucose (< 7 mmol/l) at last check (within last 6 months). Ideally the island should be able to routinely check HbA1C of all diabetes as robust point of care testing equipment is relatively cheap and the test easy to perform. The indicator would then change to % of diabetes with acceptable HbA1C level (tbc). | Planned | 57% (4 out of 7 adults) |  |  | 71% (5 out of 7 adults) | Prevalance of Diabetes on Pitcairn: 7/33 adults (21%). As of December 2020, the HbA1c machine is not operational. No new posts created without clear justification
Achieved
Source
doctor's reports
| Outcome Indicator 2 |  | Baseline (March 16) | Milestone 1 | Milestone 2 | Target (date)
|  | Planned | 10 local FTEs |  | > 10 local FTE | > 10 local FTEs
| GPI headcount target numbers | Achieved | 9.8 local FTEs | 10 FTEs
Review of government jobs completed December 2015.
|  |  |  | Restructure finalised March 2015, 60 permanent and 13 casual posts confirmed. = 10 FTEs. Kept under review | FTE 9.8
Source
PIO reports. Government of Pitcairn reports, Annual external audit report
| Outcome Indicator 3 |  | Baseline (2009) | Milestone 1 (Sept 2020) | Milestone 2 (DATE) | Target (March 2021)
| Effective governance and management arrangements in place for child safeguarding. | Planned | Continued child safeguarding measures in place building on Reconciliation workshop with external facilitators (May 17) and implementation of Child Safety Review 2018 | Terms of Reference for the Review are agreed and finalised |  | Desk based Child Safety Review 2020 is undertaken and recommendations are developed into KPIs and a delivery plan. | Child Safeguarding governance arranagements function as per the policy. There is a continued Family Community Adviser position on the island. The community on Pitcairn will engage with the Review process. The review will be completed once travel to the island resumes.
|  | Achieved | CSR 2017/18 CSR Review (Desk based) 2015 CSR Review 2013 CSR 2011 CSR Review 2009 | ToRs and review methodology have been completed
Source
Bi annual CSRs; FCA's reports
| Outcome Indicator 4 |  | Baseline | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2020) | Target (March 2021)
| Pitcairn deliver a social protection system which prevents and protects vulnerable groups from poverty throughout the lifecycle | Planned | Social Welfare Benefits Ordinance (2014) is in place, with provision for (working/non-working) pension, widows and child benefits. Financial support to all households provided under C-19 support package. | The Minimum Expenditure Basket is calculated to inform the rate set for social protection benefits. | Terms of Reference for the Social Protection review agreed | Review of social protection system is undertaken and recommendations are developed and adjustments integrated into budget for FY21/22. | The Social Protection system review is light-touch and proportionate to the population size and capacity on island to undertake the review with remote technical support.
Achieved
Source
The Social Protection Review report (2020)
| Outcome Indicator 5 | Planned | Home Support Policy (2017) is in place. |  |  | A paper and draft 5-year plan for Pitcairn’s elderly care agreed
| The long term needs of Pitcairn’s aging population are understood and appropriately planned for. | Achieved
Source
SDP
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 3.60m plus 0.878 COVID-19 mitigation |  | 0.216m |  |  | 75%
INPUTS (HR) | DFID (FTEs)
0.86
INPUTS (HR) | DFID (FTEs)
0.86
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (March 2021) | Assumptions
|  | Planned | FRA concluded 2020 | detailed mitigating strategies | implementation of mitigating strategies | ASP shows stable situation | Mitigating strategies address: • any activity under the SDP that fails to support DFIDs pro poor strategy • underspend/poor forecasting of budgets resulting in over/under spend • failure to include all general government activities in budget • budget allocations being inconsistent with medium term expenditure plans for the sector or the overall budget. • Inappropriate use of tendering/procurement procedures
Sustained budget management, in line with best practice | Government of Pitcairn to reflect the priority recommendations from the Fiduciary Risk Assessment into the risk register | Achieved
Source
Government of Pitcairn accounts and reports
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (March 2021)
| Implementation of audit recommendations | Planned | Agreement on recommendations and implementation timing. | Implementation progress as per agreed target dates | "Unqualified" annual audit | "Unqualified" annual audit
|  | Achieved |  | All recommendations implemented or ongoing. Annual audit taking place June-Sept | 18/19 audit unqualified
Source
Government of Pitcairn accounts and reports. Annual audit report
IMPACT WEIGHTING (%) | [6 empty] | RISK RATING
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (March 2021) | Assumptions
| Number and field of expatriate experts deliver basic services in line with job descriptions | Planned |  | All contracts include Code of Practice and Child Safeguarding for the Off Island Professional group ToRs. | 4 (education, health, social work and police) deliver in line with job descriptions | 4 (education, health, social work and police) deliver in line with job descriptions | Ability to attract and retain suitably qualified professionals.
|  | Achieved | 4 (education, health, social work and police) | Achieved. | Achieved.
Public Service Provision Maintained. |  | Source
Annual education, health, child welfare and policing/immigration reports; School parent reports. Routine progress & performance
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (March 2021) | Assumptions
| Percentage of children receiving full-time education appropriate to age and needs. | Planned | 100% | All children receiving appropriate full-time education, including two children in senior boarding school in NZ. | 100% (in school on Pitcairn and at boarding school in NZ) | 100% (in school on Pitcairn and at boarding school in NZ) | Ability to attract and retain suitably qualified teacher for island school. Families agree to older children attending school in NZ
|  | Achieved |  | Achieved. | Achieved.
Source
regualar education reports
| Output Indicator 2.3 |  | Baseline (September 2020 | Milestone 1 | Milestone 2 | Target (March 2021) | Assumptions
| Percentage of people with diabetes on island who completed a routine check-up during last 6 months | Planned | 6 out of 7 adults (86%) |  |  | 100% | Prevalance of Diabetes on Pitcairn: 7/33 adults (21%)
Achieved
Source
| Output Indicator 2.4 |  | Baseline (September 2020) | Milestone 1 | Milestone 2 | Target (March 2021) | Assumptions
| Percentage of overweight children and their parents receiving advice on healthy eating habits and implementing guidance on daily/ weekly physical exercise | Planned | 0% |  |  | 60% | As of September 2020, 6 of 8 (75%) < 20 are overweight
Achieved
Source
IMPACT WEIGHTING (%)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 December 2018 | Target (March 2021) | Assumptions
Regular and reliable sea access to Pitcairn supports reasonable needs. | Number of times supply ship runs to/from NZ/Pitcairn carrying freight. | Planned | 4 | 4 |  | 4 New contract in place and operational | Stability in fuel prices Vessels able to land in poor weather. Sufficient take up of berths COVID-19 restrictions lifted with normal rotations resumed
|  | Achieved | 4 | 4
| Output indicator 3.2 |  | Baseline 2019/20 | Milestone 1, 10/19 | Milestone 2 December 2018 | Target (March 2021)
| Number of times supply ship runs to/from Mangareva/Pitcairn carrying passengers | Planned | 26 |  |  | 21
Achieved
|  | Planned | 26
IMPACT WEIGHTING (%) |  | Achieved | 22
|  | Source |  |  |  |  | RISK RATING

## Template
OUTCOME | Outcome Indicator 1 |  | Baseline (March 17) | Milestone 1 (April 18) | Milestone 2 | Target (date) | Assumptions | Review action/ lead
Pitcairn’s public services are managed and delivered efficiently. | Percentage of children and adults that show excess weight (overweight or obese) as per their Body Mass Index, disaggregated by adult/child and gender. | Planned | 70% |  |  | 40% (over time) | diet and lifestyle changes made to reduce BMI No new posts created without clear justification | Pitcairn happy to change this one (needs changed)
|  | Achieved |  | Programs and protocols in place now Working at personal levels with each patient
Source
doctor's reports
| Outcome Indicator 2 |  | Baseline (March 16) | Milestone 1 | Milestone 2 | Target (date)
|  | Planned | 10 local FTEs |  | > 10 local FTE | > 10 local FTEs
| GPI headcount target numbers | Achieved | 9.8 local FTEs | 10 FTEs
Review of government jobs completed December 2015.
|  |  |  | Restructure finalised March 2015, 60 permanent and 13 casual posts confirmed. = 10 FTEs. Kept under review | FTE 9.8
Source
PIO reports. Government of Pitcairn reports, Annual external audit report
| Effective governance and management arrangements in place for child safeguarding. |  | Baseline (2009) | Milestone 1 (Sept 2020) | Milestone 2 (DATE) | Target (March 2021)
|  | Planned | Continued child safeguarding measures in place building on Reconciliation workshop with external facilitators (May 17) and implementation of Child Safety Review 2018 | Terms of Reference for the Review are agreed and finalised |  | Desk based Child Safety Review 2020 is undertaken and recommendations are developed into KPIs and a delivery plan. | Child Safeguarding governance arranagements function as per the policy. There is a continued Family Community Adviser position on the island. The community on Pitcairn will engage with the Review process. The review will be completed once travel to the island resumes.
|  | Achieved | CSR 2017/18 CSR Review (Desk based) 2015 CSR Review 2013 CSR 2011 CSR Review 2009 | ToRs and review methodology have been completed
Source
Bi annual CSRs; FCA's reports
| Pitcairn deliver a social protection system which prevents and protects vulnerable groups from poverty throughout the lifecycle |  | Baseline | Milestone 1 (Sept 2020) | Milestone 2 (Dec 2020) | Target (March 2021)
|  | Planned | Social Welfare Benefits Ordinance (2014) is in place, with provision for (working/non-working) pension, widows and child benefits. Financial support to all households provided under C-19 support package. | The Minimum Expenditure Basket is calculated to inform the rate set for social protection benefits. | Terms of Reference for the Social Protection review agreed | Review of social protection system is undertaken and recommendations are developed and adjustments integrated into budget for FY21/22. | The Social Protection system review is light-touch and proportionate to the population size and capacity on island to undertake the review with remote technical support.
Achieved
Source
The Social Protection Review report (2020)
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 3.60m plus 0.878 COVID-19 mitigation |  | 0.216m |  |  | 75%
INPUTS (HR) | DFID (FTEs)
0.86
INPUTS (HR) | DFID (FTEs)
0.86
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (03/21) | Assumptions
|  | Planned | FRA concluded 2020 | detailed mitigating strategies | implementation of mitigating strategies | ASP shows stable situation | Mitigating strategies address: • any activity under the SDP that fails to support DFIDs pro poor strategy • underspend/poor forecasting of budgets resulting in over/under spend • failure to include all general government activities in budget • budget allocations being inconsistent with medium term expenditure plans for the sector or the overall budget. • Inappropriate use of tendering/procurement procedures
Sustained budget management, in line with best practice | Government of Pitcairn to reflect the priority recommendations from the Fiduciary Risk Assessment into the risk register | Achieved
Source
Government of Pitcairn accounts and reports
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Implementation of audit recommendations | Planned | Agreement on recommendations and implementation timing. | Implementation progress as per agreed target dates | "Unqualified" annual audit | "Unqualified" annual audit
|  | Achieved |  | All recommendations implemented or ongoing. Annual audit taking place June-Sept | 18/19 audit unqualified
Source
Government of Pitcairn accounts and reports. Annual audit report
IMPACT WEIGHTING (%) | [6 empty] | RISK RATING
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target (date) | Assumptions
| Number and field of expatriate experts deliver basic services in line with job descriptions | Planned |  | All contracts include Code of Practice and Child Safeguarding for the Off Island Professional group ToRs. | 4 (education, health, social work and police) deliver in line with job descriptions | 4 (education, health, social work and police) deliver in line with job descriptions | Ability to attract and retain suitably qualified professionals.
|  | Achieved | 4 (education, health, social work and police) | Achieved. | Achieved.
Public Service Provision Maintained. |  | Source
Annual education, health, child welfare and policing/immigration reports; School parent reports. Routine progress & performance
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (03/19) | Assumptions
| Percentage of children receiving full-time education appropriate to age and needs. | Planned | 100% | All children receiving appropriate full-time education, including two children in senior boarding school in NZ. | 100% (in school on Pitcairn and at boarding school in NZ) | 100% (in school on Pitcairn and at boarding school in NZ) | Ability to attract and retain suitably qualified teacher for island school. Families agree to older children attending school in NZ
|  | Achieved |  | Achieved. | Achieved.
Source
regualar education reports
IMPACT WEIGHTING (%)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 December 2018 | Target (March 2020) | Assumptions
Regular and reliable sea access to Pitcairn supports reasonable needs. | Number of times supply ship runs to/from NZ/Pitcairn carrying freight. | Planned | 4 | 4 |  | 4 New contract in place and operational | Stability in fuel prices Vessels able to land in poor weather. Sufficient take up of berths COVID-19 restrictions lifted with normal rotations resumed
|  | Achieved | 4 | 4
|  |  | Baseline 2019/20 | Milestone 1, 10/19 | Milestone 2 December 2018 | Target (March 2020)
| Number of times supply ship runs to/from Mangareva/Pitcairn carrying passengers | Planned | 26 |  |  | 21 |  | Covid impact to be reflected
Achieved
|  | Planned | 26
IMPACT WEIGHTING (%) |  | Achieved | 22
|  | Source |  |  |  |  | RISK RATING

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.