## Annual Review Template – September 2020

Title: UK Aid Direct Fund - working with small and medium charities
Programme Value £ (full life): 174,612,290		Review date: 28 November 2020
Programme Code: 202035	AMP start date: 6 September 2010	AMP end date: 30 September 2026

Summary of Programme Performance

Year	2015/16	2016/17	2017/18	2018/19	2019/20
Overall Output Score	A	A+	A	A	A
Risk Rating	Minor	Moderate	Minor	Minor	Moderate

DevTracker Link to Business Case:	http://iati.fcdo.gov.uk/iati_documents/5557245.odt
DevTracker Link to Business Case Addendum	http://iati.fcdo.gov.uk/iati_documents/4330641.odt
DevTracker Link to results framework:	http://iati.fcdo.gov.uk/iati_documents/51546855.xls

A. SUMMARY AND OVERVIEW

Introduction

Following on from previous UK Aid Direct (UKAD) reports, this review covers UKAD grants’ performance and results between April 2019 and March 2020 inclusive and key lessons and recommendations on overall programme management from the period up to November 2020. This review is normally completed in August which allows sufficient time for analysis and verification of grant holder reporting and overall programme management. This year, however, due to the significant impact of COVID-19, this report was deferred until November 2020 to allow the UKAD team to support grant holders to adapt their projects to positively respond to the pandemic.

Description of programme

UKAD is the Foreign, Commonwealth and Development Office’s (FCDO’s) main centrally managed civil society programme and the only fund designed specifically for small and medium-sized civil society organisations (CSOs), working to achieve sustained poverty reduction and deliver the Global Goals. The UKAD fund (the successor of the Global Poverty Action Fund) has been managed by an external fund manager, MannionDaniels, since September 2015, offering funding for projects implemented in the pre-approved list of UKAD countries. The programme offers four main types of grants: Impact (up to £4m), Community Partnership (up to £250k) and Jo Cox Memorial Grants (JCMG, up to £1m). Also, following a two-year pilot, a permanent Small Charities Challenge Fund (SCCF, up to £50k) has been launched in September 2019.
[note] UKAD eligible countries are countries listed in the lowest 50 countries in the UN Human Development Index (HDI) and/or countries the UK Government considers to be of high or moderate fragility. For full list please see: https://www.ukaiddirect.org/about/eligible-countries/

The UKAD programme continues to be a highly competitive fund with a two-stage process designed to award funding only to those grantees who can demonstrate the greatest impact they can achieve with UKAD funding. The usual timeframe from the round preparation to funding award takes about 10 months.

As of March 2020, the UKAD portfolio had reached more than 7.9 million direct beneficiaries, across 30 countries, with over £17.1m disbursed to active grants in Sub-Saharan Africa, South-East and South Asia and the Caribbean in four funding rounds. The average grant request was £1.4 million for Impact grants and £230,000 for Community Partnership grants. More detailed portfolio analysis is presented below.

UKAD has been designed to respond flexibly and adapt to the UK development and ministerial priorities in the context of a rapidly changing world. The past six months have been challenging for the UKAD team with considerable work having gone into supporting grant holders to pivot projects to respond to the impacts of the COVID-19 pandemic, providing a new urgent response funding round, undertaking the Overseas Development Assistance (ODA) prioritisation exercise and budget reprofiling, and working with grant holders on optimising forecasted budgets.
[note] The UKAD team comprises staff from the FCDO Civil Society Team, and the fund manager, MannionDaniels, and consortium.

Further COVID-19 impact and relevant responses to support those affected is expected to be captured during the next annual review, as the fund manager and grant holders have dealt with lockdowns and restricted movement which limited their scope for delivery and monitoring. In addition, shrinking Gross National Income (GNI) that currently governs the UK aid budget (set at 0.7% of GNI), will continue to have a significant impact on FCDO programme budgets. Therefore, more scrutiny and savings will be required to mitigate some of those global impacts in the coming months and years.

UKAD portfolio analysis as of March 2020

List of abbreviations

JCMG: Jo Cox Memorial Grants
SCCF: Small Charities Challenge Fund
UKAD: UK Aid Direct
WASH: Water, Sanitation and Hygiene

Grants by country

UK based grant holders by region

Summary supporting narrative for the overall score in this review

The programme delivery is on track and it scores an A despite three of the 16 output indicators having not been met. This is mainly because performance for outputs 1 to 4 have been assessed based only on 102 grants out of all 138 active grants at the time. These are JCMG, Impact and Community Partnership grants, which reported during this period. The difference between the number of active grants and grants reported is for two reasons:
1. Most of the UKAD Round 3 and JCMG grants had not reported in time for this review due to delays with the start-up of these projects, mainly related to organisational capacity issues and shift in start dates to meet seasonal requirements such as school start dates.
2. The number of SCCF grant holders increased by 81% in this reporting period compared to the previous year, however, SCCF grant holders didn’t have required reporting capacity to demonstrate their results against output milestones, in time for this review.

Major lessons and recommendations for the year ahead

This section only covers a summary of key lessons and recommendations based on the UKAD delivery during this reporting period, with further detail and recommendations covered in the sections C to E below.

COVID-19

Lessons learned:
- In response to COVID-19, the fund manager has adopted a coherent approach to adaptive management. They utilised the existing systems and processes and a flexible pool of resources to fully adapt to changing circumstances. This enabled running a new funding round in a very short timeframe, following the revised processes and guidance.
- In future, more interactive approaches to webinars and stronger peer to peer networking should be adopted, to allow virtual discussions rather than in person interaction.
- Remote monitoring during COVID-19 has been challenging and works better in certain contexts. In future, stronger in-country support will be required to allow for national level monitoring and audit visits to take place where possible.
Recommendations:
A more comprehensive review of the impacts of both COVID-19 and the prioritisation exercise will be undertaken by the fund manager in the first quarter of 2021.
Prioritisation process

Lessons learned:
- Feedback from the sector highlighted that would have been helpful to have more concrete communication from FCDO about the rationale for the prioritisation exercise. The prioritisation itself was challenging to deliver given the scale of the reduction in spend required due to the UK’s own economic impacts of COVID-19 leading to a reduction in the aid budget.
- If there are similar major changes to grant workplans and budgets in future, these should be undertaken in a way that minimises disruption to the overall programme and projects to represent better VfM.
Recommendations:
- The fund manager will work with grant holders in the next reporting period to strengthen their ability to adapt and respond to changing needs and contexts e.g. by identifying activities and approaches that can be scaled up or down as necessary.
- A more strategic approach to potential future revisions in grant holders’ budgets should be developed by the fund manager to limit the impact on live grants – notably those due to end within 6 months.

Leave No One Behind (LNOB)

Lessons learned:
CSOs are benefiting communities in places where the government or private sectors have not reached, through interventions aiming at increasing opportunities for economic, political, inclusive and gender empowerment.
Recommendations:
- A systematic approach to LNOB should be developed by the fund manager to ensure progress is driven by high quality evidence and data disaggregation.
- Although improvements have been made in the disaggregation of data, this continues to be challenging, particularly around gathering disability data and more intensive efforts with grant holders are required
Civil society empowerment

Lessons learned:
- Projects that take a participatory approach to both design and implementation throughout the project lifecycle tend to support beneficiaries to have greater autonomy and control over their own development.
- Bigger and more established organisations have a greater capacity and ability to advocate and leverage efforts aimed and increasing decision-makers’ accountability for the actions and decisions that affect local communities.
- The cost of beneficiary engagement needs to be balanced by potential benefits, and investment made accordingly.
- Early evidence is emerging from the programme that some of the programme level outputs, like increasing beneficiaries’ choice and control over their own development and to hold decision-makers to account, are harder to achieve through the smaller SCCF grants.
Recommendations:
The majority of grant holders are now implementing beneficiary feedback mechanisms therefore the focus should shift towards the changes and improvements achieved as a result of implementing the mechanisms.

Other annual review recommendations

- The theory of change should be reviewed by FCDO and the fund manager during the next reporting year, to ensure major changes in context (e.g. COVID-19) are adequately reflected.
- The fund manager should strengthen its approach to measuring and monitoring of VfM at both grant and portfolio level.
- A capacity building strategy should be developed by the fund manager to effectively drive VfM and the UKAD learning offer.
- An effective learning dissemination strategy should be developed by the fund manager in consultation with FCDO, focusing on CSOs’ contribution through UKAD to wider development impact.
- During the next reporting period, the fund manager and FCDO team should consider further actions to improve access to funding of southern-based CSOs.
- Appropriate indicators for SCCF grant holders to be developed by the fund manager in consultation with FCDO, to increase capacity building efforts.
- Additional guidance to be designed by the fund manager to ensure appropriate proxy indicators for behaviour change communications (BCC) are included in grant holders’ logframes for more accurate evidence.
Future programming recommendations

Long term capacity-building:
- Given the limited scope and resources of the current programme, further incentives/approaches to improve access to funding for southern-based organisations need to be developed within the future programming, drawing on lessons learned and evidence from UKAD; this should include stronger capacity building efforts to improve quality of southern-based applications.
- To ensure the effectiveness of any future thematic rounds, it will be important to draw on lessons learned and VfM of the thematic rounds conducted to date by UKAD.

Systematic learning:
- A stronger approach to utilising learning in decision making at strategic portfolio level should be adapted within the future programming.
- Greater efforts in gathering and analysing learning from projects related to the wider development impact when delivering through CSOs should be undertaken.
- The next phase of programming should explore alternative approaches to lessons sharing and learning through variety of channels and to suit different context and needs, including allowing for greater real time communication and grant holder-to-grant holder support.

Adaptive programming:
Adaptability of the existing UKAD programme has been a critical component of the success. In future, development of effective VfM indicators in this area will be important to fully demonstrate results and provide evidence of the informed decisions.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case

The overall fund-level theory of change remains unchanged.
UKAD’s theory of change states that through a demand-led fund, FCDO can respond to the appetite in the sector for calls in the identified thematic areas and contribute to the achievement of the Sustainable Development Goals (SDGs) at the impact level. By responding to this demand FCDO can support civil society in targeted countries to have greater capacity to improve their contribution and delivery mechanisms for sustained poverty reduction in marginalised and vulnerable communities at the outcome level.
The outputs make relevant contributions towards poverty reduction and reflect the former Department for International Development’s (DFID’s) priorities through the delivery of results in the following key areas:
- Improving access, supply and quality of basic services (by them) for specific target groups
- Improving access to information to hold decision makers to account
- Increasing opportunities for economic, political, inclusive and gender empowerment
- Shifting social attitudes and behaviours resulting in positive norm change in targeted groups
- Improving delivery of interventions as a result of shared evidence and learning within the fund
- Improving access to flexible, responsive and adaptive funding
The output areas are broad and have been designed to incorporate most grant holder contributions to SDGs with a link between outputs and outcomes less direct.
The key core assumptions on UKAD as outlined below have also been upheld during this reporting period:
- Level of demand and quality of proposals: 1105 applications were received during UKAD Round 4: 211 were deemed ineligible, 100 were submitted during the full application stage and 36 were approved for funding. This demonstrate that the success rate of eligible applications increased from 4% in Round 3 to 5% in Round 4, mainly on SCCF. Generally southern-based applications were of a lower technical quality compared to their northern counterparts based on the success rates.
- CSOs have appropriate assets: The high performance and results delivered by grant holders demonstrate a level of knowledge and skills in the sector, including an additional 65 new organisations awarded UKAD grants. However, capacity levels (as noted above) of southern-based applicants are disproportionally lower (only 15% of grants went directly to a southern-based organisation against a 22% target).
- Effective selection and disbursement continue: During Round 4, of the 100 requested to submit a full application, 40 applicants were shortlisted for funding and went through to the due diligence stage. Of those, 36 (90%) were awarded grants. The total value of the UKAD Round 4 portfolio was £33.5m.
- Due diligence model proves effective: Financial and integrity due diligence checks were undertaken during each funding round. In total 620 integrity checks (including 88 full due diligence assessments) have been carried out during the reporting period. In total only 10% of applications were rated as ‘severe’, which reflects the strength of the application process and pre-application checks.
- CSOs continue to develop: More than 80% of active grants demonstrated an increase in capacity based on Organisational Capacity Assessment (OCA).
  [note] The organisational capacity assessment is a tool designed to support grant holders monitor their organisational capacity. Grant holders complete it at the start of the grant and annually thereafter. It is a self-assessment of their capacity in the areas of governance, planning, HR, financial mgmt., and M&E. This is submitted to the fund manager annually who collate all the scores and analyse change. Subsequently, feedback with grant holders specifically on their OCA is shared through the AR process and the information is used to plan the fund manager’s capacity building activities.
- CSOs can achieve their outputs and outcomes: Overall, the majority (73%) of grant holders have scored A or above through the latest annual reviews and Project Completion Reviews (PCRs).
- Assumptions to be tested through evaluation: Although an evaluation of the full programme has not been undertaken, the assumptions have been regularly tested through the quarterly and annual review processes.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

CSOs’ outputs should lead to change for beneficiaries through improvements in access, knowledge, empowerment and accountability at outcome level. This should be supported by evidence from individual projects which are achieving their outputs and outcomes. However, the results chain between outputs and outcomes is long and the change achieved at outcome level as a result of interventions not always apparent. Therefore, some of the UKAD output indicators should be reviewed during the next reporting period to ensure a strong focus on results, as opposed to the inputs invested.
Performance at impact level

Overall, only one impact level target for year 5 has not been met, with the detailed progress across all impact indicators as follows:
Impact indicator 1: 73% of UKAD grant holders demonstrated progress towards SDGs [1,2,3,4,5,6,7,8,10,13,16,17] against an 80% target based on the number of projects scoring an A or above, meaning the progress moderately did not meet expectations. However, of the poor performing grant holders from 2019, five improved their performance score, one remained the same and only one grant holder’s performance has declined.

Impact indictor 2: 99% of UKAD projects contributed to at least three of the former DFID’s strategic objectives as per detailed breakdown across the four target areas:

- 78% of projects have been tackling extreme poverty and helping the world’s most vulnerable against the 60 - 87% logframe target
- 7% of projects have been promoting global prosperity against the 17 - 24% logframe target
- 7% of projects have been strengthening global peace, security and governance against the 5 - 22% logframe target
- 7% of projects have been strengthening resilience and response to crisis against the 8 - 12% logframe target.
Performance at outcome level
Overall, only one outcome level target for year 5 has not been met with the detailed progress across all outcome indicators as follow:
Outcome indicator 1: 99 (192 cumulative) grants contributed to greater diversity of organisations funded within the portfolio against a target of 81 (159 cumulative). This is based on the number of grant holders that are either small (annual income below £1m per year), southern-based or new to FCDO funding.

Outcome indicator 2: 100% grants directly contributed to the former DFID results framework commitments (for example: in economic empowerment or WASH). Also, all grants have been implemented in countries either considered to be of high or moderate fragility or ranked in the bottom 50 of the UN Human Development Index.

Outcome indicator 3: A total unique (additional) number of 1,892,112 (7,913,532 cumulative) marginalised people were reached by CSOs in targeted countries against a target of 1,972,127 (7,903,415 cumulative). This includes 879,311 male, 1,001,421 female, and 11,380 unknown gender (due to grant holders not collecting disaggregated data). Within these figures 37,793 beneficiaries had disabilities. The overall progress moderately did not meet expectations due to the slower inception and implementation of UKAD Round 3 and JCMG grants, but cumulatively has slightly exceeded the target.

Outcome Indicator 4: 98% of participating CSOs improved their Organisational Capacity Assessment (OCA) scores against a target of 60%. This indicator has consistently performed well over the life of the programme. Grant holders have routinely been able to demonstrate a shift in capacity over time. Additional analysis will be undertaken by the fund manager in the next reporting period to understand the links between the capacity building support we give and the OCA results.

Recommendations for the year ahead
The UKAD logframe will be revisited within six months from this review, to strengthen some of the indicators or redefine the outputs, to ensure we measure the anticipated change in a meaningful way (more detail on this in the outputs section C below).

Given the number of smaller grants has increased significantly (by 81%), the outcome targets will be revised for year six, as smaller projects require a different approach to measuring their progress and results due to organisational limitations. In addition, COVID-19 will impact the next annual reporting period as grant holders deal with lockdown and restricted movement and subsequently adapt their approaches.

Given outcome indicator 2 has now been fully met, this will be replaced with a new indicator capturing grant holders’ performance and contribution towards the overall programme outcomes.

The fund manager will reflect on the individual logframes for the projects scoring B, to ensure the targets for these and other logframes are set at a realistic level, in line with the context and reporting timeframe.

The fund manager will develop a systematic approach to the disaggregation of beneficiary data (gender, disability, age, geography, urban vs rural etc.) – see recommendations under output 3.

Additional analysis will be undertaken by the fund manager in the next reporting period to understand the links between the capacity building support we give and the OCA results.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The UKAD programme has scored A overall this year and has been assessed to be delivering good VfM. The challenges related to the implementation of a complex portfolio of projects across 30 countries, resulted in a small shortfall in reaching unique (additional) beneficiaries. However, the cumulative target has been met by reaching £7.9 million beneficiaries.

The fund manager has been particularly effective in responding to changing priorities, including funding rounds that have encouraged applications on specific themes and launching a rapid response to COVID-19. The portfolio of grants has been managed effectively with the majority of grants scoring A or above, successfully contributing to the overarching UKAD impact. In addition, 98% of grant holders have reported improved capacity as a result of UKAD funding and targeted support.

The evidence shows that a greater focus should be made towards increasing access to funding for smaller and southern-based organisations, where the level of demand is not matched by the quality of proposals and many organisations do not meet the eligibility standards. However, the programme has effectively adapted by launching SCCF grants and aligning funding rounds with (at that time) DFID’s agenda. Finally, the programme portfolio has been consistently contributing 100% to at least three of the former DFID’s strategic objectives.

For these reasons, there is a strong case that the UKAD programme should continue.

## C. DETAILED OUTPUT SCORING

Output Title	Improved access, supply and quality of basic services for specific target groups
Output number:		1	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1. Number of people benefitting from improved access to quality basic services.	Unique: 493,032	Unique: 526,747

Briefly describe the output’s activities and provide supporting narrative for the score

This output has met expectations and slightly exceeded its annual target, by 33,715 (7%). Overall, the unique number of people benefiting from improved access or services decreased by 70,491 compared to last year’s results as a result of the changing portfolio (as grants end and new ones start).

Out of the 102 grants that have reported in this period, only 31 projects have an indicator relevant to this output embedded within their individual logframes, therefore only those projects provided evidence for this output. In addition, many SCCF grant holders still report at activity/input level whilst the fund manager has been investing a lot of time to strengthen their reporting capacity, so appropriate SCCF output/outcome level indicators can be set up in the next reporting period.

The most significant contributors to this output were two Impact grants delivering water, sanitation, and hygiene (WASH) interventions and a JCMG Network grant working across multiple countries to prevent identity-based violence (IBV). Overall, these three projects have delivered 71% of the total year 5 target.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Measuring quality at project level remains challenging due to varied levels of organisational capacity across the UKAD portfolio, where many organisations are very small or new to FCDO funding. The fund manager has been working with grant holders on improving performance in this area by introducing appropriate logframe indicators on all major projects and providing guidance, webinars and one-to-one support alongside regular grant monitoring.

At the same time, demonstrating that the programme’s benefits are distributed fairly and reaching the most marginalised groups is challenging without an appropriate beneficiary data disaggregation. Although the fund manager is targeting approaches to reaching most marginalised through application and grant set up process, ongoing monitoring of the targeted groups is restricted by the grant holders’ capacity to provide disaggregated data during the implementation. The fund manager has developed a new disaggregation tool that should address this in the next reporting period.

Describe any changes to this output during the past year, and any planned changes as a result of this review

The UKAD logframe will be revisited within 6 months from completing this annual review, in line with the recommendations in this report. Any changes to the logframe will be agreed by the UKAD team and Head of Department.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the previous AR

The milestone 1.1 for year 5 will be revised to reflect UK Aid Direct Round 3 and JCMG grants.
Progress: Due to the temporary FCDO funding pause which delayed some grant set-ups, this milestone has not been updated. This will be reviewed for year six.

A meaningful sample of existing grant holders to start measuring quality of services they have been delivering.
Progress: Overall, 31 projects out of 102 have now embedded appropriate quality and equity indicators, with a full roll-out on all new grants and expand onto the existing logframes where possible and makes sense.

Lessons learned this year

Based on learning from UKAD3, the fund manager reviewed the grant set-up process (for UKAD4). Where previously a lot of information was given to grant holders in an initial set-up meeting, the fund manager has now developed a welcome pack which is sent to grant holders one month before the set-up meeting, to allow review of a significant amount of information ahead of the meeting. The meeting then can focus on practical application of UKAD requirements and supporting grant holders to set-up a quality programme within reduced timeframes.

Recommendations for the year ahead

The existing indicator intends to capture both quality and equity, however these are very distinctive and the progress against the two indicators can have very different results e.g. it is possible for quality of service/supply to improve but for access to remain quite exclusive. Therefore, the existing indicator should be disaggregated to measure distinctively quality and equity.

The fund manager should focus on providing clear logframe guidance at the outset of project design, both prior to application and at individual grant set-up meetings to focus on quality and equity.

Following more intensive capacity building efforts, appropriate SCCF output/outcome level indicators to be greed in the next reporting period, to effectively evidence progress of SCCF grants against the overarching UKAD logframe.

Output Title	Better informed citizens hold decision makers to account
Output number:		2	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1. Number of beneficiaries supported to have choice and control over their own development and to hold decision-makers to account	Unique: 230,967	Unique: 170,209
2.2. No of grant holders demonstrating evidence of a fully functioning beneficiary feedback mechanism	90%	96%

Briefly describe the output’s activities and provide supporting narrative for the score

Overall, output 2.1 moderately has not met the expectations by missing on 26% of the target for unique beneficiaries. Output 2.2 has exceeded the target, demonstrating a strong shift towards grant holders’ accountability toward the affected beneficiaries.

Output 2.1
This output has moderately missed the target based on the 28 projects (out of the 102 under this review) reporting towards this output. The grant holders that significantly contributed are primarily the bigger impact grants, with one JCMG grant in particular that is strengthening the grant holder’s ability to hold duty-bearers to account and reducing the likelihood of IBV (also referenced under output 1.1). This JCMG project has successfully supported 139,000 beneficiaries in the development and implementation of the community based IBV prevention projects through effective implementation of action plans and strong stakeholder engagement.

This year’s targets had been developed assuming that many of the JCMG grants would have implemented for one year and, given that many are designed to drive greater decision-makers’ accountability, this would allow the programme to meet its milestone. However, some of the grants took longer to begin implementation due to their capacity constraints and the seasonality of the project, which dictated start dates.

There are also only three SCCF grants that are contributing to this indicator at present. The numbers of grants reporting on this indicator are expected to increase as more UKAD3 and JCMG grants will start delivering. The fund manager also plans to provide further guidance on effective measuring and reporting on grant holders’ accountability in the next reporting period.

Output 2.2
Almost all grant holders have submitted evidence of a fully functioning beneficiary feedback mechanism. Of the four who have not, three have plans to collect feedback and are in the process of establishing appropriate mechanisms. One grant holder has not reported back, further action will be taken to understand why not and confirm that mechanisms are in place.

The latest review of a sample of 30 projects conducted in July 2020 indicated that only 8 out of 30 grant holders (27%) specifically mentioned closing the feedback loop, to communicate changes implemented as a result of feedback and assess effectiveness. It is unclear whether this is a result of poor quality of reporting or whether this is not implemented in practice. However, 21 grant holders demonstrated concrete action taken as a result of feedback received and the fund manager will conduct further analysis of the existing feedback mechanisms to fully understand the process for implementing and capturing the impact over the next reporting period. In addition, the fund manager has provided guidance to grant holders on closing the feedback loops and the impact of it is being tracked by the fund manager.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

As recommended below, during the next reporting period the fund manager should work with grant holders to improve their ability to evidence the change they are achieving as a result of beneficiary engagement thus better demonstrating that their interventions are effective and impacts maximised. The overall change can then be tracked and improvements made where possible, leading to better grant design and delivery. At the same time, some UKAD grant holders have provided strong examples during this reporting period that an effective feedback mechanism leads to increased empowerment of beneficiaries to hold to account grant holders and decision makers as illustrated in a case study 2 in Annex A.

However, the cost of beneficiary engagement needs to be balanced by potential benefits, and investment made accordingly. Therefore, any future funding proposals including beneficiary engagement should have clearly defined objectives and resources budgeted at the design phase, so VfM can be fully assessed.

Describe any changes to this output during the past year, and any planned changes as a result of this review

The UKAD logframe will be revisited within 6 months from completing this annual review in line with the recommendations in this report. Any changes to the logframe will be agreed by the UKAD team and the Head of Department.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the previous AR

The fund manager will continue to provide support to ensure that empowerment and accountability is being measured through beneficiary feedback reporting and analysed within their projects.
Progress: A rapid review of grant holders’ reporting on beneficiary feedback has been undertaken. Consequently, the fund manager will develop appropriate guidance for grant holders and share lessons learned with grant holders.

New grant holders to analyse and measure accountability as part of their project implementation.
Progress: Guidance on capturing and reporting accountability will be shared with grant holders ahead of UKAD4 grant set-up process in November 2020.

Leverage the learnings of a new pilot project with Integrity Action to help grant holders use their feedback mechanisms as effectively as possible.
Progress: The pilot with Integrity Action was launched in September 2019. Four grant holders have volunteered to participate in the study.

Lessons learned this year

The bigger and more established organisations have a greater capacity and ability to advocate and leverage efforts aimed and increasing decision-makers’ accountability within the affected communities.

It is also evident that the link between beneficiary feedback mechanisms and beneficiaries’ choice and control could be strengthened alongside accountability measures beyond demonstrating feedback mechanism in place.

There are also lessons learned from the grants significantly contributing to output 2.1: i) project staff presence supports informal networks to establish and encouraging regular flow of information (or feedback) and ii) projects that take a participatory approach to both design and implementation throughout the project lifecycle tend to support beneficiaries to have greater autonomy and control over their own development.

Key learning from grant holders related to output 2.2. is that whilst they have beneficiary feedback mechanisms in place, this is not always evident in the results/impact they report (i.e. they have beneficiary mechanisms but are not measuring its impact through logframes).

Recommendations for the year ahead

In future, to mitigate significant delays to grants start up, the fund manager will conduct a review of the time it takes to deliver ‘start up’ and what the key lessons are.

Early evidence shows that the greatest progress on increasing beneficiaries choice and control over their own development and on holding decision-makers to account make larger grant holders. More detailed VfM analysis across the portfolio will be conducted by the fund manager to determine what types of grants make the most significant impact across particular sectors, to inform future funding decisions.

Given that 96% of all grant holders now have a fully functioning beneficiary feedback mechanism in place, the fund manager should begin to measure the effectiveness of feedback mechanisms by replacing 2.2. indicator with e.g.: ‘The number of projects that have been adapted as a result of a fully functioning beneficiary feedback mechanism’.

The fund manager should explore with new grant holders ways of capturing voices of people with disabilities (and their representative organisations), as a central part of VfM assessment e.g. through an additional indicator: % of people with disabilities and their representatives reached through beneficiary feedback mechanism. This would have to be supplemented by qualitative data.

The fund manager will provide support to grant holders to assess the methods for gathering beneficiary feedback, the objectives and assessing the VfM of the proposed approach.

A metric to assess accountability will be developed and shared with grant holders to encourage greater focus and attention on strengthening beneficiaries’ choice and control.

A report of the pilot on beneficiary feedback mechanism with Integrity Action to be developed and learning will be used to strengthen both feedback mechanisms and the link between mechanisms and accountability.

Output Title	Increased opportunities for economic, political, inclusive and gender empowerment
Output number:		3	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1. Number of households reporting an improvement in economic empowerment	Unique: 78,885	Unique: 178,564
3.2. Number of projects strengthening gender empowerment	91	98
3.3. Number of projects directly working on disability inclusion	45	33
3.4. Number of beneficiaries demonstrating an increased level of knowledge as a result of skills training	Unique: 30,000	Unique: 28,580

Briefly describe the output’s activities and provide supporting narrative for the score

Overall, this output has mixed results this year, with one out of the four indicators significantly exceeding the milestone, one slightly above the milestone, one indicator slightly below the target and one significantly below.

Output 3.1
This indicator has significantly exceeded the year 5 target by delivering more than double what was originally anticipated. This is mainly due to three impact grant holders delivering specific economic empowerment projects, one of them across two countries (Ethiopia and Uganda), reaching 60,024 beneficiaries collectively and two other projects reaching 105,365 beneficiaries in total (in Sierra Leone and Ethiopia). These projects all started in early 2018 and have exceeded target milestones during 2019/20. A number of households reporting an improvement in economic empowerment is mostly evidenced by an increase in income reported against individual logframes.

Grant holders are required to disaggregate the beneficiary data by gender and disability. Of the 16 projects reporting against this indicator, 75% disaggregated by gender whilst only 31% disaggregated by disability, largely due to projects not always having the right monitoring framework in place to report this data. One grant holder contributing significantly to this indicator also highlighted occasional reluctance in communities to self-identifying as having a disability. An introduction of Washington Group Questions has helped to address this challenge – please see a case study 1 in Annex A). In addition, the fund manager will be asking grant holders to report on specific beneficiary data quarterly to closely monitor progress and implement timely improvements.

Output 3.2
This output has exceeded the target by an additional seven grants reporting the strengthened gender empowerment. However, the evidence to demonstrate that the empowerment has taken place is based on proxy indicators, against which grant holders self-report. At present, the definition of ‘empowerment’ may lead some grant holders to assume that by simply adopting a gender equality approach on their project the empowerment takes place. Therefore, the fund manager is working on developing a methodology to help grant holders demonstrate the right evidence, by applying a specific scale and measuring their progress against that scale in the first quarter of 2021.

Across all projects, 1,001,112 women were reached during the reporting period, which equates to 53% of total beneficiaries reached.

Output 3.3
This output has significantly missed this year’s target with only 33 projects directly working on disability inclusion against a target of 45. Conversely, this is a significant increase from 19 projects targeting disability inclusion in the last reporting period. This rise is largely due to i) a higher number of applications received with a stronger approach to disability inclusion and ii) greater focus on providing guidance and support to grant holders on disability inclusion during the grant set-up process.

The 33 projects that have been targeting disability inclusion as a primary objective have been split by the fund manager into the following two categories:
1. 16 projects are wholly focused on addressing the issue of disability.
2. 17 projects are targeting people with disabilities as one of multiple primary target beneficiary groups.
The total number of people with disabilities reached by all the 102 projects reviewed during the reporting period was 37,793 (2% of all unique beneficiaries) including 14,957 (5739 female, 5597 male, the remainder did not have gender specified) people with disabilities reached through non-targeted interventions. The total number of projects that are inclusive of people with disabilities but do not specifically target them is 66 out of the 102. Only 2 projects have not focused on disability at all, however one of those is now reporting disability data and reviewing its approach to inclusion. However, the figures are not fully reliable, given the level of disaggregation on the programme remains a big challenge (as per output 3.1 above).

Output 3.4
This output has slightly missed this year’s target maintaining the same level of performance as in the previous year. In total 30 projects reported an increased level of knowledge among 28,580 unique beneficiaries. The target was missed due to delays in training caused by COVID-19 and grant holders overestimating. The fund manager is looking to improve this process through stronger interrogation of targets during grant set-ups and quarterly meetings.

During this reporting year, an increase in beneficiary knowledge has been reported equally by all relevant grant holders, focusing on the effectiveness of training and not just training delivery. The evidence was gathered through logframe reporting, where the effectiveness of a wide range of training is being measured at an individual grant level.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Currently, due to limited beneficiary data disaggregation conducted by grant holders and the lack of appropriate UKAD logframe indicators, it is difficult to determine to what extent the programme is inclusive. For the same reasons, it is also difficult to determine which of the most marginalised populations have been reached by the individual interventions against the targeted populations, deemed appropriate during the application stage – this is one of the weakest aspects of the programme. Improvements in this area are essential to ensure the interventions do not exclude those who are harder or more expensive to reach.

Describe any changes to this output during the past year, and any planned changes as a result of this review

The UKAD logframe will be revisited within 6 months from completing this annual review in line with the recommendations in this report. Any changes to the logframe will be agreed by the UKAD team and approved by the Head of Department.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the previous AR

Guidance on livelihoods should be disseminated, and a livelihoods community of practice established across both UK Aid Direct and UK Aid Match.
Progress: Livelihoods guidance has been developed and shared with grant holders. The microfinance community of practice (CoP) was established in August 2019 and continues to be operational.

Revise logframe guidance to stress the importance of providing relevant evidence and data to demonstrate the results of the indicators and how they contribute to the project outcomes.
Progress: The revised logframe guidance was introduced in September 2019 and various webinars on monitoring, evaluation and one-to-one support have been delivered.

Guidance should be disseminated on how to track, measure and report on gender empowerment.
Progress: Relevant guidance was shared with grant holders. A rapid review of reporting and measuring gender empowerment will be conducted in the next reporting period, which will be used to update indicator 3.2.

More support should be provided to grant holders in order to encourage and empower them to measure and report on the impact of training.
Progress: Logframe guidance has been updated and shared with grant holders, focusing on measuring results and impact. Grant holders have also received one-to-one support. This resulted in 31 logframes capturing and reporting on effectiveness of training.

The fund manager will work with grant holders to understand the challenges and limitations of beneficiary data disaggregation.
Progress: A new reporting template was introduced in June 2020 with guidance. The Accountable Grant Arrangement has also been updated to ensure data disaggregation is a clear requirement for all grant holders. The new template at minimum requires disaggregation by sex, disability and age. The fund manager then actively encourages disaggregation by other characteristics (depending on the project).
Lessons learned this year

The key lessons from the three impact grant holders are that working with local leaders to select and mobilise community members/beneficiaries supported engagement and enabled project staff to focus expertise on activities requiring technical guidance (e.g. agriculture). Also supporting local community-based organisations (CBOs) to deliver services (such as livelihood support services) and build capacity has enabled strong beneficiary engagement.

Grant holders are reporting gender empowerment in different ways and demonstrating different degrees of impact. The fund manager will amend the methodology of the gender empowerment indicator to reflect a sliding scale of the impact which will capture the extent to which projects are strengthening gender empowerment. The new reporting template has provided additional disaggregated data but grant holders need further support on demonstrating how inclusive their projects are. In the next phase, the fund manager will assess effectiveness of the approach to inclusivity at a portfolio level.

Although monitoring of the increase in knowledge has improved, there is still room to strengthen the collective impact across the portfolio by stronger interrogating of indicators at grant level by the fund manager, in order to lead to greater sustainability and a better contribution towards the Global Goals. Relevant guidance will also be shared with those grant holders identified to be monitoring inputs rather than impact, which is usually the case for SCCF, or new, less experienced grant holders.

Recommendations for the year ahead

A systematic approach to LNOB will be developed, including a strategy for monitoring, to ensure data is collected and disaggregated across all key programme strategic areas and beyond primary characteristics such as gender and disability.

The programme should incorporate an additional indicator to measure the effectiveness in disability inclusion in line with a twin-track approach i.e. measure effectiveness of all grants for implementing disability inclusive approaches where people with disabilities are not a primary target group across all strategic areas of the programme. This would be measured alongside the existing indicator 3.3 (developed for specific interventions).

The effectiveness of the approach to beneficiary data disaggregation needs to be reviewed mid-point during the next reporting period, in order to reflect on any lessons emerging from the new reporting template and, where appropriate, adjust the methodology.

Output Title	Shift in social attitudes and behaviours resulting in positive norm change in targeted groups
Output number:		4	Output Score:	A+
Impact weighting (%):		10	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1. Number of beneficiaries reached with behaviour change communications promoting positive norm change	Unique:493,032	Unique: 776,636 / Female: 88,046 / Male: 75,502 / People with disabilities: 109 / BCC events: 411
4.2. Number of beneficiaries implementing positive behaviour change in the communities where CSOs are working	Unique: 177,491	Unique: 236,532 / Female: 18,517 / Male: 13,304 / People with disabilities: 680

Briefly describe the output’s activities and provide supporting narrative for the score

Within this output both indicators have moderately exceeded the anticipated targets – this is a substantial progress, although targets for this year were significantly lower compared to last year, because fewer live projects within the portfolio were undertaking behaviour change communication (BCC) interventions (35 projects contributed to this indicator last year compared to 23 this year).

Output 4.1
There are three large Impact grants and a JCMG Network grant that are contributing to this indicator. These projects are tackling significant norm change in addressing IBV, raising awareness about good hygiene to prevent eye disease, promoting good handwashing practices and advocating for women’s economic, social and civic rights. Some of the projects’ success was driven by effective training, engagement with local markets, access to additional advice from local traders and engaging local government/civil servants in the training to support wider dissemination and knowledge change.

The beneficiaries reached under those four grants are as follows:
- Afghanaid: 350,770
- Fred Hollows: 144,720
- AIPG: 139,000 (JCMG)
- United Purpose 57,177

In previous years, we have seen that the largest contributors to this indicator are health projects; in this reporting period health projects contribute 29% of this logframe indicator, while livelihoods projects contribute 45% and conflict resolution and gender-based violence prevention contribute 22%.
There are several SCCF grant holders delivering behaviour change communications to promote positive norm change, however none have submitted monitoring data during the reporting period.

Output 4.2
There are 18 projects that contribute to this indicator, of which five contribute significantly. These grant holders focus on nutritional and food security behaviour change and improvements in WASH practices. Examples of evidence from these five projects include 198,537 people adopting handwashing as a result of the project, 12,398 people demonstrating good hygiene and sanitation practices promoted by the project and 9,650 investing in irrigation pumps and benefiting from increased production of food and income.

The intended positive change in social norm or behaviour requires measuring at outcome level over a longer period of time and therefore, it is difficult to evidence this annually. To address this challenge, in the next reporting period the fund manager will continue to guide grant holders to have proxy indicators (particularly at outcome level for this indicator).

Next year, more live JCMG grant holders are expected to report positive behaviour change and so the milestone for this indicator is likely to increase.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Key aspects of the VfM of BCC interventions are the effectiveness and reach of the messages. Therefore, in the next reporting period, the fund manager will put in place guidance for grant holders to provide better quality disaggregated data on the reach of their BCC, so it can be assessed whether it is adequately targeting the right audience, and improve their reporting on the effectiveness of the BCC. However, it is evident from this year’s results that necessary data has been provided to demonstrate the overall reach of BCC interventions.

Describe any changes to this output during the past year, and any planned changes as a result of this review

The UKAD logframe will be revisited within 6 months from completing this annual review in line with the recommendations in this report. Any changes to the logframe will be agreed by the UKAD team and approved by the Head of Department.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the previous AR

Assess the degree to which the UKAD3 and JCMG grant holders will be delivering social norm change interventions and amend the output to include only indicator 4.2 if more relevant.
Progress: Analysis of the UKAD3 and JCMG grant holders indicates that the majority (64%) of JCMG Network grants are monitoring social norm change, with an additional 27% measuring positive behaviour change.

Revise the methodology used to capture data on Output 4.2 to measure small scale changes in behaviour and support grant holders to measure these changes.
Progress: Due to the temporary FCDO funding pause which delayed some grant set-ups, this milestone has not been updated. This will be reviewed for year six to reflect the anticipated results from the JCMG grants.

Lessons learned this year

Although many grant holders are delivering behaviour change interventions, few have monitored these changes within their logframe during the reporting year. This is often because BCC is monitored only at outcome level and therefore data is not available until the final year of the project, when BCC results are reported through PCRs. Not many projects ended in this reporting period and those that did, did not significantly contribute to this output. Additional guidance will be shared with grant holders to allow them to include appropriate proxy indicators that monitor progress annually.

Recommendations for the year ahead

Appropriate SCCF logframe indictors to be agreed to measure the reach and effectiveness of BCC activities against the portfolio logframe. The reporting templates and guidance for SCCF grants will be reviewed to include regular results data.

In order to effectively reach and impact the most marginalised groups with BCC, the fund manager should work with grant holders to ensure they provide disaggregated data that demonstrates their BCC are reaching the most marginalised and providing credible evidence of change resulting from their BCC.

Output Title	Improved delivery of interventions as a result of shared evidence and learning within the fund
Output number:		5	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
5.1. Number of grant holders attending webinars or workshops	90%	95%
5.2. Number of grant holders contributing to learning materials and learning events	40%	38%

Briefly describe the output’s activities, and provide supporting narrative for the score

This output slightly exceeded on the first indicator and marginally underperformed on the second one. A similar level of performance has been maintained on this output compared to last year’s results. During the reporting period, 32 webinars and workshop events were delivered, of which 90% were delivered for grant holders whilst 10% were for applicants.

Output 5.1
This output has exceeded this year’s target by 5%, increasing the overall performance from 71% last year to 95% this year. In total 37 webinars and workshops have been delivered, aimed at providing support and capacity building to existing grant holders, as well as four reference group sessions – this is a significant increase compared with last year. These events were attended by 2,159 participants representing 131 grant holders. The fund manager has also held one in-country learning event in Sierra Leone to facilitate networking and learning between the fund manager, grant holders and downstream partners of both UK Aid Direct and UK Aid Match.

In response to grant holders’ demand, a microfinance community of practice has been established. The community of practice has proven to be successful based on the learning report undertaken by the fund manager in May 2019 and options for developing similar groups across other portfolio areas are being currently explored.

Output 5.2
During this reporting year a total of 53 (38%) grant holders out of 138 in total have significantly contributed to this output by sharing their lessons through 31 webinars (on average one webinar every 1.5 weeks). This is an 8% decrease compared to last year’s results. Grant holders contributing to webinars have been selected depending on the topic and the topic has been decided either as a result of an identified gap during grant management, or in response to requests coming directly from grant holders.

In addition, feedback from the microfinance community of practice highlighted that grant holders find presentations from other organisations active in the field most useful and use it to modify their programmes. The Sierra Leone learning event also highlighted the importance of country specific events in increasing the involvement of implementing partners in sharing learning. The fund manager plans to conduct a follow-on survey for those that attended the event to understand impact.

Lessons continue to be also shared informally through Reference Group meetings.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The ability of the fund manager to flexibly adapt to the changing context and priorities and effectively generate and use relevant learning in response, is an important component of UKAD. In order to ensure VfM is maximised through learning, a stronger focus on utilising learning in decision making at strategic portfolio level will be required. A greater emphasis on gathering learning related to the wider development impact when delivering through CSOs would also be beneficial. Overall effectiveness of learning should be measured through the decisions and changes made as a result of learning and as part of a continuous process, maximising processes such as quarterly, annual and project completion reports.

Describe any changes to this output during the past year, and any planned changes as a result of this review

The UKAD logframe will be revisited within 6 months from completing this annual review in line with the recommendations in this report. Any changes to the logframe will be agreed by the UKAD team and the Head of Department.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the previous AR

Develop a specific strategy to bring out the learning from projects that have finished and use their experiences to drive current implementation.
Progress: A clear strategy for disseminating the learning from grants and fund management from the last 5 years of the UKAD to be developed as per recommendations in the summary section.
- Consider how to incentivise grant holders into greater sharing of learning for the next phase of UK Aid Direct.
- Progress: The microfinance CoP has been successful. As part of a revised learning strategy, the fund manager will explore further incentives.
- Encourage grant holders to share their latest findings with the fund manager for onwards dissemination and discussion either on the website or in the newsletter or on Facebook.
Progress: A closed Facebook group had been created. However, it proved not to be particularly effective, so it was closed. Through the newsletter itself grant holders have been asked to share learnings.
Commission short learning analysis in specific areas of interest such as accountability and gender empowerment.
Progress: A short learning analysis has been commissioned on beneficiary feedback mechanisms and accountability, which had identified further areas for improvement to beneficiary engagement. An analysis on gender transformation has been planned for the second quarter.

Lessons learned this year

The key challenge with this output is demonstrating improved delivery as a result of effective evidence sharing and learning, based on the existing indicators. The current assessment of this output makes a significant assumption that the participation in learning events and sharing of learning by individual projects will lead to enhanced delivery, as the fund manager has not been systematically evaluating the impact of the adaptations made by grant holders as a result of learning.

Most contributions to learning events continue to be from live projects. It remains challenging to encourage those with projects that are ending to participate and share their findings. However, a pilot approach has been developed specifically for SCCF by establishing an alumni network. If successful, it will be rolled out across the portfolio. In addition, SCCF grants report against specific SCCF targets only every 6 months (and this is proportionate to the size of SCCF grants) but the reporting is inconsistent and of a low quality.

On the other hand, increased use of new digital technology such as WebEx has resulted in an increase in grant holder and downstream partner engagement, particularly at reference groups (where attendance at virtual events has increased by 6%).

Recommendations for the year ahead

An additional capacity building indicator for SCCF will be added under this output e.g. ‘Number of Small Charities Challenge Fund (SCCF) grant holders achieving a high score for quality of reporting (high score definition TBD).’ This is to ensure that there is clear evidence of how SCCF is contributing to the overarching logframe and UKAD outcome.

Based on the results of this year’s OCAs, lessons learned, and FCDO’s needs and priorities, the fund manager will develop an annual capacity building strategy, together with an updated learning offer. This is to ensure that the UKAD investment is maximised by focusing on areas of highest priority and impact. The learning offer should distinguish between the different needs of SCCF, UK-based and southern-based organisations.

Based on the evidence from the existing indicators, it is difficult to conclude whether the delivery of interventions has improved because of shared evidence and learning within the fund. Therefore, this output should shift from measuring several learning events and their attendance at input level, to more meaningful and results orientated indicators that are targeting specific gaps and/or learning objectives, critical to the overall programme success e.g. ‘Increased effectiveness on beneficiary data disaggregation across UKAD strategic areas’. These would have to be supplemented by qualitative data coming out of exit surveys and evaluation questionnaires.

Output Title	Improved access to flexible, responsive and adaptive funding
Output number:		6	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
6.1. Proportion of support (grants) going to small sized organisations (under £1m turnover)	20%	70%
6.2. Proportion of grants going directly to recipient country based CSOs	22%	14%
6.3. No of organisations that are newly funded by UK Aid Direct	Unique: 65	Unique: 80
6.4. Proposals funded as a result of focused element of a call	Yes	Yes
6.5. Proportion of successful grant holders expressing satisfaction of quality of fund management from an annual survey	80%	95%

Briefly describe the output’s activities and provide supporting narrative for the score

Overall, output indicators 6.1 and 6.5 have significantly exceeded the target; indicator 6.2 has not met expectations; indicator 6.3 has moderately exceeded expectations; and indicator 6.4 has met expectations.

Output 6.1
For this indicator, the data has been analysed from the 138 grants that were live at the time. This output continues to exceed the target this year by supporting 70% (96 grants) of small size organisations below the £1m threshold mainly through SCCF3 and 4, plus JCMG Strengthening grants (up to £1m) which went live during this period too.

Output 6.2
Only 14% of grants went directly to the recipient country based CSOs during this reporting period against the 22% target. This has been a decrease compared to last year’s results.

In UKAD Round 3, southern-based organisations were awarded three Impact grants and six JCMG grants. In UKAD Round 4, out of 894 eligible applications, applications from southern-based CSOs made up 67% of all eligible proposals. Out of all 601 eligible southern-based applications received at the concept note stage, a total of 36 were taken through to full application stage, and only six were shortlisted to a funding award. On average southern-based applicants received a high fiduciary risk rating at the concept note stage which ruled them out of the full application stage. Those making it through to the full application stage were then scoring below their peers based on the technical assessment of the proposal.
The fund manager has been analysing each funding round in detail, to identify the areas of weaknesses across all applications and share the lessons learned during application webinars, so that applicants can address those in their prospective applications.
Output 6.3
This year’s output has been moderately exceeded by reaching 15 additional organisations (who were newly funded) over and above the target, almost doubling last year’s results. This was mainly due to implementing a more intensive communications and outreach strategy and feedback from past applicants. The 80 grant holders new to FCDO are made up of: UKAD2 (16), UKAD3 (11) JCMG (10) and SCCF (43). UKAD4 grants were not included in the milestone for this year as they were not active at the time of reporting.

The results for this indicator are self-reported by applicants during the application process, however a more thorough review conducted by the fund manager showed up discrepancies in this data, making the end results unreliable. The fund manager is looking to review the questionnaire to address the issue.

Output 6.4
During the last reporting year, the fund ran a specialised, focused call on an urban poverty theme. A theory of change was developed with the then DFID policy team and guidance shared with applicants. Applicants in UKAD4 were asked to estimate the percentage of beneficiaries based in urban, peri-urban and rural areas, with applications for projects working in urban areas particularly encouraged. Projects whose target 50% or more beneficiaries in urban areas were categorised as urban-focused projects. Overall, 16 urban-based projects totalling £14 million, across 11 countries and 9 technical sectors were selected for funding.

UKAD4 also focused on menstrual hygiene management (MHM), resulting in seven MHM projects totalling £6.5 million have been awarded funding.

As all those projects are yet to start, it is too early to draw any lessons learned from the focused theme projects.

Output 6.5
A survey carried out amongst all active grant holders in July 2020 showed that 95% of respondents (15% above this year’s target) rated the fund management consortium with a three or above out of five, with regards to overall satisfaction - this is an 8% increase in satisfaction from last year’s results.
Respondents particularly valued the fund manager’s support in the areas of compliance, technical assistance (project design, monitoring, evaluation and learning, logframes, theory of change), and financial management (budget and claims); whilst findings show that improvements could be made in the areas of due diligence and capacity building. An action plan from the survey has been drafted and it will be discussed with FCDO in the next quarterly meeting.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The effectiveness of communication strategies implemented by the fund manager has been reflected in a significant increase of the small and new organisations within the UKAD portfolio, directly contributing to Outcome 1. At the same time, the target for southern-based organisations hasn’t been met for the second year in a row. As per the earlier recommendations, further incentives/approaches to accelerate progress against this target should be developed. However, given the limited scope and resources of the current programme, weighing potential capacity building efforts will be necessary.

In addition, given that the majority of applications were submitted to UKAD from the southern hemisphere and only 1% of applicants have actually been awarded grants, the application process demonstrates a small return on the investment made by southern CSOs.

Describe any changes to this output during the past year, and any planned changes as a result of this review

The UKAD logframe will be revisited within 6 months from completing this annual review in line with the recommendations in this report. Any changes to the logframe will be agreed by the UKAD team and approved by the Head of Department.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the previous AR

Milestone 6.1 will be revised upwards significantly from 20%.
Progress: Due to a delay in the launch of the next stage of the SCCF, this was not updated. Revisions have been proposed as part of the next logframe update.

In future funding rounds consider a targeted outreach campaign to reach specific defined diverse audiences.
Progress: UKAD4 focused on urban poverty and menstrual hygiene management.

The fund manager should strengthen communications between grant holders and the grant management team and review whether the grant set up process can be streamlined.
Progress: The portfolio oversight has been reviewed and additional monitoring measures introduced e.g. a dedicated SCCF Performance and Risk Manager. The grant set-up process has also been streamlined and welcome pack for grant holders launched.

The fund manager should work with grant holders to better understand what kind of technical assistance they need.
Progress: Grant holders have been consulted and targeted support on disability inclusion and safeguarding has been delivered as a result.

The UKAD team should consider how to streamline the reporting process whilst still having an appropriate level of assurance over risk, especially for SCCF grant holders.
Progress: Both the annual review and quarterly reporting processes have been reviewed with relevant templates and guidance also updated. The project completion process is currently under review.

The next phase of UKAD should consider suitable indicators to measure the outcome of adaptive programming.
Progress: This will be considered during the set-up phase of the new programme that yet to be procured.

Specific indicators which measure the overall quality of performance of the SCCF/JCMG grants rather than their specific contributions to these outputs will be introduced.
Progress: The SCCF progress reporting process is undergoing a review. Measures for assessing the quality of reports will be incorporated within this process. Once a baseline is established in late 2020, indicators and milestones will be proposed.
Lessons learned this year
The fund manager has been actively looking for ways to attract greater numbers of quality applications from southern-based organisations and promote greater localisation through conducting the funding rounds analysis, adapting application process, improving the applicant guidance and undertaking consultation with the AmplifyChange Fund.
Developing specific communication strategies using different language and terminology has proven effective on UKAD4 in increasing the number of new and southern-based organisations and the fund manager will explore how those strategies can be adapted further to target organisations delivering in countries, where there is a gap in the portfolio. In addition, further analysis of the method in which due diligence is conducted will be carried out and learnings and recommendations for further adaptations shared with FCDO.
Specialist calls within a broader call are in high demand and strategies for future themes will be developed based on portfolio gaps and potential FCDO priority areas. To ensure the effectiveness of the future thematic rounds, it will be important to draw on lessons learned and VfM of the thematic rounds conducted to date.
Recommendations for the year ahead

The UKAD team will analyse the existing application process to increase access to funding for southern-based CSOs in future funding rounds e.g. positive discrimination approaches should be considered, given the significant disparities in capacity levels between southern and northern based CSOs.

The fund manager will conduct a further review of the application and due diligence process by March 2021, to check if subsequent adaptations can improve the fund accessibility and effectiveness of those processes.

Clear lessons learned reflecting on performance, results and VfM from the UKAD thematic windows will be produced by the fund manager to inform future investment decisions. Indicator 6.4 will be removed as it is input based and a replacement will be considered for the next phase based on learnings from the current thematic windows.

D: RISK

Overview of risk management

Risk reporting and management
At a grant level, risk registers and delivery chains have been reviewed by the fund manager on a quarterly basis. At portfolio level, the fund manager is analysing all risks to understand the key areas of pressures against FCDO standard categories and subsequently these risks are reported and discussed by the wider UKAD team on a monthly and quarterly basis.

Audits
An audit strategy is in place to monitor and assess grant holders’ management practice and risk management approach. A total of 55 audits were carried out during the reporting period, an increase of more than 50% from the previous year due to the increased portfolio size. The key issues noted as a result of audits were:
- reclaims due to ineligible costs, overclaims and unevidenced spend
- incorrect salary values reported (both over and under)
- the applied exchange rate methodologies

Due to COVID-19, audits were paused between April and July 2020, shifting mainly to remote monitoring of the portfolio.

Key areas of pressure
Delivery:
- Following the FCDO internal spending review, active grant holders have been asked to reduce 2020/21 budgets by 25%. There is a major risk that this could significantly impact grant holder's project delivery and results, which in turn could impact on the ability of the programme to meet the targets. Stock of the overall progress will be undertaken before the next logframe reporting period.
- There is a major risk that project implementation and monitoring activities will be affected by travel restrictions due to COVID-19, resulting in delays, poor performance, or reduced impact at the portfolio level. Some monitoring trips have been put on hold. A remote technical monitoring framework in consultation with FCDO has been developed and is being piloted from October 2020.
- Due to travel and movement restrictions, there is a major risk that any grants will have a significantly delayed startup, or their proposed project may no longer be viable. This could impact the delivery of results within the original timeframe. The fund manager will work with all provisional grant holders to ensure their projects are viable and adapted to the new circumstances.

Fiduciary:
- There is a major risk that the agreed project budgets for grant holders may significantly reduce as a result of COVID-19 impact on global economy including the exchange rate. An approach to managing these risks has been developed by the fund manager.
- There is an increase in risk of aid diversion to major during COVID-19 due to reduced ability to monitor activities. A fraud risk assessment is being conducted by an external consultant on UKAD, with the results expected at the end of 2020. Any resulting recommendations from the review will be implemented timely.

Safeguarding:
- Whilst all grant holders on UKAD have been assessed as meeting the minimum safeguarding standards, a major risk remains due to grant holders’ capacity and capability to undertake a comprehensive assessment of their downstream partners’ compliance with the standards.
- Formal training on safeguarding was delivered in February 2020 to all UKAD Performance and Risk Managers and Fiduciary Risk Officers. Additional capacity building sessions with grant holders have also been held.
- In addition to due diligence undertaken by the fund manager, all grant holders are now expected to put in place a project specific safeguarding action plan that identifies key delivery risks and mitigating strategies. These are being reviewed prior to signing an agreement and on an annual basis by the Fund Manager.

Changes to risk rating
Overall, the risk rating for the project has increased from Minor to Moderate as a result of this annual review. This reflects the new risks related to the COVID-19 pandemic, which can potentially impact on the timely and safe delivery of interventions and reaching the programme targets. The updated rating also reflects the risks related the declining UK economy and its potential impact on FCDO’s programme budget.

Recommendations for the year ahead

The UKAD team will hold regular strategic conversations related to programme risks to understand key trends, barriers, and adapt the risk appetite e.g. across specific sectors and/or countries, in order to effectively increase access to funding.

The fund manager will ensure that the beneficiary feedback mechanism is fully maximised to effectively manage safeguarding risks, especially when managing projects remotely.

The UKAD team will work over the coming period to define the programme risk appetite to ensure the level of risk appetite is reflective of the UKAD context and enables the effective delivery of the results.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

Programme Management

During the reporting period up till August 2020, FCDO experienced challenges in matching adequate FCDO programme resources to the complexity of UKAD. Despite those challenges, the programme has been provided with strong oversight from FCDO.

The Fund Manager has responded flexibly to adapt to ministerial priorities, FCDO’s requirements and rapidly changing context in the face of COVID-19. The fund manager has very effectively adapted within a short timescale the existing portfolio of grants as well as the new funding round (Round 5) to respond to COVID-19, including launching a Rapid Response specifically for COVID-19. The fund manager has consistently met all quarterly KPIs during the reporting period.

In the upcoming reporting period, it will be particularly important for the fund manager to effectively collaborate with FCDO on disseminating learning from the programme and navigate through the handover process, whilst managing the challenges related to an uncertain financial future of the aid budget.

Quality and timeliness of narrative reporting

During the reporting period, the fund manager has continued to produce good quality reports to meet planned timescales. The fund manager’s ability to adapt and flex to short notice reporting during a challenging period has been impressive. This has enabled the wider team to make evidence-based decisions on key programme issues including responding to COVID-19 and meeting the requirements of the prioritisation exercise.

Quality of financial management

Forecasting remains challenging due to the large numbers of partners in the delivery chain, but the UKAD team continues to robustly manage budgets at all levels and challenging large variances. The fund manager continues to adjust grant holders’ forecasts by 25% to ensure better accuracy on spend/forecasting variances. The programme spend profile remains broadly on track with a financial year.

The fund manager continues to ensure that grant holders record and conduct annual checks on assets as required by FCDO policy whilst a review of the programme’s asset disposal process is currently underway to continue to ensure that any project assets bought with FCDO funds are disposed in a way that represent best VfM.

Dashboard
To improve grant holder monitoring, portfolio learning and effective fund management, a data dashboard has been developed by the fund manager this year. This provides a comprehensive snapshot of fund-wide performance, with the capability to delve into individual grant holder data and findings. Further expansion of the dashboard is planned for 2020/21.

Country Visits
The grants visited during this reporting year had been identified on a risk basis. During the reporting year, Quality Assurance Visits (QAVs) and monitoring and support visits in seven countries were undertaken by local consultants on 19 projects, representing the highest risk and consistently underperforming. These visits have provided useful insights into contexts specific challenges related to projects delivery, delivery mechanisms and provided opportunities to monitor compliance and assess the effectiveness of delivery.
34 face-to-face site visits were undertaken in the UK, mostly as part of the due diligence process. A further 79 due diligence assessments were completed remotely, and two due diligence site visits undertaken outside of the UK. Further visits outside of the UK were postponed due to the COVID-19 pandemic.
SCCF evaluation
In May 2019 an external evaluation of SCCF was commissioned to examine whether SCCF grants make a valuable contribution to international development and how SCCF can improve its design and further cater to the specific needs of smaller organisations.
Findings indicate that the SCCF grant holders address multiple developmental challenges that relate directly to the overall objectives of the fund, whilst filling the gap in development programming not occupied by larger organisations. While the SCCF grants have, in general, strengthened organisational capacity and project delivery, the overwhelming view was that the time and resources needed to apply and be an SCCF grant holder were disproportionately high compared to the funding received. It was highlighted that the SCCF strengthens and professionalises small charities in the sector, preparing them to manage larger grants. The key findings from the SCCF evaluation have contributed to the design of SCCF Phase two and the new capacity development grants.
Impact evaluations undertaken by grant holders
Nine grant holders have self-selected for additional funding to undertake an impact evaluation themselves within their UKAD grant supported by the fund manager. During the year, technical advice has been provided to all participating grant holders following initial data collection. A series of capacity building workshops are planned from September 2020 onwards to support grant holders in the analysis of initial data collection. These are not rigorous external evaluations but capacity building exercises to allow the grant holders to better understand how to undertake impact evaluations supported by the technical assistance and quality assurance provided by the fund manager’s consortium partners.

Value for Money

Economy: Fund management cost
The average fund management cost on the current programme increased from 6% at the time of signing the original contract five years ago, to 8% under the existing amendment (no 3), signed in June 2020. The increase is due to the introduction of four additional grant types including the SCCF grants. With the introduction of very small grants the size of the portfolio increased significantly. This requires a greater input, in terms of running additional and more frequent funding rounds, managing a much larger volume of grants (which increased by 70% since 2019), and more intensive work with smaller partners in terms of due diligence and subsequent capacity building. However, there are economies of scale in terms of the cost per grant type and overall, the fund manager has reduced the average cost per grant by 17% between the original contract and the last amendment.

In terms of key costs, the business case was based on the average cost per beneficiary (CPB) of £13.16 and the average CPB to date is £9.05 CPB although assessed at an application stage it is not tracked and monitored throughout the life of each individual project.

Effectiveness: Application Process
The UKAD programme continues to be in high demand with a two-stage process, designed to award funding only to grantees who can demonstrate the strongest impact they can achieve with FCDO funding. At the concept note stage, the weaker projects and ineligible projects are filtered out allowing stronger, more effective proposals to continue on to the full application stage. VfM is achieved using a competitive process to drive quality of proposals and through the robust assessment of each grant application at both technical and due diligence level. VfM and cost effectiveness are the key assessment criteria.

Equity: Improving access for southern CSOs
There is a target of 65 organisations to be newly funded by UKAD and for 22% of grants going directly to a recipient country-based organisation. However, the key quality criteria must be met regardless of the targets. This explains why the target for the recipient country-based organisations was not met this year (14%). The barriers to achieving this target will be assessed for the next funding round as per the recommendations under output 6.

VfM at a grant level
The grant holders are pro-actively managed by the fund manager through monthly touch-points. In addition, all grant holders report quarterly so the achievement and quality of outputs can be tested. At an annual review stage an assessment of performance against VfM indicators is undertaken.  All projects are regularly risk assessed and reviewed to ensure those with the greatest risk to go off track are monitored closely. Overall, the majority (73%) of grant holders have scored A or above, demonstrating results and impact. This year, the greatest challenge was that many grant holders were funded under SCCF and this was their first year of delivery. Given SCCF grant holders only report against outcome results at a project completion report stage, it was difficult to assess their impact at a shorter-term stage.

Key Challenges

The key challenges in measuring and monitoring VfM relate to using set metrics against a demand led challenge fund, with many shifting and changing parameters that are outside the fund manager’s control. At the grant level, the difficulty lies in balancing the burden and complexity of reporting of individual grant holders with increasing access to the fund and capacity building efforts.

Recommendations for the year ahead

The UKAD team should review the existing asset disposal process to ensure VfM is fully maximised at the end of the grant life.

The UKAD team should explore the most optimum opportunities/decision points for utilising the dashboard for strategic and data-driven decision making.

Cost per beneficiary (CPB) should be tracked and monitored as one of the key costs throughout the life of the project as defined in the original business case. This can be used for intersectoral analysis and benchmarking.

Over the next reporting period, the fund manager should work with an FCDO economist to develop stronger approach to measuring and monitoring VfM on a systematic basis.

Date of last narrative financial report	30 September 2020	Date of last audited annual statement	30 November 2019

Annex A Case Studies

Case study 1: How do we reach people with disabilities living in poverty?
Humanity & Inclusion’s Impact grant-funded project was designed to tackle the exclusion of people with disabilities (PWD) in Bangladesh. It aims to identify and train PWD and their families in livelihoods, enabling them to live sustainably. The project delivers in Barisal, Rangpur, and Chittagong divisions.
Why are PWD living in poverty hard to reach?
Many of these individuals have not previously received support. In Bangladesh, disability is considered a specialist issue. Organisations rarely engage with PWD. This can be due to a lack of understanding or limited capacity to cater for them.
In Bangladesh, local government departments are small, so getting complete information from them can be challenging. In parts of the country, local service providers for PWD have been set-up. They train staff to work with PWD, but even for them finding the best way to contact those in need has been difficult.
How did Humanity & Inclusion reach PWD in Bangladesh?
Through years of trial and error, Humanity & Inclusion have developed a four-step approach to identifying those PWD who are most in need.
- Step 1: Data from the local government is collected and combined with the data held by the disability inclusion organisations working in the local area. This information is then cross-checked with community leaders. The Washington Group questionnaire is used informally at this point.
- Step 2: Representatives from each of the appropriate groups or organisations meet and categorise those identified across a poverty scale.
- Step 3: The delivery team visit individual households to conduct assessments.
- Step 4: The identified list is proposed to local government for final sign off.
Why does this work?
Involving community representatives and Disable People’s Organisations (DPOs) brings together information from a variety of sources. This then helps to classify need, and when supported by a home visit, the personal circumstances of the family and what help or support may be required, can then be ascertained. For example, families led by a woman with a disability (where the man has abandoned them) would be considered more vulnerable.
Humanity & Inclusion have found that once PWD are identified, understanding the context and personal circumstances of an individual through the home assessment can create innovative and tailored solutions, and ultimately impact the successful outcome of the project.
What has been achieved?
The project team have supported 1,237 households in the local community where people with disabilities live. They listened to their beneficiary’s priorities and focused on support that would encourage economic empowerment – allowing the households to support themselves financially.
The project team provided livelihoods training to the households, allowing them to farm their own food and sell any excess. They also looked to educate the local communities on including people with disabilities.
The development of new skills to support financial security has made it easier for people living with disabilities to respond to stressors and shocks in their environments, such as floods or droughts.
Activity has also been seen in the communities where the team worked to raise awareness of disability inclusion. For example, in one area there has been adaptation to a boat allowing those with disabilities access to other communities when the area floods during the monsoon season.
Case study 2: How to build a project that offers value for money to the community and donors
Raleigh International’s UK Aid Direct funded project, aims to increase the success rate of development projects using a social accountability approach and improve the value for money of development spending in several regions of Tanzania, benefitting more than 500,000 people.
The project is empowering over 400 young women and men, including people with disabilities, to monitor development project delivery across 179 communities. These young Tanzanians are also gaining new skills and confidence so they can hold development organisations to account.
Why is development spending not meeting the needs of the community?
Development work, which supports future self-sustainability, is taking place in the Dodoma, Iringa and Morogoro regions of Tanzania. Development projects in these areas, however, do not often ask the community for feedback or address the systems which are most in need of support. This makes it difficult for communities to hold those running the projects to account when problems arise and can lead to groups, such as young people and those with disabilities, not having a voice in how the projects are delivered in their own communities. Raleigh International’s UK Aid Direct project looks to increase the success rate and value for money of development spend in the area and involve those who are often not heard.
How is the project addressing the problem?
Raleigh are empowering young people and people with disabilities as Community Monitors. These individuals are responsible for monitoring projects delivered in their communities. They identify issues with project delivery and log these onto a project specific platform called DevCheck.
The issues are shared at Joint Working Group meetings, they are discussed, and solutions agreed. These groups are made up of locally elected community members.
Identified issues are fixed by the body responsible for the project in question and data is logged in DevCheck to show the problem has been resolved. The Joint Working Groups feedback on fixes made, to the entire community through meetings or via community notice boards.
Has this worked? Are the community and the donors getting better value for money?
Raleigh International is supporting around 528,500 young people over a four-year period, with a grant value of just over £1 million. That represents a cost of £1.89 per beneficiary over the project’s lifetime. The organisation believes that increasing social accountability is an efficient investment in the community, and even more so in communities where external investment development projects have otherwise minimal accountability structures in place.
The Community Monitors, alongside other project volunteers known as Youth Cluster Coordinators and Campaign Coordinators, have brought social accountability to life in their communities, working enthusiastically and confidently to identify issues with development projects. In July 2020, the halfway point of the project, 1874 issues had been logged and 68% of these had been resolved. The number of issues that have been fixed is currently above target and the estimated value of the projects being monitored to date is over £14.5 million. When asked, 66% of community members said they have confidence that the processes put in place by the project are holding development projects to account in their communities.
Overall, this project is making sure projects in these communities deliver what the communities need. They are making sure they work well with beneficiaries and embed changes that the community will be happy to embrace. All this delivers good value for both beneficiaries and donors.