Business Case

Summary Sheet

Title: Zimbabwe Reconstruction Trust Fund (ZIMREF)
Project Purpose: To contribute to strengthening of government systems for reconstruction and development by providing resources for analytical and policy studies and programme investments. This will improve the business environment for growth, strengthen government systems for service delivery, improve resilience and human development, inform policy dialogue and re-engagement with the Government of Zimbabwe, and strengthen donor coordination and World Bank capacity in country over the coming five years.
Programme Value: £10m		Country/ Region: Zimbabwe
Senior Responsible Owner: Benedit Latto
Project Code: XXXXX	Start Date: 1/2/15	End Date:31/12/19
Quest Number: XXXXX

Intervention Summary (2 Pages)

What support will the UK provide?

The UK will provide £10m over 5 years to contribute to strengthening of government systems for reconstruction and development, with a focus on systems and capacity development and analytical and policy support, through the World Bank’s Zimbabwe Reconstruction Trust Fund (ZIMREF).

What are the main programme activities?

ZIMREF programme activities are analytical work and policy studies, as well as more programmatic support in four broad areas:
   (i) Private Sector Led Growth: Support will be provided to national and efforts to improve the business environment in Zimbabwe. Special focus will be on employment generation and reforms that would unlock the private sector potential to contribute to poverty reduction.
   (ii) Government Systems and Capacity Development: The window will finance activities that would strengthen public sector management systems, institutional reforms, enhance capacities for greater efficiency, effectiveness and accountability in services delivery for its citizens. There will also be focus on activities that promote demand side accountability.
   (iii) Resilience and Livelihoods Support: This window will support activities that would contribute to social and economic investments for reconstruction and development, including safety nets and improved livelihoods.
   (iv) Analytical and Policy Support: This window will support analytical work that is not specifically related to activities that are supported by the thematic windows but are essential for future reconstruction and development of Zimbabwe.

DFID’s contribution will focus, at least initially, on the fourth component. Support to the first component will be via the Business Enabling Environment Programme (approved in June 2013) while the Productive Safety Net component of the Livelihoods and Food Security Programme (approved in May 2013) would fall under the third component of ZIMREF.

Why is UK support required?

The World Bank has no lending programme in Zimbabwe due to Zimbabwe’s arrears to the World Bank. ZIMREF represents the main vehicle for World Bank engagement and for implementing the World Bank’s Interim Strategy in Zimbabwe. UK support to its predecessor (the Analytical Multi-Donor Trust Fund, co-chaired by DFID and the World Bank), coupled with a comparatively strong complement of technical staff, enabled the UK to significantly shape the allocation and use of available resources. DFID is widely expected – by the World Bank and by other development partners – to play a similarly significant and leading role in ZIMREF. Not doing so would not only reduce resources available for potentially transformative policy advice and technical assistance, but limit our own influence and programme effectiveness, and reduce the effectiveness of the World Bank and access to their technical expertise.

What are the expected results?

The main expected results (following the four components of ZIMREF) are:

- Improved growth conditions that are related to business environment especially financial markets, infrastructure development (energy water and sanitation) and productivity;
- Strengthened core systems for public management and service delivery;
- Enabling environment promoted for reducing vulnerabilities, improving resilience and strengthening human development;
- Foundations laid for re-engagement by development partners and World Bank in Zimbabwe. Don’t like this.
- Improved understanding of
- Robust, effective and timely advice provided on key issues

In addition, ZIMREF is expected to deliver:
 - improved donor coordination and WB capacity in country

How does the project fit with the country programme or department’s strategic objectives set out in the Operational Plan?

The programme is a key element of DFID Zimbabwe’s governance strategy and Operational Plan. It will be complemented by (and strengthen) two related governance programmes, and also support our wider programme in Zimbabwe by i) strengthening both the enabling policy environment and the donor coordination framework, and ii) positively impacting on DFID Zimbabwe’s programmes in economic development, productive safety nets and service delivery in particular.

What are the key risks to the success of the programme?

The most significant risks to delivery and programme success concern the political and economic environment that may prevent programme investments or reduce their effectiveness, or make the Zimbabean Government unable or unwilling to implement key policy reforms. Weak programme management may also compromise programme success. These will be closely monitored, with flexibility in ZIMREF design allowing for the programme to be scaled back (and contributions reduced) if necessary. Fiduciary and reputational risks are considered low owing to the rigour of World Bank procedures.

Strategic Case

A. Context and need for a DFID intervention

Overarching Context

Zimbabwe’s economic recovery after a decade of collapse (2000-2008, during which GDP halved) remains fragile. An initial rebound (2009-2012) has been followed by slower growth (3% or lower) due to a range of supply-side constraints, loss of competitiveness, high cost of capital, weak property rights and an uncertain political and policy environment which has further inhibited investment. High levels of external debt and arrears have limited access to finance and the engagement of the International Finacnial Institutions, with World Bank activities largely confined to the provision of technical and advisory support through the Analytical Multi-Donor Trust Fund (A-MDTF) to which DFID was a key contributor. The political context remains difficult following disputed elections in July 2013. Core state capability is constrained by political capture, erosion of capacity, weak public financial management systems and resource constraints for service delivery.

Despite this a process of re-engagement that commenced under the Government of National Unity (GNU) has continued under the current ZANU-PF government following their election in July 2013. An IMF Staff Monitored Programme (SMP), agreed by the GNU in June 2013, was sucesfully concluded in September 2014 paving the way for a successor 15 month SMP. The World Bank’s third Interim Strategy Note (ISN, 2013-15) was approved by the World Bank Board in April 2013 while ZIMREF (Zimbabwe Reconstruction Fund) was approved by the World Bank Board in May 2014. In October 2013, The Government of Zimbabwe published its “Zimbabwe Agenda for Sustainable Socio-Economic Transformation” (ZIM-ASSET), and has been working with development partners, including the World Bank, to develop this into a shorter term, more operational plan.

What the Programme Will Do

DFID will contribute to ZIMREF as the replacement for the A-MDTF and main instrument for implementing the World Bank’s third Interim Strategy Note. ZIMREF provides a vehicle for both further analytical work and policy studies, as well as more programmatic support in four broad areas:

   (i) Private Sector Led Growth: Support will be provided to efforts to improve the business environment in Zimbabwe. Special focus will be on employment generation and reforms that would unlock the potential of the private sector to contribute to poverty reduction. Current World Bank proposals indicate that this could cover investment climate reforms, small and medium enterprise development, agriculture, land policy, energy, irrigation, transport, mining, higher education and public private partnerships

   (ii) Government Systems and Capacity Development: The window will finance activities that would strengthen public sector management systems, institutional reforms, enhance capacities for greater efficiency, effectiveness and accountability in services delivery for its citizens. There will also be a focus on activities that promote demand side accountability. Current World Bank proposals indicate that this could cover public financial management/procurement reforms, civil service reform, statistical capacity building, urban & small town water and sanitation, environmental management, and trade facilitation.

   (iii) Resilience and Livelihoods Support: This window will support activities that would contribute to social and economic investments for reconstruction and development, including safety nets and improved livelihoods. Current World Bank proposals indicate that this could cover social protection, safety nets, food security, community development projects, rural water, basic education, health, pension reform and climate resilience projects

   (iv) Analytical and Policy Support: This window will support analytical work that is not specifically related to activities that are supported by the thematic windows but are essential for future reconstruction and development of Zimbabwe. Current issues being considered include reform of State Owned Enterprises, support to updating the mining fiscal regime, statistical capacity building and the provision of advice and support on climate change.

The Case for a DFID intervention

DFID was the largest individual contributor to the Analytical Multi Donor Trust Fund (providing c.30% of the $23m total resources 2009-2014) and was able to use this and its role as co-chair, supported by a comparatively strong complement of technical staff, to significantly shape the allocation and use of available resources. DFID is widely expected – by the World Bank and by other development partners – to play a similarly significant and leading role in ZIMREF. Not doing so would not only reduce resources available for potentially transformative policy advice and technical assistance, but limit DFID’s own influence and programme effectiveness, and reduce the effectiveness of the World Bank and access to their technical expertise.

Strategic Fit

A contribution to ZIMREF, is a key element of DFID Zimbabwe’s governance strategy, itself a central pillar of DFID-Zimbabwe’s Operational Plan. It will be complemented by (and strengthen) two related governance programmes, the first aimed at supporting Zimbabwean civil society and media efforts across a number of key governance priorities (approved June 2014), the second at strengthening state oversight and accountability mechanisms (to be designed). ZIMREF will also complement and support DFID’s wider programme in Zimbabwe by strengthening both the enabling policy environment and the donor coordination framework, and positively impacting on DFID Zimbabwe’s programmes in economic development, productive safety nets and service delivery in particular. Initially the resources of this business case will be targeted to the fourth window to ensure that DFID resources are compliant with our funding policy of not putting money through GoZ systems.

Gender Equality

Zimbabwe is a highly patriarchal society, with women facing discrimination and exclusion in many areas of society, often disadvantaged in terms of access to services and opportunities. Women’s representation and participation at all levels, from positions of leadership through to intra-household decision making, remains fairly low. Levels of exclusion of other marginalised groups (e.g. the poorest in society, disabled and chronically ill people, young people, elderly people) are often even higher, or simply not well understood due to a lack of information and debate. Official statistics and analysis are frequently not designed to address questions affecting women and other marginalised groups, and as a result, analysis of specific issues affecting these groups is not possible. Public policies often remain ‘blind’ to gender and social inclusion issues, either in how they are initially framed or in how they are eventually implemented.

ZIMREF will ensure that gender, and other potential dimensions of social exclusion, are reflected in the selection and design of specific projects and analytical studies to be supported. This will be done through ensuring that the social aspects of the environmental and social screening process are sufficiently robust, adjusting the results framework to reflect gender and social inclusion dimensions more strongly, and that there is sufficient consideration of specific programming to analyse and address gender and social inclusion issues where appropriate.

B. Impact and Outcome that we expect to achieve

Impact: Faster economic growth and poverty reduction

Outcome: Strengthened Zimbabwean systems for reconstruction and development

Intermediate Outcomes: These objectives will be met through analytical work and investments in the four ZIMREF components: private sector led growth, government systems and capacity development, resilience and livelihoods support, and analytical and policy support. Each generates a “result area” as listed below that might be considered as “intermediate outcomes”. A fifth area covering enhanced donor coordination (in line with ZIMREF documentation) and WB capacity in country (an important objective given the arrears-induced constraints on their activities) has been added.

1. Improved growth conditions that are related to business environment especially financial markets, infrastructure development (energy water and sanitation) and productivity
2. Strengthened core systems for public management and service delivery
3. Enabling environment promoted for reducing vulnerabilities, improving resilience and strengthening human development
4. Robust, effective and timely advice provided on key issues
5. Improved donor coordination and WB capacity in country

## Appraisal Case

A. Options to achieve outcome

Option 1: Contribution to World Bank ZIMREF
This would allow the UK to continue to play an influential role in shaping the use of not just our but also other donor resources to support the policy and reconstruction agenda, would facilitate access to a wide range of technical expertise, and would strengthen the voice and in country capacity of the World Bank as a key partner with the Government of Zimbabwe.

Option 2: Bilateral programme of support
Previous Annual Reviews (in 2012 and 2013) of the “Strengthening Capable Government Programme – which funded support for Pubilc Financial Management in the Ministry of Finance and DFID contributions to the Analytical Multi Donor Trust Fund - recommended that further support be provided through a single pool or trust fund. This is more likely to improve coordination and our ability to input to a wider range of activities, draw on a broader range of expertise and reduce overall transaction costs in line with the wider aid effectiveness agenda.

Option 3: Do Nothing
This option would entail no DFID resources being used to provide potentially transformative policy advice and technical assistance. It would also limit DFID influence and programme effectiveness, and reduce the effectiveness of the World Bank and access to their technical expertise.

B. Costs and Benefits: Economic Appraisal

A number of other donors have so far indicated an intention to contribute to the ZIMREF as follows:
 - EC: Euro 5-10m (c.$7-14m) over 5 years;
 - Norway: $5m over first 2 years;
 - Sweden: $5m over 5 years;
 - Denmark: $1m (initially, first year);
 - Germany: $1m (initially, first year);

A UK contribution of £10m (c.$17m) over 5 years (£2m p.a.) would bring total commitments to $36-43m, with DFID accounting for about 30% of annual contributions of around $11m (assuming similar contributions in outer years from those currently committing for first 1-2 years only). This represents an appropriate commitment, again making the UK the largest individual bilateral contributor, consistent with our previous share of the Analytical Multi Donor Trust Fund, and representing a modest but influential share (c.2.5%) of DFID’s expected annual programme in Zimbabwe.

In addition to these sums:
 - the World Bank is seeking to secure an initial $10m contribution from its State and Peace Building Fund to channel through ZIMREF.
 - DFID anticipates using the World Bank as an implementing partner for specific components under two previously approved Business Cases: the Business Enabling Environment Programme (approved in June 2013), which would fall under the first component of ZIMREF on private sector development (c. £3m over 2 years); and the Productive Safety Net component of the Livelihoods and Food Security Programme (approved in May 2013) which would fall under the third area of ZIMREF on resilience and livelihoods support (c. £10m over 4 years).

Economic Appraisal
The expected benefits cannot be readily quantified or monetised, and will depend on both the specific activities to be supported and the extent to which they result in accelerated growth and/or improved efficiencies of public spending. However, based on an annual DFID spend of £2m, GDP would have to be 0.0025% higher, or annual public spending 0.08% more efficient, for the benefits to outweigh the costs of DFID’s contribution. This assumes, very conservatively, that there will be no sustained benefits of each year’s investment. The breakeven thresholds would be reduced by a factor of 10 if it was assumed that DFID’s ZIMREF investments led to cumulative and sustained increases in GDP or public spending efficiency. While there is no firm evidence to confirm this, benefits in excess of these thresholds seem plausible.

Multi-Criteria Decision Analysis
Drawing on the key differences between the 3 options, a Multi-Criteria Decision Analysis (MCDA) was undertaken to ascertain which of the 3 options is the most desirable. MCDA is typically utilised when it is difficult to quantify a precise numerical benefit associated for a group of options. As an alternative, various options for achieving a particular objective are ranked and scored against key indicators. In this instance the 3 options have been ranked against 3 key objectives for the project which are weighted equally in the overall score. Option 1 achieves a larger score than the other 3 options for each of the 3 key objectives of the programme. As a result the MCDA clearly shows that option 1 is the preferred option.
[note] http://webarchive.nationalarchives.gov.uk/20130129110402/http://www.hm-treasury.gov.uk/green_book_guidance_mcda.htm

Figure 1: Multi Criteria Decision Analysis for ZIMREF

	Option 1	Option 2	Option 3
Improved donor coordination and harmonisation	10	4	NA
Greater influence of UK in shaping use of our and other donors resources	8	4	NA
Scope to scale up support to more successful ventures	8	4	NA
Weighted Total	8.7	4	NA

0= not fit for purpose/ 2 = marginally fit for purpose/ 4 = inadequate for purpose/ 6 = moderately fit for purpose/ 8 = mostly fit for purpose/ 10 = fully fit for purpose

C. Theory of Change

A Theory of Change is set out below:

Faster economic growth and poverty reduction
Impact

Creation of local/national coalitions around issues of public interest, informed by public policy research [piloting of Issues Based Approach]

Strengthened Zimbabwean systems for reconstruction and development
Outcome

1. Improved growth conditions that are related to business environment
2. Strengthened core systems for public management and service delivery
3. Enabling environment promoted for reducing vulnerabilities, improving resilience and strengthening human development
4. Robust, effective and timely advice provided on key issues
5. Improved donor coordination and World Bank capacity in country

Intermediate Outcomes

Creation of local/national coalitions around issues of public interest, informed by public policy research [piloting of Issues Based Approach]

Creation of local/national coalitions around issues of public interest, informed by public policy research [piloting of Issues Based Approach]

Creation of local/national coalitions around issues of public interest, informed by public policy research [piloting of Issues Based Approach]

Specific outputs to be determined during design of individual projects and programmes to be funded by ZIMREF

Outputs

Inputs
Financial contributions and staff time to World Bank Zimbabwe Reconstruction Fund (ZIMREF), focused on outputs 2 and 4 especially

Problem Statement
1. Poor business environment
2. Weak systems for public management and service delivery
3. Poor environment for supporting livelihoods and resilience
4. Inadequate policy analysis or donor-GoZ engagement
5. Weak donor coordination

And an underlying problem: WB in-country capacity and opportunity to engage constrained by GoZ arrears and restrictions on new lending

Key assumptions underpinning this are that:
- The analytical work and project investments are effectively used by GoZ
- World Bank (and wider donor re-engagement) is not compromised by the political environment
- Adequate contributions are forthcoming to make this a meaningful instrument
- The programme is effectively managed

D. Evidence

A series of annual reviews of the Analytical Multi Donor Trust Fund have been largely positive, demonstrating significant impact in informing government policy, building technical knowledge through studies and workshops, and supporting improvements in Government capacity. For example:
Capacity building for public financial management has enabled the GoZ to revive its computerised accounting system and trained over 1,800 public servants in its use, allowing the timely and accurate preparation of monthly accounts within two weeks of month end;
- A small business survey was utilised by government and other stakeholders to develop policy and catalyse developments in the micro, small and medium enterprise sector, and by International Finance Corporation to inform their advisory services;
- Support for the preparation of an agricultural development strategy led to signature of a Comprehensive Africa Agriculture Development Program (CAADP) compact in November 2013;
- Specific sub-sectoral analyses that are being used by GoZ to formulate irrigation and livestock sector policies;
- Preparation of position papers and background technical papers on water resource management, urban and rural water supply and sanitation, and water sector investment analysis that have led to adoption by Cabinet of National Water Policy (March 2013) and a draft 20 year water sector investment plan.

An independent evaluation of the Analytical Multi Donor Trust Fund is currently on-going and will help inform the management and implementation of ZIMREF. Provisional findings of the evalution are very positive about the impact of the Analytical Multi Donor Trust Fund.

The design of ZIMREF has drawn on the lessons of other post-crisis multi-donor trust funds, notably the need for a dedicated Secretariat and ready access to skilled technical staff, the need for a balance between quick results activities and policy and capacity building activities, the importance of investing early in fiduciary systems and capacity, and of developing and implementing a clear communications strategy.

E. Value for Money Statement

Value for money will be achieved through the economies of scale and reduced transaction costs of supporting through a multi-donor Trust Fund, by negotiating advantageous administration fees with the World Bank in partnership with other contributing donors, by using the World Bank’s rigorous procurement procedures, and by careful scrutiny of the costings for individual projects to be supported under ZIMREF.

Commercial Case

Choice of partner and procurement approach

DFID funds will be managed by the World Bank as part of a Multi-Donor Trust Fund, governed by an Administration Agreement. DFID joining a Multi Donor Trust Fund is more efficient and cost-effective than setting up a new Single Donor Trust Fund specifically for DFID’s contribution. This also avoids the problem of proliferating Trust Funds, a key point of DFID’s recent engagement with the World Bank, and of World Bank Board approval of ZIMREF. The Trust Fund will be an important tool for coordination, providing an effective platform for policy dialogue between the donors, and enabling them to share political and fiduciary risk. The pooling of funding will also help reduce transaction costs for the Bank and for contributing donors.

All contracting will be undertaken according to the World Bank’s procurement rules and procedures. These are robust, highly competitive, transparent and will result in contracting of the best possible suppliers on the market. The World Bank will use competition at various stages of procurement to drive costs down, minimise fiduciary risk and deliver value for money.  The World Bank’s annual fiduciary review process is comprehensive and includes both periodic post-procurement review of transactions and prior review of larger procurement activities along with an assessment of the effectiveness of the procurement processes.

Each contract will be subject to oversight by the World Bank’s supervision teams in accordance with the agreed procurement plan. During project preparation, the project supervision team’s procurement specialist will assess the capacity of procurement rules, personnel and institutional arrangement in the implementing bodies with responsibility for procurement, contracting and contract management to identify any weaknesses and to assess the risks these pose. They will then provide advice to the Project Implementation Teams on relevant risk mitigating measures and to the grant recipient on the design of appropriate procurement supports and arrangements. During project implementation, World Bank procurement staff will supervise the procurement processes according to these rules

More generally, the Central Assurance Assessment of the World Bank has provided a general assessment of Bank systems and policies in the four key areas of the due diligence framework (governance, financial stability, management of downstream partners, and ability to deliver) and confirmed that the World Bank has policies and procedures which address each area.

Value for Money

This is largely a Recipient Executed Trust Fund (RETF) and therefore the standard World Bank Trust Fund administration fee of 2% will apply, plus a negotiated management fee.  An initial quoted management fee of 15% was negotiated down by DFID and donor partners to a maximum of 10%.  The management costs primarily cover the governance structure of the ZIMREF Secretariat agreed as necessary and appropriate by contributing donors.  The actual management fee charged will be based on actual expenditures. DFID will ensure that there is strong oversight of this spend to ensure the achievement of Value for Money.  All Bank Executed Components (BETFs) will be subject to the standard 2% central administration and 3% management costs.

Costing of individual project proposals (which require approval by the relevant technical review group and Policy Oversight Committee) will be carefully scrutinised to ensure each provides value for money. The possibility of adopting a “payment by results” approach will be considered for individual projects. These costs will be regularly  monitored, and compared with implementation rates and linked to achievement of results.

To manage the programme effectively and help ensure value for money, DFID will allocate internal staff resources which include:
- Economic advisor
- Programme Manager

And support from
- Livelihood adviser
- Governance adviser (delivery systems, fiduciary risk)
- DFID procurement advice as required from PCD and DFID Commercial Officer and Advisor support.

The Multilateral Aid Review assessed VfM systems that are applicable across the World Bank.  The World Bank’s strengths were identified as: i) adequate cost control systems to ensure costs do not inflate; ii) robust financial accountability process and policies; and iii) largely predictable, transparent financing and extensive financial policies. Weaknesses were identified as being: i) limited incentives to generate cost savings in projects; ii) staff pay mechanisms leading to automatic increases; and iii) perceptions that the World Bank has high transaction costs.

## Financial Case

Programme cost and disbursement method and profile

DFID has provisionally allocated £10m over 5 years to finance this contribution, representing around 2.5% of annual spend (at least for 2014/15 and 2015/16). Details of other donor indicative contributions are set out in the Appraisal Case. Further contributions may be forthcoming, with ZIMREF designed to allow expansion in line with available contributions. It is expected that funds will be disbursed in 2 instalments of £1m per year on the basis of a request for payment from the World Bank although the first disbursement is likely to be £2m.

Financial management and disbursement arrangements

ZIMREF resources will be provided to recipients on a grant basis using a Grant Agreement. All Recipient-executed activities financed by ZIMREFwill be carried out in accordance with applicable Bank policies and procedures as set out in the Grant Agreement. All projects will have in place systems and controls that will ensure good governance and reduce the risk of fraud and corruption. World Bank fiduciary requirments will be applied to all ZIMREF projects.

During preparation the World Bank Supervision team will conduct a financial management assessment to determine whether the financial management system put in place by the implementing body is capable of supporting the implementation of ZIMREF projects. In particular, the assessment aims to determine whether (1) the implementing body has adequate financial management arrangements to ensure that project funds will be used for intended purposes only in an economic and efficient way; (2) whether the financial reports of the project will be prepared in an accurate, timely and reliable manner; (3) whether the project’s assets will be safeguarded. The financial management assessment will be carried out in accordance with the Financial Management Manual issued by Operations Policy and Country Services of the World Bank.

Based on this assessment the Project Supervision Teams will design relevant risk mitigating measures and advise the grant recipient on the design of appropriate financial management arrangements. During project implementation, Financial Management staff will review the continuing adequacy of financial management arrangements; review the performance of the financial management system, and test-check the application of controls or individual transactions. Furthermore, the interim reports, the audited financial statements and the associated financial management risks will be verified and validated throughout the project’s life.

ZIMREF will consider a variety of different project implementing modalities. In keeping with DFID Zimbabwe’s funding policy decisions on financial management arrangements and the flow of funds will be made by consensus ensuring that DFID has an effective veto over all such decisions. DFID funding will be earmarked in a manner which is consistent with our funding policy in Zimbabwe. DFID funding will flow through the Project Implementation Entity model under which procurement, funds flow and accounting take place outside the Government’s public financial management systems.

Monitoring, Reporting and Accounting of Expenditure

The World Bank will provide to each contributing donor within six months following the end of each World Bank fiscal year, the annual single audit report comprising of:
A management assertion over internal controls surrounding the preparation of Trust Fund financial reports together with an attestation from the Bank's external auditors concerning the adequacy of internal control over cash-based financial reporting for trust funds as a whole; and

A combined financial statement for all cash-based together with the external auditor’s opinion thereon

The cost of the single audit will be borne by the World Bank.
Further, the World Bank may contract a Monitoring Agent (MA), responsible for reviewing expenditures and checking compliance with (i) ZIMREF requirements and (ii) efficiency standards. The MA reviews all of the expenditures codes to ensure they are eligible for ZIMREF funding and in line with the budget. The MA also decides which expenses to examine in detail by applying a carefully designed risk-based approach to monitoring.

Management Case

A. What are the Management Arrangements for implementing the intervention?

ZIMREF has a local two-tier governance structure comprising a Policy Oversight Committee (POC) and Technical Review Groups (TRGs), supported by a Secretariat based in Harare, and Project Implementation Teams (PSTs). The effectiveness of the governance structure will be assessed by the POC after 6-12 months from the launch of the Trust Fund.
Figure 1: ZIMREF Institutional Arrangements

GoZ
World Bank
Contributing Partners

Policy Oversight Committee

Project Selection Loop

Technical Review Group
Govt PSs/Directors, Bank Program Leaders, Donor Technical Experts, Other Subject Experts
Secretariat
World Bank Staff

Ministries, Permanent Secretary and Technical Heads Level

Project Supervision Teams
Bank Staff

Project Supervision Loop

Project Implementation Loop

Project Implementation Teams

The POC consists of representatives of the Government, contributing partners and the World Bank as Administrator. The POC serves as a strategic forum for discussion of ZIMREF policies and outcomes, provides the strategic direction for ZIMREF financing, and approves specific activities. The Government will be represented on the POC by the Permanent Secretary or his designate. The contributing partners will be represented by their Heads of Agency or designate The World Bank, as Administrator, will be represented by its Country Manager for Zimbabwe or his/her designee.
The main responsibilities of the POC are to:
- Endorse the overall priorities for the ZIMREF and provide policy direction on the Trust Fund’s strategic goals;
- Ensure alignment of ZIMREF work program with various objectives – strengthening Zimbabwe’s systems for reconstruction and development, support for ZimAsset, implementation of the World Bank ISN and the contributing development partners’ cooperation strategies.
- Review and approve the Operational Guidelines, and any proposed amendments;
- Review and approve amendments to Administration Agreements;
- Review and approve overall allocation of resources among the various windows of fund.
- Review and approve (a) project concepts for preparation, and later (b) prepared projects for implementation;
- Review and approve membership of TRGs;
- Mobilise additional resources;
- Support coordination across sectors and stakeholders; and
- Provide advocacy support for the ZIMREF activities in Government, among development partners and with other national stakeholders.
The Policy Oversight Committee will be supported by Technical Review Groups whose responsibility is to provide technical guidance to the POC, ensure technical quality-at-entry of projects, oversee project implementation, provide support for cross-sectoral and stakeholder coordination, and review and analyse M&E plans and findings. The number and composition of TRGs will be decided by the POC, but initially it is expected to have one TRG per thematic window.
TRGs will be comprised of technical staff from the World Bank, contributing partners, and relevant Government line ministry/agency officials. The TRGs may invite other technical experts to their deliberations, as required. The TRGs will be chaired on a rotating basis by the permanent members. For the World Bank, the designated staff will be the relevant Program Leaders or their local alternate as delegated by the Administrator. The main responsibilities of the TRGs are to:
- Screen project concepts for eligibility and alignment to the strategic direction and priority areas set by the POC;
- Provide technical advice for projects during preparation;
- Screen prepared projects for quality at entry;
- Endorse specific implementation arrangements for prepared projects;
- Review supervision reports from project teams;
- Monitor implementation of projects and review supervision reports;
- Review and advise on M&E framework and activities
- Support POC in cross-sectoral and stakeholder coordination; and
- Foster harmonisation between activities funded by ZIMREF, Government and Development Partner programs.
Day-to-day operations will be managed by the ZIMREF Secretariat. The Secretariat reports to the Policy Oversight Committee on overall ZIMREF operational progress and to the Administrator on all administrative matters. The Secretariat is based at the World Bank Office in Harare.
The Secretariat is led by a Program Manager who reports to the World Bank Country Manager. The Program Manager will be assisted by a team with capacity in financial management, monitoring and evaluation, communications and public outreach, donor coordination and other skills as necessary. Should additional short-term expertise be required, the Secretariat will engage external consultants or bring in support from other partners.
The Secretariat will be financed from the Administration and Management Fee contributed by contributing partners. The Secretariat is responsible for coordinating the identification, appraisal and implementation support of ZIMREF-financed projects and for monitoring, evaluating and reporting on all performance aspects of these activities. The Secretariat will ensure that funds are used in accordance with the Administration, Grant and other legal agreements. The key responsibilities of the Secretariat include:
- Handling the day-to-day operations, including coordination among project teams, development partners and contributing partners;
- Maintaining the Trust Fund’s records and preparing bi-monthly updates and semi-annual progress reports, including financial statements on Trust Fund finances and performance for submission and approval by the POC;
- Arranging POC and TRG meetings and communications, as well as maintenance of records thereof;
- Developing strategic programs for financing, to be approved by the Policy Oversight Committee
- Support efforts at aid coordination between ZIMREF and other structures in government and the development community
- Reviewing and recommending grant requests to the POC;
- Coordinating project-specific activities for all projects such as, project preparation support, appraisals, supervision, monitoring and evaluation;
- Ensuring effective communication and dissemination of information on the Trust Fund activities including posting relevant reports on the ZIMREF website and coordinating the Trust Fund external relations.
The Secretariat will serve as focal point for any comments or complaints about the functioning of the Trust Fund, including consistency with the overall guidance provided by the POC, the identification and selection of projects, and monitoring and evaluating project implementation. The Secretariat will report immediately to the members of the POC any serious breach of the rules established for the Trust Fund. In addition, it will report on an annual basis any comments or complaints received by the Secretariat, and the actions taken in response.
Project Implementation Teams (PIT) will comprise Government ministry and agency staff, implementing bodies as per implementation arrangements and any consultants financed by the implementation grants to support these teams. The PIT will be responsible for preparation of the projects for submission to the TRG and POC, and for the implementation and completion of the projects in line with approved implementation arrangements as described in the project-level Project Implementation Manual.
The World Bank will appoint task teams (staff and Bank-contracted consultants) to support the Project Implementation Teams in the development of project concepts, preparation, implementation and completion of projects. These Project Supervision Teams will also act as the supervision teams for the Administrator in line with World Bank rules and procedures. Project Supervision Teams are responsible for:
- Supporting project preparation by Project Implementation Teams, by providing technical expertise, and guidance of World Bank policies);
- Preparing required Bank project documents, appraising and negotiating projects on behalf of the Administrator.
- Provide technical support to Project Implementation Teams during project implementation, Monitoring project progress and recommend changes as necessary to achieve project development objectives, e.g. additional capacity building support, adjustment in targeting etc;
- Supervision of project implementation, including approval of procurement and work plans, and any amendments, sign off on procurement and financial management processes, provide technical expertise on contract management issues, identify implementation weakness and recommend remedial steps, monitor compliance with Bank policies, etc.
- Conduct periodic formal supervision missions, including a Midterm Review and prepare Implementation Supervision reports and Aide Memiores;
- Communicating project information and providing regular financial and progress reports, to the ZIMREF Secretariat;
- Provide expertise to support monitoring and evaluation of programs and projects by monitoring results, capturing lessons learned and measuring cost effectiveness;
- Prepare implementation completion reports.
B. What are the risks and how these will be managed?

A summary assessment of risks and their mitigation is set out in the table below. The most significant risks to delivery concerns the political and economic environment that may prevent programme investments or reduce their effectiveness. This will be closely monitored by the Policy Oversight Committee, and flexibility in ZIMREF design allows for the programme to be scaled back (and contributions reduced) if necessary. Fiduciary and reputational risks are considered low owing to the rigour of World Bank procedures.

Risks	Risk Rating	Mitigation	Residual Risk Rating
Political environment compromises ability of World Bank to sustain re-engagement and “high case” ISN scenario.	Risk: Medium / Impact: High	Constant assessment of the political environment with opportunity for review at World Bank Board level as necessary. Flexibility of ZIMREF design would allow reversion to more modest analytical work if required	High
GoZ unable or unwilling to implement key policy reforms due to political or economic instability	Risk: High / Impact: High	Political economy analysis to inform project selection and design. Ongoing dialogue around debt relief to incentivise maintenance of reform agenda. Complementary DFID governance programmes will also contribute to holding government to account and delivering better policies	High
Weak programme management leading to delays or ineffective implementation	Risk: Low / Impact: Medium	Review of governance structure and management arrangements scheduled after first 6 months. Regular opportunities to amend Operational Guidelines and strengthen World Bank secretariat as necessary	Low
Fraud or misuse of donor funds	Risk: Low / Impact: Medium	World Bank procedures will be followed, and Operational Guidelines ensure high levels of oversight over management of funds.	Low

C. What role, if any, will the Partnership Principles play in the management and monitoring of the programme? What other conditions apply?

DFID Zimbabwe undertook a country-level assessment of the UK Partnership Principles in September 2014. This confirmed the DFID policy that no UK aid should be managed by or be under the direct control of the Government of Zimbabwe using its own financial systems and procedures. We only provide direct support to other Governments when they commit to improving the management of public finances, tackling concerns about human rights abuses and corruption, and improving domestic accountability. The assessment highlighted shortcomings in all of these areas. The ZIMREF programme is in line with this policy and does not use Government of Zimbabwe systems.

D. How will progress and results be monitored, measured and evaluated?

The World Bank has developed a results framework to monitor the achievement of the ZIMREF objectives. This framework will be prepared and maintained by the ZIMREF Secretariat in collaboration with the Techincal Review Groups and approved by the Policy Oversight Committee. Project Supervision Teams will be responsible for developing project-level results frameworks. The Secretariat will be responsible for consolidating and reporting to the POC on the Results Monitoring Indicators at an aggregate level for the program, and for updating the results framework.

A dedicated monitoring and evaluation (M&E) officer will be housed in the ZIMREF Secretariat.The M&E Specialist will liaise with project teams and local government counterparts to coordinate and consolidate M&E activities across the ZIMREF portfolio.The M&E officer will also be responsible for developing the logical framework and for identification and collection of baseline data and information.

Project Supervision Teams will be responsible for developing project-level results frameworks, including quantifiable and quantified baselines, at the time of project preparation. Project Teams will continuously monitor the agreed performance indicators and provide updated results indicators on a semi-annual basis in the Implementation Supervision Reports and year-end project progress reports. Any changes in results indicators should be reviewed by the Technical Review Groups, prior to revising the results frameworks.

The Secretariat will provide contributing partners with semi-annual reports on the progress of activities financed by the Trust Fund. Within six months of the final disbursement date of the ZIMREF, the Bank will provide contributing partners with a final report on activities financed by the Fund. Such reports will also be posted on the ZIMREF website.

The Secretariat will also commission independent evaluations, such as a mid-term review of the portfolio, and possibly other reviews that help assess the quality of implementation and results. Through these efforts, the Policy Oversight Committee will gain insight into the performance of the portfolio in addition to project-based reporting.

The Administrator and, where applicable, the Project Teams, will supervise ZIMREF-financed projects in accordance with standard World Bank policies and procedures. It is expected that a supervision mission for ZIMREF projects will be fielded as frequently as considered appropriate for the activity, but at least once every six months. Members of the Secretariat will be invited to join these supervision missions and members of the Policy Oversight Committee may also be invited.

In addition to supervision and monitoring, the Administrator may decide to periodically review a selection of ZIMREF projects in more depth to validate reports and obtain a greater understanding of obstacles to achieving results and how these could be overcome.

The Secretariat will disseminate a quarterly newsletter which will provide updates on ZIMREF’s progress. Additional information will also be provided through the ZIMREF website and regular e-mail communications. The ZIMREF Secretariat will submit a semi-annual progress report to the Policy Oversight Committee.