## Annual Review Template – September 2020

Title: Better Education Statistics (BESTA)
Programme Value £ (full life): £24 million		Review date: 23/11/2020
Programme Code: 204695	AMP start date: 1/1/17	AMP end date: 31/1/2024

Summary of Programme Performance
Year	2018	2019	2020
Overall Output Score	A	A	A
Risk Rating	Moderate	Minor	Minor

DevTracker Link to Business Case:	link
DevTracker Link to results framework:	link

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme

The Better Education Statistics for Global Learning (BESTA) programme is working to improve the data, tools and resources to tackle the global learning crisis, central for delivering Sustainable Development Goal (SDG) 4 for Education and the DFID 2018 Education Policy, and for supporting
12 years of quality education for all girls.

The programme supports this through:
1. New global data, tools, and methods available to measure learning;
2. Improved publication, dissemination and analysis of data and evidence on learning and equity;
3. New research methods and evidence on how to improve learning and data; and
4. New global approaches to tackle learning challenges/constraints.

Delivery in these output areas is through a number of multi-year strategic partnerships with education data partners, and short-term initiatives.

Summary supporting narrative for the overall score in this review

A key assumption in the BESTA programme theory of change is the absence of major shocks affecting the global education sector. The COVID-19 pandemic has caused disruption to education systems around the globe on an historic and unprecedented scale, increasing the numbers of students out of school and deepening the challenge of getting children learning. As such, the pandemic has presented clear and immediate challenges to BESTA’s programme partners in the delivery of many aspects of their work, such as data collection, in-person analysis or advice.

In some cases, this has resulted in delays to programme activities, but all partners have been able to adjust, either pivoting activities to respond more directly to COVID-related disruption, or using remote and online approaches to continue with planned and still-relevant work. As such, the programme continues to make a valuable contribution to the collection and use of global education data and evidence. During the reporting year, key activities included:

- Supporting the UNESCO Institute for Statistics (UIS) to develop new global learning and equity metrics and tools and to strengthen SDG4 reporting data, including the collection and analysis of COVID-education impacts.
- Largest donor to the Global Education Monitoring Report (GEMR), supporting improvements in the analysis of education data and policy recommendations, with a focus on inclusion.
- Supporting the People's Action for Learning Network to conduct community led learning assessments, including new approaches to cross-country comparisons.
- Development and piloting of a learning assessment ‘policy linking’ tool that will enable cross-country comparison of learning measures where statistical comparison is not possible due to data gaps.
- Support for the development of a ‘Minimum Service Package’ for the inclusion of mental health and psychosocial support activities within Education in Emergencies programming.
- Sole funders of the Education Workforce Initiative research project testing policy options to address education workforce planning and resourcing challenges.
- Sole funders of the ‘DeliverEd’ initiative to build the knowledge of partner country policy makers on the use of delivery units in the education sector.
Assessed against output-level progress, the programme remains highly relevant to education sector data and evidence challenges and is meeting its objectives. However, in light of increased HMG ambition on girls’ education, and the ongoing disruption caused by the pandemic, it is a major recommendation of this AR (set out below) that the programme review its component elements and adapt where necessary to ensure that it continues to contribute to the overall impact-level objectives, as set out in the Business Case.

Major lessons and recommendations for the year ahead

- In context of the COVID-19 pandemic and emerging FCDO education targets and ambition, review programme outputs (in particular for GEM and UIS partnerships) to ensure they reflect key education trends and UK priorities. Timeline: within three months of annual review publication.
- Use the BESTA partnership as an entry point for a strategic planning discussion with UIS on emerging COVID-related education data needs and adequacy of existing funding sources to support these needs. Timeline: to commence within three months of annual review publication / ongoing.
- FCDO team to make the case for more funding to support new project activities in 2021, specifically, policy linking work and the CGD education aid survey (detailed below). Timeline: alongside 2021 Spending Review Process.
Specific output-level recommendations are also included in this Annual Review, within the relevant output sections.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The diagram above shows the programme theory of change as presented in the original Business Case. One key continuous assumption – no shocks or major events globally, nationally or regionally – has proved challenging in the light of the COVID-19 pandemic. However, adaptations were made to respond to this situation and the overarching Theory of Change as originally set out, still holds.

The emergence and impact of the COVID 19 virus is having a major global impact on school attendance and learning. However, the pandemic has not signficantly affected the programme’s ability to deliver most of its principal activities as most of these draw upon data sources that are still producing material. Additionally, the driving factors behind the programme – namely the need for improved robust education data and evidence – are even more relevant in light of COVID’s impact on the education sector. The programme’s lead delivery partners – such as UIS and GEMR – are playing a major role in the collection and use of data that enables education delivery partners to respond to this changing education context. One key recommendation of this Annual Review (AR) is to review existing programme outputs and make necessary adaptations to ensure progress is captured effectively for the remainder of the programme in light of COVID disruption.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Both on its own merits and in the context of the wider education portfolio and ambition of the FCDO, this programme continues to be a positive strategic fit. It is performing well overall, and several components including the GEMR, the support to the PAL network, and strategic initiatives supported during the reporting year have delivered high quality outputs to influence education policy. Progress by UIS, while satisfactory against agreed programme milestones, is not maximising its potential contribution to action in response to broader sector data challenges and needs. This should be strengthened through a joint review exercise (UIS and FCDO) that involves more strategic identification and prioritisation of sector data needs, especially in light of COVID, and a related assessment of currently available and potential future support in response to those needs.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	New global data, tools, and methods available to measure learning, and make sure no one is left behind
Output number:		1	Output Score:	A
Impact weighting (%):		35	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 / Development of new, widely accepted, Children Not Learning (CNL) Indicator: / (i) Methodology established and promoted / (ii) CNL and comparable learning data published / (iii) Key technical documents reviewed* and published / (iv) Coverage and content of Catalogue of Learning Assessment (CoLA)	Comparable learning data (indicator 4.1.1) and CNL methodology refined and made more robust. / Updated Indicator 4.1.1 and CNL published globally and regionally and for 80 countries, 15 from sub-Saharan Africa, including at least 5 using social moderation / DART (data reporting tool) used in at least 7 assessments from sub Saharan Africa / CLA Modules I and II published for at least 55 countries (covering most learning indicators under SDG4, including 4.2.1)	Achieved / Partially achieved / Partially achieved / Achieved
1.2 / (i) Publication of an education equity database, and coverage of data on equity measures; / (ii) Publication of internationally agreed methods for measuring equity in education	Equity database updated with 9 indicators covering 125 countries disaggregated by sex, location and wealth, and 20 countries by disability status. / UIS fact sheet on indicators of equity in education, including disability	Achieved
1.3 / Improvements in SDG4 indicator data: / (i) Coverage and timeliness of core SDG4 indicator data / (ii) UIS restructured in line with SDG4 data needs / (iii) PAL - Quality and use of citizen-led assessments in measuring and promoting SDGs and the Global Learning Indicator both nationally and internationally	(i) Agreement on methodology reached for 33 indicators, and data being reported on 30 / Coverage of 18 key SDG4 global and thematic indicators produced by the UIS / *Global Learning Indicator analysis published using CLA data, and actively disseminated	Achieved / Achieved / Achieved

Briefly describe the output’s activities, and provide supporting narrative for the score.

UNESCO Institute of Statistics (UIS)
During the reporting period, UIS have continued to make an important contribution to improved global education data as per their mandate and have broadly delivered against most expected outputs and milestones in the BESTA logframe. This is within the context of instability and uncertainty caused by the COVID 19 pandemic affecting all delivery partners.

Where UIS has partially achieved milestones for Output 1.1, good progress has nonetheless been made: for Output 1.1(ii) UIS published for 77 out of 80 countries; for Output 1.1(iii) it expects this to be achieved by the end of this calendar year; and for Output 1.1(iv), the CLA Module 1 has been published for 58 countries, surpassing the milestone.

Milestones for Output 1.2 focusing on equity and disability inclusion have been achieved. The equity database includes data for 172 countries and UIS have produced a Disability and Education Dashboard, covering 37 countries. This AR notes this as a positive start, however, we also note that the data quality is mixed (e.g. some tools used are likely to lead to underreporting in certain contexts). This Review recommends that UIS develop an accompanying technical note on how to read/interpret this data. The Use of UIS Data and Education Management Information Systems to Monitor Inclusive Education (also an output in the UK GPE programme logframe) provides a useful overview. The proposition and justification for funding UIS as presented in the Business Case for this programme continues to be relevant.
[note] This note is also an output in the UK GPE programme logframe and provides a useful overview, though has a strong focus on Fiji – a middle-income country – and is therefore not representative of the capacity and resources in many FCDO education focus countries.

During the reporting period, UIS published a paper Combining Data on Out-of-school Children, Completion and Learning to Offer a More Comprehensive View on SDG 4, which presents global and regional figures for a positive Children Learning (CL) Indicator (or 4.1.1. Adjusted). UIS proposes to replace the CNL indicator with the CL Indicator with the aim of better measuring SDG 4.1 by combining both completion rate and learning outcomes data. This represents a position change and progress in the combination of two key data strands. By working to bring both access and learning measures together in the same quality-adjusted metric, this change is intended to deliver an easier-to-understand single indicator across all education stages. This represents positive progress towards better global measurement of two key education priorities for FCDO.

In line with the overall programme recommendations outlined above, the key recommendation for this output is to ensure that the strategic partnership with UIS, to whom FCDO is a major contributor, is focused on and delivering support for the most strategic and pressing education data issues. This is particularly significant given the impact of COVID-19 upon key metrics of education progress (access, learning quality, out of school populations etc). UIS have played a key role in providing global education stakeholders with critical information during the pandemic, and as the education community is seeking to both respond to COVID-19 disruption and accelerate progress toward SDG4, further improvements in sector data are essential. At present, UIS could be supported to do more to capitalise on this enhanced need for better data and to maximise the impact of its efforts across the sector. This AR therefore recommends that FCDO conducts a joint review exercise with UIS that involves more strategic identification and prioritisation of sector data needs, especially in light of COVID, and a related assessment of currently available and potential future support in response

PAL Network

With UK support, the PAL network has had a productive year working to both improve the quality of citizen-led assessments (CLA) among network members, and expanding the potential for cross-country comparison of CLA through the development and trailing of new methods. CLA work provides a valuable complement and/or substitute for learning assessment data in contexts where formal assessments are not conducted, or not conducted with regularity. Key activities and outputs (additional to involvement in the policy linking work highlighted below) from the past year include:
[note] Citizen-led assessments run by PAL network members use oral one-on-one assessments conducted in households to generate robust evidence on learning outcomes that complements, or supplements formal assessments conducted by state actors.

- PAL launched the International Common Assessment of Numeracy (ICAN) on July 9, 2020. ICAN is an open-source assessment tool, available in 11 languages, that offers international comparability of data on children’s learning levels, aligned to SDG 4.1.1(a). The virtual event brought together 1,842 participants across 42 countries from Africa, the Americas, Asia, Australia, and Europe. This was followed by regional launch events in South Asia and East Africa. On August 10, 2020, the South Asia Hub of the PAL Network, comprising ASER Bangladesh, ASER India, ASER Nepal, and ASER Pakistan, hosted a webinar on “Understanding foundational numeracy: South Asian perspectives on ICAN, a new global tool”. The virtual launch, which brought together 208 participants, featured keynote education specialists from Pratham, World Bank, IBCC, GPE, and BRAC who advocated for a common regional tool that is appropriate to diverse contexts (schools, households, refugee camps among other contexts. As a complement to ICAN, PAL has led work to develop an international common assessment for reading, ICARE.
- PAL network members published key CLA material during the reporting year, including Uwezo Tanzania and Uwezo Uganda publication of learning assessment reports, and reports by ASER Pakistan and India.
- PAL network members have also played a key role in supporting the education response to COVID 19 in many countries. In Kenya, PAL Network’s Chief Executive Officer was appointed to Chair the COVID-19 Education Response Committee. Through the Policy Dialogues project, the PAL network supported online collation and analysis of public opinions about school reopening from concerned citizens and institutions related to education. The Committee submitted the report to the Ministry of Education on May 29th, 2020.
- PAL have also been engaged in the policy linking in-country piloting and testing work detailed below.
UK funding continues to deliver value for money and supports a key contribution to the global education landscape in terms of data collection and accountability and transparency

Strategic initiatives support:
Policy Linking
This workstream supports better national comparability of learning assessments, using a ‘policy linking’ approach piloted jointly by UIS, USAID, the World Bank, and the Gates Foundation. Policy linking is a methodological innovation to overcome the issues stemming from incomparable learning assessments across countries and within them (e.g. across different administrative regions). Where the commonalities required for statistical linking are not available, policy linking methods bring experts together to agree on thresholds of learning measured by different tests. BESTA funds have secured the time of an assessment expert based in UK Department for Education (DfE) to provide technical input, quality assurance and piloting supporting for this process. Whilst not originally foreseen in the Business Case, it has been funded through the programme’s responsive Strategic Initiatives fund. Outputs are outlined below and there are future recommendations/activities related to this workstream in which the FCDO could usefully be involved.
Policy linking toolkit – the draft toolkit has been developed for use by organisations to deliver a national policy linking process, and will be shared by partners in the Policy Linking Coordination Group with their counterparts (e.g. UIS to national government partners). The toolkit has been tested through four country pilots that have taken place during the reporting year (Bangladesh, India and Nigeria delivered by MSI and PAL Network delivered by the DfE assessment expert and the UIS consultant). Four pilots were delivered to test the policy linking process, all pilots were successful and provided useful ‘lessons learned’ for future activity:
1. Bangladesh, grades 3 and 5 in mathematics and reading run by MSI
2. India, grades 3 and 5 in mathematics and reading run by MSI and observed by the DfE assessment expert
3. Nigeria, grades 2 and 3 in reading (EGRA) run by MSI
4. PAL Network, grade 2 and 3 mathematics (ICAN) run by the DfE assessment expert and the UIS consultant.

- Global Proficiency Framework (GPF) revision and expansion – the GPF is the document that sets out global expectations in reading and mathematics for each grade, against which assessments of national comparability can be made The DfE technical expert co-authored the updating of the GPF to cover grades 7 to 9 in partnership with UIS and a USAID consultant.
- Quality Assurance Policy and Panel – the Quality Assurance Policy (to be renamed) sets out technical requirements an assessment would need to meet in order to be considered appropriate for policy linking. The Policy will be reviewed by the Quality Assurance Panel (once recruited) before being finalised. Terms of reference for the panel have been developed and a recruitment process started.
- Ad-hoc advice including presentations to DFID/FCDO staff and country teams, and advice to UIS and the World Bank on the Global Item Bank and the WB primer on large-scale assessments of education achievement was also provided by the assessment expert under this workstream.
The ’policy linking’ work is a significant and highly strategic response to a persistent gap in learning assessment data, and a good example of the kind of work that the BESTA strategic initiatives fund is designed to respond to. The technical input and leadership provided by the leading DfE assessment expert has improved the quality of the GPF and the country pilots, and has supported UIS (as the current lead agency and eventual ‘home’ of policy linking work) in designing a more strategic and comprehensive approach to consultation across stakeholders, validation of outputs and process, and building in early considerations of sustainability (e.g. quality assurance panel). Further work would enable piloting in FCDO partner countries providing further direct benefit to the FCDO education portfolio, as well as indirect benefit by filling an important missing piece in the current learning assessment global infrastructure, relevant to a large number of Low – and Lower-Middle Income Countries.
Aid architecture survey

FCDO resources, alongside funding from the Asian Development Bank and the Bill and Melinda Gates Foundation, supported a survey conducted by the Centre for Global Development on the issue of cohesion or fragmentation of international support in education. This involved phone and in-person surveying of over 900 education officials in 36 countries, using a combination of direct and experimental questions. The focus of the survey was to better understand the perception of senior officials in education Ministries and agencies on ‘aid architecture’ cohesion or fragmentation and education system priorities.

The survey demonstrated a number of highly relevant policy findings, related to the delivery of education support by external actors, the prioritisation of education sub-topics (e.g. girls’ education, TVET, foundational learning, higher education), and the preferred sources of education policy and technical support across a range of bilateral and multilateral education agencies. These findings are being developed into a number of policy products including presentations, blogs and policy notes that will be used to support several global education system reform initiatives that FCDO is supporting. This includes supporting partners at UNESCO and the World Bank, and consultations with key bilateral education partners in the improvement of education aid architecture. They will also be used in the coming year to help inform programme design and monitoring in key areas such as girls’ education and data and evidence usage.

World Bank SABER trust fund (education systems diagnostics and data)

BESTA resources supported the development and piloting of the World Bank-led Global Education Policy Dashboard, alongside the Gates Foundation. This is an initiative that measures the key drivers of learning outcomes in basic education in a cost-effective manner. The dashboard uses three data collection instruments to report on 39 indicators and highlights gaps between current practice and what the evidence suggests would be most effective in promoting learning. A final contribution to the World Bank trust fund supporting this activity was made during the reporting period and enabled the finalisation of the Dashboard indicators and methodology, full piloting (data collection, validation, presentation) in Peru, Jordan, and Rwanda, and partial data collection in Ethiopia before COVID restrictions on travel and in-country work delayed progress from March. Support to this World Bank trust fund also enabled the preparation and publication of country data underlying the World Bank flagship Human Capital Index, and the education specific indicator, ‘Learning Adjusted Years of Schooling’. The results so far seen suggest that the Dashboard is providing a valuable overall view of education system functioning that is based on reliable and robust data. The delays in delivery caused by COVID can expect to be overcome once restrictions on data-collection work are lifted. The World Bank, with pressure from FCDO and Gates Foundation, have made sure to anchor Dashboard processes and outputs into wider programmes (e.g. on foundational learning), meaning that there is an emerging pipeline of demand for Dashboard processes to be completed in a number of countries. Some of the Dashboard indicators have also been picked up and used in FCDO internal measurement processes, demonstrating positive alignment and likely further uptake.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

As the partnerships with UIS and GEM are the principal financial commitments covered under this output area, these are assessed in detail here. The overall assessment of the value for money of this output area is that it is continuing to deliver good value for money.

UIS

Main cost drivers for UIS are staff costs (salaries), staff travel (in-country/regional technical missions), consultants, and dissemination/consultation workshops. Since 2018, the goal of the UIS to improve financial stability has resulted in a decrease in the organisational core budget through, for example, reductions in staff travel and a shift to lower-cost regional workshops where associated participation and minimal travel costs incurred were lower. Delivery through implementing partnerships and consultancies were increased also reducing overall demands on overall core budgets.

The costs of Outputs 1.1 and 1.4 comprise expenditure for learning outcomes assessments both within the regular programme and from earmarked extrabudgetary resources. The increase in costs between 2018 and 2019 reflect the investment in piloting of methodologies for comparable learning data (indicator 4.1.1) and refinement of CNL methodology. The costs of Outputs 1.2 and 1.3 are from expenditure related to support the data collection and dissemination of education indicators including standards and methodologies and regional field support. The decrease in these costs reflects the reduction of budgets and staffing, particularly in regional field support, with a strategic repositioning exercise. This exercise sought to increase overall financial stability by focusing on a core set of indicators, defined core work, and delivery through partnerships and regional work.

GEM
The GEM Report team monitors and reports against a set of VfM indicators in order to quantify measurable achievements. The VfM reporting in this reporting period shows reduced cost drivers in economy against production and staff costs, and, in efficiency, a larger and more diverse audience reached through the switch to physical to online communications. These changes were largely driven by changes to GEMR operations as a result of COVID-19, however, there are VfM lessons on cost savings and efficiency that can be taken forward. The GEM Report remains a strong advocate of equity analysis throughout all its publications and the focus of the 2020 report was on the topic of inclusion in education.

Economy:
- (cost driver: production) established multiple long-term agreements for graphic design services with three reputed companies with financial bids that were in line or lower than previous graphic design costs.
- (cost driver: staff) outsourced some research and communication work to junior and mid-level consultants, which resulted in savings of about 40% per consultancy contract compared to a staff contract, and diversified the experience levels represented on the team.
- (cost driver: staff) secured a junior research officer funded by the Government of Italy.
- (cost driver: research) launched a large call for proposals for commissioning background papers resulting in competitive bids and an expanded pool of qualified consultants.
Efficiency:
(cost driver: communication/outreach) switched from physical to online events, which led to significant savings and yet presented a chance to reach a larger and more diverse audience
Effectiveness:
(all cost drivers: staff, research, production, communication/outreach) has begun working with regional partners though implementation partnership agreements for the development and dissemination of its regional reports series (Latin America and the Caribbean; Central and Eastern Europe, Caucasus and Central Asia; South Asia; Africa), whereby partners provide in kind contributions through administrative, human resources, and communications support; partners’ subject knowledge and strong networks across their respective regions support our outreach
Describe any changes to this output during the past year, and any planned changes as a result of this review.

The most significant change to this output during the reporting period was the disruption caused by the COVID-19 pandemic. This has impacted upon the ability of partners to operate as planned and driven changes in the global education landscape to which BESTA partners are responding. Therefore, a key recommendation of this AR is for the remaining UIS programme milestones to be reviewed in partnership with UIS to ensure they are fit for purpose.

Through the Strategic Initiatives fund, the programme was able to respond to demand from international partners (USAID, World Bank, UIS) to engage in the technical working group on policy linking (detailed above), delivered by the DfE assessment expert. For the reasons detailed above, this Review recommends that the BESTA team seek to secure further funding to enable this piece of work to carry on in the forthcoming reporting year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

No previous recommendations.

Output-level recommendations in this AR related to Output 1 are focused on ensuring that FCDO maximises the benefits of these funding arrangements across the breadth of the FCDO education portfolio. For the forthcoming reporting period, these are:
- CYED technical lead conducts quarterly technical check-ins with UIS on the specific BESTA milestones and updates to ensure focus over remaining progress period remains on delivery of these.
- CYED technical lead to convene broader discussion with UIS and relevant CYED staff on bigger picture education data needs and gaps, with a view to a more comprehensive view on priority areas for support and improved strategic alignment.
- CYED technical lead to take oversight of engagement with UIS across CYED portfolio.
- Consider how FCDO can support data and evidence work on disability inclusion led by GEM – for example – delivering paper on disability inclusive education financing through resources such as Inclusive Education Initiative.
- Explore opportunity to fund part two of policy linking work, including establishment and inception of QA policy and panel.

Output Title	Improved publication, dissemination and analysis of data and evidence on learning and equity
Output number per LF		2	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 / Number of people reached with Global Monitoring Report messages: / - copies of the report / - outreach events, and senior officials reached directly by report messages / - blog readers	80% of printed copies distributed/ Distribution strategy in place/ 5% annual increase in report downloads / 80 outreach events, launches and presentations / 30 senior officials attending high profile events / 16,200 average blog visitors per month	Exceeded: / Distribution of print copies on hold due to COVID restrictions on launch events. / 53,000 downloads of full and summary report (increase on 34,000 in 2019) / Major disruption to national launch events but 47 still proceeded, in addition to global and regional events, youth campaign events, social media events / 30+ senior official attending national and global launch events, including UK Minister. / World education blog receiving 31,777 views / month during reporting period
2.2 / Progress towards publishing cost effective annual authoritative Global Education Monitoring Report: / - timeliness of publication / - Commissioned background papers used in the final version of each report / - number of policy papers published, and gender/youth review / - Management reforms on track, as part of broader UNESCO reforms	2020 report published / 2020 regional report published / 90% of background papers commissioned for the 2020 report feature in the final report / 5 policy papers published / 1 gender/youth review published.	Achieved: / -2020 report published successfully / - 2020 regional report publication delayed due to COVID / - 96% background papers of GEM2020 report published / - 5 policy reports published + development of 2 website resources to make GEMR more interactive. / Gender 2020 report published (focus on 25th anniversary f Beijing Declaration)

This year’s Global Education Monitoring (GEM) Report focused on the topic of inclusion in education. In line with its mandate, the 2020 GEM Report assesses progress towards Sustainable Development Goal 4 (SDG 4) on education and its ten targets, as well as other related education targets in the SDG agenda. The Report also addresses inclusion in education, drawing attention to all those excluded from education, because of background or ability. The exclusionary factors explored that impact education outcomes include gender, geography, religion, ethnicity, language and poverty, and challenges to achieving exclusion examined include lack of teacher support, absence of data on out of school children, inappropriate infrastructure, and persistence of parallel systems and special schools.

The first ‘virtual’ launch of the GEM report in June 2020 was very successful – delivering impressive engagement and a high calibre of expert involvement. FCDO education Minister Baroness Sugg delivered keynote remarks as part of the launch event. Celebrity engagement supported dissemination of the report leading to impressive reach and a host of online launch initiatives including a Ministerial Q&A and a photo competition further boosted visibility and engagement.

Obtaining reliable disability data is challenging but the GEM makes the most of UNICEF Child Functioning Module data. Lack of data and evidence in low and lower-middle income countries led to more input from middle-and-higher income country contexts. Given data constraints this is partially unavoidable, but this AR recommends that GEMR consider developing an additional background paper on financing for disability inclusive education.

The GEM team adapted to meet emerging data and evidence needs caused by COVID 19. Two policy papers were published on the impact on the cost of achieving SDG 4 in low- and lower-middle-income countries and on aid flows to education, respectively. The GEMR’s costing model was updated accordingly and, a module was developed to assess the potential financial impact of the crisis. Preliminary results were presented at the High Level Political Forum side event on education (July), while the paper was a key input in the UN Secretary General Policy Brief on education (August), a background document to the Global Education Forum meeting (September), and key input to background document on finance for the UK-co-hosted Global Education Meeting (October). The GEM Report team worked closely with key multilateral partners, notably in the context of the Save Our Future education campaign and the resulting White Paper.

The 2020 GEM Report launch was complemented by the launch of a new website, Profiles Enhancing Education Reviews (PEER). The objective of the website is to present comparable, systematic and up-to-date information on national education laws and policies, with a focus on the theme of the Report. PEER aims to document the report’s research; engage countries by asking them to validate the information collected by the team; and provide a basis for policy dialogue and peer learning at the sub-regional or regional level. The material is also a core resource informing the report: qualitative information collected has been mapped in order to describe how countries approach inclusion in education and selected summary indicators have been used notably in Chapter 2 of the 2020 Report.

A new website created by GEM this year, Scoping Progress in Education (SCOPE), features an online, interactive report that complements the printed version of the monitoring part of the GEM Report. It is designed as a digital publication in the form of five long articles (on access, equity, learning, quality and finance) with about six interactive visualizations each. These provide a snapshot of the main trends in key education indicators across countries with regional and global averages as well as a concise narrative of the reasons behind the observed trends. The aim is for SCOPE to become the go-to website for those interested not only in the statistics, but also in comparing differences between countries or regions, understanding trends towards SDG 4 targets and having an analytical narrative about different patterns. SCOPE was launched on the International Day of Education on 24th January 2020.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

No previous recommendations.

This AR recommends that the GEMR team consider developing an additional background paper on financing for disability inclusive education to complement policy recommendations included in 2020 Report.
Output Title	New research methods and evidence on how to improve learning and data
Output number per LF		3	Output Score	A
Impact weighting (%):		15%	Impact weighting % revised since last AR?	No
NB. Programme-level output indicators for this output have not been developed as the broader work on new research methods – beyond the ‘Delivery Approaches’ work specified below, has not yet been agreed.

Briefly describe the output’s activities, and provide supporting narrative for the score.

The Delivery Approaches Research project is funded by FCDO’s Education Research Team through the BESTA programme. It is leading an assessment of the value and impact of ‘delivery unit’/’delivery lab’ approaches in the education sector. Despite several examples of such approaches in a range of countries, there is very little independent research on the topic in low and middle-income countries. The project is developing a taxonomy of delivery unit approaches in the education sector globally to allow for comparison and analysis and is conducting in-country research on five delivery unit approaches in Ghana, Pakistan, Tanzania, Jordan, and India. The in-country research will investigate how national education priorities in these governments are translated into desired outcomes and what mechanisms are most effective in improving implementation practices

Accounting for substantial delays to the in-country research work due to COVID-19 beyond its control, the programme has performed satisfactorily over the reporting period. Having completed its inception phase in July 2019, the project has made progress on developing an overarching conceptual framework and finalised research designs for in country activities.

The project has also modified some of its planned activities to provide COVID-19 related research, including broadening the global mapping of delivery units to include a consideration of the role of delivery approaches in crisis resilience and response. In Ghana, the project is providing technical assistance to the government on the design of a rapid phone-based survey to understand the impact of digital teaching and learning interventions and the challenges faced by students, parents and the education workforce.

Progress in 2020:
The DeliverEd project focused on building consensus around the research methodology and work plan with the country teams. In January, the team held an in-person design workshop to ensure alignment in conceptual framework and research design. In addition, the team developed a research protocol for the global mapping exercise of delivery approaches and met with high-level advisory group members and other key stakeholders.
- The team focused on finalising the first research and policy outputs, identifying and meeting with the High-Level Advisory Group Co-Chairs, gaining approval for research in Ghana, and conducting a global mapping exercise of delivery approaches.
- The research team finalised Working Paper #1 on the conceptual framework titled Deliver Education Reforms: Delivery Approaches to Improving Policy Implementation. They focused on conducting the global mapping exercise and developing the methodology for the country case studies. The policy team finalised Policy Brief #1 and its accompanying blog and continued outreach to High-Level Advisory Group members and had one-on-one meetings with four potential and confirmed members. The policy team identified three Co-Chairs and planned a virtual Co-Chair meeting. The policy team also met with a range of additional stakeholders who work on issues related to delivery, including the country research teams and stakeholders in the four research countries (five, including India).
COVID-19 has affected the country research plans and the production of the final research deliverables on the previously agreed timeline. In May as the extent of COVID-19 became clearer, the team outlined the expected impact on two work strands:
1. Country research: The field work was scheduled to begin in mid-2020. Due to travel restrictions and social distancing guidelines imposed in our research countries and our collaborators’ host countries, it is highly unlikely we would be able to carry out any field work before early 2021.
2. Stakeholder engagement: Due to the delays to the country research, the final policy briefs on the findings of the country and cross-case research, and the dissemination of the project’s overall conclusions will be delayed until the production of these papers is complete.
In order to ensure the relevance of DeliverEd research in light of COVID-19 and other crises, the team has outlined several proposals for research adjustments in terms of the global mapping of delivery units, engagement with stakeholders and in-country research.
- Global mapping and engagement with stakeholders: To ensure that the global mapping and stakeholder engagement activities are relevant to policymakers concerned with COVID-19, the team will research examples where delivery units are playing a role in disaster response or crisis management situations and explore whether there are useful lessons from this that could potentially be further researched and shared with stakeholders.
- Ghana country work: The team proposed potential new research activities which would directly address current issues raised by COVID-19. The research team is currently offering technical assistance to the National Education Reform Secretariat (NERS) on their rapid phone-based survey which aims to understand the impact of digital interventions to support students rolled out by the government, including challenges faced by parents/students and the education workforce. In particular, the research team is helping NERS devise a sampling strategy for the survey, developing instruments, and assisting in bringing together other actors within the Ministry who are interested in conducting COVID-19-related surveys.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

No previous recommendation.
Changes to the ‘DeliverEd’ project level results framework have been agreed reflecting the major impact of the COVID 19 pandemic on the research, ensuring an ambitious, but effective and deliverable set of outputs. This AR recommends that these are incorporated into the overall BESTA logframe, alongside any finalised or updated indicators related to the output area on new research methods. This should be done in the first three months of the reporting year.

Impact story: Understanding the impact of digital intervention during COVID in Ghana

Through our support for the Delivery Approaches work, the UK has worked with the Education Commission to support the Government of Ghana to design a telephone survey assessing Ghana’s COVID-19 education response. The survey seeks to understand the Ministry of Education’s digital interventions, including the reach and impact on students and parents, as well as how the education workforce is supporting learning during school closures and is preparing for school reopening. The Commission team has had policy impact in three areas: (i) the scope of the survey, which has been broadened to include the education workforce; (ii) the sampling strategy, which has been revised to include students for whom recent pre-COVID learning assessments are available; and (iii) coordination and alignment with other survey initiatives within the Ministry of Education.

Output Title	New global approaches to tackle learning challenges/constraints
Output number per LF		4	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Robust Education Workforce Report produced and publicised	3 peer reviewed final country reports, including funded, education workforce reform plans with evidence of government ownership / capacity	Achieved: All three country reports have now been finalised and published on the Education Commission’s website here.
4.2 / New or improved reports, evidence, networks to tackle major constraints to learning delivered through BESTA funding : Humanitarian actors have access to a MHPSS Minimum Services Package (MSP) that enables improved MHPSS programmes in education response in emergencies	Structure and content of the education chapter developed of minimum services package for mental health and psychosocial support (MHPSS) developed / 20% member organisations of IASC MHPSS Reference Group demonstrate commitment to Strengthened integration of MHPSS through endorsement of the MSP for MHPSS.	Met Expectations (structure and content of the education chapter developed in July 2020) / Moderately exceeded (27% from IASC MHPSS Reference Group) from targeted (I)NGOs took part in a multi-stakeholder key informant interview and consultation process).

Briefly describe the output’s activities and provide supporting narrative for the score.

The Education Workforce Initiative (EWI) project is jointly funded by Children Youth and Education Department and the Education Research Team through the BESTA programme. It aims to take a fresh look at how to tackle one of the main constraints to improving learning in many developing countries: quality and number of teachers and other education staff. It draws on evidence from in-depth case studies on how education workforce reform is implemented and examples of innovation. An international High-level Steering Group is overseeing this work. Its objectives are to: (1) Catalyse innovative approaches to expanding, strengthening and diversifying the education workforce; (2) Generate new insights in to how workforce reform has been implemented; (3) Establish cross-sectoral and geographical learning and collaboration; (4) Support the development of country-specific options for education workforce reform.

The project was originally due to close in December 2019 but was extended to September 2020 when it became clear that Covid-19 related disruption would create significant delays to final planned activities. Following the publication of the Transforming the Education Workforce Report in October 2019, the Education Commission have developed 3 country reports in partnership with Ministries of Education in Ghana, Sierra Leone and Vietnam with good levels of government engagement and ownership.

In Ghana, the EWI Country Report has been well received and the Minister for Education has expressed his commitment to implementing the proposed new workforce designs. EWI is currently pursuing funding for the implementation phase. The in-country partner, PwC, has held multiple stakeholder sessions, and pivoted activity to deliver some additional valuable COVID-19 outputs such as a report on ‘Implications on schools’ closure for the future of the Ghana Education Service workforce’ providing recommendations for how to accelerate implementation of the most relevant elements of the new workforce design.

In Vietnam, work has been completed to evaluate the efficacy of an innovative ‘High Touch High Tech’ model, which promotes teacher interaction with students and shows the value of technology-enhanced tailored instruction (adaptive learning). The evaluation results, which have been shared with the Ministry of Education, reflected substantive improvements in both teacher and student outcomes, demonstrating the promise and potential impact of the approach. The Vietnam country report was produced and published as planned, and also translated into Vietnamese. Country engagement around the report and evaluation results has been challenging due to the ongoing urgency of the COVID-19 response and changes in leadership at the Ministry.

In Sierra Leone, a country report, research and policy papers and flipbook were shared with the Ministry of Basic and Secondary Senior Education (MBSSE), and Sierra Leone Teacher’s Corner. The team have now secured follow on funding from the FCDO Sierra Leone office to continue work into a third phase and translate the research and analysis undertaken so far into policy and practice. A highlight of this period was the contribution of the EWI project in terms of policy dialogue and design of Covid-19 educational response.

The EWI team embarked on a series of COVID-related communications harnessing the research and findings from both the report and country work and leveraging these assets for an additional purpose and audience. The first piece in this communications series was a blog “Responding to COVID-19: Harness the Education Workforce” (April 24, 2020) outlining how the three visions from the report can help shape responses to school closures, school re-openings, and long-term school disruptions. The team collaborated with Cambridge REAL/RISE, Pratham and Education Development Trust. Many EWI and EC partners cross-posted and shared the blog (see comms section). The second piece of the comms series was the first of a set of briefs on Transforming the Education Workforce and COVID-19 which aims to take key concepts from the report and highlight their relevant insights for responding to the COVID crisis. The first in this set - Learning Teams - was developed, will be published (quarter 4, 2020) and promoted with accompanying social media.

EWI Spotlight: Innovative Analysis to Support the COVID-19 Response and a Learning Team Approach

To support the Ministry of Education and TSC with the COVID-19 response, the team created the Sierra Leone Vulnerability Index to help prioritise schools for provision of support services. The index has two dimensions: urgency and vulnerability. The individual measures of each dimension are weighted according to their relative importance by the choice of the user:
- Urgency - identify where students are lowest performing and least served
- Vulnerability – identifies where schools and communities are most geographically remote from urban centers and access to utilities, and most exposed by poverty
The index can be used for regular programming purposes but has also been developed with special attention to the current COVID-19 crisis. As a result, a number of indicators particularly relevant to this criteria were added within the index, including school water access and mean distances from schools to water points and health centres.

This programme component is also funding UNICEF to develop a Minimum Services Package (MSP) for implementing mental health and psychosocial support (MHPSS) in education in emergencies (EiE). This will address the knowledge gap on ‘what works’ for integrating MHPSS in education. The Education MSP is one of three packages within a larger initiative. The other two packages are integrating MHPSS in health and child protection which is funded by the Government of Netherlands. Output 1 measures progress of the Education MSPs development.

Member organisations of the Inter-Agency Standing Committee on Mental Health and Psychosocial Support (IASCC MHPSS) Reference Group have demonstrated their commitment to the MSP through their engagement in the development process. The IASC MHPSS Reference Group includes: UN agencies such as UNICEF, WHO and, UNHCR; networks such as Inter Action and The Inter-agency Network for Education; and over 30 International NGOs such as Save The Children, War Child Holland and Jesuit Refugee services.100% of the reference group members participated in the in-person meeting in November 2019. A virtual multi-stakeholder key informant interview and consultation process was held throughout March and April, and involved 51 participants (27%), representing targeted (I)NGOs implementing EiE and MHPSS work. Feedback has developed key recommendations for moving forward which include a focus on end-user engagement, ensuring the package can be contextualised, and maximising integration of the three areas.

Covid-19 had a minimal impact on the programme, but it did mean adaptions to in-person consultations were required. The multi-stakeholder key informant interview and consultation process had to be changed from one single, large consultation in-person to online. With feedback focusing on usability and an emerging need to adapt to Covid-19 to gather the best possible inputs and bring the advisory group together to make some key decisions, a Human Centred Design team has been engaged to support field engagement, the feedback process and end-design of the MSP product.

Progress has been made on the development of the Education MSP in its first year. As well as consultations, a literature review was completed, and key resources gathered from contributions on MHPSS and Education in Emergencies online fora were analysed. The first draft of the education content was developed in July 2020 based on international standards, evidence of best practices and consultation with education and MHPSS experts. The first integrated MSP (including education, health and child protection) was also developed and is currently undergoing internal revision by UNICEF, WHO and UNHCR. The full peer review will take place immediately.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

No previous recommendations.

One challenge found in the MHPSS work was that existing guidance for MHPSS within education tends to be less detailed and there is a greater need for expert consultation and consensus. More frequent and detailed expert consultations have been scheduled to address this. Relatedly, to be of operational value, the MSP will need to be a more fully integrated product, with the different content areas linked and supporting each area, as opposed to siloed and distinct, separate content areas. This AR recommends that FCDO explores how to test the integrated MSP in the same demonstration or pilot sites, during the same time period to address this integration. These sites will be selected in the coming reporting period and testing will take place in the following year, lead by UNICEF.

D: RISK

Overview of risk management

Key changes to the programme’s risk profile and exposure over the past year centre on the COVID-19 pandemic, resulting lockdown and related implications. The impact has varied across the programme and key mitigations by project delivery partners include:

- Extending timeline for some activities
- Collecting research via online instead of in-person methods
- Ramping up ‘virtual’ engagement of key stakeholders
- Reviewing/ amending delivery outputs to ensure they remain ambitious but achievable, in context of the global situation.
Despite these changes, there are no major changes to the programme theory of change – and the majority of programme milestones remain unaltered.

As the effects of the pandemic continue to play out, the programme team will continue to work with project leaders to continue to identify, monitor and mitigate emerging or developing risks, tracked through quarterly partner reporting, engagement with component leads and regular programme management conversations.
E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

This is a multi-component programme, working with several large tier-one delivery partners. The programme also draws on expertise from across the Department (statistics, education advisory capacity). To appropriately manage this, the SRO and programme team take a proactive and hands-on approach to programme management and technical delivery.

The FCDO’s Education Research Team (ERT) in the Research and Evidence Division provides technical leadership and provides funding through BESTA for two projects covered in this AR: the Education Workforce Initiative, and the ‘DeliverEd’ delivery approaches research. Additionally, ERT also lead overall work in Output area 3 on new research methods.

CYED’s programme team (consisting of SRO/Programme manager, governance adviser and project lead, programme officer, and several technical component leads) maintain oversight of the programme and ensure it is compliant with FCDO Smart Rules and delivering effectively. This oversight ensures that BESTA programme outputs are satisfactorily delivered as well as taking advantage of complementarities with other FCDO programme and policy priorities. Effective management of the programme has been delivered by the core team and individual component leads ensuring strong financial management and programme compliance. The team meets weekly to review the BESTA delivery plan, identify any key issues and milestones, and agree actions and processes, discuss risk and agree any relevant mitigations. At least quarterly reporting is provided by programme partners – managed by individual component leads.

The programme team coordinate the end-of-month finance processes in partnership with CYED’s finance business partner and CYED Central Programme Lead. Programme spend and forecasting have been on track this year. Funding from BESTA’s strategic funding component this year was reallocated through the FCDO ODA prioritisation exercise resulting in some delayed payments and a slight reduction in the strategic funding pot available for FY 2020/21.

The programme is continuing to deliver good value for money across FCDO’s ‘four Es’ measures: Economy, Efficiency, Effectiveness and Equity. The programme teams are in regular contact with key partners on programme finances and deliverables. As detailed with examples in the above section on Output 1, UIS have undertaken extensive work to support and improve their financial stability, improving sustainability and reducing costs where appropriate. The GEM team have implemented a series of Value for Money indicators, against which they report to FCDO. A full update for 2020 has not yet been provided due to the impact of COVID 19 on data collection abilities in particular areas, however they continue to demonstrate good progress against key cost drivers and making changes to make savings and maximise development impact. Both UIS and GEM are playing a significant role on improving equity of data across a range of exclusionary factors and exploring the barriers to effective inclusion of marginalised children. The MHPSS project continues to deliver against expectations and FCDO benefits from an economy and efficiency perspective because Dutch support to the overall development of the packages offsets some associated costs. The EWI project was able to make effective use of existing project knowledge assets, adapting existing in-country networks and expertise to provide COVID19-specific advice to partner governments on workforce issues as well as producing several knowledge products addressing workforce implications of COVID.

Date of last narrative financial report	Various – up to date for all delivery partners	Date of last audited annual statement	Various – within 1 year