## Annual Review of UK ACT 2021

Title: UK Action to support Developing Countries Fighting Corruption
Programme Value £ (full life): £39.7m		Review date: 24.03.21
Programme Code: 300597	AMP start date: 24.12.19.	AMP end date: 31.03.25

Summary of Programme Performance

Year	2016	2017	2018	2019	2020 (PCR)	2021
Programme Score	A	A	A+	A	A	A
Risk Rating	Major	Major	Moderate	Major	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Project GB-GOV-1-300597 Documents (fcdo.gov.uk)

GLOSSARY

AC / AFO / AML / BCIU	Anti-Corruption / Asset Freezing Order / Anti-Money Laundering / Bribery and Corruption Intelligence Unit
CoLP	City of London Police
CPS / CRT	Crown Prosecution Service / Civil Recovery and Tax Team
FCDO / HMG	Foreign Commonwealth and Development Office / Her Majesty’s Government
IACCC	International Anti-Corruption Co-ordination Centre
ICU	International Corruption Unit
NCA / OACU	UK National Crime Agency / Overseas Anti-Corruption Unit
ODA	Official Development Assistance
OGD / PCR	Other Government Department / Project Completion Report
PEPs	Politically Exposed Persons
POCU	Proceeds of Corruption Unit
ToC	Theory of Change
UK ACT	UK Action to Support Developing Countries Fighting Corruption Programme
UKCA	UK Central Authority
UWOs	Unexplained Wealth Orders

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme

The UK ACT Programme from 2020-2025, provides up to £39m to UK law enforcement authorities to pursue and investigate money laundering and bribery related to developing countries and with links to the UK. The year under review, is the first year of a new phase of the UK ACT Programme, which has run in several phases since 2006.

The aim of UK ACT is to reduce the incentives for corrupt individuals in developing countries to use the UK to launder money, and to reduce incentives for UK companies and nationals to bribe in developing countries. The main effort of the Programme is delivered through the International Corruption Unit (ICU) and Bribery and Corruption Intelligence Unit (BCIU) of the National Crime Agency (NCA), which identifies and then investigates cases, progressing them towards criminal prosecutions or asset seizure through civil asset recovery. UK ACT also funds a small team within the Proceeds of Crime Unit (PoCU) of the Crown Prosecution Service (CPS) to progress asset recovery following conviction. A further two staff in the UK Central Authority (UKCA) in the Home Office support developing countries’ mutual legal assistance requests. One remaining staff member in the Overseas Anti-Corruption Unit (OACU) at the City of London Police (CoLP) is bringing an important legacy case to a conclusion.

The Programme has been and remains very successful. Since it began in 2006, 49 money laundering and 86 bribery cases have been concluded and over £1.1billion of assets have been frozen, confiscated or returned to developing countries. £741million of the that sum relates to the past five years since the ICU was created from the two police teams who previously carried out the work. The ICU currently manages a portfolio or around 25 live cases. A real and symbolic success during this year, was the return of £4.2million of stolen assets to Nigeria in relation to the long-running case of James Ibori, a former governor of Delta State in Nigeria. The Metropolitan Police Unit, a forerunner to the ICU, had investigated the Ibori, the assets were confiscated by the CPS Unit funded by the Programme and the assets were returned as part of a cross-HMG effort.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

In March 2020, UK ACT was due to gradually expand by 25% over the five years of the Programme. However, because of the COVID pandemic and consequent reduction in UK GNI, the aid budget was cut during the reporting year and this had a consequent impact on funding. Plans for expansion were stopped halfway through the year and the initial programme budget for 2020/21 was reduced by 14.79%, reducing the budget to levels in previous years. This meant that the proposed increase in NCA staff in ICU, BCIU and the Civil Recovery and Tax Team (CRT) did not go ahead. This has had a particular impact on the CRT which works on Unexplained Wealth Orders (UWOs) and Asset Freezing Orders (AFOs), which are a high-profile addition to the law enforcement toolbox on corruption. Further reductions are anticipated. However, the budget for the coming financial year 2021/22 will not be known until after this Annual Review is completed and this creates significant uncertainty for the staff and for the future work of UK ACT.

The pandemic has also had an impact on the work of the Programme, with travel curtailed and most work moving online. The pandemic has increased the already serious constraints posed by the lack of capacity in the court system with many hearings being listed for one, and sometimes two years ahead. These delays are damaging to the work of the Programme and a major contributing factor to the length of time it takes to recover and return stolen assets and to bring perpetrators to justice. The discussions around the budget prioritisation exercise have, however, made it clear how important the Programme is to HMG’s efforts to tackle corruption.

The Programme is performing well across all outputs and has therefore scored A. Some of the indicators were adjusted during the year to address the impact of the pandemic and the budget cuts. Most indicators have been met and only some minor indicators have been missed. This is a testimony to the work of programme partners who have worked hard to deliver the programme targets in challenging circumstances.

Major lessons and recommendations for the year ahead

This phase of the Programme was re-designed in 2019 and the Annual Review does not recommend any fundamental changes to the objectives or operation of the Programme at this stage. Once the new budget position is known, adjustments may need to be made and this is reflected in the Review recommendations.

#	Summary of Main Recommendations
1 / and 12	Once the 2021/22 budget is confirmed, the programme team and programme partners should review priorities and adjust the financial proposals in the business case.
2	The log-frame should be reviewed to ensure targets are stretching but achievable in the new budget situation and as a result of findings in this Review. The new targets should take account of the continuing impact of the pandemic; and they should be re-calibrated for over- or under-achievement in the reporting year. Particular attention should be paid to indicators 1.1 (cumulative number of money laundering cases); / 1.2 (cumulative number of bribery cases) / 1.4 (cumulative number of foreign mutual legal assistance requests supported and processed by UK Authorities and UKCA); / 4.1 (intelligence packages to ICU); and / 5.2 (ICU visibility).
3	The programme team and programme partners should monitor the impact of any budget cuts on the work of the programme, the capacity to deliver on government priorities and raise this as appropriate at senior levels.
6	As the partnership with the City of London Police (CoLP) comes to an end, FCDO should capture learning from the COLP team.
7	It is recommended that the programme team and programme partners monitor the impact on the Programme of delays in courts in the UK and raise these issues at the appropriate level.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The Theory of Change (ToC) was refreshed as part of the 2018 Evaluation of UK ACT, reviewed in the 2020 Programme Completion Review (PCR) and is as follows:

‘The increased reputational risks, decreased financial rewards and reduced public tolerance for corruption will reduce incoming money laundering, bribery and corruption to the UK by Politically Exposed Persons (PEPs) and reduce outgoing money laundering, bribery and corruption by UK companies and nationals.’

The desired Programme impact is that the culture of impunity for corruption is reduced in developing countries by the UK taking action to recover and return assets stolen from developing countries; and by pursuing companies and nationals who bribe in developing countries. The Programme outcome is that incentives are reduced for corrupt individuals in developing countries to use the UK to launder money: or for UK business and UK nationals or their agents to bribe in developing countries.

Before the current phase of the UK ACT Programme, the log-frame was revised to include indicators to capture the increased results from the plans to expand NCA capacity and the new workstream of the UK Central Authority (UKCA). However, the log-frame has had to be readjusted during this reporting year because of the impact of the pandemic on budget and consequently programme activities. The indicators originally reflected an anticipated increase in investigations because of the increase to core NCA headcount. This would have recruited more intelligence officers, digital forensic officers, investigators, and civil recovery officers.

Unfortunately, the intended expansion of the Programme had to be stopped due to the reprioritisation of the budget in 2020. Over the reporting year, FCDO programme staff and partners agreed to the necessary changes to the log-frame to adjust to the reduced budget situation. The main impact is to indicators relating to proposed new staffing in the Civil Recovery and Tax Team (CRT) dealing with Unexplained Wealth Orders (UWOs). Because of the budget cut during 2020, this CRT work is not going ahead, and the relevant log-frame targets have been reduced to zero. Some NCA and UKCA indicators have also been reduced because of travel restrictions during lockdown and social distancing restrictions.

Describe where the Programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Despite external factors such as the pandemic and the budget cut which have impacted delivery and milestones, the Programme has performed well, scoring A.

The log-frame adjustments during the course of the year have resulted in the Programme remaining largely on track. For the year ahead, it is important that the log-frame targets are regularly reviewed, especially once budgets for the next financial year are confirmed.

Some log-frame targets were not met, all due to the pandemic. For example, 3.2(b) (assets confiscated) did not meet the targets because of court delays. While courts are now operational again, there are still lengthy delays due to lockdown backlogs. Corruption cases are not regarded as priority, compared to cases where individuals are in custody, therefore the court delays are likely to impact the programme results for several years. On the indicator relating to intelligence activities, other agencies have had to scale back their activities because of the pandemic and this has impacted indicator 4.2. The ICU is hopeful that activities will increase in 2021.

While the future funding of the Programme remains uncertain, it is difficult to accurately plan for the year ahead. This will only be possible when the budget for 2021/22 is confirmed.

Recommendation 1

Once the 2021/22 budgets are confirmed, the programme team and programme partners should review priorities and adjust the financial proposals in the business case.

Recommendation 2

The log-frame should be reviewed to ensure targets are stretching but achievable in the new budget situation and as a result of findings in this Review. The new targets should take account of the continuing impact of the pandemic; and they should be re-calibrated for over- or under-achievement in the reporting year. Particular attention is needed on indicators 1.4 (cumulative number of foreign mutual legal assistance requests supported and processed by UK Authorities and UKCA); 4.1 (intelligence packages to ICU) and 5.2 (ICU visibility).

Recommendation 3

The programme team and programme partners should monitor the impact of any budget cuts on the work of the Programme, the capacity to deliver on government priorities and to raise this as appropriate at senior levels.

## C. DETAILED OUTPUT SCORING

Output Title	The sustained and increased level of investigation of grand corruption (the theft of significant public assets by senior foreign officials) and international bribery impacting lower income, lower middle-income countries (priority), middle-income and upper middle-income countries (lower priority), and with a connection to the UK. This includes the investigation of related activity by professional enablers and efforts to recover assets using civil powers.
Output number:		1	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	N/A

Indicator(s)	Baselines and Milestone for this Review	Progress
1.1 Cumulative number of MONEY LAUNDERING cases (a) concluded over duration of programme since 2006 and (b) cases currently under investigation and (c) number of file submissions to the CPS.	Baseline / (a) 44 (b) 11 (c) 1 / 20/21 Target: / (a) 44 / (b) 12 / (c) 1	(a) Target exceeded - 49 / (b) Target not met - 6 / (c) Target exceeded - 5
1.2 Cumulative number of BRIBERY cases (a) concluded over duration of programme since 2006; (b) cases currently under investigation and (c) number of file submissions to the CPS.	Baseline / (a) 79 (b) 11 (c) 1 / 20/21 Target / (a) 80 / (b) 12 (c) 1	(a) Target exceeded – 88 / (b) Target not met - 6 / (c) Target met - 1
1.3 Cumulative number of UWO / PART 5 CIVIL RECOVERY investigations commenced since April 2020.	Baseline Previously Not Collected / 20/21 Target- / N/A	Removed from the log-frame due to reduced budget in 2020/21
1.4 Cumulative number of foreign mutual legal assistance requests supported and processed by UK Authorities and UKCA	Baseline Previously Not Collected / 20/21 Target- / 1	Target exceeded - 5 Kenyan cases are being supported/progressed.

This output performed well. The ICU has had a successful year with six cases submitted to CPS for charging and this represents a significant amount of work over the last months and years. The high number of cases at an advanced stage this year is because the portfolio of cases has been progressing since the ICU was established in 2015 which is when all most of these new cases were started. In the reporting year, ten bribery cases and five money laundering cases have also been concluded. ‘Concluded cases’ can also include civil settlements, civil forfeitures or disruptions where action is concluded.

Indicators 1.1(b) and 1.2(b), were not met, with six cases currently under investigation for money laundering and bribery against targets of 12 in each indicator. This is because many cases under investigation have moved to charging or have been completed during the reporting year, which are successful outcomes. On reflection, these two indicators do not fairly reflect the success of moving out of the investigation stage into later stages of the process. This has resulted in targets not being met, when the reason for missing the targets is because of good progress in the investigation stage. It is therefore recommended that the ICU and FCDO programme staff review and adjust these indicators to fairly measure progress in the next reporting year.

The main impact of the reduced budget in 2020/21 on this output, has been on the UWO indicator 1.3. Because no staff were recruited, the CRT could not expand and could not increase the number of UWO investigations. While the budget for the next financial year is yet to be agreed, it is unlikely that funding will be available to recruit to these posts in the near future.

In the previous phase of the Programme, there was a concern that insufficient attention was being given to anti-bribery cases because of the NCA’s historic expertise in money laundering and because the ICU anti-bribery capacity was being built from scratch. However, in this reporting year six bribery cases are under investigation and ten cases have been concluded, indicating a better balance of bribery and money laundering cases in their caseload.
## The nature of the ICU’s investigations means that international requests for evidence are an essential part of the work. This includes evidence requests made by the ICU overseas, but also evidence requests made by overseas law enforcement of the UK. A new part of the Programme this year has been the addition of UKCA as a programme partner. UKCA supports ICU in processing mutual legal assistance requests from developing countries which need extra work and supports developing countries to build their capacity to use the international and UK systems. Therefore, this phase of UK ACT is providing support to UKCA for travel to meet overseas partners to advise on preparation and submission of mutual legal assistance requests. In UKCA’s first year of operation, they have made great progress, exceeding their target (indicator 1.4). They took advantage of a gap in lockdown to travel to Kenya to carry out training in person.

Recommendation 4:
It is recommended that the ICU and FCDO programme staff review indicators 1.1 (cumulative number of money laundering cases) and 1.2 (cumulative number of bribery cases) to ensure what is being measured correctly reflects progress.

Recommendation 5:
## It is recommended that UKCA and FCDO staff review indicator 1.4 to identify and measure the impact of the training being delivered in country and how this links to new requests. The wording in the log-frame is ambiguous and it should be clear that this includes cases which the UKCA are supporting/progressing, and not just new cases. This adjustment will give a true reflection of the work undertaken.

Output Title	The sustained and increased level of prevention and disruption of grand corruption (the theft of significant public assets by senior foreign officials) and international bribery impacting lower income, lower middle-income countries (priority), and middle-income and upper middle-income countries (lower priority) and with a connection to the UK. This includes prevention and disruption activity targeting professional enablers and efforts to deny access to proceeds of corruption and recovery of assets using civil powers.
Output number:		2	Output Score:	A+
Impact weighting (%):		25%	Weighting revised since last AR?	N/A

Indicator(s)	Baselines and Milestones for this review	Progress
2.1 Cumulative number of LIC, LMIC and MIC jurisdictions to which investigations in 1.1-1.3 above relate.	Baseline / 46 / 20/21 Target / 47	Target exceeded – 48 / Two new jurisdictions added.
2.2 Cumulative number of referrals by ICU & BCIU to other UK authorities or overseas authorities	Baseline / 98 / 20/21 Target / 103	Target exceeded -107
2.3 Cumulative number of instances where other law enforcement agencies in UK or overseas have taken on new work or broadened the scope of existing activity due to referrals, engagement, advice or support from ICU/BCIU.	Baseline / 10 / 20/21 Target / 11	Target significantly exceeded - 20
2.4 Cumulative number of outcomes resulting from POCU, ICU case disposals: / (a) number of individuals / entities charged with offences / (b) number of individuals/ entities successfully prosecuted / (c) number of alternative disposals / disruptions/ other significant outcomes (incl asset recovery and DPAs).	Baseline / (a) 4 / (b) 3 / (c)2 / 20/21 Target - / (a) 4 / (b) 3 / (c) 2	(a) Target exceeded -10 / (b) Target met - 3 / (c) Target met - 2

This output has been very successful with each target being met or exceeded and this has been achieved despite the difficulties caused by the pandemic and the budget reduction during the reporting year. Also significant, is the high level of referrals to other law enforcement agencies in the UK or overseas. These types of referral involve significant work by the ICU to advise and support other agencies, and often lead to new cases and broadening of the work of other law enforcement agencies.

Two new jurisdictions have been added this year to a cumulative number of jurisdictions where the Programme has worked. As this total is unlikely to change much in future, as the Programme has worked in most LICs and LMICs, the programme team should consider whether to remove this indicator. During this reporting period ICU have arrested and charged 10 individuals concerned in laundering the proceeds of crime through developing countries including DRC, Uganda, and India. This is measured in indicator 2.4.

This output also includes the legacy work of the City of London Police (CoLP). Until 2015, CoLP was responsible for investigating cases of bribery and corruption. Since the remit of the work was moved to the ICU, CoLP has worked to complete its portfolio of legacy cases under the Programme, and this is now down to one remaining case. CoLP are in the final stages of their investigation and have made significant progress in the last year. The pandemic delayed the processing of evidence, although this has not impacted the investigation to a large extent.

This output has been very successful overall. However, there is a risk that these results will not be sustained if there are further budget reductions and if the delays in the court system in England and Wales continue at current levels.

Recommendation 6

CoLP are in the final stages of their investigation, therefore it is recommended FCDO capture any further learning from the partner which can feed into the future of UK ACT.

Output Title	Sustained and increased level of stolen assets frozen, recovered and returned to developing countries by HMG or leading to referrals to other agencies.
Output number:		3	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	N/A

Indicator(s)	Baselines and Milestones for this review	Progress
3.1 Cumulative number of instances of criminal confiscation on POCU, OACU and ICU investigations, broken down by: (a) number of restraint orders obtained; (b) number of confiscation orders obtained.	Baseline / (a) 11 / (b) 6 / 20/21 Target / (a) 11 / (b) 6	(a) Target met – 11 / (b) Target met - 6
3.2 Cumulative £ of assets: / (a) subject to restraint; / (b) confiscated (value of confiscation orders) / (c) enforced (value of funds received) / (d) returned to developing world from confiscation work.	Baseline / (a) £370M (b) £14M (c) £5m (d) £74M / 20/21 Target- / (a) £370M (b) £14M (c) £5m (d) £74M	(a) Target significantly exceeded – 460M / (b) Target not met - £7M + / (c) Target exceeded - £6.98m / (d) Target significantly exceeded - £199m+ £4.2m pending in March 2021.
3.3 Cumulative number of referrals by ICU to CRT or other UK agency for Part 5 civil recovery disposals.	Baseline / 59 / 20/21 Target- / 65	Target exceeded - 78
3.4 Cumulative number of civil asset denial / recovery instances (NOT CRT): / (a) number of account freezing orders obtained / (b) number of account forfeiture orders obtained / (c) number of cash detention orders obtained / (d) number of cash forfeiture orders obtained / (e) number of listed asset detentions / (f) number of listed asset forfeitures	Baseline / (a) 12 (b) 3 (c) 5 (d) 5 (e)1 / (f)1 / 20/21 Target: / (a) 15 / (b) 4 / (c)6 / (d) 5 / (e) 1 / (f) 1	(a) Target significantly exceeded – 23 / (b) Target marginally not met – 3 / (c) Target marginally not met - 5 / (d) Target exceeded - 8 / (e) Target met –1 / (f) Target met -1
3.5 Cumulative £ of assets: / (a) frozen under AFO / (b) forfeited or settled further to AFO / (c) detained under cash detention order / (d) forfeited as a result of seized cash proceedings.	Baseline / (a) £750k (b) £139M (c) £46k (d) £99k / 20/21 Target / (a) £1M / (b) £139M / (c) £100k / (d) £145k	(a) Target significantly exceeded - £6.54m / (b) Target met - £139m / (c) Target significantly exceeded -£855k / (d) Target significantly exceeded - £384k.
3.6 Cumulative number of instances of CRT using UWO / other Part 5 powers for asset denial / recovery; / (a) number of UWOs obtained; / (b) number of standard civil recovery cases taken forward	Baseline – not previously collected. / 20/21 Target- / N/A	Removed from the log-frame due to reduced budget in 2020/21
3.7 Cumulative £ of assets: / (a) frozen in connection with UWO and / or Part 5 investigations / (b) recovered due to settlement or CRO	Baseline - not previously collected. / 20/21 Target- / N/A	Removed from the log-frame due to reduced budget in 2020/21

This has been a very successful year for the Programme in relation to freezing, recovering and returning stolen assets to developing countries. Several milestones have been significantly exceeded, particularly under 3.2 with £460million of new stolen assets frozen; and £199 million returned to Pakistan in a civil settlement. Overall, this has contributed to the £1.1billion of assets which have been frozen, confiscated, restrained, or returned under UK ACT, since the Programme began in 2006. This figure highlights the outstanding value for money of the Programme.

A relatively small but symbolic milestone has been the £4.2 million agreed for return to Nigeria in relation to the Ibori case. The investigation of this case was begun over ten years ago by the Metropolitan Police who led the asset recovery work under this Programme at that time. James Ibori was convicted and imprisoned by UK courts in 2012. However, because of the number of appeals by Ibori and his associates over the intervening years, the first return of money relating to this case could not be agreed with the Government of Nigeria until March 2021. The nature of anti-corruption cases is that they take a long time to conclude as is illustrated by the Ibori case, it can take several years for cases to be investigated, brought to trial and for assets to be confiscated and returned to developing countries. As the court system was under immense pressure before the pandemic, the speed of cases is unlikely to improve in the near future, now cases are subject to even further delays.

While some targets were narrowly missed under this complex output, most were exceeded, and the overall figures were impressive. The reason for the complexity of the indicators is to measure progress across a range of processes to get a good overall picture of the work of the ICU. However, as there can be more progress on some areas than others in any given year, it is expected that not all indicators will be met every year. Two indicators (3.6 and 3.7) have been removed from the log-frame due to the budget reduction in financial year 20/21. There was a freeze on recruitment to the CRT Team dealing with Unexplained Wealth Orders, therefore the Programme funded no work in that Team and the indicators have been paused.

Recommendation 7

It is recommended that the programme team and programme partners monitor the impact on the Programme of the delays in the courts in England and Wales and raise these issues via the Inter-Ministerial Group on Anti-Corruption, as appropriate.

Output Title	Enhanced tactical and strategic intelligence on UK-linked corruption affecting developing countries leads to new investigations and to inform existing investigations and planning by the ICU and FCDO.
Output number:		4	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	N/A

Indicator(s)	Baselines and Milestones for this review	Progress
4.1 Cumulative number and quality of intelligence packages supplied to ICU to initiate and support AML-related or bribery-related asset recovery, as well as disruption and prevention activity, in LIC, LMIC or UMIC jurisdictions, and to generate case work. This should include intelligence supplied to support: investigations by other UK enforcement authorities; prosecutions by overseas jurisdictions; prosecutions for separate but related crimes; and instances where the scope of other investigations is widened.	Baseline / 450 / 20/21 Target: / 500	Target significantly exceeded: / 901 packages were supplied.
4.2 Number and quality of strategic intelligence outputs relating to LIC, LMIC or UMIC jurisdictions or specific sectors/thematic areas, which are supplied to the ICU and FCDO in order to generate tactical work or strategic insight for NCA or other law enforcement agencies/HMG.	Baseline / 32 / 20/21 Target: / 40	Target marginally not met - 38

This output performed well. The Bribery and Corruption Intelligence Unit (BCIU) supplied 901 packages to ICU and these packages range from a simple Suspicious Activity Report to complex referrals. A package can be dealt with in hours or sometimes takes weeks, depending on the content. The high number of packages collected by BCIU, is based on the strong relationships BCIU have with the International Anti-Corruption Co-ordination Centre (IACCC) and the wider International Liaison Officer (ILO) network of the NCA. These relationships mean the BCIU can tap into networks overseas which enhance the quality of the intelligence packages. However, with such a variation in the level of time and effort required in an intelligence package, this is not the best method of assessing the input of BCIU to the work. This should be reviewed in the log-frame for the next reporting year.

The purpose of output 4.2, is to draw on intelligence, insight, and expertise from teams across the NCA more broadly than those funded by FCDO. While this has slightly missed than the log-frame target, there is no cause for concern regarding BCIU performance. The pandemic has stalled intelligence work across various agencies therefore the 38 cases are an impressive result.

Recommendation 8:

It is recommended that the target for indicator 4.1 is reviewed to capture the intensity of effort on different intelligence packages, as this overachieved by more than 50%.

Output Title	Increased ICU capacity and leadership enhances UK and developing country capacity to fight global corruption and the effectiveness of international law enforcement activity in AC.
Output number:		5	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	N/A

Indicator(s)	Baselines and Milestones for this review	Progress
5.1 Stock of human capital, measured as: / (a) an annual calculation of the % of permanent ICU personnel who have been on the unit for more than 12 months / (b) ICU staff annual attrition rate better than the industry average	Baseline / (a) 45% / (b) less than 13.6% / 20/21 Target / (a)50% / (b) less than 13.6%	(a) Target marginally not met - 45% / (b) Target met - less than 13.6%
5.2 ICU visibility, measured as (cumulative): / (a) Number of new meetings with industry & civil society on bribery & corruption matters; / (b) Number of new meetings with HMG & LEA partners on B&C policy, legislation / (c) Number of new meetings with developing country partners on B&C matters / (d) Positive ICU references in media reporting / (e) National, international, or sectoral conferences and workshops attended where ICU perspective sought (e.g., IFBT, OECD, UNCAC)	Baseline – Not previously collected. / 20/21 Target - / (a) 4 / (b) 3 / (c) 2 / (d) 1 (e) 2	(a) Target exceeded – 11 / (b) Target exceeded - 13 / (c) Target not met - 0 / (d) Target not met – 0 / (e) Target met - 2
5.3 Cumulative instances of ICU/BCIU/CRT being called on to deliver: / (a) training / (b) capacity building / (c) other substantive support to any other partner in UK or overseas.	Baseline – Not previously collected. / 20/21 Target - / (a) 1 / (b) 2 / (c) 1	(a) Target not met - 0 / (b) Target not met - 0 / (c) Target met - 1
5.4 ICU outreach work with business & civil society, targeting the risks posed by professional enablers. / (a) cumulative number of regulatory bodies engaged with; / (b) cumulative number of trade bodies / associations engaged with; / (c) instances of potentially actionable intelligence on professional enablers being generated or shared / UKCA outreach to improve asset recovery outcomes by providing training on MLAs and related evidence gathering. (d) number of MLAs	Baseline – Not previously collected / 20/21 Target - / (a) 1 / (b) 2 (c) 1 / (d) 1	(a) Target exceeded - 5 / (b) Target exceeded - 5 / (c)Target met - 1 / (d) Target exceeded – by 4. / 5 cases are currently being worked on since delivering training.

During this year, this output has performed well. Some indicators (5.2(c) &(d) and 5.3(a) and (b)), could not be met due to the pandemic. However, despite the challenges partners faced, most targets were exceeded.

Keeping experienced staff is critical. While the retention rate for ICU did not meet the target in indicator 5.1(a), this was only missed by 5%. The majority of staff who did leave during the first year of the new phase, did so for promotion or for a post overseas as part of natural churn. The freeze on recruitment for most of the year has also affected the achievement of this indicator. However, a good level of experience and knowledge from the ICU is being retained overall.

The outreach indicators under this output were strong and exceeded expectations. (Indicator 5.2 (a), (b) and (e)). The variety and quantity of meetings with industry, civil society and HMG is impressive and demonstrates the importance that ICU have placed on outreach to raise awareness of the issues surrounding corruption within various forums. As a result of this, the visibility of ICU continues to increase.

Indicator 5.2(c) and (d) were not met as these activities were suspended due to the pandemic. With restrictions, it has been challenging to arrange meetings with developing country partners.

Indicator 5.3 (a) and (b) were not met as training and capacity building was not possible due to pandemic restrictions. Indicator 5.3(c) was met, with ICU providing substantive support to an African country, regarding a corruption investigation.

The UKCA have exceeded the target under this output (5.4 (c) and (d). These cases relate to the only visit UK CA was able to make this year, when UKCA team members delivered training in Kenya.

Recommendation 9:

FCDO and ICU to review indicators 5.2 (c), (d) and (e) to consider whether it remains achievable as social distancing and travel restrictions are likely to remain in place during 2021. This indicator measures the visibility of ICU.

Recommendation 10:
## It is recommended that UKCA and FCDO staff review indicators 5.4(c) and (d) to identify and measure the impact of the training being delivered in country and how this links to new requests.

D: RISK

Overview of risk management

The most severe risk to the Programme is any future budget cut in 2021/22 which could seriously affect the work of all the programme partners. However, at the time of writing, the decisions about budget cuts have not been made. If the Programme goes ahead at a comparable level, the ICU will be able to continue with its current portfolio of cases but may not be able to take any new ones. This will have an impact on the pipeline of cases and the larger impact of the work.

Overall risk rating: Moderate

Risk Description	Gross Risk	Mitigation	Residual Risk
Covid-19 related partner risk - Partners may have to rapidly re-prioritise work as the pandemic continues and may not meet objectives.	Severe	Regular discussions with partners to readjust priorities.	Major
Pipeline of cases reduce because of reduced staffing in BCIU and ICU to develop cases. If there are further budget cuts, it is likely that no new cases will be possible until other cases are disposed of.	Major	Monitoring of the pipeline of cases on a quarterly basis to assess impact of budget cuts and to identify opportunities to develop new cases.	Major
Recovered assets not returned in a timely way and risk increased because of UK court delays caused by the pandemic.	Major	Legal proceedings are not within Programme’s control and recovery of assets takes time. Raise issue of court delays with seniors as appropriate.	Major
The budget may be reduced in 2021, which could affect the Programme achieving its objectives.	Severe	Cross-HMG discussion to raise awareness of impact of potential budget cuts. The programme team will work with UK ACT partners to ensure as much work as possible can continue and targets are met. However, PM staff will discuss possible log-frame changes with partners once budget situation is known.	Major
Low priority countries divert resources from work on FCDO priority countries.	Moderate	Issue raised and monitored in quarterly reports and meetings.	Minor
Low availability across agencies of additional law enforcement officers for anti-corruption / financial investigation work and expansion of unit.	Major	Issue raised and monitored to ensure prioritisation of new anti-corruption work and ensure appropriate staffing levels are retained. Skilled officers successfully recruited for NCA posts but monitor vacancy rates.	Minor
Fraud and corruption risk from partners misusing programme funds.	Moderate	All partners are OGDs therefore also have zero tolerance to fraud/corruption However, safeguards in place for approving payments of ensuring SRO approval. Programme team provide any conflict of interest returns as and when they arise. We alert parners to Aid Diversion Standards and encourage regular discussion about risk.	Minor
Partner organisations do not have robust safeguarding procedures in place, and this results in staff being at risk.	Moderate	All partners are OGDs so no enhanced due diligence checks and procedures are required by FCDO. The programme team will regularly engage with partners to check understanding and compliance; and to request regular updates of partner risk registers and review.	Minor

The UK ACT Risk Register is held on both AMP Risk Register and on the Delivery Plan. This is reviewed by the programme team on a monthly basis and a quarterly basis with the Senior Responsible Owner.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

All partners have performed well this year, with most log-frame targets being met or exceeded. Partners have worked in challenging circumstances, due to the pandemic. This has included travel restrictions, remote working, and court delays due to lockdown. The pandemic resulted in the reprioritisation of the ODA budget in 2020. Under UK ACT the budget was cut by 15.2%, reducing the budget to levels in previous years. While log-frames were amended to reflect this change, partners still produced impressive results.

Commercial Performance and Financial Management

At the start of the reporting period, the combined budget for the four implementing partners was £7.338m. This was an increase from the previous year's budget of £5.251m. The impact of the pandemic on the UK economy meant that GNI reduced, and this had an impact on the overall ODA budget. The consequent budget reprioritisation exercise meant that the programme budget was reduced to £6.252m during the reporting year, representing an overall budget cut of 14.79%. Most of this budget cut fell on the NCA International Corruption Unit and Bribery and Corruption Intelligence Unit because they receive most of the programme funding. In order to achieve this reduction of £1.086m, the planned expansion of the Programme was stopped, all staff recruitment was frozen, and the travel budget was cut. This did however allow the existing portfolio of work to continue.

All partners have achieved good financial management across the year. Due to the uncertainty of the budget due to reprioritisation, UK ACT programme staff maintained regular dialogue with the partners to ensure accuracy of forecasting and invoicing. The CPS quarterly forecast and timely submission of invoices has been excellent. NCA and UKCA forecasting is harder to predict given that UK ACT funds more than salaries. Despite the challenges facing these partners in their finance management, both performed well.

The expected yearly variance is less than 4% for the revised budget. This represents good progress since last year when variance was 6.6%. The forecasted out-turn across all programme partners is expected to be around £6.056m. This is a moderate forecast underspend when compared to the overall revised programme budget allocation for 2020/21 and primarily relates to vacancies in the NCA teams.

Across all programme partners, salaries are the major programme cost driver and staff vacancies continue to have the most significant impact on spend. The financial proposals in the business case recognised this and budgets were tapered over the 5-year programme period to account for teams building up to their full complement. However, the impact of the pandemic means that the planned expansion could not go ahead in the reporting period and is unlikely to be possible in following years. It is therefore recommended that the financial proposals in the business case for the remainder of the Programme are reviewed and revised once the budget for 2021/22 is known.

Financial management is a constant focus of the FCDO programme team through regular dialogue with partners and budget forecasting updating. This dialogue has increased during the reporting period because of both the completed budget prioritisation exercise for 2020/21 and the current exercise for 2021/22.

 Programme Management

The pandemic and budget changes have increased the demand on the programme management workload for this financial year. Despite the increased tasks for UK ACT team and partners, the programme management of UK ACT has been effective.

Programme staff and partners maintain regular contact and issues and risks are escalated quickly and partners respond to ad hoc queries quickly. FCDO staff ensure the Programme is compliant with Smart Rules throughout the year. The Senior Responsible Officer is an experienced manager of programme and policy issues.

As a result of the pandemic, all partners have faced challenges in achieving the programme expectations. However, all the partners have been flexible in adopting new ways of working and this has mitigated some of the adverse impacts. For example, UKCA have been unable to carry out the number of in-country visits as planned to deliver training but have pro-actively used virtual training methods to achieve log-frame targets. In some cases, mitigating the impact of the pandemic is outside partners’ control. For example, lengthy delays in the court system are adversely impacting the work of ICU and CPS but there is little that can be done.

In relation to assets, the ICU are the only partner with physical assets, including seven vehicles, laptops, and software, for which they maintain an asset register which is checked with partners quarterly. This would normally undergo a visual check annually but due to the pandemic travel restrictions, this has not been possible.

Throughout the year, all programme partners have produced a high standard of narrative reports, (although CPS can often be slow in its submission) which are used during quarterly meetings between the Programme team and partners. The programme team meet on a more frequent 6-weekly cycle with UKCA, because they are a new partner in the Programme and are becoming familiar with FCDO programme management requirements.

Recommendation 11:

It is recommended that the programme Team undertakes this visual asset register check as soon as possible after travel restrictions are relaxed.

Value for Money

The measures of value for money set out in the business case are:

1. Cumulative total of assets frozen compared to cumulative total of money spent to fund the units.
2. Average length of time for cases from inception to prosecution as compared to OECD average of 7 years.
3. Number of additional cases taken on by ICU compared to increases in number of staff, weighted for size of case.
The pandemic and the budget cuts this year have impacted on the measures of value for money. Court delays have increased, which will impact on measure 2; and as the budget was reduced, no additional staff were recruited so no additional cases could be taken on. New measure will be introduced for the next reporting year.

However, the Programme is excellent value for money on several measures. In FY 2020/21, the programme costs were £6.252m with the total value of assets restrained being £460m; and assets recovered and returned, £199m. In March 2021, a Memorandum of Understanding was signed by Nigeria and the UK to return £4.2m of assets confiscated in the Ibori case which has been ongoing for over 10 years and was investigated under this Programme. More of these assets will be returned in the next year. Over the lifetime of the Programme, assets restrained, confiscated, and returned now exceed £1.1bn.

The Programme’s significant achievements also extend beyond these quantitative results. Tackling impunity is also a key aim of the programme and the Ibori return had great symbolic and deterrence impact, as the case also tackled the impunity of a State Governor in Nigeria. The ICU and UKCA through outreach work, have contributed to increasing awareness of corruption issues. Capacity building and increased co-ordination with overseas law enforcement have demonstrated results, most notably, in the increase of law enforcement outcomes or widened investigations by overseas law enforcement because of ICU investigations.

On the issue of efficiency, the primary costs of all programme partners are fixed cost salaries. The ICU have managed to make some savings by moving from buying to leasing cars as this saves some costs.

Monitoring, Evidence and Learning

An in-depth evaluation was completed in March 2019 and the findings were integrated into the 2019 business case. There has not been any new evidence work completed since then. A planned baseline survey was planned for March 2020 however this has been put on hold due to budget cuts in 2020/21.

Monitoring of the Programme continues through quarterly reports and regular meetings with each partner. There has also been significant additional engagement with senior staff in NCA and FCDO, particularly with regards to reprioritisation of budgets, managing risks and the Interated Review.

Learning has been an ongoing process through this year of the Programme. Specific examples are as follows:
- The CoLP have provided narratives of their cases and outreach work.
- The NCA, CoLP and FCDO held a joint workshop to share learning of the outreach section of UK ACT.
- Quarterly Reports and the Programme Completion Review in 2020 have provided an ongoing learning process which has led to adjustments to the Programme, additional meetings, and action as appropriate.

Recommendation 12:

Once the budget for 2021/22 is known, FCDO and partners to review financial proposals in the business case for the remainder of the Programme and revise.

Date of last narrative financial report	N/A for Other Government Department (OGD)	Date of last audited annual statement	N/A for OGD