## Annual Review Template – September 2020

Title: UK Partnerships for Health Systems
Programme Value £ (full life): £30,000,000		Review date: 5 Feb 2021
Programme Code: 205243	AMP start date: 30 Jan 2018	AMP end date: 31 Mar 2024

Summary of Programme Performance
Year	2018	2019	2020
Overall Output Score	B	A	A
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	Business Case
DevTracker Link to results framework:	Logical Framework

A. SUMMARY AND OVERVIEW

Description of programme

UK Partnerships for Health Systems (UK PHS) is a £30 million programme, which aims to help Low and Lower-Middle Income Countries (LMICs) build stronger, more resilient health systems and make progress towards Universal Health Coverage (UHC). The programme supports health partnerships, which are institutional relationships between UK health organisations and their counterparts in LMICs. These partnerships enable the reciprocal exchange of skills, knowledge, and experience, drawing on NHS volunteers working with counterparts and building capacity for improved health worker and health service performance for poor and vulnerable people.

The Tropical Health and Education Trust (THET), is the primary supplier delivering the programme and managing the grants. THET works closely with the Liverpool School of Tropical Medicine (LSTM), which provides technical support and leads on the Monitoring, Evaluation and Learning (MEL) functions. There are three partnership categories:
- Large grants, worth up to £350,000 each for 30 months, are for long-term strategic health partnerships focusing on health workforce development and health systems priorities. These are planned in ten focus countries: Bangladesh, Ethiopia, Ghana, Myanmar, Nepal, Sierra Leone, Somalia/Somaliland, Tanzania, Uganda, and Zambia.
- Small grants, worth up to £50,000 each for 18 months, will focus on innovation, learning and scaling-up existing health partnership activities in a wider range of LMICs.
- COVID-19 Response Fund (CRF) grants, worth up to £10,000 each for six months, support virtual health partnerships to share learning and psychosocial support between health workers working on the COVID-19 response in the UK and LMICs. The CRF was set up in 2020, recognising that health partnerships can offer an important source of support and expertise for the COVID-19 response while international travel is not possible.
Summary supporting narrative for the overall score in this review

The programme has been significantly affected by the COVID-19 pandemic: international lockdowns, travel restrictions and a reduced programme budget for 2020/21 (including some spend being moved into later financial years) have affected and delayed planned activities. The programme has flexed well in response to COVID-19 however, and overall has met the agreed deliverables, scoring an A.

One of the main deliverables this year included eight of the ten LMIC scoping visits and assessments, a major achievement during the COVID-19 pandemic. These aimed to identify the main needs of the health systems in the ten focus countries and areas that could be addressed through the UK PHS health partnerships. THET also set up five of the ten National Oversight Mechanisms (NOMs), with FCDO Health Adviser engagement and government representation, to ensure close alignment of health partnerships with country health system needs. THET responded well to the COVID-19 pandemic, switching to virtual scoping assessments, and rapidly designing the CRF: a new type of partnership grant specifically to support work on COVID-19, not included within the original Business Case. THET and LSTM have developed the MEL framework and database to facilitate evidence gathering across partnership projects and countries, and the programme strategy for gender equality and social inclusion (GESI). THET has also worked to increase the supply of available UK volunteers for health partnerships, designed an online platform to facilitate learning between partnerships (THET Pulse) and is working with LSTM and FCDO to refine the logframe.

Major lessons and recommendations for the year ahead

The main lesson arising from the COVID-19 pandemic has been the importance of applying a flexible and adaptive approach to programme management, including planning for worst case scenarios. There have been times where THET postponed some activities and deadlines, only to find that the situation worsened, and another postponement was unexpectedly required. Further changes came in the form of changes to the programme management team in FCDO and a corresponding adjustment period. The success of the UK PHS programme requires clear communication and agreed processes and ways of working between FCDO and THET.

The success of this programme will also heavily depend on its ability to remain aligned with the needs of country health systems as well as on the supply of UK volunteers. UK PHS aims to go beyond improving health workers’ technical skills to also contributing to wider health systems reform. This is a complex area depending on many factors beyond technical capabilities, and the scope of volunteer-driven partnerships, such as political and economic factors. The health partnerships must be realistic with their ambition, selecting the areas for joint working that are appropriate for volunteer-led learning, and involve the appropriate mix of technical and capacity building activities to ensure the Theory of Change (ToC) holds. COVID-19 is putting the NHS under pressure and has had detrimental effects on staff capacity and morale, and on their ability to participate in UK PHS. The programme design depends on the ability to travel, which is highly restricted at present. Developing effective ways of working virtually is challenging for this type of programme, which relies on face-to-face interaction and relationship building at lower levels of the health system.

Recommendations:
- THET and FCDO should continue to have regular discussions to ensure the programme remains flexible and adaptive.
- THET and FCDO should work together to set clear expectations related to programme management and clear, regular communication related to processes, such as deliverable approvals.
- THET should ensure greater quality assurance and scrutiny of deliverables, including from downstream partners, prior to submission and to allow adequate time for FCDO review.
- THET should set clear criteria and processes to assess the appropriateness of inputs to outputs to ensure that the health partnership is fit for purpose i.e. that it can offer the required technical inputs to address the priority issues defined in the scoping assessment.
- THET should continue to collaborate closely with country NOMs to ensure close alignment of health partnerships with country health system needs and complementarity with other projects to avoid duplication of efforts.
- THET should continue to review the demand and capacity for the programme from the NHS given the impact of COVID-19 on staff.
- THET should also continue to review to what extent the programme can adapt its volunteer model while travel restrictions remain in place, learning from other FCDO-funded partnership programmes, such as the Better Health Programme.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The ToC is underpinned by three interconnected outputs to outcome pathways:
1. The partnership change pathway describes how targeted, more strategic and coordinated partnerships can potentially improve health worker and health service performance in a more systematic way, reinforced by innovations through smaller partnerships;
2. The volunteer and UK health system change pathway describes how a stronger approach to UK volunteering will strengthen strategic partnerships’ outcomes; and
3. The host country change pathway describes how health partnership projects and volunteers should result in a strengthened health workforce, delivering higher quality health services.
The partnership and host country change pathways are expressed under Outputs 1 and 2 while the volunteering pathway is expressed under Output 3.

The ToC and the proposed steps for achieving outcome and impact remain valid, although the impact of the COVID-19 pandemic on travel requires a change in approach for delivering the outputs, to a virtual model, which the CRF aims to test. Health partnerships will collect data which will be useful in assessing this as will the planned independent evaluation.
THET, LSTM and FCDO have worked to refine and agree outcome and impact indicators as the programme has continued to take shape (see below). Output indicators and targets will be further refined as the health partnerships are established.
Impact statement: / SDG 3: Ensuring healthier lives and promotion of well-being for all at all ages, with a focus on universal health coverage (SDG Indicator 3.8	Impact indicator	Number of UK PHS projects demonstrating contribution to access to quality essential health services for people of all ages, in areas where partnerships are active
Outcome statement: / Improved capability of the health system to address national priorities, especially to meet the needs of the poor and most vulnerable populations	Outcome indicator 1	Number of UK PHS projects demonstrating positive outcomes in health worker performance
	Outcome indicator 2	Number of UK PHS projects demonstrating positive outcomes in health service performance (for the poor and most vulnerable)

The major change since the programme started has been the emergence of COVID-19, which has impacted on the programme’s activity timelines and budget profile. Since the programme was in the early stages when the pandemic started, it has not, to date, resulted in changes to the outcome and impact levels of the logframe. Indeed, COVID-19 provided an opportunity for the programme to flex and respond to the pandemic through the new CRF. Should the pandemic continue to disrupt travel for the foreseeable future, the ability of the programme to continue as planned in the Business Case, and therefore to achieve the planned outcomes and impact, may be hindered.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Overall, it is too early to assess the programme’s effectiveness in achieving its outcomes and impact since planned partnership activities have not yet begun due to COVID-19 related delays. There have been significant changes to the programme, including its staffing, budget, workplans and timetable due to the pandemic’s impact on health worker capacity, international travel, and FCDO’s need to flex UK ODA to the multilateral COVID-19 response. The ODA prioritisation exercise in summer 2020 to reallocate budget available to the COVID-19 response resulted in reprofiling £2.6m from financial year 2020/21 for UK PHS to 2021/22. This, as well as the inability to travel internationally, resulted in postponing the award of large grants until May 2021. An eight month no-cost extension to the programme, moving the contract end date from 2nd July 2023 to 31st March 2024, was secured and will enable the large health partnerships to maintain the planned 30-month duration.

The COVID-19 pandemic may have hindered the ability of some LMIC national stakeholders to fully engage in the programme so far and is likely to have had similar impacts on the UK workforce. Indeed, several partnerships reported to THET that health workers were too busy to contribute to applications towards the end of 2020. It is likely there will be fewer applications received than if there had been no pandemic, and health partnerships will not have the breadth of volunteers to choose from. The impact of the new COVID-19 variant on the NHS during winter 2020/21, when most of the proposal development for the large grants should be taking place, is particularly concerning. This, along with THET’s reduced staff capacity on the programme and the lack of face-to-face events in 2020 to stimulate volunteer supply, is likely to reduce the number of applications from newer, less established partnerships especially. A diminished pool of health partnerships could prevent the programme from having a system-wide impact in LMICs. THET has devised various approaches to address this, including a national level ToC, greater alignment with national health system priorities through NOMs and exploring greater synergy and collaboration between health partnerships. Through an analysis of potential new partners in the UK, THET has identified over 200 additional individuals and institutions not already part of a partnership, which may also help offset any reduced supply. THET will also develop a stakeholder engagement plan to raise awareness among UK stakeholders of the value of health partnerships both to LMICs and to the UK.

Despite these challenges, the programme has adjusted well and is on budget and making progress where possible. Establishing the CRF should enable the programme to contribute towards the achievement of programme outcomes while limited activity in other areas is possible. The relatively high number of applications received in response to the first round of CRF grants is encouraging. THET is going beyond Business Case requirements on GESI by ensuring that each large grant takes a GESI-specific approach to their projects. DFID committed to spend £5 million of UK PHS funds on capacity building for nurses and midwives and the programme has included a logframe indicator to measure progress on this and ensured this was considered within scoping assessments.

For the year ahead, THET will prioritise establishing the CRF grants and launching the call for applications for the large and small health partnership grants. FCDO will complete the work to secure a supplier for the independent evaluation, which was put on hold in 2020 due to COVID-19 and will establish a Steering Committee with relevant and appropriate expertise to help guide the programme to ensure greatest impact. THET, LSTM and FCDO will work together to ensure the target output milestones are appropriately ambitious to ensure outcome and impact indicators are achieved. Ensuring value for money will also be a key focus of the programme and THET will achieve this by ensuring health partnerships focus on the highest priority needs of LMIC health systems; collecting VfM data from health partnerships; and supporting partnerships to maintain cost-effective budgets.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The UK PHS programme follows the Health Partnerships Scheme programme (HPS) (2011 to 2017), which trained over 93,000 health workers in LMICs, contributed to health system strengthening and represented good value for money. The UK PHS aims to build on and learn from the HPS by fostering greater collaboration between partnerships and countries. The UK PHS’ focus on strengthening the health workforce and systems in LMICs and supporting the COVID-19 response, in line with the FCDO’s global health priorities to support health system resilience and recovery in the time of COVID-19. The scoping exercises and the number of applications received for the first round of the CRF demonstrate appetite for the programme both from LMIC and UK health institutions, although capacity to volunteer may be limited. There would be reputational risks if the programme were not to continue to both THET and FCDO.

Conversely, if the pandemic continues to hinder international travel and absorb the capacity of health workers, the feasibility of the programme to achieve its intended outcome and impact will be limited. THET aims to demonstrate through the CRF that the programme model can be adapted to a virtual one, and hence manage travel restrictions. THET should explore further adaptations to the programme model, learning from other partnership models, to enable the programme to continue despite COVID-19’s continued impact this year. However, the challenges of implementing a virtual model are likely to restrict effectiveness for this type of technical collaboration. FCDO and THET should also reflect on whether an altered model could still achieve intended outcomes and impact.

## C. DETAILED OUTPUT SCORING

Output Title	Accelerated and sustainable progress on selected health systems priorities in 10 focus countries [to be determined by scoping activities] (delivered by large strategic health partnership approaches that are aligned with UHC roadmaps and national health plans)
Output number:		1	Output Score:	A
Impact weighting (%):		45%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of large health institutional partnerships grants delivering activities aligned to national plans and FCDO commitment to nursing and midwifery development	Country priorities aligned with national plans & amendable to change through UK PHS health partnerships defined for Wave 2 and Wave 3	ACHIEVED: Wave 2 & 3 country priorities agreed in eight of ten scoping assessments (awaiting final sign-off from the Tanzanian Ministry of Health, Community Development, Gender, Elders and Children (MOHCDGEC)). Wave 4 scoping exercises (Ghana & Sierra Leone) are underway.
Number of large health partnerships performing to agreed HSS quality standards	HSS priorities defined by country ToCs for Waves 1, 2 & 3 / HSS quality indicators defined.	ACHIEVED: Complete for Waves 1, 2 and 3. Underway for Wave 4 countries. / HSS Quality standards defined.
Number of large health partnerships projects demonstrating contribution to gender equality and social inclusion (GESI) particularly for the poor and vulnerable	GESI strategy developed & approved by FCDO / GESI priorities for focus countries identified for health partnerships to respond to	ACHIEVED: GESI strategy approved by FCDO / All completed focus country scoping reports include GESI priorities
Evidence of national engagement and ownership in the programme (e.g. Countries with NOMs playing an active role in programme; HPs engagement at national level and/or with relevant decision makers etc.)	NOMs established for Waves 1, 2 & 3 countries / # and % of NOMs with national/federal government representation	PARTLY ACHIEVED: NOMs established in Myanmar, Nepal, Somalia/Somaliland, Uganda, & Zambia. Delays in Ethiopia due to difficulties engaging with MoH - should be resolved in January 2021. Recruitment of the NOM for Wave 3 countries delayed due to delay launching the call for applications to Q1 2021. / All five NOMs created so far have national/federal government representation. All NOM members (or potential NOM members) participated in the scoping assessments.

Briefly describe the output’s activities and provide supporting narrative for the score.

THET and LSTM have completed scoping assessments in eight out of the ten focus countries (Bangladesh, Ethiopia, Myanmar, Nepal, Somalia/Somaliland, Tanzania, Uganda, and Zambia), with the final two (Ghana and Sierra Leone) due for completion in early February. Separate scoping assessments were conducted from Somalia and Somaliland and these will also have separate NOMs, however for grant purposes they will be considered a single country. These were designed to take place in-country, with several days of key individual interviews (KIIs) and stakeholder workshops to validate the findings and agree on the health system priorities. While this happened for the Wave 1 countries (Myanmar, Nepal, Uganda, and Zambia), COVID-19 made many of the planned activities for other countries difficult. The methodology was adapted to self-administered questionnaires, remote KIIs, KIIs conducted by THET Country Directors, and, where feasible, workshops and small group discussions with UK staff joining remotely. However, it proved more difficult to engage LMIC stakeholders. As a result, the scoping reports are not as holistic and nuanced as originally planned, but they are aligned with national plans and identify priorities appropriate to volunteer-led organisational partnerships, although more work will be needed to ensure that the applicant partnerships can address these priorities effectively. THET produced full reports for each country outlining the status of the health system, gaps to be addressed and priority focus areas for health partnerships. Nursing and midwifery were identified as core components across all countries. A summary of the scoping assessments for each country can be found at Annex 1.

THET has also launched the call for applications for Waves 1 and 2 of the large grants this year for partnerships in Myanmar, Nepal, Uganda, Zambia, Somalia/Somaliland, and Ethiopia. The application window for Wave 1 has now closed and Wave 2 will close in early February. THET will review all applications and submit a short list to FCDO for approval. Part of Wave 3 launched late in 2020 for partnerships in Bangladesh and will close for applications in March. Tanzania was also due to launch at this time, however issues in securing approval on the scoping report in-country have caused delays. This call is due to launch in February.

LSTM developed a robust GESI programme strategy that was approved by FCDO, along with a GESI toolkit for health partnerships. GESI will underlay all aspects of the programme, and so far, has formed part of the core questions for scoping assessments and has been incorporated into the grant application form and budget.

NOMs have been successfully established in most countries based on recommendations from the MoH senior management and the FCDO Health Adviser. Members participated in the scoping assessments and agreed to the NOM Terms of Reference, including reviewing grant applications, and engaging with the programme on a quarterly/biannual basis. The NOM in Bangladesh is awaiting the appointment of the new focal point for development partners, and in Tanzania, on the appointment of a new THET Country Director. Both should be addressed by the end of March 2021.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The pandemic has meant delays and limited the progress planned for this output this year. THET have adapted their approach to drive forward progress. The redesign of the in-country scoping assessments has improved the economy of the scoping exercises. Each assessment originally entailed two UK staff travelling overseas for one week. Switching to a remote approach has cut out international flights, visas, vaccinations, accommodation, subsistence, and in-country travel across six countries. This cost-saving was slightly off-set by the need to pay for extra support for THET Country Directors to conduct the workshops and KIIs where it was not possible for UK staff to do this remotely. THET and LSTM were also able to reach more stakeholders, particularly those based outside of capital cities, increasing the equity. Several of the same LSTM and THET staff being involved in the scoping assessments in different countries increased the efficiency. As above, GESI formed a key component of the scoping, with all stakeholders requested to outline how the priorities identified would reduce inequalities based on factors such as gender, disability, age, etc.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The programme planned to award several large grants by March 31st 2021. Due to the budget reprofiling, THET and FCDO agreed that all large grant awards should be delayed to 2021/22. Another substantial change was the change in the design of the scoping exercises.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from 2020: During the remainder of the inception phase and start of delivery, special attention should be paid to the coherence of health partnerships within the focus countries, how they are well-placed to respond to the health system priorities identified, and their cumulative impact on the strength of the health system. This will need to be considered iteratively throughout the programme and driven by THET’s country teams.

Partly addressed: The programme’s scoping reports detailed each focus country’s priority health system needs. In some cases, these were ambitious in relation to the budget available. The priorities also needed to identify better which health system priorities were most amenable to being addressed specifically by a volunteer health partnership model rather than other models of development assistance. Following discussion, THET and LSTM have more clearly reflected this in the reports. NOMs will have oversight of the health partnerships to help ensure coherence and alignment with the health system needs of each country.

Recommendation from 2020: The programme should ensure delivery of the commitment to provide at least £5m of partnership grant funding to support nursing and midwifery development where this is identified as a priority by national governments and other stakeholders. Opportunities to align with initiatives for the Year of the Nurse and Midwife in 2020 should be identified and taken up.

Addressed: The logframe includes an indicator to measure the number of projects and amount of grant funding spent on nursing and midwifery activities. Many of the scoping reports highlighted health system priorities in relation to nursing and midwifery and several of the applications received for round 1 of the CRF focused on nurses and midwives. A member of the UK PHS Steering Committee will have expertise in nursing and midwifery from a health partnership perspective.

Output Title	Relevant UK expertise shared, new initiatives tested and taken up to address specific health systems constraints (delivered by smaller partnerships with potential for innovation, learning, and scale-up), and lessons learnt shared in countries and with the UK
Output number:		2	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of small partnerships supported to foster innovation, disseminate lessons, and influence scale-up (including as a contribution to the FCDO commitment to nursing and midwifery and GESI)	Small grant call for application documents completed and approved	ACHIEVED
Number of institutions demonstrating evidence of take up of innovations and lessons through the small partnerships, in both partner countries and the UK (reverse innovation)	N/A	N/A
Number of institutions supported to address the aims of COVID-19 response in LMICs	CRF established. / CRF grants processes agreed; agreed indicators and targets. / 1st cohort CRF applications awarded	ACHIEVED: CRF established and all processes agreed and signed off. Indicators and targets for grants agreed. / COMPLETED: 8 grant applications selected for award.

Briefly describe the output’s activities and provide supporting narrative for the score.

THET developed documents for the call for applications for the small grants. These will be available for projects focusing on innovation, learning and scale-up of existing health partnership activities to address clinical and health system challenges, or specific themes. THET have developed documents for the call for applications, which will be open to any LMIC in South East (SE) Asia and Sub-Saharan Africa on the themes of innovation, GESI (although GESI will also be mainstreamed through all grants), climate change, and blended and remote learning. THET worked closely with academics at Imperial College to ensure the call documents and accompanying guidance facilitate innovation. The call was due to be launched in 2020 and was postponed until early 2021 due to budget reprofiling.

Following a survey of health partnerships soon after the COVID-19 outbreak, THET proposed the establishment of the CRF, with grants of up to £10,000 for virtual partnerships. The fund aims to address health worker gaps in skills and knowledge to prevent and treat COVID-19, support the safety and well-being of health workers in LMICs, and/or provide support in maintaining essential health services. FCDO approved two rounds of the fund at a total of £500,000 taken from the small partnerships grant fund and we expect to award 30 grants in total. THET launched the first call for applications in September 2020, received 34 applications and recommended eight of these to FCDO for award (total funding of £79,145). The projects in eight countries (DRC, Somaliland, Myanmar, Rwanda, Uganda, Bangladesh, Zambia and Malawi) include online classrooms to support LMIC partners as they respond to COVID-19, strengthening the psychosocial support available to health workers responding to COVID-19, and supporting LMIC partners in maintaining essential sexual, reproductive and maternal health services throughout the pandemic.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The CRF was designed and the programme adapted using the same selection and staffing model and requiring no additional inputs compared to the other small grants fund, demonstrating efficiency. The nature of the CRF grants are economical, as partnerships will conduct projects involving no international travel, although it will be important to monitor the effectiveness of virtual partnerships. The virtual nature of these grants will enable partnerships to work more easily in multiple locations in the LMICs increasing the equity. As with the large grants, GESI is a key part of the application forms and reviewing criteria and including a specific GESI stream within the small grants we hope will provide real impetus and learning for the health partnership community.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Again, COVID-19 hindered the progress under this output, however the introduction of the CRF marks a significant step forward.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead - N/A

Output Title	The right conditions are in place in the UK for sufficient volunteers with the right skills to meet partner countries’ needs.
Output number:		3	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of UK institutions providing and supporting volunteers to work in programme countries	Mapping of potential UK partners not yet in a partnership in line with neglected country priorities completed	ACHIEVED: 83 individuals/ institutions identified and contacted which have not previously been in a partnership to address thematic gaps in partnerships
Robust evidence generated of the value of HP activity to the UK health workforce and health system and shared with UK health system stakeholders (CEOs of trusts, etc)	N/A	N/A
Number and % of key UK stakeholders aware of and supportive of sharing UK expertise through partnerships/volunteering	N/A	N/A

Briefly describe the output’s activities and provide supporting narrative for the score.

The activities this year focussed on increasing the supply of potential UK volunteers by encouraging institutions new to health partnerships to consider establishing one with an LMIC institution. THET conducted desk research to identify all existing health partnerships between the UK and LMICs, categorising findings by geographic location within the UK and LMIC, type of institutions involved and partnership themes. This allowed the identification of countries and health themes that have been under-represented to direct efforts. THET identified areas from each LMIC’s ToC that were under-represented in the existing health partnerships, and mapped UK institutions with the expertise to support these specific areas (through engagement with THET’s clinical advisers and trustees, LSTM, and desk research). Eighty-three senior-level individuals from UK institutions were identified and contacted to explain the programme and partnership model, encouraging them to apply. These institutions included royal colleges, universities, hospitals, regulatory bodies, health institutes, arms-length bodies (e.g. Health Education England, Public Health England, NHS Innovations), professional associations, NGOs, and campaigns (i.e. Nursing Now).

There were fewer opportunities to engage with UK health system stakeholders face-to-face this year to raise awareness of the programme. THET attended virtual conferences and events run by health institutions, particularly those without an established health partnership. THET presented the UKPHS at some of these online events, including at the NHS International Engagement Beyond COVID-19 webinar run by NHS Confederation, the NHS International Group, the THET annual conference in October and the THET April conference, ‘Partnerships in a time of COVID-19’.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

THET and LSTM staff time on UK PHS was reduced following the budget reprofile: the External Engagement Manager’s time reduced from 40% to 10%, and the Policy Manager’s time from 50% to 15%. However, efficiencies were gained since COVID-19 meant meetings and stakeholder events all took place online, saving time and money through not travelling. The costs of both THET conferences were absorbed by other programme income with THET receiving significant contributions from the Health Partnership networks at no cost. Due to the online nature of the THET conference, each panel included a speaker from an LMIC increasing the equity of the conference. Thirty percent of delegates attended from Africa or Asia and health workers from LMICs were able to attend at a subsidized rate or through a bursary scheme funded by another THET managed programme. The CRF aims to test whether virtual partnerships are effective in supporting mutual learning, improved health worker performance and other programme outputs, in line with proposal objectives.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

THET’s reduced capacity on the programme and COVID-19 restrictions meant they were less able to progress activities to increase interest from potential volunteers and support new partnerships. As outlined above, THET progressed these activities by conducting a desk review of potential UK volunteers and engaging them where possible online rather than in-person.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead - N/A

Output Title	Efficient and effective programme, partnership, and grant management to ensure VFM, and drawing on monitoring, evaluation and learning to continuously improve performance (working with the external evaluation provider, contracted separately by FCDO)
Output number:		4	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Robust system for UKPHS monitoring, evaluation and learning embedded at all levels and enabling adaptive programming, working with the independent evaluation provider	Working version of logframe completed as much as possible and approved / Programme MEL framework operationalised (Reporting templates finalised; database developed; tools identified)	ACHIEVED: Logframe agreed as much as possible. Cannot be completed until all grants established. / MEL Framework developed.
Effective grant management and timely completion of quality programme deliverables	Grant applications documents (Large/Small grants) finalised / Waves 1,2 and 3 Country scoping reports finalised / Supply strategy developed / # of deliverables completed within the agreed time frame / Quarterly reports submitted on time	PARTLY ACHIEVED: all deliverables completed to agreed timelines, however more focus on QA, analysis and VfM required.
UKPHS grant holder surveys and feedback demonstrate satisfaction with support provided by THET/LSTM (services include technical assistance for capacity strengthening, financial management, risk management, logframe and MEL plan development, facilitating learning, performance management, timely completion of partnership deliverables etc).	N/A	N/A
Number of large health partnerships that reach agreed benchmarks in prioritized principles of partnerships (i.e. reaching a score of 4 and above)	Partnership strategy approved	ACHIEVED: Partnership strategy developed and approved
Number of institutions demonstrating evidence of uptake of UKPHS knowledge products	N/A	N/A

Briefly describe the output’s activities and provide supporting narrative for the score.

THET and LSTM have done well to prepare the programme for supporting grants and grantees and to develop the MEL framework and processes. This Output has scored a B because, whilst most milestones were met including development of scoping reports, supply strategy, grant application documents, and the MEL strategy, further work was needed to produce final, quality assured deliverables, including clear methodology in the full and summary scoping reports and VfM through the CRF grants that we expect will be addressed going forward.

THET, LSTM and FCDO have developed a working version of the logframe, which will continue to be developed as grants and partnerships become established. A MEL framework has been developed and approved, including a programme-level ToC, MEL approach and evaluation measures, a value for money framework, grant holder MEL approach and reporting structure, and an outline of the guidance THET and LSTM will provide to grant holders. The MEL database draws on the GESI strategy and will capture data disaggregated, at a minimum, by age, sex, disability, different health worker categories and cadre of health professionals. It will also measure the different levels of vulnerability and exclusion for target populations to ensure equitable access to project outputs and outcomes. It is in the testing stage and should be ready for the start of the large grants in May 2021. THET also developed a partnership strategy, taking their Principles of Partnerships as its basis and outlining how they will carry out partnership assessments throughout the grant management cycle and implement a tiered capacity development plan with each grant holder.

To ensure the programme embeds learning at all levels and to remain adaptive, THET is developing a virtual learning and exchange platform, THET Pulse, launching in the Spring of 2021 to support health partnerships. This will provide a central point for the health partnership community to share their expertise. It will directly benefit health workers in LMICs participating in health partnerships who will have increased access to resources and support from the UK health community. Health workers in the UK will also be able to capture learning from low-resource settings, which may be applicable to the UK.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

The level of LSTM capacity for Output 4 was reduced this year due to the budget reprofiling, with LSTM focusing mainly on the scoping assessments. THET was able to negotiate both a delay and reduction in payments to the MEL database providers reducing outgoing costs and increasing economy. THET was also able to build on its own existing resources in the development of several of the processes and tools from previous experience managing health partnerships, making the process more efficient. Based on the GESI strategy, areas of GESI have been built into several components of Output 4, including the logframe, ToC, grant application forms and health partnership reporting templates, which ensures equity will form a core part of the programme.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The delay (due to budget re-profiling for the wider COVID-19 response) in appointing the evaluator to 2021/22 has hindered the progress of finalising the logframe as originally this was intended to be a collaborative process between the evaluator, FCDO, THET and LSTM. The delay in awarding grants means some of the milestones are not yet applicable, such as gathering evidence from established partnerships.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from 2020: Monitoring and evaluation will need to be carefully coordinated, particularly to establish the impact of the programme robustly and assess whether the ambition to promote a systems approach through the partnership model has been delivered. The programme’s Steering Committee should play an active role in supporting coordination between THET, LSTM and the appointed independent monitoring provider to achieve this.

Addressed by THET: THET and LSTM have developed the MEL Framework and THET has worked to increase the supply of UK volunteers available to increase the likelihood of achieving a system-wide impact. THET has also developed the Partnership Strategy, which will assess the health partnerships’ effectiveness throughout the grants. The budget reprofiling necessitated delaying the procurement of the M&E provider to 2021/22 and the Steering Committee has not yet been established. However, this is a priority for FCDO and will include a range of stakeholders to guide the programme towards success and ensure it remains adaptive.

Recommendation from 2020: The programme should remain flexible and adapt to UK priorities, such as the manifesto commitment to end preventable deaths of mothers, newborns and children. UK expertise has much to offer to these ambitious goals and the programme should seek to maximise the contribution of health partnerships to these agenda.

Addressed: The programme has already demonstrated its adaptability by quickly designing and establishing the CRF to respond to the pandemic. The design of the UK PHS programme, involving waves of applications for the various grants, will allow it to remain adaptive to changing needs and contexts. The Steering Committee, once established, will also help to ensure this.

D: RISK

Overview of risk management

Overall, the programme is facing major risks, mainly from the COVID-19 pandemic and its impact on health worker capacity and preventing international travel. However, with the agreed mitigation strategies in place, the overall risk rating of the programme remains moderate, reflecting that, while the nature and aims of the programme itself are not high risk, its ability to deliver effectively during the pandemic is constrained. Restrictions implemented to stop the spread of COVID-19 affected many programme activities and the budget reprofiling reduced the budget available for activities and THET staff time. Mitigating actions included delaying some activities to later years and securing an eight month no-cost extension to ensure that these delays don’t impact the duration of the large grants. Going forward, COVID-19 continues to be the biggest risk to the success of the programme as travel restrictions remain in place and the NHS and LMIC health systems remain under pressure, reducing capacity for potential volunteers to participate in the programme. The success of the programme is heavily dependent on the availability of volunteers, so this is a significant concern. The CRF grants mitigate the risk of travel restrictions, however the virtual partnership model, as it currently stands, will not be sufficient to achieve the intended impact. THET has alerted FCDO in advance of potential risks and has developed mitigation strategies with LSTM to offset these. We will continue to monitor programme risks at quarterly monitoring meetings.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

THET has submitted quarterly narrative and financial reports on time throughout the year along with updated risk and asset registers. THET and FCDO meet quarterly to discuss progress, plans going forward and risks. THET has finalised all deliverables within timelines agreed by FCDO. Considering the challenges the programme has faced this year, the volume of deliverables and breadth of activities THET have completed is impressive. Improved quality assurance of deliverables prior to submission to FCDO is necessary, however THET has been responsive to such discussions to date. THET should ensure that future grant applicants propose well-structured grant budgets that offer VfM prior to submitting to FCDO for approval.

The ODA prioritisation exercise in the summer reprofiling £2.6m from 2020/21 into later financial years meant delaying grant awards. The no-cost extension aims to protect the planned duration of grants. The no-cost extension also allowed THET to move funds from the grants budget line to help cover programme management costs, such as staff time, this year. THET and LSTM also secured other project income enabling them to maintain staff but reducing their time spent on this programme.

Due to COVID-19 and the limited international travel, the altered scoping assessment model was slightly more economical although more funds were required for in-country support. The CRF also aims to improve the economy of the programme by enabling partnership activities to proceed without the added costs relating to travel. THET efficiently adapted the programme to respond to the COVID-19 pandemic by designing and incorporating the CRF as a new stream and launching the first call for applications in September. THET and LSTM also swiftly amended the scoping assessment methodology for Waves 2, 3 and 4 to conduct these remotely, which saved both time and money relating to travel and increased the range of stakeholders they engaged. By hosting the THET Conference virtually, THET were able to secure a much broader scope of LMIC delegates attending improving the equity.

THET has fulfilled the majority of areas of the Supply Partner Code, with exceptions around Recognition of ILO and ETI standards, Principles 1 & 2 of the Global Compact, and having systems in accordance with the HMG Cyber Essentials Scheme. These will be in place by 31st March 2021.

Date of last narrative financial report	30th Oct 2020	Date of last audited annual statement	2019

Annex A – Summary of scoping exercises in ten focus countries
Country	Date of scoping	Stakeholders involved	HS priorities identified for HP action
Myanmar (Wave 1)	Jan-Feb 2020	Policy makers, inc MoH and other Ministries, in-country FCDO teams, Professional associations, inc nursing, training institutions, development partners, UN agencies	Improve retention & strengthen role of nurses / Improve emergency medicine / Build capacity of allied health professionals / Build research capacity
Nepal / (Wave 1)	Feb 2020	Ministry of Health and Population, Department of Health Services, UN agencies, FCDO Health Advisers	Strengthen HRH for MNCH and community-based services / Strengthen Leadership & Governance, support Nursing Council / Strengthen Health Information Systems by generating and using data to inform decision-making / Community health promotion – support demand creation for MNCH services
Uganda / (Wave 1)	Jan 2020	Government, professional councils and associations, service delivery units, non-state health institutions and healthcare personnel training institutions	Health Information Systems – build capacity to use data for decision-making. / Improve human resources performance including leadership training / Strengthen community health systems e.g. by training CHWs
Zambia / (Wave 1)	Jan-Feb 2020	Policy-makers, inc MoH and other ministries, in-country FCDO teams, professional associations inc nursing, training institutions, development partners, UN agencies.	Improve quality of MNCH service delivery / Strengthened HRH for MNCH through competency-based curricula for non-midwives / Health Information Systems – improved collection and use of data for decision-making / Strengthen Leadership & Governance – planning, oversight, accountability at all levels / Health promotion & education – strengthen linkages between PHC and community
Ethiopia / (Wave 2)	Mar-May 2020	Federal Ministry of Health and key health system stakeholders	Service delivery – Revise Health Extension Program and create roadmap / Develop HRH strategy based on HS needs and develop HRH development plan / Strengthen Governance & Leadership by increased citizen’s and civil society participation / Health Information Systems – develop standards and guidelines for digital solutions / Medical products & technologies – establish National Medicine and Poison Information Centre
Somalia/ Somaliland / (Wave 2)	Mar-Aug 2020	Somalia Federal MoH, Somaliland Ministry of Health and Development, key health system stakeholders	Strengthen leadership & governance capacity & sector coordination / Develop plan, protocols and guidelines for health emergency preparedness, risk mitigation and response at all levels. / Strengthen in-service training and CPD systems, aligned with performance management & accreditation systems, & informed by training needs assessment. / Develop M&E tools to monitor health sector achievements, progress, and gaps. / Service delivery - Develop plans to reach marginalised & underserved populations with essential services.
Bangladesh / (Wave 3)	Sep-Nov 2020	Bangladeshi Ministry of Health and Welfare, FCDO Health Adviser, other health sector-related stakeholders	Service delivery – improve quality of Community Clinic services / Strengthen systems and capacity of MOHFW to plan, manage and develop the health workforce / Strengthen governance and leadership capacity at all levels to address and mitigate health sector corruption / Health financing research to examine the effectiveness of existing approaches and schemes to reduce costs and catastrophic health expenditure among the poorest populations / Develop & strengthen IT capacity & health information systems management to enhance and support the digitalisation process across all hospitals
Tanzania (awaiting final sign off from MoHCDGEC) / (Wave 3)	Mar-Oct 2020	MOHCDGEC, President’s Office of the Regional Administration & Local Govt (PO-RALG), other health sector-related stakeholders	Build governance & leadership capacity of MoHCDGEC / Improve NCD & mental health services & quality of care / Improve pre- and in-service training for health workers / Improve availability of data for planning & decision making focused on MCDs, mental health, disability, poor &vulnerable / Strengthen capacity of MoHCDGEC to coordinate emergency & pandemic preparedness & response.