Memorandum of Understanding (“Memorandum”)
Between
The Government of the United Kingdom of Great Britain and Northern Ireland acting through
the Department for International Development (“DFID”)
and
United Nations High Commissioner for Refugees (UNHCR) (“the Partner”)
together called “the Participants”
DFID Project Name: COVID-19 Emergency Education Response (CEER)
DFID Project Number: 301207
1. In any correspondence with DFID with regard to this Memorandum, reference must be made to the Project Name and Project Number shown above.

Provision of grant

2. The arrangements and the purpose for which resources will be used are set out in this Memorandum of Understanding, its annexes, the business case, logframe and budget. The aforementioned documents are collectively referred to as the “Memorandum”.

3. The activities to which this Memorandum relates will start on 28 August 2020 (“Start Date”) and end on 30 April 2021 or an earlier date if terminated in accordance with the relevant provisions in this Memorandum (“End Date”).

4. DFID will make available an amount not exceeding £5,300,000 (five million, three hundred thousand pounds). The amount is expected to be allocated in this financial year and paid in full once this Memorandum is signed.

DFID Financial Year Annual Allocation (GBP) 1 Apr 2020 – 31 Mar 2021 5,300,000
5. This agreement shall be supplemented by the terms of the Core Funding Memorandum of Understanding (“original MoU”) concluded between the Participants on 22 September 2017. The terms of the original MoU will apply to this contribution, except as otherwise explicitly provided in this agreement.
6. Funding under this Memorandum is provided in response to the Urgent Appeal for Coronavirus (Covid-19) and are to be used for the provision of goods and services as set out in the attached Business Case and logframe. Disbursements are expected to be allocated in line with the schedule
above.

Eligible expenditure

7. The funding amount will be used solely for costs included as part of the budget approved by DFID for the delivery of the outputs and outcomes set out in the logframe included as part of this Memorandum.

8. It is agreed and acknowledged that in line with UNHCR’s policies, the Arrangement is subject to six and a half percent (6.5%) Income Support Cost.

9. In line with the Partner’s rules, the Partner will use its best efforts to ensure that the Grant is not used for the payment of any import and customs duties on goods procured as part of the activities funded pursuant to this Arrangement. In the event that the Grant is used for such payment the Partner will use its best efforts to recover the amount expended.

10. DFID funding is not to be channelled through any Government agencies (i.e. the Commissioner for Refugees (COR)) either directly or through any downstream partners.

11. UNHCR will administer and account for the Contribution in accordance with its financial regulations and other applicable rules and procedures and practices.

Disbursement and reporting

12. The funding amount approved is as per the Sterling (GBP) value, as at the date of signature of this Memorandum. DFID’s preferred currency for disbursements is in GBP. Where it is more efficient to pay in foreign currency, DFID may do so, however, the funding amount will still be that approved in GBP as at the date of signature of this Memorandum.

13. When requesting payment, the Partner should complete Annex 1, payment request form. Payment will be made to the bank account details provided on the DFID supplier portal. The Partner should confirm the appropriate bank details on the portal and the Payment Request Form.

14. The Partner will be solely responsible for the administration of DFID financing covered by this MoU and will carry out such administration in accordance with its financial regulations, rules, policies, procedures and directives (“Partner’s rules”), with the same degree of care and diligence ordinarily applied to the administration of its other programme and projects.

15. In line with UK Government financial regulations, DFID will not pay in advance of operational needs unless this has been justified and approved in writing by both Participants. It is recalled that Partner funds, prior to imminent disbursement, may be invested in line with the Partner’s rules. Any interest earned by UNHCR on the Grant will be recorded in accordance with the UNHCR Financial Rules and used for activities approved by the Executive Committee of the High Commissioner’s Programme.

16. The funds in the Account may be freely exchanged by UNHCR into other currencies as may facilitate their disbursement.

17. The Partner will reimburse DFID any overpayment or erroneous payment made by DFID within 30 days, using the form at Annex 3.

18. The financial reports which UNHCR agrees, in the Agreement, to provide to DFID shall be prepared in accordance with UNHCR’s Financial Rules and regulations and administrative policies and practices. Reports by UNHCR shall be expressed in US dollars. Where necessary, reporting regarding the Contribution shall be converted into US dollars using relevant operational rate of exchange set by the UN Treasury Department.

19. The Partner will provide DFID with a mid-term narrative progress report no later than four months after the start date, and a final narrative progress report on the execution of the project and its activities. This will comprise a narrative report that describes performance against the performance indicators contained in the Results Framework, explaining differences between targets and achievements, the associated budget lines and utilisation of resources (including evidence of payments to beneficiaries), challenges and risks managed, in the one report (including financial reports). This report will be submitted within three months after the end date of the Project. In addition, the Partner will provide DFID with an interim result table by the 15th November 2020 to feed into DFID ‘s Annual Review process. This table it to show results achieved against planned targets with explanations if results are not on track. All beneficiary data shown in any report is to be disaggregated by sex, age and people with disabilities.

20. The Partner will immediately notify DFID of any delay, obstruction or event which interferes with or threatens to interfere with this Memorandum.

21. As part of the regular reporting requirements outlined above, the Partner will provide a proportionate and meaningful assessment of how the specific needs of girls, women, boys and men are considered, and reflect to what extent women and girls have been included in design, implementation and monitoring. The Partner should also assess how DFID’s contribution is contributing to reducing gender inequality including a specific assessment on progress against any gender related commitments made as part of this Memorandum and demonstrate consideration of potential unintended negative consequences, such as gender-based violence.

22. The Partner will seek to ensure that beneficiary feedback is integrated in the design, mobilisation, delivery, monitoring, evaluation of activities to which this contribution relates, including annual review processes, and takes account of the voices of both women and men. The Partner should work with, through and represent the diversity of communities in order to respond to their needs more effectively and strengthen accountability.

Audit and assurance

23. As an important development partner, DFID may request consultations at senior level between DFID and the Partner to determine any appropriate action to ensure that the results laid out in the DFID Business Case are achieved. The Partner shall receive and administer the Grant in accordance with the Partner’s rules. The Grant shall be subject exclusively to the internal and external auditing procedures provided for in the Partner’s rules. In line with the Partner’s financial rules, the Partner’s annual financial statements are audited and reported upon by the UN Board of Auditors to the General Assembly. The Partner accounts for the use of funds on an annual basis to the Partner’s Executive Committee and to the General Assembly of the United Nations and will provide its annual financial report and audited financial statements together with the Report of the Board of Auditors to DFID as soon as this report becomes available.

24. In the event that DFID becomes aware of information (except information in the relation to the allegations of fraud and corruption which is dealt with in section “fraud, corruption, bribery, theft, terrorist financing, and other misuse of funds”) that would indicate a need for further and closer scrutiny of its programmes, projects or activities, DFID agrees to bring this information promptly to the attention of the Partner. The Partner will, in accordance with its rules including its accountability framework, take such action as it determines is appropriate, in a timely, appropriate and effective manner.

25. Financial records, including documentation to support entries on accounting records and to substantiate charges against contributions, will be maintained in accordance with Partner’s rules, including retention period.

26. The Contribution will be used by UNHCR for the provision of goods and services as specified in the project document. UNHCR will make every effort to ensure timely and full implementation of the project, taking into account the operating environment.

Due diligence

27. In utilisation of this funding, the Partner will exercise the same care in the discharge of its functions under this arrangement as it exercises with respect to the administration and management of its own resources and affairs. The Partner shall co-operate with diligence assessments to the extent that such co-operation is consistent with the ‘single audit principle’, as well as relevant Partner’s rules (including but not limited to its accountability and oversight framework and its information disclosure policies). Local diligence assessments will be informed by the Central Assurance Assessment (CAA). These assessments should be completed prior to project implementation and will last for 3 years, unless there is a significant change to the Partner’s procedures and controls or operating environment.

28. The Partner will undertake suitable due diligence and take the necessary steps prior to transferring DFID funds and at regular intervals throughout the implementation to assess the internal controls and systems of any Downstream Partners.

Delivery chain risk mapping

29. The Partner will maintain and provide to DFID an up to date and accurate record of its Downstream Partner(s) in receipt of DFID resources. This forms the basis of the delivery chain risk map which should demonstrate the flow of funds from the initial source to end beneficiaries, and the risks and potential risks along the chain.

30. The delivery chain risk map should be updated regularly by the Partner and when there are material changes to the risk assessment associated with this Memorandum or to any delivery partner(s) in the chain.

31. The Partner will provide to DFID, as a minimum, an updated delivery risk map at the following intervals:

- within 60 days of the Start Date; and
- at the conclusion of activities, within 90 days of the End Date.

Information and data protection obligations

32. The Partner acknowledges that DFID is subject to the requirements of the Freedom of Information Act 2000, the Environmental Information Regulations 2004, the General Data Protection Regulation (GDPR) (EU) 2016/679, the Data Protection Act 2018 (DPA), subordinate legislation and guidance and codes of practice issued by the Information Commissioner and relevant Government Departments.

33. The Partner, to the extent that it is not contrary to the Partner’s status and mandate, its information disclosure policy and data protection principles and protection of its Commercially Sensitive Information, and to the extent that such assistance and cooperation does not exceed an appropriate limit, agrees to assist and co-operate with DFID to enable DFID to comply with its information disclosure and data protection obligations whenever a request is made for information which relates to or arises out of this Agreement.

34. The Partner will perform its obligations under this Memorandum in such a way as to protect the personal information of individuals.

35. All information including personal information which comes into Participants’ possession or knowledge in connection with this Arrangement or the project is to be treated as strictly confidential. No personal information shall be communicated to any third party without the prior written approval of the person concerned. The Participants shall comply with UNHCR Data Protection Principles in the event that it collects, receives, uses, transfer or stores any personal data in the performance of this Arrangement. The obligations under this paragraph shall survive the expiration or termination of this Arrangement.

Transparency

36. The Partner publishes information about its operations transparently within its Annual Programme and Budget and UNHCR’s annual financial statements available on its website, which details on funding received for its project activities. The Partner issues its project financial and narrative reports in accordance with its rules and procures. Subject to its privileges and immunities and to the extent applicable, the Partner will publish to the International Aid Transparency Initiative (IATI) standard on all the funds received from DFID. Consistent with IATI, the Partner will make substantive efforts to publish information about DFID funded projects, in line with relevant categories of the IATI standard, on its own website.

37. The Partner gives consent for this Memorandum (and any subsequent amendments) and associated funding information to be published on DFID’s website, unless explicitly approved in writing by DFID.

Risk management

38. The Partner will develop and maintain an up to date risk register that, as a minimum, enables individual risks to the achievement of the Memorandum be clearly identified. The risk register should include an assessment of their likelihood and impact, and details of the risk owner responsible for monitoring, reporting and escalating individual risks.

39. The Partner will manage all risks associated with the activities to which this Memorandum relates unless otherwise approved as part of the risk register and in writing with DFID. Where the Partner transfers risk to any Downstream Partner, the Partner will remain accountable to DFID for the effective management of that risk. Fraud, corruption, bribery, theft terrorist financing and other misuse of funds.

40. DFID and the Partner have a zero-tolerance approach towards fraud, bribery, theft, terrorist financing, and corruption and any other misuse of funds including an associated inappropriate behaviour and agree to undertake reasonable efforts to recover any funds lost. The Partner has a written policy on combatting fraud and corruption, which will be fully implemented. The Partner will take all necessary precautions to prevent fraud, corruption, bribery, theft, terrorist financing, and other misuse of funds in line with Partner’s rules and, in particular, its policies for combatting fraud and corruption.

41. DFID and the Partner will promptly inform the other Participants of any investigation pertaining to an event which interferes or threatens to materially interfere with this MoU, whether financed in full or in part by DFID, including credible allegations of actual fraud, corruption, bribery, theft, terrorist financing, and other misuse of funds. The Partner should assess credibility based on the source of the allegation, the content, and the level of detail or evidence provided. The Partner should notify the DFID Counter Fraud Section (reportingconcerns@dfid.gov.uk or +44 (0) 1355 84 3747). All information will be treated with the upmost confidentiality. Information can also be reported directly to the DFID programme team where appropriate; this will be immediately passed on to the DFID’s Counter Fraud Section.

42. DFID may at any time during, and up to five years after the end of this MoU, arrange for additional programme reviews to be carried out subject to the provisions of paragraphs 18 and 29 of this MoU. The Terms and Reference of such reviews will be mutually agreed in advance.

43. The Partner will take timely and appropriate actions to investigate suspicion of fraud, corruption, bribery, theft, terrorist financing, and other misuse of funds in accordance with its accountability and oversight framework. To the extent that such investigation confirms any suspicion, the Partner will give due consideration to timely and appropriate action, including sanctions, in accordance with Partner’s rules. Consistent with numerous United Nations Security Council resolutions including S/RES/1269(1999) and S/RES/1373 (2001) and related resolutions, both DFID and the Partner are firmly committed to the international fight against terrorism, and in particular, against the financing of terrorism. It is the policy of DFID to seek to ensure that none of its funds are used, directly or indirectly, to provide support to individuals or entities associated with terrorism. The Partner will seek to ensure that no resources provided under this Memorandum are made available or used to provide support to individuals or entities associated with terrorism, including those named on the United Nations Security Council Sanctions List.

Safeguarding for the prevention of sexual exploitation, abuse and harassment

44. The Partner will take all reasonable steps to prevent the sexual exploitation, abuse and harassment of any person linked to the delivery of this Memorandum by both its employees and any Downstream Partner, in line with the commitment to action by the Secretary-General in his report on Special measures for protection from sexual exploitation and abuse: a new approach (A/71/818). This includes the requirement in accordance with the report of the UNSG to report annually on allegations of sexual exploitation and abuse in UNHCR, progress being made in combating it, and support to victims, e.g. use of the Trust Fund in Support of Victims of Sexual Exploitation and Abuse.

45. The Participants have a zero-tolerance approach towards sexual exploitation, abuse and harassment. The Partner will promptly contact DFID’s Safeguarding Investigations Team at reportingconcerns@dfid.gov.uk or +44 (0)1355 843747, to report any credible allegations of, or actual incidents of sexual exploitation, abuse or harassment related to this Memorandum. The Partner should assess credibility based on the source of the allegation, the content, and the level of detail or evidence provided.

46. The Participant will adhere to the IASC Six Core Principles Relating to Sexual Exploitation and Abuse, and the United Nations Protocol on Allegations of Sexual Exploitation and Abuse Involving Implementing Partners, 21 March 20181 and require that potential suppliers accept the UN Supplier

Code of Conduct

47. The Partner will inform DFID about any credible or actual incidents that would be of significant importance to the implementation of this MoU. Further, as part of existing central reporting and consultation mechanism and oversight frameworks, DFID and UNHCR’s management will bring to each other’s attention matters of which that party becomes aware concerning the mandate, governance or operations of DFID or UNHCR that are likely, in the estimation of that party, to have a significant impact on the partnership between the parties or the reputation of either party, or UK aid. For example, events that affect the governance or culture of the Partner, such as those related to senior management, must be reported.

48. Both Participants will fully co-operate with investigations into such events, whether led by DFID or any of its duly authorised representatives or agents, or the Partner.

Cyber security

49. Cyber security is the protection of systems, networks and data to prevent cybercrime. The Partner is responsible for managing cyber security risk under its own policies and procedures.

Assets and inventory.

50. Programme assets specifically identified to be procured under the provisions of this arrangement will be operated and controlled by the Partner in line with Partner’s rules. The transfer of ownership of such assets by the Partner (if relevant) shall also be done in accordance with the Partner’s relevant rules and, where applicable, in accordance with the Partner’s agreements concluded with the relevant host Government and any implementing partners.

Communication and branding

51. The Participants will collaborate and proactively look for ways to build support for development and raise awareness of DFID’s funding. The Partner may use DFID’s “UK aid from the British People” logo (“UK aid logo”) in conjunction with other donor logos. Where DFID’s contribution to the programme is acknowledged, the UK aid logo should be given due prominence with those of other donors, and DFID support should be acknowledged in any public statement, written or verbal communications where other donors contributions are also acknowledged, in accordance with DFID’s standards for use of the UK aid logo, unless otherwise agreed in advance by DFID, and in all cases subject to security and safety considerations of the Partner. Neither DFID nor the Partner shall use the other’s name, logo and emblems unless prior permission is given in writing.

52. The Partner will provide a visibility statement using the template provided in Annex 2: UK Aid Visibility Statement of how and when they will acknowledge funding from DFID and where they will use the UK aid logo, which should be approved by DFID prior to the Partner releasing any public communications. The Partner will include reference to this in its progress reports and annual reviews.

[Footnotes]
1 https://www.un.org/en/pdfs/UN%20Protocol%20on%20SEA%20Allegations%20involving%20Implementing%20Partners%20-
%20English_Final.pdf
2 https://www.un.org/Depts/ptd/sites/www.un.org.Depts.ptd/files/files/attachment/page/pdf/unscc/conduct_english.pdf

Conflict of interest

53. Neither the Partner nor any individual employed or contracted by the Partner shall engage in any personal, business or professional activity which conflicts or could conflict with any of their commitments in relation to this Memorandum.

Accountability and Indemnity

54. DFID will not be responsible for the activities of any person employed or funded by the Partner, nor will DFID be liable for any costs incurred by the Partner in terminating the engagement or funded activity of any such person. Furthermore, DFID will not be responsible for the activities of the Partner as a result of this MoU.

55. Unless otherwise stated, the Partner is solely accountable for compliance with the provision of this MoU at all times, including when the Partner engages with any Downstream Partner(s).

Termination and closure

56. This Memorandum will terminate six months after the End Date unless terminated earlier in accordance with the provisions below. The Partner will return any unspent and uncommitted funds remaining at the End Date unless otherwise agreed by DFID in writing.

57. If DFID becomes concerned that the provision of this MoU has not been fulfilled by the Partner, or if any activities occur which in DFID’s opinion will significantly impair the development value of the project, DFID will discuss and negotiate with the Partner in an attempt to resolve any issues that may arise. Following such negotiations, DFID may then take any of the following actions:

- Signal a possible future response.
- Delay or reduce the applicable funding.
- Stop aid under the termination provision set out within this arrangement.

58. Both participants will at first negotiate in attempt to resolve any issues that might arise throughout the project. However, this Arrangement can be terminated, at any time, by three months’ written notice by either participants. All remaining funds other than those irrevocably committed in good faith before the date of termination, in line with project objectives and approved between the two participants as being required to finalize activities, will be returned to DFID.

59. Additionally, any unspent and uncommitted funds remaining at the scheduled end of the project, must be returned to DFID unless specially decided between both participants in writing. The template in Annex 3 should be used when returning funds.

60. Any dispute, controversy or claim arising out of or in relation to this Arrangement, or the breach, termination or invalidity thereof, shall be settled amicably by negotiation between the parties.

61. Nothing in or relating to this Arrangement, shall be deemed a waiver, expressed or implied, of any of the privileges and immunities enjoyed by UNHCR as an intergovernmental organization.
Prevailing language and amendments

62. In the event of translation, the English text of this document will prevail.

63. Any amendments to this Memorandum will be set out in writing and approved through DFID’s standard amendment letter or, where appropriate, a revised Memorandum.

Signature

64.This Memorandum places on record the understanding of the Participants and comes into operation on the date of signature below.
Signed on behalf of DFID:

Name:

Position: Head of Department, Children Youth and Education

Address/Contact Details:
Department for International Development, Abercrombie House, Eaglesham Road,
G75 8EA

Date:

Signed on behalf of the Partner:

Name:

Position: Head, Donor Relations & Resource Mobilisation Service

Address/Contact Details:
UNHCR Case Postale 2500 1211 Geneve 2 Switzerland

Date:

ANNEX 1: PARTNER PAYMENT REQUEST FORM
To:

Children Youth and Education Department

When submitting this payment request the Partner must include the following supporting documentation:

Detailed financial reports related to this contribution that set out in both cash and resource terms actual expenditure to date against the approved budget and quarterly forecast expenditure for DFID’s financial year (1 April-31 March).

In multi-donor arrangements, reports should clearly segregate the DFID proportion of funding.

For payments in advance, a copy of the Partner’s justification and DFID’s arrangement.

Title and Details and Summary of Funding

Organisation: UNHCR

Title of contribution: COVID-19 Emergency Education Response (CEER)

Location of activities: Chad, Kenya, Malawi, Mauritania, Pakistan, Rwanda, South Sudan, Sudan, Uganda, and Yemen

DFID Component Code / Purchase Order No.

Date of Claim

Period of detailed statement of Expenditure
[dd/mm/yyyy] to [dd/mm/yyyy]

Period of detailed Forecast of Expenditure

28/08/2020 to 30/04/2021

Only for payments in Arrears

(a) Unspent balance of DFID funds for the quarter ending [dd/mm/yyyy]

(b) Partner Expenditure for the quarter ending [dd/mm/yyyy]

Payment requested for previous quarter

((b)-(a))

OR

Only for Payments in Advance

(c) Unspent balance of DFID funds for the quarter ending [dd/mm/yyyy]

(d) Forecast of Expenditure for next quarter ending 30/04/2021

Payment requested for next quarter
((d)-(c))-

For All Payments

Partner Forecast Expenditure to 31 December
Partner Forecast Expenditure to 31 March

Partner Bank Details
Bank Name:
Bank Postal Address:
Name of Account:
Bank Sort Code:
Currency of Bank Account:

IBAN number: [required for bank accounts within Europe]

SWIFT number:

Intermediary bank details:

AUDIT DISCHARGE

UNHCR’s resources, including the contribution from DFID under this Contribution Agreement, are exclusively subject to the external and internal audit procedures provided for in UNHCR’s rules. UNHCR’s activities will be audited by the United Nations Board of Auditors in accordance with UNHCR’s rules. In accordance with its rules, each year UNHCR will produce and transmit to the United Nations Board of Auditors its certified, signed financial statement. The Board of Auditors, which is elected by the General Assembly, conducts the audit of UNHCR’s financial statement as an independent external audit body. The Board of Auditors issues its report on the audit of the financial statements of the Partner (which includes the audit opinion and a copy of the financial statements) to the General Assembly and thereby the report on the audit of the financial statements becomes a public document.

Certification

I certify that this claim is correct and that the sum requested is properly due on the basis of the information provided, outputs and outcomes and on the work carried out or future work plans. I confirm that receipt of this payment will not result in double funding of the work carried out or future activities. I have the authority to sign this on behalf of the United Nations High Commissioner for Refugees (UNHCR).

Signature:
Date:

Name:

Job title: Head, Donor Relations & Resource Mobilisation Service

Address & Contact Details: UNHCR Case Postale 2500 CH-1211 Geneva 2

ANNEX 2: UK AID VISIBILITY STATEMENT

As part of this Memorandum, the Partner will acknowledge funding from the UK government, in written materials and verbal statements. Please refer to the UK aid branding guidance for further information on how to acknowledge funding from the UK government. By completing and signing this statement the Partner accepts to fulfil these requirements.

As part of the reporting requirements for this Memorandum, the Partner may be asked to provide evidence of the branding in use, including photographs of the logo in the field and examples of communications materials. Branding Guidance and details of how to access the UK aid logo files can be found here: https://www.gov.uk/government/publications/uk-aid-standards-for-using-the-logo

Partner Name
[INSERT PARTNER NAME]
Project Number
[INSERT PROJECT NUMBER]
Project Title
[INSERT PROJECT TITLE]
Project Description
[INSERT PROJECT DESCRIPTION]

Please list the assets that will carry the UK aid logo or acknowledgement of UK aid funding
List all assets including physical items and supplies, and other non-physical items, such as information assets that will be delivered using this contribution e.g. annual reports, research reports, press releases, websites, other communication or event materials (refer to Sections 4 & 5 of the branding guidance for more information on where UK aid branding should / should not appear).
Please list the assets that will not carry the UK aid logo or acknowledgement and explain clearly why these items will not carry UK aid branding

All exceptions require approval by the Head of Department of the team in whose portfolio the programme sits and a record of this approval, e.g. an email, should be kept along with the programme documentation (refer to Section 5 of the UK aid branding guidance for more information on branding exceptions).

Declaration I understand that no UK aid funds may be used to procure any promotional communications goods or activities that do not have a direct impact on the successful delivery of activities associated with this contribution or serve to increase the transparency of funding. By signing this statement, the Partner accepts to fulfil the commitments stated above.

[INSERT PARTNER NAME] Representative:
Name:
Job title:
Signature:
Date:
Approved by DFID Representative:
Name:
Job title:
Signature:
Date:

ANNEX 3: NOTIFICATION OF RETURN OF FUNDS TO DFID

To:
Children Youth and Education Department
Cc: Treasury and Banking, DFID, Abercrombie House, East Kilbride, Scotland
Project Details Partner Name
UNHCR Title of Grant / Project name
COVID-19 Emergency Education Response Purchase Order / Component Code
Payment Date
Payment Amount to DFID
Bank Details DFID Bank:
DFID Sort code:
Account number:
Account Code

Payment Method

For UK Payments under £10,000 we recommend the use of BACS. For UK Payments in excess of £10,000 we recommend the use of CHAPS. Cheques should be made payable to ‘Department for International Development’ and sent to the DFID Programme Manager. All payments direct from overseas bank accounts should also quote the following:

Pay
Partner Contact Details Name:
Position:
Address:
E-mail: