ADDENDUM TO CASIP BUSINESS CASE TO INCLUDE BRITISH SUPPORT TEAM DELIVERED COMPONENT

SUMMARY INFORMATION
Project Name	Palestinian Security Sector Capability Accountability, Sustainability and Inclusion Programme in the Occupied Palestinian Territories (CASIP) / No. 300611
Country or region targeted	Occupied Palestinian Territories
Type of cost extension (if applicable)	To move approved funding from CSSF/MoD onto the FCDO ODA baseline.
Original project budget	£2.3m from CSSF (amended to £2.2m in first BC addendum approved in July 2020).
Original project start and end dates	January 2019 – March 2021 (amended to March 31st 2022 in first BC addendum approved in July 2020)
Cost extension value (if applicable)	Total budget of £3.3M for FY21/22 (now under FCDO baseline rather than from CSSF).
New project end date (if applicable)	N/A – the project end date remains March 2022.
Business Case Quest Document No.	N/A
[note] See the additional and total support section below for further details of the breakdown of spend.
[note] As set out in the MEPP CSSF Programme Document and DFID CASIP Business Case Addendum (approved July 2020).

INFORMATION
What is the project’s purpose?
The Capability Accountability Sustainability and Inclusivity (CASIP) Programme is designed to support Campaign Goal 3 in the Country Business Plan to: Improve stability within the OPTs and its neighbours, through mitigating the most likely triggers to instability. In turn, this supports the Shared Security pillar of the MENA strategy. As outlined in the Country Plan, CASIP will contribute to a “more capable, accountable inclusive, sustainable Palestinian security sector”. The key outcomes of this goal are: / By 2023 the Palestinian Authority Security Sector (PASS) has improved internal West Bank stability. The Palestinian security forces have better capabilities to improve safety and security for Palestinian citizens, restructured with greater frontline capacity. / They are better led and directed, with a legal framework and mechanisms to improve ministerial leadership, prioritisation, and command and control of operations. / Their leadership is supported by more effective planning, personnel, financial management, and training functions across the sector. / They are more accountable and inclusive (particularly of women within PASS), with improved internal and external oversight; more human rights compliant, more responsive to citizen needs, and more trusted by them (open societies). / These improvements will benefit a) the safety, security, and welfare of more Palestinian citizens in a larger area of the West Bank than at present and b) Israeli security and coordination between the two security forces. / Background / From April 19 to March 2021 CASIP has been funded by CSSF but entirely administered on the baselines of the Ministry of Defence (MOD) and the Department for International Development (DFID) and delivered by their respective teams. The CSSF programme documents for FY19/20 and 20/21, approved by Ministers and HMT, set out the Business Case for CASIP up to a value of £11.1m. The UK military led British Support Team (BST) was responsible for direct support to the Palestinian Authority Security Forces (PASF). The DFID Business Case had two main components: / Component 1: DCAF (The Geneva Centre for Security Sector Governance) providing technical assistance to strengthen financial and human resource management, policy-making capability, and internal accountability of the Palestinian Authority Security Forces (PASF). This component was terminated in April 2020 and responsibility for delivering its outputs moved to the MoD led British Support Team (BST) . / Component 2: Improving governance and transparency in Palestinian Authority (PA) institutions and public services (delivered through an accountable grant by local Palestinian NGO, AMAN).
What is the objective of the cost extension or other changes?
In early 2021 BCG Jerusalem undertook a comprehensive whole of ODA review, taking into account the current context in the OPTs as well as the reduced funding envelope. In recognition that CASIP is a well-developed and mature programme focused on long term development and strengthening in the security sector it was agreed all components of CASIP would now be funded by the FCDO ODA baseline rather than by CSSF. / The objective of this Business Case Addendum is to reflect the transition of CASIP from CSSF to the FCDO ODA baseline in FY21/22. This includes the CASIP work stream delivered by the BST (now Component 3) as well as all existing CASIP programme funded staff. This arrangement is for FY21/22 only.
What is the additional and total support the UK will provide?
The CSSF three-year programme document set out a total allocation of £11.1m for CASIP. / This included the BST which is forecast to spend £5.63m over FY19/20 and FY20/21. / It also included DFID which allocated £2.762m over three years (FY18/19 to 20/21) in its original business case. The first DFID Business Case Addendum adjusted DFID’s total spend down to £2.2m and extended the programme duration to FY21/22. DFID is forecast to spend £1.59m over FY19/20 and FY20/21. / By moving the totality of CASIP out of CSSF and onto the FCDO ODA baseline with this addendum, the FCDO is now allocating £3.3m for CASIP in FY21/22, bringing the total CASIP spend by the FCDO up to £4.9m over three years (from £2.2m over three years). The £2.75m lift will be spent by the BST and subject to an MoU between FCDO and the MoD. It does not affect the level of total UK support to CASIP (£11.1m) set out in the CSSF MEPP programme document.
What are the expected results?
The expected results are summarised below and are detailed in the CASIP logframe. They have also been recently refreshed at output level in the BCG OPTs Country Plan: / Strengthened and more engaged civil society, citizenry and media in holding PASS to account / The PA security sector will have more effective national strategic decision making and coordination capabilities to plan, prepare, and respond to complex security challenges, civil emergencies, and to expand operations. The Strategic Leadership Committee and national command and control capability will be established and in operation in 2022. / The PASS will have more effective core strategic planning (linking prioritised plans to development budgets by end 2021), human resources (direct entrant scheme developed by 2022), financial (budget cycle improvements rolled out by March 2022), and training (with training management cycle near completion by March 2022) functions that underpin a capable and sustainable force. / Civil society scrutiny and capacity for engagement with PASS will be enhanced, and PASS transparency & accountability systems improved, including its handling and oversight of citizen complaints (by 2023). / The PASS will have the skills to implement more effective policy making and coordination between the security sector and the international community by 2022. Improved women’s representation and participation in the PASS will be facilitated (including plans developed for better recruitment and women’s career progression by March 2022) and help given to ensure other UK programming activity is inclusive and gender sensitive (ongoing). / The outputs are all consistent with the aims and strategic case set out in the original business case, but the scope has been broadened to include ongoing BST-led CASIP interventions on strategic decision making (1), training (2), and on gender (4). These results will be refreshed in the CASIP logframe and Theory of Change in Quarter 1 of FY21/22 (the current theory of change and intervention logic can be found at Annexes A and B).
What is the approach to implementation?
The approach to implementation for component 2 (AMAN) remains as set out in the original DFID Business Case. Component 1 (previously implemented by DCAF) is now closed with all activities moved to component 3 and delivered by the British Support Team since April 2020. These arrangements are reflected in the first CASIP Business Case Addendum. / The MOD’s British Support Team (BST) consists of six serving UK military personnel, led by a Brigadier (SCS equivalent) who is the CASIP Programme Director. The BST are seconded into the multinational United States Security Coordinator’s mission, which is commanded by a US 3* General. The BST are supported by an MoD civil servant and five FCDO Country Based Staff, whose primary objectives are the delivery of programme outcomes. All six salaries, as well as accommodation and life support for the whole BST, will continue to be funded from the programme and according to MoD procurement rules. The BST routinely deploy additional military personnel in the form of MOD Short Term Training Teams and the MOD provide additional financial resource to meet CASIP programme outcomes. BST also deploys consultancy expertise through an MoD framework contract. / In addition, a A2 legacy-DFID Security Sector Advisor, to date CSSF funded, will now be programme funded from CASIP, supporting the BST in their delivery as a USSC coalition member as well as the Consul General as deputy chair of the Security Sector Working Group.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work? / The case for investment for CASIP as well as the original management, governance, and implementation structures are all outlined in the CSSF programme documents for FY19/20 and FY20/21 for the 3 year programme from March 2019 – March 2022. As these documents have been signed off by Ministers and HMT and in line with FCDO guidance for the merger no further business case, or due diligence for existing contracts, is required. The details of the first Business Case addendum remain accurate. / Further amendments to the CASIP Business Case, in addition to those outlined in the addendum dated July 2020, are as follows: / A new component (component 3) has been added to finance the work of the BST, retaining the existing approach to implementation and staffing as set out above. / An MOU between FCDO and MOD will be established before 1 April, with quarterly payments in arrears provided by FCDO to MOD upon production of evidence of last quarterly expenditure from the BST CASIP Programme Manager. / The legacy-DFID A2 security sector advisor and B2 Programme Manager (in the original business case) will continue in their current responsibilities. Rather than being CSSF funded however the A2 role will now be programme funded by FCDO for FY21/22 and the B2 role will be moved to FCDO Front Line Delivery. The B2 is already on the FCDO workforce plan. / Annual profile of programme spend: / The table below sets out the annual spend and budget profile under the DFID CASIP Business Case and subsequent addenda – to note, this does not include BST spend in 19/20 and 20/21 on component 3: / Budget 2019/20 / CSSF 2020/21 / CSSF 2021/22 / FCDO ODA / DCAF (Component 1) £616k £576k £40k £0 / AMAN (Component 2) £584k £84k £250k £250k / BST (Component 3) £2.75m N/A N/A £2.75m / Salary & related costs £0.94m £281k £359k £300k / DFID / FCDO Totals £4.89m £941k £649k £3.3m / Governance arrangements: The BCG Consul General is the Strategy Senior Responsible Owner (SRO) for CASIP as a whole. The Senior British Officer is responsible for delivery of the CASIP project as a whole, is the Programme SRO for Component 3 delivered by BST, and reports to the BCG Consul General on CASIP performance, finances and risk. The CASIP Security Sector Advisor will remain the Programme SRO for Component 2 delivered by AMAN. The Security Sector Advisor and B2 Programme Manager will be responsible for managing the performance, finances and risks of the AMAN component and keeping the BST notified of AMAN’s activities so that BST can align its own interventions accordingly. Further details on Governance and Reporting are detailed in Annex C. / Assets: All financial management, including asset and equipment management (e.g. of vehicles) will adhere to the HM Treasury’s Managing Public Money rules. The BST have a small fleet of vehicles funded from CASIP and will continue to follow the asset management guidelines established by the MOD, including the maintaining of an asset register.
[note] DFID CASIP Business Case Addendum (July 2020), and DFID’s CASIP 2019/20 Annual Review (August 2020).
[note] See Annual Profile of spend below.
[note] The original DFID CASIP Business Case can be found on Devtracker.
[note] DFID CASIP Business Case Addendum (July 2020).
[note] The capitation costs, circa £920K per annum, for the six military personnel is paid directly by the MOD and is not charged to the programme.
[note] DFID CASIP Business Case Addendum (July 2020).
[note] The amounts here under have been spent.
[note] BST spend in FY19/20 was £2.274. This spend was authorised under the CSSF Programme Document approved by Ministers. It did not fall under the DFID Business Case as it was administered by MoD/BST.
[note] Forecast BST spend in FY20/21 is for £3.36m (£2.98m plus an additional £0.38m for a command and control project). This spend was authorised under the CSSF Programme Document approved by Ministers. It does not fall under the DFID Business Case as it has been administered by MoD/BST.

Annex A: CASIP Theory of Change

Problem Statement: The Palestinian Authority Security Sector (PASS) operates under occupation and has minimal, restricted West Bank access and control. PASS lacks an agreed framework for strategic decision-making and the political will to change, impeding reform. Capability is challenged by weak leadership and sustainability (human and financial resources). Poor PASS transparency and accountability erodes PA legitimacy and popular citizen consent.
Because of . . .
Context: The political, economic, social, institutional, and historical factors that result in the current scenario (key actors, relationships, interests). See intervention logic for details.
However, if we . . .
Strategies: Develop and deploy approaches that respond to the context (mitigating issues, exploiting opportunities and leveraging strengths). See intervention logic for details.
And deliver intervention activities to. . .
(Through inclusive, gender and conflict sensitive programming) Improve PASS: / capability to design, deliver, manage and sustain training / joint operations at scale through command and control systems (including emergency & crisis mgt) / human resources management / public financial management and oversight / transparency and complaints mechanisms / governance, policy, planning and M&E capability / Strengthen effective engagement and accountability between: PASS & community; + PASS & Israeli Security Sector
Then we expect this to lead to . . .
Outcome Statement: A more capable, accountable, sustainable and inclusive PA security sector
As a result, we will contribute to:
Impact Statement: Construction of the conditions needed for successful negotiations resulting in a lasting state solution

Annex B: CASIP Intervention Logic

Annex C: GOVERNANCE AND REPORTING ARRANGEMENTS

The governance, funding and reporting arrangements are summarised as follows:

  1. Programme Management. CASIP management is devolved from FCDO to the BST Commander/Programme Director (SBO). This includes devolving the responsibilities for internal funds allocation, staffing, resourcing, expenditure, outputs, and risk management to the SBO.

  1. Funding. Quarterly instalments to be transferred to the MOD-BST baseline in arrears based on evidence of quarterly spend produced by the BST Programme Management Office.

  1. Reporting. Continue with the current reporting mechanisms and add a quarterly financial report on output level actuals.

ROLES AND RESPONSIBILITIES

HM Consul General. HMCG (Strat SRO) is responsible for the overall oversight of the project, reporting to Director MENA, FCDO, providing strategic direction and guidance to the project, and signing off quarterly narrative and financial reports.

British Support Team.

BST Commander/Senior British Officer (SBO). The SBO is the programme director, reporting to HMCG, overseeing all aspects of the programme: chairing the programme management board, allocating and moving funds across outputs, resourcing the outputs with local and international expertise, monitoring programme performance, risk, and assurance.

Programme Management Office (PMO). The PMO oversees the day-to-day management of the programme on behalf of the SBO. the core functions are to:

Oversee and run all programme management functions for BST, including budgeting, financial and risks management.

Manage the procurement of material, equipment, and local and international expertise in support of outputs delivery according to MOD rules and regulations.

Produce quarterly performance and financial reports to the HMCG according to the details and intervals described at paragraph 5 below.

MOD. In addition to providing the military staff to BST and funding their capitation cost (c£1M), MOD will continue to perform similar roles and responsibilities performed in FY20/21 including:

Processing the payments of the MOS Civil Servant (HR Advisor) and UK-based consultancy firm (Adam Smith International) against the BST’s UIN.

Review and approve project-level business cases that are above the delegated authority of the SBO.

Manage issuing the Electronic Payment Card (ePC) and related letters of delegated authority to the BST.

Development Team. The FCDO programme management team are responsible for:

Ensuring CASIP budget, forecasting, risks, and reports are uploaded onto the development system.

Issuing quarterly payments in arrears based on receipt of necessary reporting from BST (see Annex B below) and approvals from HMCG. The Development Team SRO will be responsible for authorising each payment.

Guiding and supporting the BST in developing the next programme cycle beyond FY21/22.

Other. The BST will also be responsible for:

Due diligence and engaging third parties in delivery.

Immediate reporting of allegations of fraud, corruption, and aid diversion to FCDO (and notifying MoD).

Safeguarding and SEAH following MOD/FCDO rules, reporting any concerns or allegations to FCDO (and notifying MoD).

BST is a silent mission but will identify communications & branding opportunities that the FCDO can capitalize on. BST will support FCDO in its responsibility for responding to Parliamentary and public scrutiny and inquiries.

Auditing of financial accounts under MoD rules.

Health and safety, duty of care, and conflict of interest policies under MOD rules and regulations.

Fulfilling project closure obligations as required and specified by the FCDO.

Recording and managing programme assets and inventory in accordance with MOD policies and procedures.

REPORTING ARRANGEMENTS

Reporting. The SBO reports directly to HM Consul General (Strat SRO) on results copying the Development Director. The reporting submissions are (flowchart overleaf):

  1. Quarterly Narrative Results Report. The report includes a RAG rating on progress, what impact the programme had in the past quarter, assessment of Context, update on human rights, gender, and conflict sensitivity, key risks, and lessons learned.

  1. Results Framework. A detailed results framework to be submitted at the beginning of the FY and thereafter updated and submitted quarterly to support the quarterly results report. The results framework includes: Outcome, Outputs, Indicators, Baselines, Milestones and Assumptions.

  1. Quarterly Financial Report. A programme budget will be submitted directly to the development team detailing the FY output-level forecasts charted against 12 accounting periods. Subsequently, a quarterly financial report will be submitted to the development team to include output-level actuals, percentage of overall spend against the allocated budget, narrative explaining any major deviations from the original forecast, and any risks of over/underspending.

Funding & Reporting Flowchart