AATF Programme Completion Review – September 2020

Title: African Agriculture Technology Foundation
Final Programme Spend £ (full life): 8,174,500.00	Review Date:	30/12/2020
Programme Code: 204988	Start Date: 05/10/2015	End Date: / 30/09/2020

Summary of Programme Performance
Year	2016	2017	2018	2019	2020
Programme Score	A+	A	A	B	A
Residual Risk Exposure Rating	Moderate	Moderate	Moderate	Moderate	Minor

DevTracker Link to documents	https://devtracker.FCDO.gov.uk/projects/GB-1-204988/documents

A. Summary and Overview (1-2 pages)
Description of the programme and what it has achieved [1/2 page]
This programme was the final phase of support to the African Agricultural Technology Foundation (AATF) and built on the UK’s previous support to AATF from 2010-2015, during which AATF consistently met or exceeded expectations. AATF is a not-for-profit organisation dedicated to increasing the productivity of resource-poor farmers in Sub-Saharan Africa by providing smallholders with greater access to improved agricultural innovation through public/private partnerships. In addition to supporting project activities, this phase of funding aimed to support the transition to the end of funding from FCDO. AATF implements a suite of projects across five programmes:
[note] On 2nd September 2020, the Department for International Develpoment (FCDO) merged with the Foreign and Commonwealth Office (FCO) creating the Foreign, Commonwealth and Development Office (FCDO)
- Productivity and Stress Management
- Mechanisation and Digital Agriculture
- Nutrition, Food Quality and Post-harvest Management
- Market Systems for Commercialisation
- Policy Environment and Public Participation
Details of current projects are provided at Annex 1.
The programme supported AATF activities in two areas: support to specific projects and support to organisational systems. The expected impact of support to the proposed intervention is increased productivity of smallholder farmers in SSA. This impact was to be achieved through two outcomes:
1. Increased access/availability of appropriate agricultural technologies for smallholder farmers in target countries in SSA.
2. A financially sustainable organisation/mechanism that is responsive to the needs of small-holder farmers in ensuring that market failures in the development and adoption of appropriate agricultural technologies continue to be addressed.
FCDO’s funding supported AATF’s institutional change agenda to adapt and embrace a more inclusive and sustainable business model.
Over the past five years, AATF has marked up some considerable successes, including the commercial release of Nigeria’s first transgenic food crop variety (pod-borer resistant cowpea), establishment of two spin-out companies to provide agricultural mechanisation services (AgriDrive) and foundation seed for seed companies (QualiBasic Seed), and a new partnership with the African Development Bank’s Technologies for African Agricultural Transformation (TAAT) programme. In total it has delivered commercialised agricultural innovations to over 3 million households over the past five years. They have also diversified the range of investors they receive funding from and added new projects to their portfolio. The changes they have made to their business model, including a new strategy and business plan, have helped them to take a more commercial focus to agricultural innovation.
As an Africa based institution, AATF have focused on negotiating technology from the private sector, commercialising new technologies and improving the regulatory environment. This has meant they are well placed to continue to deliver for small-holder farmers in Africa. However, they operate in a challenging environment, which is further complicated by the impact of COVID-19. They therefore need to remain focussed on delivering impact at scale through a range of channels and partnerships to maintain their position in the agricultural innovation landscape in Africa.

Major lessons learned, evidence generated and recommendations [1/2 page]
1. Making a rapid shift in the strategic approach of an organisation that works in a challenging and dynamic environment was particularly difficult for a small organisation dependent on project funding. Although AATF did develop a clear strategy and business plan, their dependence on project funding and partnership approach limited the speed at which changes could be made. This situation was hampered by the early departure of the new Commercial Director in the middle of the transition period
2. AATF’s support to the development and scaling of agricultural innovation in Africa has demonstrated the need for, but also the challenges of, an end-to-end approach. Consistent support from the Bill and Melinda Gates Foundation (BMGF) led to the successful development of 121 Water Efficient Maize for Africa (WEMA) maize varieties that performed well in field trials and received regulatory approval. However, despite working through seed companies to deliver seeds to farmers as part of the WEMA project, it became clear that many of these did not have the capacity to produce high quality hybrid maize seed. This led to the establishment of the QualiBasic Seed Company to tackle the lack of capacity.
The key lesson here, particularly when considering the development of new crop varieties, is to have a clear view of the route to delivering the new varieties at scale, understanding the weak points along the route and being prepared to invest in addressing those weak points if you wish to achieve scale.
AATF’s partnership approach, working with a range of public, private and other organisations including African government research organisations and extension services, private seed companies (both small and large), development partners (including NGOs) and research organisations in developed countries has proved essential to delivering technology at scale, enabling them to take an end-to-end approach to innovation. Although managing a larger number of partners does have resource implications, with respect to financial management and risk, it does mean that they have been able to manage and deliver a significant portfolio of projects with a small number of AATF staff (currently 46).

Actions following approval of this report [1-2 paragraphs]
- FCDO to ensure AATF’s audited accounts for 2020 are received and filed with programme documentation.
- AATF to ensure that evaluation reports are published on their website.

Table 1: Summary of AATF projects (see Annex 1 for further detail)
Project	Summary
AgriDrive	is a social enterprise wholly owned by AATF to engage in various commercial ventures in the agricultural sector. Mechanization services are being offered on a commercial basis across various crop value chains.
Agro-processing for Post Harvest losses management	This initiative seeks to improve agroprocessing services to farmers growing cassava, sweet potato, yam and other tropical roots and tubers,
Bacterial Wilt resistant potato	aims to develop and deploy disease resistant transgenic potato varieties resistant to bacterial wilt disease stacked and late bacterial blight.
Cassava Mechanization and Agroprocessing (CAMAP) Project	aims to increase cassava yield per unit area through adoption of mechanization and best agronomic practices across the entire cassava value chain.
Digital Agriculture Project - Drones	AATF is exploring the use of drones to characterize the production environment of AATF’s seed-based technologies to boost the production capacity of farmers.
EGS - Nigeria	Through a business entity the project is seeking to increase maize hybrid adoption in Nigeria by addressing the availability and sustainable supply of quality foundation seed that is presently limiting certified seed supply.
Hybrid Rice	Aims to commercialise 2-line hybrid rice varieties that are well adapted to African conditions and efficiently satisfy market needs/demands.
Maize Lethal Necrosis Diagnostics and Management	aims at mitigating grain yield losses incurred by maize farmers in Africa as well as preventing the spread of MLN from endemic countries to non-endemic areas on the continent.
NEWEST Rice	Aims to develop and disseminate genetically improved African rice varieties with enhanced agronomic traits, specifically Nitrogen-Use Efficiency (NUE), Water-Use Efficiency (WUE) and Salt Tolerance (ST).
Open Forum for Agricultural Biotechnology (OFAB)	focuses on strengthening the policy and regulatory environment required to accelerate agricultural biotechnology development and promote the uptake of its products in Africa.
Orange Maize Project	is seeking to improve food and nutrition security in Sub-Saharan Africa through the deployment of climate resilient, nutritionally enhanced pro-vitamin-A maize varieties/hybrids to address maize deficit gaps and malnutrition challenges in Africa with Burundi as the first pilot country of intervention.
Pod Borer Resistant (PBR) Cowpea	is focused on developing and disseminating pod-borer resistant transgenic cowpea varieties in Burkina Faso, Ghana, and Nigeria.
QualiBasic Seed Company (QBS)	aims at ensuring the production of quality foundation seeds for demand driven commercial hybrid maize towards strengthening the maize value chain in Africa.
Seeds2B	applies a market-led methodology to transfer seed technologies from research programs/technology developers from different parts of the tropical world to seed enterprises in Africa.
Technologies for African Agricultural Transformation Maize Compact	aims to harness high-impact proven agricultural technologies of maize to raise agricultural productivity in Africa by promoting the dissemination and massive scale-up of proven water efficient maize varieties in combination with other complimentary technologies
Technologies for African Agricultural Transformation Policy	is facilitating the creation of a conducive policy and regulatory environment for accelerated deployment of agricultural technologies and efficient marketing/trade of outputs from other TAAT programmes
TELA	is developing drought tolerant and insect resistant transgenic hybrid maize varieties.
USDA-FAS	this initiative was begun by the USDA-FAS to help develop a regional bio-pesticide regulatory framework for Africa.

## B: Theory of Change and Outcome Assessment (1-2 pages)

	Starting point	Final result
Budget	£10million	£8,175,000.00
Timeframe	5 years	5 years
Outcomes	Two outcomes were sought from FCDO funding to AATF / Increased access/availability of appropriate agricultural technologies for smallholder farmers in target countries in SSA. / A financially sustainable organisation/mechanism that is responsive to the needs of small-holder farmers in ensuring that market failures in the development and adoption of appropriate agricultural technologies continue to be addressed.	AATF has successfully delivered a number of agricultural technologies for smallholders in Africa over the past five years as detailed below, including 97 new crop varieties. / AATF has made progress to becoming more financially sustainable, reducing dependence on core funding from FCDO. This has been achieved through cost saving measures, winning new projects and implementing a clear Overheads Policy to cover central costs. / However, there is still a risk as to whether this is sufficient in the medium term given dependence on a small number of investors, particularly given the potential impact of COVID-19 on donor funding.

Overall assessment of programme outcomes, sustainability and VfM [1/2 – 1 page]
Overall, AATF has delivered moderate success with respect to the two intended outcomes of the programme. The have delivered appropriate agriculture technology to small-holders in Sub-Saharan Africa and made some progress in becoming a financially sustainable organisation.
For Outcome 1, over the past five years they have continued to deliver agricultural technologies for smallholders in Africa, diversifying the range and type of technologies they work with. As shown in the table below, the final year of the programme saw a significant increase in the number of households reached. This includes households cultivating AATF maize varieties and mechanising cassava production. AATF’s target is to reach two million households per year by 2022. They are on track to reach this target should progress made in 2020 be sustained.
Table 1: AATF Reach Figures
2015/2016	2016/2017	2017/2018	2018/2019	2019/2020	Total
112,975	227,650	529,363	631,600	1,600,385	3,101,973

AATF also have a number of promising agricultural technologies in the pipeline which have not yet reached smallholders. Specific examples of success include:
- the Cassava Mechanisation Programme (CAMAP), which has gone from pilot to commercial spin-out in eight years. CAMAP has been wholly supported by FCDO. Cassava yields have increased 7–11t/ha to 23–33t/ha through the programme and farmers increased profits per hectare by 86% in Nigeria, 52% in Uganda and 78% in Zambia. The commercial spin-out, AgriDrive Ltd, is now providing cassava mechanisation services on a commercial basis, and in 2020 has achieved almost double the initial revenue target. A total of over 4,500 farmers purchased services in 2020 in 5 countries in Africa. AgriDrive is expanding its mechanisation offering and also establishing an App based platform for farmers to access services. AgriDrive has also successfully won contracts for mechanisation on larger farms.
- the establishment of QualiBasic Seeds (QBS) with support from BMGF. QBS aims to tackle a key constraint in quality seed supply in Africa by providing high quality foundation seed. From the start of operations in mid-July 2017 and with sales of 3t of seed to two customers, QBS has steadily built its customer and product base. By the end of 2020 the company will have sold 197t of Foundation Seed to 43 seed companies in 10 countries.
  [note] Foundation seed, is a crucial step in the production of quality seed, and is the seed used to produce and multiply certified commercial seed for the farmer to plant. It is generated from what is known as breeder seed, which is original seed produced from best selected plant materials that meet required standards e.g. yield, resistance to insect-pest, diseases, drought etc. that is often handed over to seed companies for further multiplication and production of foundation seed. Quality foundation seed maintains purity and the characteristics of the breeder seed. Certified seed is a product of foundation seed.
- research and development of a pod-borer resistant cowpea variety (co-funded by the United States Agency for International Development (USAID)). This variety received approval for commercial production in Nigeria in 2019 and was the first genetical modified food crop in the country, and the first in Africa, outside South Africa. The variety is now being commercialised in Nigeria through a partnership with a private seed company.
- becoming a key implementing partner for the African Development Bank’s Technologies for African Agricultural Transformation (TAAT) programme on maize and agriculture policy. Not only is this a new investor, but the TAAT programme has provided new opportunities to deliver AATF developed technologies at scale, enabled expansion to new countries and provided new partnership opportunities.
- the Water Efficient Maize for Africa (WEMA) project, which has now transitioned in to the TELA project has released 126 hybrid maize varieties for commercialisation in Africa. Through the WEMA, TELA and TAAT Maize projects a total of 21MT of seed have been produced since 2013, benefiting an estimated 2.5 million households.
- significant improvements in the regulatory environment for genetically modified crops in Africa. The OFAB project, initially funded by FCDO, but now funded by BMGF, has worked with partners to support the development of functional biosafety systems comprising of policies, legislation and institutional mechanisms that could oversee experimental field trials with GM crops leading up to environmental release for cultivation. In 2015, only 6 countries were assessed to have functional systems, but by 2020 this had increased to 11.
A full list of current AATF projects is provided at Annex 1 and further details of projects and outputs are provided in AATF’s Annual Reports, which are publicly available on their website: 2019 Annual Report. Figure 1, below, highlights the progress between 2015 and 2020 for AATF’s core crop breeding projects. Notably, in 2015 21 varieties had been released to the market, but in 2020 a total of 97 have been released.
Figure 1: Core crop breeding pipeline 2015 and 2020
For Outcome 2, the Business Case set out four potential scenarios at the end of the five-year period, with the optimum being that AATF had become financially sustainable having changed its business model, achieved impact at scale and attracted significant investment from diverse sources.
In the 2019 Annual Review the assessment was that AATF had made considerable changes to their business model and achieved some progress on impact at scale and diversifying investors. However, there were still issues around financial sustainability. This is still the case at the end of 2020. AATF have:-
- made some changes to their business model, although this has taken longer than hoped. They now have two wholly owned subsidiaries (AgriDrive and QualiBasic Seeds) with the potential to deliver revenue to AATF, and are in the process of establishing a consultancy arm as an additional revenue stream. AgriDrive has delivered a more commercial focus to AATF’s work, with the focus on generating revenue.
- started to demonstrate impact at scale, commissioning independent evaluations of programmes, and developing a more nuanced approach to estimating the number of farmers reached through their partnerships with the private sector. However, launching the evaluation work has been slower than anticipated, with only the CAMAP evaluation delivering in 2020.
- had some success in diversifying their investor base, developing a much more proactive strategy to identify and apply for new funding opportunities. New investors contributed over £1.5m in 2020, up from only £300k in 2017. At the time of this review, AATF were waiting to hear the outcome of 12 additional funding applications. However, AATF are still heavily dependent on funding from the Bill and Melinda Gates Foundation (BMGF) and the United States Agency for International Development (USAID). Funding from the two organisations has reduced over the past five years meaning that AATF’s annual budget has decreased from £28m in 2016 to £14m in 2020. 2020 saw the approval of approximately £23m of funding for new projects.
- reduced costs in a number of areas, by streamlining staffing, streamlining procurement and implementing a clear Overheads Policy. This has reduced their dependence on FCDO funding to support core institutional costs, which will contribute to sustainability in the medium-term.
A key component of FCDO funding was a Performance Related Funding Component. This new component of funding was structured to incentivise more rapid progress by AATF in key areas of interest to FCDO, including: achieving and assessing impact at scale, financial sustainability, gender, and strengthening of the commercial product pipeline. Of the total funding of £2million/year, £500,000 was Performance Related Funding and was awarded following assessment of AATF’s performance against an agreed set of performance indicators. These covered: commercial focus, gender and inclusion, development of a new business plan, fundraising targets and reach/scale of AATF technologies. As highlighted in the 2019 APR, there was mixed evidence that the Performance Related Component had incentivised more rapid progress. In some areas, notably commercial focus, change was rapid, but in others, most significantly the development of a new strategy, the pace of chance was too slow. As a result, and following the recommendation from the 2019 Annual Review, the Performance Related Funding Component was not used in 2020.
The key cost drivers for AATF are Personnel and Administration costs (including financial and audit), monitoring and evaluation, and accessing technical expertise. AATF have maintained a stable cost structure with a major proportion of the budgets being designated for project and programmatic work, with a lean budget for core functions (resource mobilisation, monitoring and evaluation, governance, administration). AATF also have robust systems in place to deliver Value for Money, both within the organisation and with their sub-grantees. Over the past five years FCDO support has enabled AATF to maintain strong management systems and develop a track record of delivery, enabling them to attract additional donor funding, multiplying the impact of FCDO funding and delivering Value for Money.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators. [1/2 – 1 page]
The Theory of Change for AATF is that investment by FCDO in both the project pipeline and institutional development will deliver the parallel outcomes of increased availability of technology and a financially sustainable organisation. The figure below, taken from the original Business Case for funding to AATF, provides details on the Theory of Change.

In the 2019 Annual Review a detailed analysis of the assumptions underpinning the Theory of Change, was carried out. This assessment is still an accurate reflection of the assumptions made. The assumption with the most relevance for this Project Completion Review is “A sustainable business model for AATF can be identified and institutional development of AATF enables the transition to the new model.” It is still the case that although there have been shifts in their business model, AATF continues to be heavily dependent on public investment from investors for specific projects. In the past year progress has been made in setting up an AATF Consultancy Arm, but this has not yet delivered revenue for AATF. The Project Pipeline has continued to move forward, but Institutional Development has not been as swift as hoped.

## C: Detailed Output Assessment [aim for max. 1 page per output. Repeat for each output]
Output Title	Diversify agricultural technologies accessed for use in SSA
Output number per LF		1	Output Score	A
Impact weighting (%):		35	Impact weighting % revised since last AR?	Y

This output forms the core of AATF’s work accessing, developing and delivering agricultural technology to small-holder farmers in Africa. This output scores an A as the key targets on accessing technology and delivering new varieties have generally been met or exceeded. Of particular note, AATF have delivered new crop and vegetable varieties, worked to raise awareness of innovations with farmers and supported digital innovation. The CAMAP programme worked closely with AgriDrive to offer mechanisation services, the latter now leading on mechanisation work. Where a few targets were not met this was due to factors primarily outside AATF’s control (COVID-19 and budget cuts on projects)
Indicator(s)	Final Logframe Target	Final Result Achieved
Number of new agricultural technologies accessed targeting agricultural productivity, nutrition and post-harvest loss.	3	1 – Not Met / Nutrition and post-harvest are new areas for AATF and whilst discussions are on-going with a number of technology providers, agreement on access has not yet been reached.
Number of products/ varieties accessed	279	321 – Exceeded / This indicator covers AATF’s traditional focus on crop breeding and has seen considerable progress. In 2020, a significant number of vegetable varieties were accessed through the Seeds2B programme.
Number of Products/ varieties developed	35	66 – Exceeded / AATF have significantly exceeded their target in this area since the launch of their new strategy, with a total of 26 varieties (maize, cowpea and rice) developed in the final of FCDO year, notably 13 transgenic drought tolerant and insect protected maize varieties under the TELA Maize project.
Number of Products/ varieties released	23	36 – Exceeded / This is a key indicator as it reports on the varieties that have been released and approved for cultivation in target countries. In the final year of the programme, 18 varieties have been released across seven different AATF projects.
Number of farmers participating in AATFs agricultural education sensitization and outreach activities (demos, field days, trainings, workshops etc.)	187,000	91,009 - Partially Met / Raising awareness of new agricultural innovations is a key part of AATF’s projects, but activities in 2020 were impacted by COVID-19 restrictions meaning the target was not met.
Number of nutrition-based technologies being deployed by AATF	1	0 – Not met / AATF aims to deploy at least one new nutrition technology by 2022 and aims to access biofortified sorghum or rice in 2021.
Number of farmers aware of mechanization services by AATF (engaged through training workshops, seminars, outreaches, field days etc.)	2,300,000	1,763,566 – Partially Met / This indicator relates to the CAMAP project which works with AgriDrive to raise awareness of mechanization services. While there was considerable progress in 2018 and 2019, COVID-19 restrictions meant the target was not met.
Increased number of digital platforms used by farmers	3	4 – Met
Number of farmers linked to AATF technologies using digital solution platforms	45,000	26,000 – Partially Met / This target was not met due to cuts to the TAAT Maize programme by the African Development Bank, which had planned to make use of digital platforms to reach farmers. / The AgriDrive app enables farmers to book mechanisation services.

Output Title	Accelerate commercialization of agricultural technologies for improved farmer livelihoods
Output number per LF		2	Output Score	A
Impact weighting (%):		25	Impact weighting % revised since last AR?	Y

Following on from Output 1, this Output covers AATF’s work on commercialising agricultural innovation through a range of channels, including directly with farmers and engagement with value chain actors.
This Output is scored an A, as the majority of indicators have been met, or exceeded. Particularly significant are developments made to launch AgriDrive and QualiBasicSeeds as commercially driven models to take innovation to scale as part of an end-to-end approach to deliver innovation. CAMAP and TAAT Maize have also worked to build linkages with off-takers to provide farmers who adopt improved varieties and clear route to market. One indicator was only partially met, but this was due to COVID-19 restrictions on travel and field work in AATF target countries.
Indicator(s)	Final Logframe Target	Final Result Achieved
Number of business models for licencing, production ,distribution to ensure quicker and faster technology adoption	2	4 – Exceeded / AATF has successfully launched AgriDrive and QBS as new approaches to deliver impact at scale more rapidly. / Additionally, in the past year new approaches to seed licencing for TELA Maize and Cowpea have been rolled out to accelerate commercialisation.
Number of extension agents trained as TOTs	260	834 – Substantially Exceeded / AATF works through public and private extension agents on six projects and has significantly exceeded expectations on this indicator as approval of the new PBR Cowpea project enabled more training to be carried out. They are updating targets in their business plan.
Number of value chain actors that AATF works with to create market systems supportive of agricultural development.	13,000	9,135 – Partially Met / Since the launch of their revised strategy in 2018, AATF have worked with a range of value chain actors including seed companies, agrodealers, seed producers, grain traders, processors, transporters etc to strengthen technology dissemination networks. / This activity has been slower than planned in 2020 due to COVID-19.
Number of farmers linked to off-takers (CAMAP 55,000; TAAT Maize 1,400)	55,000	91,740 – Exceeded / Under CAMAP and TAAT Maize, AATF has worked to link farmers to off-takers in order to strengthen market linkages.
No. of technology policies, laws, regulations and standard operating procedures harmonized across countries and regions	1	1 – Met / With support from AATF, 2019 saw the approval of harmonised pesticide regulation guidelines for the East African Community.

Output Title	Create an enabling environment for increased uptake and use of agricultural technologies
Output number per LF		3	Output Score	A
Impact weighting (%):		20	Impact weighting % revised since last AR?	Y

Ensuring a favourable regulatory environment for AATF technologies is a key part of project activities as unfavourable regulation poses a major risk to the approval and commercialisation of new technologies and approaches. AATF’s work in this area receives funding from BMGF under the OFAB project and under the TAAT Policy Compact. AATF works to support governments and policy makers to develop the appropriate regulatory framework for biotechnology in African countries. This is not to promote a particular technology over another, but to ensure that African governments have the necessary legal framework and capacity to implement their own regulatory frameworks. In general, over the past five years, there have been positive shifts in the regulatory environment across Africa particularly for seed systems and biosafety. AATF maintains a detailed listing of the current state of play with respect to the regulatory environment in order to monitor changes.
This output is scored as an A as the majority of targets have been met. This is an impressive achievement given that delivering enabling environment is largely outside AATF’s control.
Indicator(s)	Final Logframe Target	Final Result Achieved
Number of countries with functional biosafety systems	2	3 – Met / Legislative changes supported by AATF include: / 2020 / Plant Variety Protection Law and Regulations in Malawi; / Seed Law in Liberia, / 2019 / Mozambique implemented an institutional framework for review and processing applications in 2019. / More detail is provided below.
Number of polices/legislations passed/amended to aid testing and commercialization of improved technologies in target countries	5	5 – Met / In 2020, Egypt became the eighth country to recognise the COMESA regionally harmonised seed regulations. And, supported by AATF, ECOWAS has finalised the regional quarantine pest list and is working to harmonise seed import/export regulations. / In 2019, Biosafety Regulations were passed in Ghana and Biosafety Directives in Ethiopia
Number of governments engaged on policy deliberations on commercialization of agricultural biotechnology/technologies	9	9 – Met / At the time of reporting, nine government are engaged in policy deliberations across Africa, supported by AATF and partners under the OFAB project..
Number of governments indicating formal commitments to implement policy, regulatory reforms for technology deployment	6	2 – Partially Met / At the time of reporting, two governments have indicated that they will make a formal commitment to implement policy, regulatory reforms for technology deployment
Number of beneficiaries reached through advocacy, outreach and regulatory interventions that will bolster enhanced capacity for private sector and seed systems in general.	4,800,000	4,291,024 – Met / AATF delivers targeted advocacy activities with respect to regulatory changes, with clear assumptions about reach through social media and other channels.

AATF tracks the status of the regulatory environment in Africa as part of the OFAB project. Figure 2 shows the changes over the period of this current phase of funding to AATF. Countries in dark green have a functioning National Biosecurity Framework (NBF), 6 in 2015 and 11 in 2020. The overall picture is positive, notwithstanding challenges in specific countries.
Figure 2: Regulatory Environment for GM Crops in Africa.

Output Title	Cross cutting focus areas for the organization
Output number per LF		4	Output Score	A
Impact weighting (%):		20	Impact weighting % revised since last AR?	Y

This output covers a number of cross-cutting focus areas that are split across three areas in AATF’s organisational results framework (partnerships and communications; IP licencing; HR and finance).
The majority of targets were met, or exceeded, with two not being met due to unsuccessful project applications by AATF. AATF has continued to build on its expertise in building and managing partnerships and managing technology licences and strengthening their stakeholder engagement following the launch of the new communications strategy in 2018.
Indicator(s)	Final Logframe Target	Final Result Achieved
Number of requests for partnerships; specialist technical expertise/ experience and knowledge sharing on agricultural technology transfer among key targets.	70	103 – Exceeded / Partnership is a key principle for AATF’s work and they are regularly contacted by potential new partners. Their expertise, particularly in licencing of technology in Africa also attracts interest from other organisations. / AATF keep a detailed record of engagement with other organisations.
Number of new partnerships/ collaborations/strategic alliances actualized to enhance the quality of AATF interventions	15	7 – Not Met / The target for this indicator was ambitious and contingent, in many cases, on successful applications for funding. However. notable new partnerships are with the International Rice Research Institute, The Seed Assure Alliance and the African Union.
Increase (quality and quantity) in number of mentions in both traditional and social media and drive stakeholder engagement (retweets, likes, clicks, views and responses) to support organization goals	82,500	135,405 – Exceeded / AATF’s new communication’s strategy has enabled a more proactive approach to communications, to raise awareness of AATF’s brand, following a rebranding exercise in 2018. This has resulted in significantly more media interest in AATF’s work than was previously the case.
Knowledge products developed and disseminated (Impact stories, books and booklets, journal articles, policy briefs, conference proceedings published, book chapters)	101	41 – Not Met / Over ambitious targets were set for this indicator at the launch of the new strategy in 2018. AATF have consistently produced around 15 different publications each year including institutional reports and policy briefs. Recent publications include several outputs on mechanisation services in Africa.
Number of trademarks/patents/PVP filed in project countries	8	8 – Met / AATF seed varieties compete with others in the market place and therefore need a clear brand. Registering and maintaining trademarks in target markets is vital and is an ongoing activity. / In 2020 four trademarks were renewed in Tanzania (WEMA, TEGO, DroughTEGO and TELA)
Number of sub-licenses negotiated and signed with partners	77	60 – Partially Met / As part of its partnership approach, AATF sub-licences technologies to project partners as needed. This is required by the organisations from which AATF has licenced technology. / This indicator was only partially met as fewer sub-licences were required than anticipated, and some project applications were not successful. However, this doesn’t reflect poor performance.
Percentage of review/audit/evaluation recommendations implemented.	100%	100% - Met / AATF has consistently implemented all audit findings/recommendations after each annual audit.
Staff turnover rate	5%	Met every year apart from 2018 / AATF generally has a low staff turn-over rate and this has been the case throughout the programme apart from 2018. / In 2018, 12 staff left the organisation / 1 retirement. / 3 posts ended as a cost-saving measure. / 4 found opportunities in other organisations / 4 contracts were terminated for disciplinary issues, identified during internal audit.

D: Risk [½ - 2 pages]
Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance. [1/2 page]
The risk associated with FCDO funding to AATF has been consistently rated as moderate throughout the life of the programme. Following reduction of FCDO funding and programme closure in 2020 the risk to FCDO has reduced to minor. There are no outstanding issues that give cause for concern. In the medium term, the primary risk to AATF is failure to continue to attract funding from investors.
AATF have a robust approach to Risk Management and their Risk Management Committee reports to AATF Management and the Board. AATF have a detailed Strategic Risk Register which clearly sets out Risks and Mitigation steps being implemented by Management across a range of categories, including procurement, finance and project management. Of specific interest to FCDO as a core investor in AATF is the strategic risks identified by AATF Management. A number of others relate to the regulatory environment and management of intellectual property.
AATF have a zero-tolerance approach to any fraud or corruption and have internal control systems in place to adequately identify and prevent misuse of funds in Finance and Procurement. In 2018, AATF’s systems identified three potential fraud cases, which were investigated, following AATF procedures. The concerned individuals no longer work for AATF and funds were recovered from them. This demonstrated the effectiveness of the systems.
While COVID-19 did impact the ability of AATF staff to travel to project locations and engage directly with partners, the direct impact on project activities was relatively limited. They have clear plans in place to support resumption of project fieldwork upon easing of restrictions in countries of operation and based on public health developments and guidelines

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation [1 - 1 ½ pages]
Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency. [1 page]
During the five year funding period, funding remained at £1.5 million per year until the final year. However, the payments for the final two quarters of funding (April – September 2020) were reduced by 50% due to the need to find cost savings across FCDO’s agricultural research portfolio as a result of COVID-19. Additionally, following the 2019 Annual Review, the Performance Related component of funding was ended due to the mixed evidence of effectiveness in incentivising institutional change at AATF. In total, £1,825,000, of the budgeted £10 million was not disbursed to AATF, primarily because the full performance related component of up to £500,000/year was not disbursed every year.
Quality of financial management
AATF have consistently demonstrated good financial management during the programme, submitted invoices on time and responding promptly to queries. Invoices and Financial Reports are submitted quarterly to FCDO outlining the expenditure incurred against the agreed budget from the previous quarter and the forecast for the next quarter. Full explanations are recorded for any significant differences between forecast and actual spend. Payments are made quarterly in arrears. The Pound Sterling/Dollar exchange rate remained stable during the year and therefore had minimal impact on Budgets.
Disbursement	15/16	16/17	17/18	18/19	19/20	20/21	Total
Core Funding	1,380,000	1,350,000	1,320,000	1,450,000	1,500,000	375,000
Performance Payment		250,000	0	400,000	150,000	0
Total	1,380,000	1,600,000	1,320,000	1,850,000	1,650,000	375,000	8,175,000

A full audit of AATF is carried out on a yearly basis by external auditors and the report provided to FCDO. Throughout the funding period, no findings have caused concern and AATF is rigorous in responding to any audit recommendations.
AATF also carries out audits of sub-grantees’ control systems to ensure management and financial accountability and a summary report is provided to FCDO. Generally, the controls in place are good; however, there were instances where financial controls could have been more robust. AATF follows up issues with the sub-grantees, and if necessary, will withhold funds until satisfactorily resolved. Additional Audits were conducted in October/November 2019 and AATF continues to engage with Project Managers and Partners to remind them of their financial management responsibilities.
AATF has provided FCDO with regular delivery chain updates and in 2020 has implemented a more nuanced approach to how they manage risks in their supply chain.
The key cost drivers for AATF are Personnel and Administration costs (including financial and audit), monitoring and evaluation, and accessing technical expertise. AATF have maintained a consistent cost structure with a major proportion of the budgets being designated for project and programmatic work, with a lean budget for core functions (resource mobilisation, monitoring and evaluation, governance, administration). AATF also have robust systems in place to deliver VfM, both within the organisation and with their sub-grantees. In anticipation of the end of FCDO funding to AATF they have also implemented cost saving measures and, over the life-time of the programme, have implemented various VfM measures as set out in previous Annual Reviews. Specifically, in 2020, as a result of COVID-19 many costs have been reduced as field visits and travel have been curtailed. This has forced AATF to consider new ways of doing business which may deliver further efficiencies in 2021 and beyond.

Programme-level approach to monitoring and evaluation [1/2 page]
FCDO has maintained a strong relationship with AATF throughout the live time of the programme, attending Board meetings and visiting Head Office at regular intervals over the past five years. This has been supplemented by regular engagement over email.
Improved monitoring and evaluation capacity and quality formed a part of the Performance Related Funding component of support to AATF. After a slow start, AATF has commissioned three independent evaluations in the past two years. The completed evaluation of the CAMAP project has demonstrated the positive impact of the mechanisation project.

Progress on recommendations from 2019 Annual Review (1/2 page)
#	Recommendation	Progress
1	If AATF is not able to position itself effectively in the market as a key player in taking innovation to scale, allowing it to set a clear innovation agenda, they need to consider other options for the future of the organisation. This could be simply as a trusted implementer of projects for donors or in providing services to the private sector. (by June 2020)	AATF still seeks to position itself as an organisation that takes innovation to scale, but they recognise that they operate in a very competitive environment. As highlighted in this review the slow pace at which they are making changes, compounded by the impact of COVID-19 is making this harder. / They remain a trusted implementer of donor projects, particularly for BMGF and USAID. / They are also exploring partnerships with the Syngenta Foundation for Sustainable Agriculture and the African Union and looking into setting up a consultancy arm.
2	AATF to consider the opportunities for more projects like CAMAP, given the success on the project. This has the potential to deliver impact more quickly and diversify the portfolio (by March 2020).	AATF is consciously trying to diversify their portfolio with technologies that can deliver impact more rapidly, as opposed to their core business of crop breeding. / For example, AgrDrive has initiated new projects on feed and fodder production, which have the potential to deliver impact more rapidly. In the past year there has also been a focus on developing projects in the new impact areas of their strategy, notably digital, nutrition and post-harvest. These have the potential to deliver impact more rapidly.
3	Given current slow progress on organisation change, despite consistent engagement from donors, FCDO will consider options for support to and engagement with AATF over the remaining year of the programme, taking into account resource constraints and challenges. (by February 2020)	After consideration, FCDO took two actions. / The Performance Related Funding Component of support to AATF was ended as a result of limited evidence of its effectiveness. / The final two quarterly payments were reduced by 50% to £187,500.

Date of last narrative financial report	October 2020	Date of last audited annual statement	July 2020 / (Vault ID: 56737187)

Annex 1: Current AATF projects
Project	Summary
AgriDrive	is a social enterprise wholly owned by AATF to engage in various commercial ventures in the agricultural sector as a business platform that complements AATF’s initiatives in agricultural development in Africa. It provides mechanization services, inputs and agribusiness support to farmers in Nigeria. The mechanization services are being offered on a commercial basis across various crop value chains.
Agro-processing for Post Harvest losses management	This initiative seeks to improve agroprocessing services to farmers growing cassava, sweet potato, yam and other tropical roots and tubers, by exploring processing equipment that has the capacity for processing these group of crops into high quality flour for human and animal consumption, and for other industrial uses (to increase access to domestic and global markets). It therefore seeks to support value creation and post-harvest management i.e.(reduction in root/tuber losses). The first pilot crop in the project is cassava taking benefit of CAMAP. The expected outcome is that agroprocessing will stimulate further increase in cassava productivity by over 200% and income by at least 150% for over 10,000 cassava smallholder farmers in SSA by 2022.
Bacterial Wilt resistant potato	is exploring two transgenes – pflp and EFR as proof of concept for efficacy in the control of bacterial wilt disease (BWD) caused by Ralstonia solanacearum in potato. The project aims to develop and deploy disease resistant transgenic potato varieties against BWD stacked with late bacterial blight. The expected outcome is commercial disease resistant popular potato varieties in Ethiopia and Nigeria in partnership with CIP.
Cassava Mechanization and Agroprocessing (CAMAP) Project	negotiates access and transfer of cassava mechanisation and agro-processing technologies for the benefit of smallholder farmers by increasing production efficiency and reducing drudgery. It aims to increase cassava yield per unit area through adoption of mechanization and best agronomic practices across the entire cassava value chain.
Digital Agriculture Project - Drones	this is a new AATF initiative being implemented under the digital Agriculture Impact Area of the current corporate strategy. AATF is exploring the use of drones to characterize the production environment of AATF’s seed-based technologies to boost the production capacity of farmers. The drones will be used for aerial monitoring to generate robust field data for strong analytics of crop cycles in selected fields of AATF projects (from planting through harvest) towards efficient input utilisation and agronomic management of the crop. It is also complementing mechanization in the CAMAP project to improve cassava field performance under a farmer clustering strategy that further maximizes drone application. The project intends to commercialize drone applications for the benefit of small holder farmers.
EGS - Nigeria	this project complements the efforts of the QBS project in Africa by building seed systems in Africa by focusing on Nigeria and the West Africa sub-region. Through a business entity the project is seeking to increase maize hybrid adoption in Nigeria by addressing the availability and sustainable supply of quality foundation seed that is presently limiting certified seed supply. The anticipated impact is the increased adoption of recently improved CGIAR maize genetics specifically adapted to Nigeria and West African (WA) environments. It will expand the land area under improved hybrids and will improve farmers' livelihood and profitability in West Africa.
Hybrid Rice	explores the breeding by Design approach to develop hybrids based on the use of 2-line hybrid rice technology to increase the productivity of rice in Africa. The expected outcome is commercialisation of 2-line hybrid rice varieties that are well adapted to African conditions and efficiently satisfy market needs/demands.
Maize Lethal Necrosis Diagnostics and Management	aims at mitigating grain yield losses incurred by maize farmers in Africa as well as preventing the spread of MLN from endemic countries to non-endemic areas on the continent. The expected outcome of establishing a functional MLN Phytosanitary Community of Practice in Africa has been successful accomplished with reduced incidence of MLN. While the current funding from USAID has lapsed, AATF has been engaged by CIMMYT to do Impact studies of the project’s intervention on MLN control
NEWEST Rice	is a multiple-partner collaboration project aimed at developing and disseminating genetically improved African rice varieties with enhanced agronomic traits, specifically Nitrogen-Use Efficiency (NUE), Water-Use Efficiency (WUE) and Salt Tolerance (ST) for the benefit of smallholder farmers in Africa. The project is under a no-cost- extension (NCE) until 2022 when the project is expected to result in the deregulation of an NUE product.
Open Forum for Agricultural Biotechnology (OFAB)	focuses on strengthening the policy and regulatory environment required to accelerate agricultural biotechnology development and promote the uptake of its products in Africa. The project aims to enhance capacity of stakeholders to understand, accept and safely use ag-biotech products for agricultural transformation in Africa.
Orange Maize Project	A new project which will be executed under the new Nutrition Impact Area of AATF strategy. The project is seeking to improve food and nutrition security in Sub-Saharan Africa through the deployment of climate resilient, nutritionally enhanced pro-vitamin-A maize varieties/hybrids to address maize deficit gaps and malnutrition challenges in Africa with Burundi as the first pilot country of intervention. The project aims to increased climate smart pro-vitamin-A maize hybrid production by at least 30% in target countries. The TAAT maize Compact (phase II) will complement this AATF initiative.
Pod Borer Resistant (PBR) Cowpea	addresses the high infestation of Maruca that accounts for high yield losses of cowpea in SSA. The PBR cowpea project is focused on developing and disseminating Maruca resistant transgenic cowpea varieties Burkina Faso, Ghana, and Nigeria. Following the successful release of the first GM Cowpea in Nigeria, the project is strengthening seed company capacities for the production of transgenic PBR cowpea seeds to drive commercialisation of PBR cowpea varieties.
QualiBasic Seed Company (QBS)	is a special initiative set up as a business entity to mitigate the paucity in supply of early generation seed and more specifically foundation seed. It aims at ensuring the production of quality foundation seeds for demand driven commercial hybrid maize towards strengthening the maize value chain in Africa.
Seeds2B	applies a market-led methodology to transfer seed technologies from research programs/technology developers from different parts of the tropical world to seed enterprises in Africa. The initiative strengthens farmers access to quality seeds for a wide range of new improved varieties of strategic crops.
TAAT Maize Compact	aims to harness high-impact proven agricultural technologies of maize to raise agricultural productivity in Africa by promoting the dissemination and massive scale-up of proven water efficient maize varieties in combination with other complimentary technologies (including fertilizers, seed treatment with pesticide for Fall Army worm etc). The project aims to increase maize productivity by up to 30%, through increased uptake and use of high yielding climate smart maize hybrids as well as increased profit margins for actors in the maize value chain.
TAAT Policy	is facilitating the creation of a conducive policy and regulatory environment for accelerated deployment of agricultural technologies and efficient marketing/trade of outputs from other TAAT compacts. Anticipated outcomes include drafting/review, adoption and implementation of regulations, laws, guidelines and standard operating procedures (SOPs) in Africa south of Sahara.
TELA	is developing drought tolerant and insect resistant transgenic hybrid maize varieties. This phase aims is to secure regulatory approvals and initiate commercialization of transgenic drought-tolerant (DroughtGard® trait) and insect-protected (Bt trait) maize hybrids (TELA® maize hybrids) in at least four African countries to enable deployment of these maize varieties to smallholder farmers in sub-Saharan Africa.
USDA-FAS	this initiative was begun by the USDA-FAS to help develop a regional bio-pesticide regulatory framework for Africa. It is presently focused on providing technical assistance in developing guidelines for registration of bio-pesticides in Sub-Saharan Africa (SSA). This effort largely seeks to increase availability of pest control products and it primarily addressing the outbreak and rapid spread of the fall armyworm (FAW) by empowering African farmers to sustainably manage FAW.
[note] Technologies for African Agricultural Transformation (TAAT) programme funded by the African Development Bank (AfDB)