## Annual Review

Title: Migration for Development Programme (M4D)
Programme Value £ (full life): 4,490,026		09 December 2020
Programme Code: 300901	AMP start date: 14/05/2019	AMP end date: 31/03/2022

Summary of Programme Performance
Year	2020
Overall Output Score	(A)
Risk Rating	Moderate

DevTracker Link to Business Case:	http://iati.fcdo.gov.uk/iati_documents/53126071.odt
DevTracker Link to results framework:	http://iati.fcdo.gov.uk/iati_documents/55983898.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The Migration for Development (M4D) programme aims to increase knowledge and capacity on migration and migration governance amongst key UK partners to facilitate safe and orderly migration, as per Sustainable Development Goal (SDG) 10.7, and prevent unsafe and unregulated migration. It has three components:
[note] Purpose statement taken from original business case.

Support the global governance of migration through a carefully targeted contribution: Provide a multi-year financial contribution (£3m over three years) to the Multi-Partner Trust Fund (MPTF) for Safe, Orderly and Regular Migration, set up by the UN Network for Migration (UNNM) to support implementation of the Global Compact for Migration (GCM), using our position as a donor to influence programming decisions and drive support from other actors. (70% results weighting).

Address the gap in capacity & knowledge: Funding for the Overseas Development Institute (ODI) to deliver knowledge generation, advocacy and capacity-building activities, and develop evidence-based policy recommendations and case studies for GCM and wider SDG implementation in UK priority countries. (20%)

Choose further programmes responsively as the global approach evolves: Hold back a proportion of the funds to flexibly respond to opportunities to deliver tools, knowledge or capacity on the UK’s priorities within GCM and migration-related SDGs. (10%)

During the first year the programme has disbursed £868,000 to the MPTF, funded an agreed work plan with ODI (£70,560) and made one grant (£250,000) under component three to the modern slavery NGO The Freedom Fund. In response to the C-19 crisis and the consequent fall in UK ODA linked to GNI, M4D payments were suspended in August 2020 for the rest of the financial year.
[note] £793,000 in 19/20 and then £75,000 in 20/21. The UK Mission to the United Nations in Geneva made an additional contribution of £207,000 in 19/20, which are not included in M4D’s budget

Summary supporting narrative for the overall score in this review

This programme has scored an A overall (“project outputs met expectations”).

As part of DFID’s ODA reprioritisation exercise in response to COVID-19, M4D was forced to suspend all payments and most activities from August 2020 for the remainder of the financial year 2020/21. Unused funds are expected to be rolled into FY 2021/2022.

- Component 1 – Contributions for the financial year were reduced from a planned £1m to £75,000
- Component 2 – Workplan was suspended.
- Component 3 – Activity suspended except for a £250,000 grant to The Freedom Fund to carry out COVID-19 emergency relief projects.
  [note] https://freedomfund.org/about/covid-19-emergency-response-fund/
Changes to workplans, particularly under components 2 and 3, were agreed at the time and clearly justified. However, for consistency, this review assesses performance against expectations at the beginning of 2020, before the pandemic had struck, and consequently components 2 and 3 down score relatively poorly. This is a reflection of the scoring methodology and should not be taken as any criticism of project partners.

Despite the pandemic, M4D has still achieved most year 1 objectives. This reflects strong progress in early months before funding was suspended, and the ability of the MPTF to continue operations throughout the crisis, using funds already disbursed by the UK and funds from other donors.

Major lessons and recommendations for the year ahead

	Recommendation	Owner
Programme Level:
1	Refresh overall programme log frame and risk register.	M4D programme team
2	Reassess how M4D sits within HMG objectives in light of the NSC refresh.	M4D programme team
3	Continue to work with the Home Office to understand how their domestic work aligns with GCM objectives and ensure awareness within the Home Office of GCM.	M4D programme team
Component 1:
4	Create stretching indicators and milestones for next year, in particular to measure the impact of MPTF projects once operational, & UK influence on the fund’s strategy.	M4D programme team
5	Ensuring the integrity of the MPTF: The UK should advocate for all project allocations to be based on evidence of potential impact, and to work with the Fund Management Unit to ensure donor earmarking does not limit fund effectiveness.	M4D programme team & UKMIS Geneva
6	UK leadership: The UK should continue to position itself as a leading member of the Steering Committee of the MPTF and advocate a holistic portfolio approach, e.g. supporting proposals for underrepresented geographies and innovative proposals.	M4D programme team & UKMIS Geneva
7	UK priorities: The Programme Team should continue to work with HMG partners to ensure priorities from across government are reflected in UK positions on the Steering Committee. It should also continue to calibrate its position to the wider interests in the Steering Committee, ensuring the portfolio remains balanced.	M4D programme team & UKMIS Geneva
8	Resources: Monitor the Fund’s resource mobilisation closely, as this will dictate its direction in the coming year.	M4D programme team
Component 2:
9	Work with ODI ahead of next financial year to develop a refreshed workplan for 21/22.	M4D programme team
Component 3:
10	Create a clear set of criteria for future project allocations. Criteria should ensure allocations align with the refreshed objectives of the programme.	M4D Programme team

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

A theory of change (ToC) is included in the business case. This was developed with input from an M&E adviser and in consultation with colleagues across HMG, proportionate to the size of the programme.
[note] See page 10 of original business case for the ToC.

Log frame objectives (see below) are directly derived from the ToC, though the first and third outcomes have been slightly modified to cover all components and to improve clarity, respectively.
[note] The first outcome has changed from: The Start-Up Fund delivers programmes in line with our objectives and ambition, that demonstrate a joined-up approach to implementing the GCM and relevant SDGs (Covers component 1).
[note] The final outcome has changed from: Additional evidence of what works in global migration management (covers all 3 components).

Outcomes	Impact
1. Multilateral system is able to drive implementation of the GCM in line with HMG objectives and level of ambition;	The multilateral system and UK target countries have additional tools, resources, and knowledge to act in a more joined-up way towards the delivery of the migration commitments in the SDGs.
2. There is greater technical expertise in target countries and other stakeholders to support delivery of the migration SDGs and UK migration priorities;
3. National and global policy is more informed by evidence of what works in global migration management, policy implementation and migration-related development programming;
[note] Impact indicator: GCM implementation reviews demonstrated that GCM has made a positive contribution towards the achievement of SDG 10.7. Outcome indicator: More countries and international actors are aware of, or using, the learning and tools developed by the outputs of the Start-Up Fund.

The ToC assumes that an effectively implemented GCM will support a stronger multilateral approach to migration. By providing financial support to the MPTF, supplemented by research and other activities under components 2 and 3, the programme aims to help GCM to become embedded in the global architecture and to assist with implementation.

Value for Money (VFM)

On programme value for money, and noting the project’s disruption this year, UK contributions to the MPTF have this year helped set the groundwork for future project outcomes, as was foreseen in the project log frame. The UK has played a prominent role at the Steering Committee leading to better coherence of the fund. The programme team are also content with the outputs from ODI and the impact of component three support to The Freedom Fund.

Apart from the disruption of COVID-19 on planned funding, there have not been major changes since the beginning of the programme.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Overall, the programme is on track to contribute to the expected outcomes and impact.

Two years after a challenging negotiation process, the GCM has consolidated its support among signatory states and is starting to build its framework for implementation, including the establishment of a secretariat, the UN Network on Migration (UNNM), the MPTF (see next section) and the first regional reviews of national implementation. This is a promising start, particularly given the challenges of COVID-19. The UK also has a better sense of the ambition and ability of both states and the UNNM to implement the GCM’s goals, especially in light of the impact of COVID-19 on migration and on funding. Whilst the GCM remains coherent as an agreement, it is ultimately for signatory states to translate its principles into action, and the GCM will likely continue to face political challenges from some states and funding challenges from others, given changing global and national contexts. The UK should continue to demonstrate leadership in order to maintain the Compact’s coordination and implementation.
[note] See https://migrationnetwork.un.org/country-regional-network/europe-north-america

UK funding to the MPTF, participation in its Steering Committee, and contribution to the first ever Regional Review of GCM has helped the UNNM to build visibility and performance steadily over its first two years of existence. The UK has also effectively used its profile to encourage other actors to consider and implement GCM objectives in policy and programming, nationally as well as internationally. The dissemination of ODI research papers to diverse stakeholders has also begun to contribute to global knowledge on migration, thereby supporting the overall objective of M4D.
[note] The UK’s submission to the regional review of GCM implementation can be found here.

A central assumption in the ToC is that ‘the UK projects a consistent position on migration across the HMG network and wider migration portfolio’.  This underlines the need for close cross-HMG working as the new UK immigration system comes into place.  The programme team will want to work closely with Home Office and other colleagues over 2021 to ensure there is a common understanding of the links between the new UK immigration policy and GCM commitments, and this feeds through into UK international messaging.

Similarly, the ToC’s assumption that ‘the components will contribute to creating a joined-up approach’ should also be monitored and reviewed against the original business case objective that activities should all relate to GCM and migration related SDGs. Some activities, including funding for The Freedom Fund are a loose fit to these criteria (though were appropriate to the ad-hoc nature of the grant in the context of COVID-19). The team will want to take a view on how directly activities support the GCM per se, as opposed to broader GCM principles.

In the next year the programme team will recalibrate the log frame to include a set of indicators for the second year, taking into account wider HMG contextual priorities when commissioning research and activities from components two and three. The team will also monitor the changing political context within HMG, especially noting the new immigration system and its alignment to GCM principles, as well as the international support for the GCM.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

M4D is delivering on its objectives, despite the significant setback of funding deferral due to the COVID-19 pandemic. The programme remains an important component of the wider FCDO migration portfolio, complementing protection of migrants under the SSSII programming and any forthcoming work to support the socio-economic benefit of regular migration through productive migration programmes. This programme directly supports the international dimension of the current National Security Council Migration Strategy, which is currently undergoing a refresh.
## C. DETAILED OUTPUT SCORING

Output Title	The MPTF delivers effective programmes that demonstrate a joined-up approach to implementing the GCM and relevant SDGs, in line with UK objectives and ambition.
Output number:		101	Output Score:	A
Impact weighting (%):		70%	Weighting revised since last AR?	No

	Indicator(s)	Milestone(s) for this review	Progress
1.1.	MPTF builds effective project portfolio based on funds available, as evidenced by a) creation of project pipeline, b) measures of project impact	Project pipeline developed by first annual review; first tranche of projects ready starting implementation.	Achieved
1.2	Impact as measured by Fund’s framework.	Results framework developed and approved by Steering Committee by first annual review.	Achieved
1.3	UK influence – UK achieves seat on steering committee in year 1.	Membership of steering committee achieved.	Achieved

Context

The UK’s pledge of £3m to the Start Up Fund (now known as the Multi-Partner Trust Fund) remains, but due to COVID-19 £925,000 of payments in financial year 2020/21 were deferred until 2021/22. A contribution of £75,000 was still made this FY to demonstrate the UK’s continued commitment. The UK has also played an active role in the Steering Committee and related technical groups this year.

All output indicators have been met during the reporting period. The intention for the first year of the programme was to establish the foundation of the fund and the UK’s position as a leading and influential donor within the Steering Committee. As well as agreement of allocations, this has involved the development of the fund’s operations manual (April), results framework, including new human rights markers (September), and risk register (November / December), which have all now been agreed.

In the next year, the programme team should work to develop new log frame indicators to reflect the implementation phase, which are specific, realistic and measurable.

Indicator 1.1 (Met)

The fund has built an effective and diverse project portfolio, as per the milestone. At the most recent Steering Committee in October, the fund agreed six joint programmes for funding which sit across five thematic areas, with implementation to start in early 2021. Seven other projects were identified as “Tier 2”, to be reviewed if additional resources were received. In the wider project pipeline, there are around 30 technically suitable project proposals which could be implemented if further funding becomes available. This is positive and demonstrates the fund’s continued relevance and profile. However, the fund has faced challenges mobilising resources, with only $17m pledged in the first year against a target of $25m. Given ongoing challenges due to COVID-19 there remains a risk that the number of proposals is not proportionate to the budget - relatively small for a pooled donor fund – which could pose a risk to its reputation if enough projects are not launched. Project impact will begin to be measured in the next review.
[note] Despite the FMU not undertaking outreach activities after the beginning of the Fund, there is continued interest from UN Country Teams with a total of 74 concept notes submitted to date. Of these, 35 were selected for the pipeline, with six allocated funding as above.

On the integrity of the fund, it has been evident that geographic diversity can be a point of tension amongst donors and broader stakeholders as well as the impact of earmarking of funding, which could restrict thematic diversity. The UK should work with the Fund Management Unit (FMU) to ensure these issues are mitigated and uphold the integrity of the operations manual.

Indicator 1.2 (Met)

The fund has now developed a results framework with donors that was agreed at the last Steering Committee, noting that targets can be adjusted if necessary. The results framework operates at fund level and does not directly measure project impact. As discussed with the FMU during this review, disaggregation of results and establishing common global indicators for projects is not possible. However, individual project results will be available and project teams will be encouraged to reuse indicators from previous projects where possible to improve impact analysis. It will be important to ensure this information is monitored and reflected in UK year 2 indicators.

Indicator 1.3 (Met)

UK influence is perhaps the most challenging indicator to measure during the first year. Nonetheless, the UK has achieved the milestone of securing a seat on the fund’s steering committee, which will be held until summer 2021 or 2022. It has also demonstrated influence during the preparation for the last meeting, where the UK played a leading diplomatic role to ensure agreement on the thematic projects based on proposal quality, despite contention over geographical diversity. Going forward, the UK should continue to play a brokering role, ensuring there is a diversity of projects in the fund and allocations are guided by quality. This will require the Fund to balance all interests and resist calls to prioritise particular geographies or themes. The UK can support the FMU in this regard, but also support concept notes submitted from underrepresented geographies or in underserved thematic areas.
[note] In this round, projects from North Africa and the Middle East were not selected.

In this context, the FCDO programme team has worked to ensure UK priorities are reflected without distorting allocations, noting that 50% of UK funds will be earmarked to thematic areas 2 & 3. The Home Office has also asked for UK geographical priorities to be echoed where possible. These priorities were reflected in allocation preferences and selection at the steering committee demonstrating UK influence.
[note] Thematic area two: Protecting the human rights, safety and wellbeing of migrants, including through addressing drivers and mitigating situations of vulnerability in migration Thematic area 3: Addressing irregular migration including through managing borders and combatting transnational crime

The Head of the FMU has fed back the important and balanced role the UK has played at the Steering Committee noting that ‘there is no [MPTF] donor community without the UK’. The FMU requested that the UK uses its leadership role to help mobilise future funds from other donors, recognising that the fund needs more resources to reach its initial objectives. Nonetheless he believes the Fund is in a good position having allocated funding to its first round of projects and considering disruptions of COVID-19.

Lessons identified this year, and recommendations for the year ahead linked to this output:

M4D Programme Team to review and create stretching log frame indicators and milestones for next year to measure impact of the fund & UK influence.

Ensuring the integrity of the Fund: The UK should advocate for project allocations to be based on evidence of potential impact, and to work with the FMU to ensure donor earmarking does not limit fund effectiveness.

UK leadership: The UK should continue to position itself as a leading member of the steering committee and advocate a holistic portfolio approach, e.g. supporting proposals for underrepresented geographies and innovative proposals.

UK priorities: The Programme Team should continue to work with HMG partners to ensure priorities from across government are reflected in UK positions. It should also continue to calibrate its position to the wider interests in the Steering Committee, ensuring the portfolio remains balanced

Resources: The Programme Team should monitor the Fund’s resource mobilisation closely, as this will dictate its direction in the coming year.

Output Title		ODI: Case studies and policy recommendations contribute to international evidence base for how migration can contribute to poverty reduction, including in UK target countries.
Output number:	102		Output Score:	B
Impact weighting (%):	20%		Weighting revised since last AR?	No

	Indicator(s)	Milestone(s) for this review	Progress
2.1	ODI demonstrates progress against workplan agreed with DFID	Workplan agreed with DFID (April 2020) / By first annual review, all agreed activities for 2020 completed	Available outputs in workplan met.
2.2	Progress on case study	N/A	Suspended
2.3	Completion of case study of productive migration opportunities in a DFID partner country	Agree	Suspended

Context

Component two comprises an accountable grant to ODI, which aims to address gaps in FCDO’s capacity and knowledge in migration issues. Due to COVID-19 the agreed workplan ran until July, and the review therefore covers a subset of this year considering only indicator 2.1 as the case study (indicators 2.2 and 2.3) was not undertaken. The available indicators have been met during the reporting period.

Indicator 2.1

As agreed with FCDO officials, ODI produced two papers and hosted an academic roundtable. The first, for the ‘Productive Migration’ workstream (Migration as an Opportunity: Innovation, Policies and Practice Primer), aimed to ‘create a repository of existing evidence of selected examples of operationalising productive migration’. The primer received extensive peer review and was presented at a roundtable in May for discussion and feedback. It was published in mid-July and disseminated across ODI online platforms. FCDO teams have noted the impressive quality of both the paper and the roundtable, even in the virtual format. The FCDO Productive Migration Team use this paper to regularly inform policy making and ODI have noted its impressive pickup.
[note] This first roundtable was titled migration as opportunity: innovation, policies and practice.
[note] To demonstrate its impact, one month after publication it had received 493-page views and 148 downloads as well as being featured on the ICMP reading list.

Similarly, the second paper on climate and migration (Migration and Skills for the Low Carbon Transition) was well received by FCDO and has been used extensively to inform policy. In feedback, a specialist climate adviser described the report as ‘a top piece of research, which was well written, clear and accurate’. It has also received praise for its innovation and the different perspective it provides. The paper was shared widely.
[note] UNDP, Robert Bosch Siftung (now featuring as the knowledge basis for an event in February 2021), IKEA Foundation, Open Society Foundation, Green MEP Damian Boeselager, HMI Advisory Network (featured in our newsletter attached), SDC GMPD, EBRD, UNICEF, IOM, ILO, OECD Development Centre

Both ODI and FCDO teams have reflected that communication has been clear and professional, including the handling around fund deferral to next financial year. FCDO should work with ODI before the next financial year begins to refresh the work plan. Teams could build on the success of the climate paper to provide additional insights ahead of the UK’s hosting of COP26 in 2021. Reflecting on any broader log frame changes in year two, FCDO should continue to consider how products agreed in component two fit into the wider FCDO migration portfolio.

The suspended work on the country-level case study had been expected to commence later in the year and had only reached early stages of planning when it was paused. ODI and the programme team may want to restart this in 21/22 but should not be bound by the previous workplan. They may equally decide jointly to substitute alternative work depending on emerging priorities

Lessons identified this year, and recommendations for the year ahead linked to this output:

M4D programme team to work with ODI ahead of next financial year to develop a refreshed workplan reflecting successes so far, relevance to overall portfolio and upcoming priorities.

Output Title	New financial capacity within DFID to respond flexibly to needs of international community and deliver on the Impact Statement.
Output number:		103	Output Score:	B
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1	Rules and procedures for use of fund complete by end of year 1	Completion by first annual review (suspended)
3.2	Levels of uptake	£500,000 by April 2021 / £1m by April 2022

Briefly describe the output’s activities, and provide supporting narrative for the score

Context:
Component 3 seeks to enable urgent and flexible response to emerging issues related to the UK’s sub-set of priorities within GCM and migration-related SDGs. In the review period it made a single grant before the ODA reprioritisation due to COVID-19. This was a £250,000 accountable grant to the Freedom Fund’s Emergency Response Fund (ERF) as part of COVID-19 response, which has provided critical small-scale funding to frontline partners working with vulnerable communities in India, Nepal, Myanmar, Ethiopia and Thailand.

Performance was on track at the time of suspension. As discussed below, the Freedom Fund grant was also successful and contributed to the headline objective of flexibly funding activities when opportunities arise. Nonetheless, suspension meant that neither performance indicator was met and as such, the component did not meet expectations. Recognising the progress made before suspension, the review scores it as “moderately did not meet expectations”. The component will be able to start activities again relatively quickly when funding is available again and should be able to make up for lost time in the second year. Nonetheless, the review notes that the Freedom Fund grant was made on an exceptional basis before rules on criteria were agreed. Before any other activities can be funded, the programme team should establish criteria for any future funding, both to ensure the transparency of the process and to make sure that selected projects align with the overall objectives of the programme.

Freedom Fund ERF

Results

The ERF has distributed vital assistance to vulnerable communities throughout the pandemic in the form of cash grants, and was the only NGO working in this space. Overall, The Freedom Fund has reported that the ERF was able to successfully support over 230,000 individuals, 55% of whom were women and girls, and 38% were children. As this grant was managed by the FCDO Modern Slavery Team, it was important to ensure that it sufficiently aligned with their priorities. The Freedom Fund targeted the community level and vulnerable populations, including migrant workers, who are both less likely to receive government support and at a higher risk of modern slavery. Specific examples include the connection of 60,000 vulnerable adults and children in Bihar and Uttar Pradesh to government pandemic welfare programmes, and the distribution of food, PPE and help with shelter and transport to 7,000 individuals in Thailand.
[note] Exact figure 249,048. Taken from The Freedom Fund’s draft report, to be published shortly.

Lessons identified this year, and recommendations for the year ahead linked to this output:

M4D programme team should seek to create a clear set of criteria/guidance for future project allocations. Criteria should ensure allocations align with the refreshed objectives of the programme.

D: RISK

Annual Statement of Progress

Current level of fiduciary risk and direction of travel since last ASP	Minor
Specific assessment of corruption risk and direction of travel since last ASP	Minor
Is a full FRA update required?	No

Overall risk level: Moderate

Prior to this review, the programme team undertook an evaluation of the risk register established in the business case at the start of the programme. The following risks were identified as highest impact:

	Risk type	Description	Rating
1	Reputational	Because migration is a topical issue which attracts a great deal of public attention, there is a risk that the programme receives hostile media scrutiny that affects the ability of the programme to deliver its objectives. Mitigation: / • Regular communication with Private Office (ExCo and Ministers), updating them on the programme when needed. / Have defensive lines prepared.	Moderate
3	Delivery	There is a risk that there is a lack of co-ordination between key donors – resulting either in donors to the MPTF disagreeing or UN Agencies unable to progress the UN reform agenda. / Mitigation: / We will work through FCDO posts in donor countries to promote donor agreement and UN reform priorities.	Moderate
4	Delivery	There is a risk that some parts of the multilateral system might lack the capability to deliver against our objectives both in terms of technical competence and flexibility to innovate. / Mitigation: / We will work closely with FCDO posts and contacts within the multilateral system to identify issues and mitigate these where possible.	Moderate
5	Context	There is a risk that changes in UK domestic politics could lead to an increasing securitisation of the migration agenda, which would deprioritise our development agenda. / Mitigation: / The programme itself will generate data, statistics and evidence to support the value of our interventions.	Moderate
6	Reputational	There is a risk that Civil Society organisations are unsatisfied with our outputs and call for a higher level of ambition. / Mitigation: / Design an engagement strategy and engage with civil society organisations to understand their asks of the GCM and identify ways to collaborate.	Minor
7	Safeguarding	There is a risk of sexual harassment, exploitation, abuse or fraud to occur within our delivery chain. / Mitigation: / Work with trusted partners and ensure that they meet FCDO's requirements on safeguarding. Ensure regular meeting and communications with implementing partners and proactively engage where we feel there are potential issues.	Minor

Risk narrative

In subsequent years, programme risks will shift to become more delivery focused, as the initial controversy surrounding GCM likely falls away. The M4D programme team will continue to monitor all risks at a programmatic, global and reputational level and review periodically. For component one, prior to this review the team took part in a workshop with other donors organised by the MPTF FMU and chaired by a risk analyst to establish a matrix for the fund. The team flagged possible priority risks for the UK, including safeguarding at project level, like sexual exploitation and harassment (SEAH) and potential for donor fatigue. These were subsequently reflected in the fund’s risk matrix alongside mitigations. More broadly, M4D will monitor the changing domestic migration context and any possible implications for the GCM, though impact on the programme is unlikely. There is a low level of risk for component two, especially as ODI are a trusted FCDO partner and the workplan is relatively simple. Risk in component three largely depends on the grant recipient. This year, risks were carefully managed by The Freedom Fund through the use of existing partners and limiting the numbers of tiers. As discussed with The Freedom Fund, there were no fiduciary or safeguarding risks reported by the fund and programmes were adapted where potential risks were identified. There should be a comprehensive review of the risk register early next year.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

Component 1

Admin costs for the Start Up Fund are lower than normal UN costs (pooled fund contributions are exempt from the 1% UNDS Reform Levy), which - although higher than the cost of delivering a programme internally - offer economy as the MPTFO is the Hub for delivering complex pooled funds, with expertise and experience in such projects. There is not currently resource available in DFID to undertake such a task. Pooled funds also offer significant efficiency savings for the UN, by avoiding competition for funding between agencies and negating the need for duplicative reporting to different donors. The programme team have been content with the management of the fund and the FMU has delivered all financial reporting and invoicing on time and to the required standard.

The UK has used its seat on the steering committee to comment on and improve project proposals, for example by advocating quality over geographical focus at the last meeting. The fund has now set out its results framework which, as discussed in this review, measures only FMU’s success. Although challenging, the UK should continue to press for a disaggregation of project results, tracking economy, efficiency and equity, alongside standardised project indicators where possible.

It is hard to measure the VFM of the UK contribution to the MPTF in its initial year and very difficult to assess efficiency until projects are underway. Individual projects implemented as part of the MPTF will provide evidence of VfM. Admin costs remain standard for a UN MPTF, which though potentially higher than the cost of delivering a programme internally offer established systems for complex fund management, risk control and financial monitoring, and access to established migration expertise in the UN system.

One of the ways we will judge the effectiveness of this programme is by assessing whether other donors and/or partner countries provide funding to and work with the MPTF. In its first year, donors and partners have worked well together, and funding from other donors is now increasing at the time of writing. Germany have recently committed a further $4m and Sweden pledged $387,374 in September.
[note] See http://mptf.undp.org/factsheet/fund/MIG00

Regarding equity, the MPTF framework will monitor gender inclusion. Data will begin to be collected beginning of 2021. The effect is assumed to be positive through the Theory of Change – the programme will help implementation of the GCM, which should lead to improved outcomes for migrants, who are some of the most marginalised people. We intend to use our seat on the Steering Committee to ensure that the MPTF includes projects that have a focus on ensuring equity, and that there is an equitable spread of projects across thematic areas and geographic regions.
[note] Results framework to be published on the MPTF website once agreed by SC.
Component 2

ODI fully delivered all the aspects of the project work plan before its suspension and provided regular and punctual financial reporting and invoicing. Slightly more was spent than expected in FY20/21, making up for the lower spend in year one. A large proportion of this went on staff and consultant costs to prepare for the roundtable as well as writing and finalising the two primers which had associated production costs. The remainder of the budget will be put into 21/22 FY. The programme team were pleased with the value for money of the outputs produced by ODI.

Component 3

The Freedom Fund were able to ensure value for money through a range of mechanisms, while complying with their primary aim of distributing funds as quickly and flexible as possible, with minimal bureaucracy. They used their existing network of partners in country, aiding efficiency and economy, and did not use any funds to cover staff costs. Additionally, the FCDO’s £250,000 donation helped to leverage further funding for the ERF as it was matched by another donor. The Freedom Fund effectively adapted their monitoring and evaluation mechanisms to cope with the COVID-19 pandemic, including holding online evaluation meetings, planning retrospective community monitoring, and creating a specific set of guidelines for partners. Overall, the programme team was content with the value for money provided by this grant.

	Date of last narrative financial report	Date of last audited annual statement
Component 101	Rolling reporting	N/A
Component 102	August 2020	N/A
Component 103	August 2020	N/A