## Sheet1
PROJECT NAME | Ethiopia Portfolio Assurance Programme (EPAP)
IMPACT | Impact Indicator 1 |  | Baseline November 2017 | Milestone November 2018 | Milestone November 2019 | Milestone November 2020 | Target March 2021
- Improved effectiveness and efficiency of FCDO Ethiopia funds - Fewer funds channelled through critical and high risk entities | EPAP provides significant added value to the rigorous management systems currently in place without increasing transactions costs and enhances the assurance for FCDO Ethiopia | Planned | - | - | - | - | EPAP is used as one key source of evidence to manage risk at a portfolio level and also for design of new programmes
Achieved
Source
Evidence from EPAP used for decision making in FCDO Ethiopia at the highest level.
OUTCOME | Outcome Indicator 1 |  | Baseline November 2017 | Milestone November 2018 | Milestone November 2019 | Milestone November 2020 | Target March 2021 | Assumptions
Improved financial, risk management and governance structures of implementing partners of FCDO Ethiopia | EPAP lead to strengthening of systems and process. | Planned | No Milestone | No Milestone | - High risk areas identified for 2 programmes - Clear recommendations made to address the weaknesses - Key stakeholders (e.g. SMT, FACC, TLs) recognise the positive contribution of EPAP to reduce risks that impact on the portfolio | No milestone (AR exempted) | - High risk areas identified for further 3 programmes and effectiveness of existing anti-corruption interventations of GoE are assessed. - Tools and/or analysis developed to help enhance FCDOE's control and assurance environment - Key stakeholders (e.g. SMT, FACE, TLs) recognise the positive contribution of EPAP to reduce risks that impact on the portfolio - Lessons shared to help enhance the capability and knowledge of DFID Ethiopia | - Partners incentivised to improve control design and operating effectiveness - FCDO is willing to cease funding in case of non-compliance - Organisations dismiss individuals found guilty of fraud - GoE willing to cooperate transparently for the anti corruption study.
Achieved
Source
EPAP programme review and recommendation reports and progress review reports. Minutes of meetings and lessons shared.
| Outcome Indicator 2 |  | Baseline November 2017 | Milestone November 2018 | Milestone November 2019 | Milestone November 2020 | Target March 2021
| Increased evidence base to make better funding decisions | Planned | No Milestone | No Milestone | No Milestone | No milestone (AR expemted) | EPAP used as a source of evidence for funding decisions
Achieved
Source
Fundings, Programme submissions and Annual reviews
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£)
| £ 1 million |  | N/A | £1m | £ 1 million
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline November 2017 | Milestone November 2018 | Milestone November 2019 | Milestone November 2020 | Target March 2021 | Assumptions
Inception phase successfuly completed | Portfolio level consideration undertaken to agree selection of programmes for review | Planned | No Milestone | No Milestone | - Approcah to programme selection presented to FACC (and whole office at MMM) and agreed - Working Group to agree criteria for selection of programmes and programme selection formed - At least one programme selcted from each team (i.e. 3) to be screened/assessd for inclusion in year 1 reviews |  |  | - Programme teams accurately assess overall risk level in entities - DFID teams are forthcoming with programmes to be included in reviews and are engaged to facilitate the reviews. - Provider produces good quality work
Source
Meeting Minutes and email exchanges.
| Output Indicator 1.2 |  | Baseline November 2017 | Milestone November 2018 | Milestone November 2019 | Milestone November 2020 | Target March 2021
| Programme specific work undertaken | Planned | No Milestone | No Milestone | - Methodology for reviews developed by imlementing partner, discussed with DFID prog teams and all comments incorporated - Decision made on 2 programmes to be included for reviews - Engagment with partners held and field visits undertaken to develop a deeper understanding of risks and potential solutions - Reports issued which identify risks, outline recommendations with agreement on 80% of the recommendations between all parties involved - Risk review of 2 programmes initiated
| Field visits | Achieved
Source
Programme progress reviews
IMPACT WEIGHTING (%) |  | Source
0%
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£)
|  |  | N/A | £0.2m | £0.2m
INPUTS (HR) | DFID (FTEs)
0.5
OUTPUT 2 | Output Indicator 2.1 |  | Baseline November 2017 | Milestone November 2018 | Milestone November 2019 | Milestone November 2020 | Target March 2021 | Assumptions
Quality reports and effective action plans established and managed in accordance with identified needs within the FCDO portfolio | Number of risk reviews completed for addressing key risks | Planned | N/A - No reviews started | N/A - No reviews started | Two reviews completed | No milestone (AR expemted) | Three reviews completed | - FCDO programme teams and partners will colloberate with EPAP's implementing partners fully. - Timely access provided to implementing partners offices and documentation
Achieved
Source
EPAP Programme reviews
| Output Indicator 2.2 |  | Baseline November 2017 | Milestone November 2018 | Milestone November 2019 | Milestone November 2020 | Target March 2021
| % of members of FCDOE's programme team (whose programmes are reviewed) agree that the risk reviews were of high quality and helpful to their programme delivery | Planned | N/A - No reviews started | N/A - No reviews started | 80% 'agree' | No milestone (AR expemted) | 70% 'agree'
Achieved
Source
Survey of FCDOE's programme team whose programmes are reviewed
| Output Indicator 2.3 |  | Baseline November 2017 | Milestone November 2018 | Milestone November 2019 | Milestone November 2020 | Target March 2021
| % of EPAP Review recommendations received / agreed by programme teams | Planned | N/A - No reviews started | N/A - No reviews started | 80% of recommendation accepted | No milestone (AR expemted) | 70% of recommendation received
Achieved
Source
Programme progress reviews, meeting minutes
| Output Indicator 2.4 |  | Baseline November 2017 | Milestone November 2018 | Milestone November 2019 | Milestone November 2020 | Target March 2021
| Action plans established and monitored by SRO's (e.g. in delivery plans, stand-alone trackers). | Planned | N/A - No reviews started | N/A - No reviews started | 100% of received recommendations included in action plans | No milestone (AR expemted) | 100% of received recommendations included in action plans and monitored
| Field visits | Achieved
IMPACT WEIGHTING (%) |  | Source
80% |  | EPAP programme team monitoring of progress against recommendations. Follow-ups by EPAP review team.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID Share (%)
|  |  | N/A | N/A |  |  | 100
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline November 2017 | Milestone November 2018 | Milestone November 2019 | Milestone November 2020 | Target March 2021 | Assumptions
Enhanced capability within FCDO Ethiopia to manage programme risks. | Review of smaple reports from various partner organisations to assess robustness and make recommendations for improvement | Planned | N/A - No reviews started | N/A - No reviews started | 0 | 0 | At least 6 reports reviewerd. Assessment report produced. | There will be sufficient levels of major issues identified to warrant the development of tools to help solve the issues, and organise lesson learning session.
Achieved
Source
Programme reports reviews
| Output Indicator 3.2 |  | Baseline November 2017 | Milestone November 2018 | Milestone November 2019 | Milestone November 2020 | Target March 2021
| Build capability of staff through delivering training and sharing of lessons. % of staff who find the capability building useful. | Planned | N/A - No reviews started | N/A - No reviews started | 0 | N/A | At least 1 capability building session held. 70% or more find this uesful.
|  | Achieved |  | NA
Source
Learning sessions held with staff
| Output Indicator 3.3 |  | Baseline November 2017 | Milestone November 2018 | Milestone November 2019 | Milestone November 2020 | Target March 2021
| Number of tools developed to help improve reporting by partners and staff's capability to assess these | Planned | N/A - No reviews started | N/A - No reviews started | 0 | 0 | 2
|  | Achieved |  | NA
IMPACT WEIGHTING (%) |  | Source
20% |  | Tools produced
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
|  |  | N/A | N/A
INPUTS (HR) | DFID (FTEs)