Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Building Core Systems in Sierra Leone
Programme Value: £25m		Review Date: January 2017
Programme Code: 205192	Start Date: 10th Feb 2016	End Date: 31st Dec 2017

Summary of Programme Performance
Year	2017
Programme Score	A
Risk Rating	Severe

Summary of progress and lessons learnt since last review

The programme began to see results in the latter part of 2016 and scores an A. DFID is monitoring progress, effectiveness and Government of Sierra Leone (GoSL) commitment with a view to making changes swiftly if required. There is limited time left for the programme to run and even less time before GoSL attention may be diverted to the 2018 elections. It is crucial to see results in the next six months.

The rationale for a 100% performance-based financial aid programme with associated technical assistance (TA) was threefold: to i) relieve pressure on the national budget; ii) incentivise core systems strengthening; and iii) maintain policy dialogue with GoSL.

The first of these has proven critical, as GoSL struggled to close the financing gap during compilation of the 2016 and 2017 budgets and only collects around 11% of GDP in revenue (compared to around 20% in neighbouring countries). The disbursed financial aid was helpful in closing the gap.

In terms of improving core systems, the objective was to ensure GoSL can increasingly absorb international aid, better deploy its own revenues and be better equipped to respond to future crises without leaning on development partners (DPs). This involves tackling legislation and systems and the practice and culture. Performance against four disbursement-linked indicators (DLIs) was assessed in 2016. Results against these showed the GoSL staying on track with the IMF programme (indicating a broadly stable macroeconomic environment) and enhanced transparency in procurement. Goods and services tax (GST) collection fell short of the target, however, indicating a lack of progress in improved revenue collection systems. The DLI on budget credibility measured performance in 2015 (against a pre-agreed target) and showed a severe decline in control of budget execution. Preliminary data for 2016 do not suggest an improvement. With the GoSL meeting two of the four targets, DFID disbursed half the budgeted financial aid to GoSL (£5m out of a possible £10m).

The DLIS were designed to incentivise completion of reforms. Of the three DLIS capturing performance in 2016, the first was missed and the second two were met. The second two were met partly as a result of senior Ministry of Finance and Economic Development (MOFED) staff driving delivery; this was indicated by regular dialogue at the political and technical levels. DFID adhered to the agreement and did not disburse against the missed DLI despite proximity to the target. This may have boosted momentum to meet the second two and the timing of the second two meant they could benefit from assistance from the TA. This suggests that the GoSL has recognised the importance of meeting the DLIs (albeit too late to achieve the first one) and is working with the TA to deliver on them. Engagement from GoSL around design of the 2017 DLIs has been strong.

The case for this programme rested on whether this type of programme is the most effective to achieve development progress and the impact on our relationship with GoSL and programmes of other DPs. In the past, general budget support provided the main platform for dialogue with GoSL on critical reforms, primarily essential economic policy measures and those to build accountability. To withdraw from financial aid would mean losing our voice in policy discussions, or at least the strength of our influence would be significantly weakened.

Bilateral policy dialogue between DFID and GoSL has been regular and the relationship with senior MOFED staff is strong. This part of the assumption in the business case has proved correct. Where the dialogue falls short of expectations in the business case is with other DPs. Staffing has led to the other DPs lacking presence or engagement on these core issues. This reduces the strength of the messages we can deliver. DFID now chairs the public financial management (PFM) donor working group to help solve this problem and while it has increased dialogue, the lack of available staff, especially from the African Development Bank and the World Bank, to attend has yet to be resolved.

Policy dialogue only works when there is commitment and drive to reform on the part of GoSL. The strength of this commitment was specified in the business case as a key risk to success. MOFED senior management share the objectives of the Building Core Systems (BCS) programme and have been pushing to ensure they meet the DLIs. Indeed, MOFED and the National Public Procurement Authority (NPPA) together met two of the three DLIs which covered performance in 2016. There are some decisions eing taken that call into question the level of commitment, though, such as reducing the share of the budget afforded to health. Commitment of the National Revenue Authority (NRA) has been called into question in light of the poor revenue collection performance compared to peer countries, and missing the revenue DLI in 2016.

The business case articulated that sustaining the momentum of reforms in the face of resistance from those who oppose change would be a risk. There is not yet evidence to suggest that reforms spoken about during policy dialogue will be followed through and completed. There is a year to go before elections and momentum is likely to decline in the months before the election. It is vital that we agree on what can be done in the limited time available until then, prioritise these actions and work with GoSL to see them completed. Dialogue with senior MOFED management suggests revenue collection, payroll cleaning and improvements in procurement practices is where focus should lie. With commitment behind reforms in these areas, the programme will orient to ensure it capitalises on the commitment.

The project scores an A at output level, reflecting that progress is broadly on track. Outputs achieved this year involve improvements to the process and tools that MOFED uses to forecast developments in the macroeconomy; better processes to track revenues; a more clearly defined strategy underpinning fiscal policy and better systems to enable publication of information on procurements and contracts. Next year’s targets will build on these, requiring these changes to be embedded and see changes in practice, leading towards the 2017 DLIs. It will be important for the TA to maintain its flexible approach – in terms of being supportive to MOFED’s emerging needs. It is also important to maintain focus on essential reforms, particularly on making sure expenditure is directed as approved, and that revenues are increased. The GoSL needs to make some tough decisions on structural reforms, particularly in the areas of revenue raising, payroll and procurement; the 2017 DLIs will reflect this. DFID’s engagement and support to GoSL on PFM will be led through this project across 2017 and, as explained above, be oriented to deliver on a few pressing priorities where GoSL commitment is strong. Given the importance of the commitment levels, progress on reforms and the trajectory of commitment to the UK Partnership Principles will be monitored closely. A significant drop in the commitment and momentum would result in DFID terminating financial aid to GoSL.

Summary of recommendations

DFID Sierra Leone is revising its approach to PFM in early 2017, which will take into account an assessment of what is achievable before an election. Plans for 2017 for the BCS programme should be reviewed in February and March 2017 to ensure consistency with the new approach. The DLIs and log-frame will be reviewed as well for consistency and the log-frame needs to ensure it holds GoSL accountable for action as well as the TA.

Several assumptions have been made regarding outputs to be delivered by the World Bank Trust Fund working in MOFED on PFM issues (PFMICP). Progress of PFMICP has been slower than expected and outputs have been of considerably lower quality than expected. This poses threats for the successful completion of several BCS outputs. The programme will need to revisit milestones that rely on PFMICP outputs and redesign them, catering for the highly likely event that PFMICP does not deliver as planned.

A renewed drive to engage in strategic level discussion with other DPs is urgently required.

There is a lot of DP funded activity on PFM reforms; the TA team has made progress on co-ordination with these, but will need to continue to devote time and energy to this activity.

Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-205192/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-205192/documents

The Building Core Systems programme is intended to improve GoSL’s core PFM systems, increasing its capability to raise domestic revenue, formulate and execute a sound budget, spend public money wisely and promote accountability, including in procuring goods and services.

There are three components to the project. The first is performance-based financial aid, which is intended to incentivise reforms. This provides up to £10m a year earmarked to health workers salaries, in eight tranches over two years. To get this funding GoSL has to meet eight pre-agreed targets – the DLIs. The DLIs specify output and outcome level targets that the GoSL can decide how to achieve. The second component is TA, which supports GoSL to implement its reforms, and in particular to meet the DLI targets. The third is a diagnostics and monitoring component, from which a PEFA will be funded.

Both the financial aid and TA components are focused on five areas that will make an impact on improving service delivery, increasing revenues, and making better use of their resources. These are i) budget credibility (including budget calendars and disbursement controls, but also fiscal and macro planning), ii) wage bill and payroll control; iii) public procurement practices iv) revenue mobilisation and v) macroeconomic management.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment Two of the four outcome milestones were met.

Outcome Indicator 1: Improved budget credibility. Not Met

The milestone was “variance in expenditure composition between actual and originally budgeted primary expenditure”. Performance in 2015 and 2016 significantly deteriorated, and missed the target of 15%. This was in large part due to contracts signed in the previous year but not accounted for in the budget. The funding attached to this indicator was not disbursed.

Year of performance	Variance of composition of spending against budget
2014	13.6%
2015	26.1%
2016	39% -provisional (early data)

Outcome Indicator 2: Wage bill sustainability. Met
The milestone for 2016 required that the public sector wage bill for 2017 is reduced to 60% of the forecast revenues in the 2017 budget. This was met; the 2017 wage bill is budgeted at 50.28% of forecast revenues. This is primarily due to a significant jump in forecast revenues compared to last year, but is also a result of support to GoSL in enforcing difficult policy instruments such as the recruitment freeze; and bringing the sub-vented agencies (SVAs) onto the payroll to control wages.
Outcome Indicator 3: Sound macroeconomic management. Met

The milestone for 2016 required that Sierra Leone stays on track with the IMF programme. The Board passed the final review of the IMF programme in Sierra Leone in December 2016, indicating that the programme was on track.

Outcome Indicator 4: Increased domestic revenue collection. Not met

The milestone for 2016 was “Domestic GST increases by 15.6 billion Leone in first half of 2016 compared to same period of 2015”. This was narrowly missed; an increase of 15.1 billion Leones was recorded and sent to DFID. The funding attached to this indicator was not disbursed.

Overall output score and description

The programme scores an A. Progress was made across the programme in developing the systems and processes required to help GoSL improve its ability to better manage revenues and expenditures. The project team have developed strong relationships quickly, and have shown flexibility to focus resources on areas which are government priorities and where there is an appetite for reform. Detailed progress is set out in subsequent sections.

Key lessons

It is early in the project to learn lessons. However, two lessons from other DFID projects are very relevant to this project. First, that the TA team dedicates time to understanding the institutional politics; the incentives that drive policy change.

Second that windows of opportunity for changing policy open, sometimes for short periods. Projects need to be flexible to respond to these.

Key actions

Following from the recommendations, the actions are as follows:

Action	Actor	Timing
DFID SL PFM strategy revised to focus on critical priorities where there is demonstrated commitment, and ensure BCS aligned with this.	DFID then BCS TA	By end April 2017
BCS to work with MOFED on articulating the strategy for improving procurement practices.	DFID and BCS TA	By end March 2017
Revisit milestones that rely on PFMICP outputs to redesign them	BCS TA with donors	By end March 2017
Update 2017 log-frame milestones to specify the requirement that NRA and RTPD should routinely share data.	BCS TA and DFID	By end Feb 2017

Has the log frame been updated since the last review?

N/A – this is the first Annual Review.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Well-developed and well-executed national budget
Output number per Log frame		1	Output Score	A
Risk:		Severe	Impact weighting (%):	25%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator	December 2016 Milestone	Progress
Budget data and monitoring improved	Prototype dashboard established using consolidated information from Access data, FMIS and Budget Book	Met: A prototype dashboard (a DataMart portal) has been developed to provide tools for budget analysis, and sample data has been put into the system.
Orderly budget process	Indicative budget calendar for formulation of 2018 budget approved by MOFED.	Met: The calendar was developed and approved following consultations with the Budget Bureau (BB), the Public Investment Management Unit (PIMU) and the Economic Policy and Research Unit (EPRU).

Key points:

This output socres an A. This is despite the decline in budget credibility at the outcome level in 2015 and the first part of 2016, because of the timing. The outputs have been designed with help from the TA, starting mid-2016. These outputs pave the way for an improvement in budget credibility towards the end of 2016 and to be reflected in 2017 outcomes. Monitoring will need to take place throughout 2017 to ensure the outputs are correctly designed to result in a vast improvement in budget credibility at the outcome level.

The new dashboard provides a single source of all data required to produce monthly, quarterly and annual budget analyses and reports. Previously the data were in different systems whereas now they feed into one user-friendly system which allows MOFED staff to undertake in-depth analysis and provide detailed reports on the status of budget execution, including the tracking of virements within MDAs. The latter is particularly important because the use of virements (moving funds between lines of an MDA budget and between MDAs) reduces the credibility of the budget. The dashboard was tested during the preparation of the 2017 budget; it was used at budget hearings to show the spending of MDAs in the prior year, and whether bids for the coming budget year were within the budget ceiling. The Budget Bureau and Public Investment Management Unit are committed to training and full use of the dashboard next year. One milestone for the end of 2017 specifies that the Budget Bureau should be conducting quarterly analysis on budget execution, i.e. focusing on institutionalising some of these reforms.

The current budget calendar is not robust enough to support effective budget planning and implementation. It is an administrative process that currently limits the involvement of political actors, and negatively impacts budget credibility. The new calendar developed under the programme is designed to ensure the budget preparation process starts in the first quarter of the financial year and provides sufficient time for all stakeholders to be fully involved in the process. This includes allowing Cabinet to allocate the resource envelope identified in the Fiscal Strategy Statement according to national policies and priorities, as it provides more time for political oversight. The new calendar also brings together some of the reforms which are the focus of other project work streams, including macroeconomic and wage bill components. Consultations with the EPRU have focused on how the macroeconomic framework can be prepared in time for Cabinet to make policy choices within the available resource envelope. Consultations with the Budget Bureau and PIMU has focused on when to issue the Budget Call Circular, the timing of policy hearings, the negotiation with MDAs on various issues including procurement, and discussions with the IMF. The new calendar smooths out several anomalies, for example, the timing of the announcement of budget ceilings to MDAs in the Budget Call Circular is now such that proper account can be made of the result of the IMF’s annual mission. The 2018 budget must be formulated in line with the new budget calendar, as set out in next year’s milestones.

Output Title	Better processes and increased capacity for management of the public sector wage bill
Output number per Log frame		2	Output Score	B
Risk:		Major	Impact weighting (%):	20%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator	December 2016 Milestone	Progress
Wage bill data and capacity for analysis increased	Automated payroll system established and piloted for 75% of sub-vented agencies who have provided data (that is 50 agencies)	Not met in full: The programme has processed data of all 66 sub-vented agencies which have submitted data. 7 have been piloted with salaries being paid through bank accounts in December. / MOFED is now working to import the data of 59 more agencies. 23 are expected to be done by end of January.
	Total 2017 wage-bill budget compiled and analysed in relation to achieving 2017 DLI	Met: A dashboard for wage bill preparation was prepared. It was used as an aid to forecast expenditure actuals for fiscal year 2016, and to perform multi-dimensional analysis on the wage bill. This tool was then used to develop the 2017 wage bill at 50.28% of forecast revenues, meaning it remains within the DLI target of 60%.

Key points:

This output scores a B because, although an important reform is being pushed through, GoSL timelines slipped from those expected.

In tackling the unsustainably large wage bill, the programme has focussed on improving wage bill analysis and forecasting and gaining a better understanding and control over sub-vented agencies’ (SVAs) payrolls. The programme team also sit on the MOFED Payroll Working Group and offer advice and support to the multiple initiatives aiming to clean the civil and public sector payrolls. These initiatives aim to clean the payroll, and give GoSL the data and tools they need to keep it clean and sustainable. We measure sustainability in terms of the proportion of domestic revenues that are accounted for by the wage bill. In 2014 this was 65%, 74% in 2015 and 64% in 2016. The DLI for this focus area required that the 2017 budget showed wages at less than 60% of forecast domestic revenues.

The key reform the programme has supported is the decision to transfer all SVA payroll management to MOFED, so that MOFED pays staff from SVAs directly through bank accounts rather than a lump sum payment to the SVA. GoSL will be better able to control the wage bill.

The wage-bill for 2017 has been prepared in compliance with the DLI, i.e. the wage bill is budgeted at 50.28% of forecast domestic revenue (the indicator setting out a cap of 60%). The programme contributed to this through provision of analytical tools (to understand the wage bill holistically), support to other interventions to clean the payroll, and highlighting the DLI[1]. Specifically on the analytical tools, a dashboard was developed by the team to monitor and forecast wages. It was used by the Budget Bureau to analyse and set wage-bill figures in the preparation for the 2017 budget.
[1] i.e. alerting MOFED to the incentives at play to encourage actors within government to take greater ownership of reform processes and related decision-making, and for monitoring progress towards milestones.

Milestones for next year will revolve around institutionalising the reforms and need to also account for proper completion of the education payroll clean up.

Recommendations:

The automation of SVA payroll data and payments reform has yet to be completed and the TA team will need to continue to support MOFED to ensure MOFED completes the reform. There has been some discontent among a couple of SVAs as they fear loss of their protected autonomy over their payrolls. This is a delicate balance that MOFED needs to understand and strike well. The BCS team should continue to support MOFED in achieving this.

Output Title	Improved transparency and more competition in national procurement
Output number per Log frame		3	Output Score	A
Risk:		Severe	Impact weighting (%):	25%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator	December 2016 Milestone	Progress
NPPA website functioning and contracts are being uploaded	Full details of 24 contracts above the national competitive bidding threshold are uploaded to website	Met and exceeded: 55 were uploaded before the deadline. / http://publicprocurement.gov.sl/files/contract_awards.pdf
Improving processes and capacity for national procurement	Selected procurement regulations amended and harmonized with new Procurement Act, internally approved by NPPA	Met: The harmonization of the regulations was conducted between July and October. Following iterative drafting and review, these were internally approved by NPPA in November.

Key points:

This output has the most resources dedicated to it and is one of the Minister’s top priorities. At the request of the Minister of Finance, an additional full-time consultant was added to the programme to work on procurement from the MOFED side, largely on strengthening the Expenditure and Contract Management Committee (ECMC). Two other consultants are based in NPPA. The milestones have been met or exceeded but this area is the most politically sensitive and the programme is running into obstacles that threaten the planned outputs for 2017. There is a need to ensure the programme aligns well with MOFED’s strategy, over which clarity is needed.

The programme has achieved a step forwards in making the government procurement process more transparent. Prior to the programme no contracts were uploaded and the NPPA website was not operating in such a way that they could be uploaded. This has been fixed and 55 have been uploaded, exceeding the target of 24. Citizens and potential bidders are now able to access important contracting information thereby helping to increase accountability and the competitiveness of public procurement. The details that can be accessed by the public include the name and address of successful bidder, the type of procurement process (i.e. competitive bidding or sole sourcing etc), the value of the contract and the expected date of completion. These are all contracts signed in the last year, cover a wide range of MDAs and vary in size. This indicator is a DLI and hence £2.5m was disbursed against it. Next year this push for transparency is being significantly scaled up. There is also a plan for 2017 to ensure that civil society organisations that focus on monitoring the state budget are aware of this newly available information.

The harmonization of the regulations in line with the 2016 Procurement Act has been completed internally at the NPPA following an extensive and iterative drafting process. This harmonization provides consistency across the regulatory framework, ensuring on the ground practices are guided in a manner which is in line with the legislation. Work in 2017 will ensure the regulations are followed.

The Auditor General released a special audit report in August 2016 focusing on procurement. This spurred debate as it highlighted critical weaknesses in the system. The debate was used by BCS to raise awareness of the issues around the need to put in place a credible procurement system.

Recommendations:

MOFED’s plan of action with regards to improving procurement practices needs to be articulated and the programme should ensure it is aligned with that. The 2017 DLI should ideally be tied to the most demanding, highest impact actions of that. If the 2017 DLI is still specified at the output level, an outcome indicator needs to be designed in this area.

Output Title	Better processes and increased capacity for macroeconomic management
Output number per Log frame		Output 4	Output Score	A
Risk:		Major	Impact weighting (%):	20%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator	December 2016 Milestone	Progress
Improved processes and capacity for fiscal strategy and risk management	Pilot Fiscal Strategy Statement produced by MOFED	Met: Pilot Fiscal Strategy Statement (including a fiscal risk statement and all required components) has been produced by MOFED, and was tabled in Parliament along with the budget in November 2016.
	MOFED is conducting in-year and ongoing monitoring of key fiscal performance indicators (including DLIs, IMF performance criteria)	Met: Fiscal risk template and tools created that track key indicators, which allowed an initial fiscal risk report to be prepared. Tools developed and being used by PIMU to enable the Budget Committee to link the macro model to fiscal ceilings. / Expanded detailed risk analysis is now routinely performed by MOFED. As a result of BCS support, a unit of EPRU has now taken on risk monitoring.
Improved processes and capacity for fiscal forecasting	Macro model updated to incorporate deflator (by sector), inflation and terms of trade	Met and exceeded: The Sierra Leone Integrated Macroeconomic Model (SLIMM) was comprehensively updated and presented to members of the macro-fiscal working group. These updates incorporated: stochastic estimates, new outputs including standard tables and analysis, terms of trade, a new inflation tool (as well as suggested new inflation equations), and deflator indicators by sector.

Key Points:

This output has focused on meeting requirements under the new PFM Act, improved in-year monitoring of selected variables, better modelling of macroeconomic variables, and preparation for the next IMF programme. Taken together, these advancements have enhanced the macroeconomic analysis that underpins the budget. This in turn improves the credibility of the budget process by helping GoSL to make better informed fiscal policy decisions, which allow more realistic plans for future expenditures and limit unnecessary fiscal interruptions to spending plans.

The production of Sierra Leone’s first Fiscal Strategy Statement (FSS) is part of a broader process of institutionalising the reforms required under the new PFM Act. This reform will see the FSS forming part of the budget calendar, and being an important tool for GoSL to analyse the resources it has at its disposal as a result of the economic policy options taken, and make informed policy decisions.

A fiscal risk template and analytical tools have been created alongside MOFED counterparts. These allow the EPRU to track and analyse exchange rates, inflation, revenue performance, debt and interest payments. These tools also include a monthly updated risk database, real effective exchange rate tool and realism analysis tools. These have been used by EPRU already; a first fiscal risk report has been prepared for reporting to senior managers. The risk report focuses on (1) updating the risk matrix during the year, flagging the key risks, likelihood and severity; and (2) tracking key indicators related to the risks (e.g. non-performing loans, revenue performance, etc.). In this way, the risk report will serve as an early warning system and help triage senior managers’ time in mitigating the most pressing risks. BCS’ on-the-job training has resulted in a unit of EPRU taking on risk monitoring as part of its ongoing workload.

Tools have also been developed for the Budget Committee to help link the macro model to fiscal ceilings, so that when setting ceilings they can take account of the expected macroeconomic situation and hence set realistic ceilings for spending. The models are being used to track revenue collection and hence monitor the 2017 DLI on revenue as well as IMF targets.

A crucial aspect of the programme’s work on updating the Macro Model (SLIMM) has been its ongoing interaction with the macro-fiscal working group of MOFED. This group has actively followed the reform processes, and has been sensitised in the nature of and rationale for changes to the model. The changes have allowed for the generation of more analysis which can feed into the budget process, thereby enhancing budget credibility. Training is being provided to different departments on the technical methods used in the changes to the model so they can become part of wider government work.

Finally, TA has been able to support MOFED in its interactions with the IMF. Briefings prepared on IMF negotiations and likely areas of concern for the next program, and a report on perceptions of performance, actual program performance, and topics of focus for next program.

Output Title	Better processes and increased capacity for revenue policy, coordination and collection
Output number per Log frame		5	Output Score	A
Risk:		Severe	Impact weighting (%):	10%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator	December 2016 Milestone	Progress
Better processes and increased capacity for revenue policy, coordination and collection	NRA's Ministries, Departments and Agencies (MDA) revenue data shared with and analysed by MOFED	Met: An Excel monitoring tool has been developed and shared with the Revenue and Tax Policy Department (RTPD) of MOFED, capturing historical National Revenue Authority (NRA) data. They have begun to use it.
	Total revenue data tracked at NRA and MOFED for progress towards DLI	Met: A second Excel monitoring tool has been developed, which shows all revenues across MDAs disaggregated by month. MOFED and NRA are using this to track performance for different revenue types, indicating whether collection is above or below target with comparisons to last year.

Key points:

This output has focussed on bridging the gap between RTPD and the NRA. The RTPD is responsible for designing revenue raising policies and the NRA is responsible for collecting revenue. It is vital that data and information are shared and monitored so that policies and forecast can reflect realities. To date, the NRA has been the custodian of revenue data in respect of MDAs. But this has never been shared with MOFED (for either policy monitoring or tracking purposes) – and even if it had been, it is not prepared in a format which is compatible with the government’s chart of accounts. Indeed, revenue data from across GoSL has never been an input into the policy and budget process, meaning that MDAs are not held accountable for their revenue performances, nor are revenue policies assessed and scrutinized by MOFED as part of budget policy-making.

The second issue is that at a strategic level within MOFED there is no tracking of revenue performance and, as a result, no input from any analysis into the budget and policy process. Taken together, these challenges pose significant threats to budget credibility.

The BCS team has tackled these issues via sensitive engagement in politics and relationship building as well as producing technical solutions. Three integrated tools have been developed:
- An Excel tool which consolidates historical data held by NRA;
- A more detailed tool disaggregating data at MDA level; and
- A tool developed in Tableau which identifies all revenue streams across MDAs, and records it in a format consistent with the Chart of Accounts.

These are discussed below.

In terms of revenue data sharing, the BCS team has now developed an Excel tool which has consolidated comprehensive historical data (2006- October 2016) from the NRA on domestic revenue, and been shared with RTPD. This has enabled monthly monitoring and enhanced revenue performance analysis, allowing comparison with previous years’ performance and seasonal variations. Progress relied on trusting relationships being established between TA and GoSL colleagues allowing the TA access to the data and to make the case for sharing of data.

A second, more detailed tracking tool has also been designed which shows detail at MDA level. This tool is integrated with the higher-level tool.

Significant work has also been undertaken to enhance revenue recording and reporting. A number of MDAs still retain revenue, and either do not report it or revenue is not properly captured. According to the new PFM Act, all MDA revenues collected on behalf of GoSL must be transferred to the Consolidated Revenue Fund. To this end, BCS has identified all revenue streams within each MDA, as provided for in the different legislation and regulations, and established a template for reporting it. This tool will help in enhancing MDA revenue administration, accountability and reporting.

The tools are also being used by MOFED and NRA in tracking progress against the revenue targets (the GoSL budget target, the IMF target and this programme’s DLI). From now on, the NRA will collate revenue information and RTPD will monitor the outturns and highlight key issues for the department's management. The result of these reforms is to ensure there is proper oversight and monitoring of revenue performance, and that revenue plays a proper role in the budget and policy-making process.

Recommendations:

The challenge now will be to ensure the sharing of data and cooperative working continues, throughout 2017 and beyond. The log-frame milestones for 2017 do not explicitly require this and should be amended to ensure that the cultural change is embedded.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers are:
Financial aid disbursements to the GoSL (£5m in 2016 out of a possible £10m)
- Milestone payments to service provider (TA)
- DFID management of the programme

Should all milestones be met, the total payments to the service provider will be over £750,000 less than the DFID business case budgeted. The programme’s monitoring and evaluation framework was deliberately designed to reduce administrative and transactional costs, thereby saving DFID staff time.

VfM performance compared to the original VfM proposition in the business case

The indicators are a mix of quantitative and qualitative measures.

Type of VfM	Indicator
Economy / (cost of inputs)	The cost of each milestone as set out in the contract / Ratio of expenses to programme delivery (TA) costs
Efficiency (inputs to outputs)	Programme is on track against implementation tracker / Outputs are assessed as high quality by DFID and GoSL / Inputs are flexibly allocated across different workstreams to ensure outputs are met in a high-paced, evolving environment
Effectiveness (outputs to outcomes & impact)	Progress against logframe outputs and outcomes / Leverage of complementary reforms

Economy:

Milestones have been achieved at agreed cost to date and the costs were based on benchmarked rates for fees and expenses. The service provider absorbed costs owing to local inflation via careful management of input costs. As a result, the cost and timing of the milestones set-out in the contract are retained.

Efficiency:

The programme is on track against its workplan. As of 15 December 2016, 81 activities were on track, 44 completed and 6 were experiencing delays. On-going monitoring ensures potential delays and programmatic obstacles are flagged in advance. A flexible team structure has limited the need for additional inputs and enhanced the efficient use of existing inputs; rather than focus solely on their own workstreams, team members’ varied skills are actively used to fill gaps in other workstreams.

Flexibility in the deployment of staff has also allowed the programme to efficiently respond to both DFID and MOFED’s emerging needs. An example of this was the rapid deployment of an additional procurement adviser during the inception phase. 15% of staff days are unallocated to enhance the speed and ease with which the project can respond. As well as deploying new advisers, the unallocated funds have also been used to increase the intensity of inputs from existing advisers during high-demand periods, such as during the finalisation of the annual budget process.

As a 100% milestone-based payments by results contract, the service provider must deliver high-quality outputs against an agreed milestone schedule in order to be paid. To evidence the quality of programme outputs and release payment, the project provides presentations to DFID, a summary quarterly report explaining the outputs and firm evidence that the milestone has been met. This includes, where relevant, confirmation from senior MOFED or NPPA officials that the support provided by BCS and the output produced represents the desired value-added. To date, feedback from counterparts has been exceptionally positive indicating that the BCS support is being efficiently delivered.

Effectiveness:

Effectiveness is difficult to assess at this stage. The one indicator in the business case that can be assessed now is “take up of TA advice by GoSL”. This has been good, as indicated by the level of satisfaction from MOFED expressed to DFID and by reforms GoSL have initiated following discussions with TA, such as wage bill reforms to bring SVAs onto the central payroll. DFID needs to take a view in mid-2017 on whether the programme design is effective in incentivising GoSL to reform. To this end DFID will specify what will signal effectiveness.

Assessment of whether the programme continues to represent value for money

Costs remain within the budget and outputs are on track, indicating the BCS programme continues to represent value for money. This needs continual assessment through 2017 with particular focus on whether the programme is effective in incentivising reform.

Quality of financial management

The total forecast for 2016 was £10m in financial aid, against four DLI’s (£2.5 million each).The GoSL met two DLIs and so £5m was paid. Payments followed agreed provision of proof that funds have been spent on health workers salaries in the form of the approved and processed payroll and the evidence of bank transfers to the accounts of the health workers. Another DFID programme has led on validation of the health payroll, with 446 “ghost” health workers permanently removed as a result. The quality of financial management by the TA provider has been good. They provide financial reports against their budget and spend every quarter. They have provided timely invoices with a breakdown of expenditure and a short narrative of activities. Rigorous checks are carried out to ensure that payments are only made where the partner has demonstrated satisfactory delivery of milestones which must be evidenced against criteria agreed.

Date of last narrative financial report	9th December 2016
Date of last audited annual statement	Due December 2017

E: RISK (½ page)

Overall risk rating: The risk after mitigating activities have been applied is assessed as severe, due to the threat posed by the external context.

Overview of programme risk

The programme risk register articulates a number of risks and mitigating actions across five types of risk: external context; fiduciary; delivery; operational; and reputational risk. Gross risk and net risk are tracked, where net risk is defined as the risk after mitigating actions have been applied. The diagram below plots the position of the net risk across the five categories. This shows that the threat from the context in which the programme is operating is considered to be the greatest overall risk even after mitigating actions have been applied.

The greatest[2] risks from each category are as follows, with corresponding mitigating actions:
[2] Greatest in this case refers to those with higher probability of happening and would cause at least a moderate level of impact if it occurred.
- External context risk: GoSL commitment to the reform process is mixed with strong vested interests working in the opposite direction to the reform agenda. This is considered to be a particular issue in procurement. This risk is considered to be severe due to known, entrenched weaknesses ad uneven buy-in to reforms.
  - To mitigate this risk, DFID and the service provider maintain regular dialogue at political and technical levels to understand the political environment and work in tandem with reformers. We plan to enhance dialogue across 2017 and bring the net risk down. This has been supported by a shift of resources at inception phase towards procurement.
  - Mitigation against the election risk is through careful planning of activities to avoid trying to push important reforms through at the end of 2017.
- Delivery risk: deterioration in fiduciary environment, including weakening of public financial management controls is one risk under this heading. Another is the risk stemming from some fractious relationships between different agencies across MOFED and the SVAs.
  - The programme is designed to build the core PFM systems and hence the work towards meeting the DLIs should reduce the fiduciary risk that the financial aid is exposed to. Furthermore, DFID and the TA discuss these issues at the donor PFM working group. Implementation of DFID Sierra Leone’s anti-corruption and counter-fraud strategy and annual statement of progress on fiduciary risks also serves to mitigate this risk.
  - To manage the relationships between some GoSL agencies the BCS team have worked to ensure clear lines of communication, and to support engagement and clarity on roles and responsibilities between senior-level officials.
- Fiduciary risk: DFID is invoiced for outputs that have not been delivered in full. And DFID disburses against receipts to show spending on health workers’ salaries.
  - Dialogue with beneficiaries in GoSL, a detailed implementation tracker and spot checks on documents. Regular reporting to DFID also helps.
  - DFID has funded an exercise to validate all health workers on the payroll and remove those who cannot be validated. DFID is supporting the drive to keep the payroll clean.
- Operational risk: short-term horizons lead to a focus of resources on short-term, low impact initiatives and detract from high-impact reforms.
  - The programme has designed the DLIs with sustainability in mind, in particular setting them mostly at the outcome level which leaves GoSL free to decide which method works best for them to achieve the targets. The TA team balance assistance on short term goals with longer term goals and this mitigation strategy is regularly reviewed.
- Reputational risk: corruption scandals or GoSL spending pattern choices.
  - DFID completes an assessment of the GoSL’s commitment to the UK Partnership Principles twice a year. DFID has recently increased the dialogue with GoSL around these issues in order to highlight the risks involved and work with them to mitigate them.

Outstanding actions from risk assessment

As the 2017 DLI wording is finalised, the work plan will be reviewed to identify any activities which face risks that have not been identified so far.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Two of the DLIs were not met in the expected timeframe and hence only half of the financial aid was disbursed, in line with the agreed plan. In terms of the contribution of the TA component, as of 15 December 2016, 81 workplan activities were on track, 44 completed and 6 were experiencing delays.

Performance of partnership(s)

Relationships between GoSL, DFID and the service provider are strong, demonstrated by productive communications between all parties and swift problem solving. All actors have gone to great lengths to involve other donors in design work and decision making, to ensure the programme complements other programmes. DFID coordinates and chairs a donor PFM working group meeting every two months which brings together all the relevant representatives from DFID, World Bank, IMF, EU, AFDB, US embassy and consultants working on PFM programmes funded by these institutions. This has allowed pertinent topics to be discussed and donor coordination enhanced. There is still room for enhanced dialogue between donors, given the large number of PFM projects ongoing in MOFED. Coordination needs to be through the PFM Reform Unit in MOFED and the TA team will need to continue to dedicate time to supporting it and managing relationships with other donors, which have at times become fractured.

Asset monitoring and control

Under the financial aid component there are no DFID assets to monitor as this is direct support to GoSL, earmarked to the health workers salaries. The TA component maintains an asset register, which contains assets transferred from another DFID supported programme (closed) and assets procured to help set up the office. Assets will be monitored through a routine field visits and asset spot checks. The partner provides an update on the status of all assets as part of their progress reporting requirements.

G: CONDITIONALITY (½ page)

Update on partnership principles

The financial aid arrangement is guided by a memorandum of understanding between DFID and the Government of Sierra Leone that requires the latter to demonstrate commitment to the UK’s partnership principles, in line with the UK’s conditionality policy. A comprehensive assessment is made twice a year, prior to any financial aid disbursements. The most recent update took place in December 2016. In summary, there continues to be evidence of commitment to each of the partnership principles, which are:

PP1 Poverty reduction and the MDGs
PP2 Respecting human rights and other international obligations
PP3 Strengthening financial management and accountability, and reducing the risk of funds being misused through weak administration or corruption
PP4 Strengthening domestic accountability

The DFID assessment is that commitment from GoSL is relatively uneven across and within departments. In the case of PP1 the credibility of this assessment is “high”, whereas for the others it is “medium”. The impact of the Ebola crisis and systemic governance failures demanded a step change in the GoSL’s approach to development - particularly in service delivery. This has led to the Presidential Recovery Plan led by GoSL with high levels of engagement from the President himself. The Recovery Plan is ambitious but credible, focussing on health, education, water, energy, governance, private sector and social protection. This contributes to the higher assessment for PP1. Successful implementation of the Recovery Plan, alongside execution of planned PFM reforms could also enhance the assessment made against PP3 and possibly PP4. These improvements are important in light of a lack of visible progress on PFM, corruption and accountability in recent years. DFID needs to see a positive trajectory.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

There have not been many changes in the context, and hence the assumptions made that guide the theory of change for this programme. Politics is more complex than originally envisaged in the procurement area and a staff change and new strategy has been required. Furthermore there has been some disagreement in MOFED over activities that should be pursued to improve procurement practices and hence the vision for improved procurement practices should be shared so that the programme can be sure it is aligned behind the Ministry’s plans.

Several assumptions have been made regarding outputs to be delivered by the World Bank Trust Fund working in MOFED on PFM issues (PFMICP). Progress of PFMICP has been slower than expected and outputs have been of considerably lower quality than expected. This poses threats for the successful completion of several BCS outputs. The programme will need to revisit milestones that rely on PFMICP outputs and redesign them, catering for the highly likely event that PFMICP does not deliver as planned.

Monitoring progress throughout the review period

DFID monitors the programme through monthly reports sent from the TA, quarterly assessments of payment milestones (including a presentation to DFID and letters from the relevant MOFED staff), regular meetings with the TA and ad hoc meetings with MOFED counterparts at technical and political levels to hear their assessment of the programme. Feedback from MOFED has been consistently positive.