Annual Review

Title: Policy Development Facility Phase II (PDF II)
Programme Value £ (full life): £18.5m		Review Date: 22/01/2020
Programme Code: 203922	Start Date: 23/10/2013	End Date: 31/03/2020

Summary of Programme Performance
Year	2014/15	2015/16	2016/17	2017/18	2018/19	2019/20
Programme Score	A / Pre-contracting	A / Inception phase	A / First full year of implementation	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203922/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203922/documents

A. Summary and Overview

Description of programme

The Policy Development Facility Phase II programme (PDF II) provides targeted assistance to help Nigerian reformers implement economic and social policies that lead to poverty reduction. PDF II is an £18.5m five-year programme that runs from 1 April 2015 to 31 March 2020. It is delivered through a programme management unit (PMU) managed by DAI. The programme provides technical assistance by:

- Backing key economic and public sector reformers in Nigeria with technical support; and
- Conducting research and studies that can be used to influence and shape Nigeria’s economic reform agenda, including explorative studies for potential complimentary DFID programming.

The Impact PDF II seeks is that the Nigerian Government implements policies that lead to poverty reduction. The Outcome is that Nigerian reformers make increased use of capacity and evidence to enable them to pursue vital economic and social reform. PDF II is comparable in most respects to the first PDF programme (£14m from September 2009 to April 2016) but has a more robust approach to knowledge management.

PDF II is fully aligned with DFID Nigeria’s current business plan. It has helped leverage better use of Nigeria’s resources for its national development with the aim of unlocking its growth potential. The programme’s approach reflects the rationale in the business plan that better governance and growth are inter-dependent. PDF II also aligns well with the HMG Africa Strategy as it seeks to address long-term issues that matter most for Africa’s prosperity.

The programme supports policy makers who can make an impact on inclusive growth including developing Nigeria’s trade partnerships. It has done this with research and technical support to the Office of the Vice President (OVP), the Ministry of Budget and Planning, the Senior Economic Advisers to the President, the Finance Minister and others. The programme has also supported climate change and natural resource management via technical advice to the Ministry of Environment and supported stability within Nigeria through support to addressing the humanitarian crisis in the North-East. Finally, PDF made a contribution towards the government’s approach to job creation through support to the Job Creation Unit (a recent programme study estimated PDF II to have supported over 20,000 persons across a selection of its projects with more expected as the projects continue to be implemented).
[note] This annual review incorporates findings from a draft independent impact assessment and two studies undertaken by the PMU (on VFM and on job creation activities).

Context for PDF II in the last 12 months:
The four main factors in the last 12 months affecting implementation of PDF II have been:

- Slow recovery in economic growth and weak job creation despite a growing population;
- Continuation of unorthodox economic policies and more vulnerable economic situation Government elections and time taken to appoint ministers;
- Reconfiguration of responsibilities for economic policy making; and
- .

During 2019, economic growth continued to recover slowly from the 2016 recession but too slowly to begin to create jobs on the scale needed for a growing, youthful population. Economic recovery was supported by oil prices that rallied from $40 barrel in early 2016 to average over $70 per barrel in 2018. However, economic growth remains lacklustre. Juxtaposed to population growth of 2.6%, growth on a per capita basis remains almost stagnant or negative with significant poverty implications. A World Bank report released in December highlighted the demographic challenges and the inadequacy of current growth for jobs and regional inequality. Between 2015 and 2018, the number of unemployed nearly quadrupled, and the unemployment rate reached 23 percent with most of the new jobs concentrated in Lagos and a handful of other wealthier states. Nearly five million people had joined the labour market in the most recent year. Nearly 30 million new jobs would be needed by 2030 just to keep the current unemployment rate constant.
[note] World Bank Nigeria Economic Update, Fall 2019

Against the worrying economic backdrop, the implementation of the government’s growth plan during the last year was slow and inadequate; unorthodox policies have been used to shore up trade/current accounts and to promote local production. This has increased the country’s vulnerability to economic shocks. The lack of an implementation plan that will deliver on the goals set out in the government’s 2017-20 Economic Recovery and Growth Plan may be partly evidenced in the dampened economic growth over the past three years. Distortive economic policies have been highlighted in successive International Monetary Fund (IMF) reviews of the economy. For instance, there have been border closures with neighbouring countries with a significant impact on trade in West Africa. The Central Bank of Nigeria (CBN) continues to intervene in the foreign exchange market to support the Naira. Other well-meaning yet counterproductive policies remain such as the restrictions on foreign exchange for 41 imported class of goods and recent ban on foreign exchange for textile and milk imports. A tier system for accessing foreign exchange remains, creating hurdles for businesses and rent seeking opportunities. Consequently, should crude oil supply disruptions reoccur, or there be a significant decline in crude oil prices, foreign exchange access may be back to levels observed in 2016 which had a detrimental impact on the economy. As well as the IMF highlighting increasing economic vulnerabilities, credit ratings agencies, Fitch and Moody’s, both lowered their outlooks for Nigeria in late 2019, citing worsening macroeconomic policies.

The election season also weighed on the government’s policy response as government machinery was distracted with politics. Elections meant that this year was going to involve the PDF II taking stock before and picking up again post elections; but critically for PDF II, following elections the President was slow to appoint a cabinet which has stalled policy development. PDF II slowed down before the elections in order to gauge the level of commitment of a new government to economic reforms supported by the programme. There was a hiatus before a number of key economic positions were filled. Nevertheless, some ministers, returning from the previous administration have retained their portfolios. For instance, the Finance minister continues to hold responsibility for the Strategic Revenue Growth Initiative which was developed during the last administration.

Beginning in September, responsibilities for economic policy formulation have started to be reconfigured and the new arrangements are yet to bed down, however. There has been a loss in momentum in economic policy direction during the last year as there is uncertainty on how economic policy will be designed, implemented and evaluated. The Economic Management Team supported by PDF II (largely responsible for overseeing other areas of economic policy other than monetary policy) has been disbanded by the President and the new arrangements have taken time to firm up. The President’s office will now handle general economic oversight supported by a new Economic Advisory Council, composed of a group of distinguished Nigerian economists. The Vice-President will no longer drive economic reforms at the federal level as the Economic Management Team. The VP will still chair the National Executive Council and play an important role in advising the President on measures necessary for the coordination of the economic planning efforts across all levels of government (Federal, State and Local). Ultimately, it will take some time to see how policy will be developed at senior levels of government.

Implementing Partner’s performance

The DAI-managed PMU has provided targeted assistance where it would be effective based on sound understanding of the political economy. In the year under review, the PMU undertook political economy analyses to gauge where advisers and analyses were likely to be effective. DAI has continued to identify embedded advisers recruited by the PMU who are well qualified and provide highly specialised technical advice depending on the requested area of support by the beneficiary. Over the life to the programme, it has responded to specialised needs over a broad spectrum; programme management and financial advisory services on climate financing, legal and project management services on electricity projects, business environment reforms, infrastructure and supporting humanitarian efforts in the North-East of Nigeria. The team has managed to identify and retain consultants in most cases despite needing to use shorter contracts to manage programme uncertainties over the last year.
[note] PDF provided an embedded adviser to support humanitarian efforts targeted at internally displaced persons as a result of the North East humanitarian crisis earlier in the programme so not highlighted in this annual review. The EA’s work was related to the first set of priority challenges earlier identified through consultations with NGOs and affected persons in the region.

The PMU has done well to be responsive to requests initiated by DFID Nigeria, but this has sometimes meant lower quality first drafts of outputs where there wasn’t expertise in the PMU. Given the programme design, DFID staff play a more significant role in quality-assuring outputs where these are in specialist areas not initially specified in the programme. A lesson to consider for future programmes is that the PMU be could be configured with more either additional knowledge management resource and/or enhanced backstopping support to provide technical inputs to a broader range of technical areas that can arise under a programme of this type.

DFID Nigeria

The expansion of programme to include infrastructure projects stretched DFID Nigeria advisory and programme management staff. The approach for 2019 was to reduce the level of activity in early 2019 and then pick up pace once more when the new government signalled its interest in PDF support to implement its plans. The design of the programme places significant demand on DFID staff. DFID advisory staff provide technical inputs on a large number of individual outputs, including on ToRs and quality assurance of studies. A high workload was anticipated but was made more challenging by the delay in government appointments. There was a significant number of requests for new embedded advisers requiring discussions with beneficiaries and inputs to terms of references. Within DFID Nigeria, there was a turnover of advisory staff in the latter part of the year. The approach to implementation was also felt by programme staff who needed to do more monitoring, ensuring compliance with ToRs and tracking finances.

PDF II implementation has been adjusted in 2018 and 2019 to support enable continuity in DFID’s support to infrastructure. Starting in 2017, a significant share of PDF II resources was allocated to infrastructure-focused activities previously supported by another DFID programme, Nigeria Infrastructure Advisory Facility phase 2 (NIAF 2). By making space for infrastructure support, PDF II ensured key reforms in the power sector continued, and that past gains were maintained. The successor programme, UK-NIAF, is now in place.

Plans for continuing PDF activities are in place but will require careful management to ensure continuity. DFID Nigeria is appraising a successor programme to PDF II and this will come on stream if a new business case is developed in the first half of 2020 and when delivery routes are identified and go live. An interim arrangement will provide a bridge between PDF II and any successor programme – a 15-month component called Champions of Change under DFID’s Partnership to Engage Reform and Learn programme (PERL). The transitional arrangements – along with the support to infrastructure – have added to the complexity of making best use of PDF II resources before programme closure in March 2020.

The UK Government’s ability to be responsive and provide support to increase the likelihood and quality economic reform uptake through PDF II has continued to constitute a valuable offer to Nigeria. PDF continues to be a highly visible programme which gives the UK government the opportunity to influence evidence-based policy making by the Nigerian government. The work that PDF has done in building an evidence base on policy has been complemented by UK Government influencing through DFID and the wider British High Commission.

Summary supporting narrative for the overall score in this review

PDF II is scored an ‘A’ this year with both outputs – support from embedded advisers and research/studies – meeting expectations. The programme has also made progress towards its outcome objective of increasing the capacity of reformers to pursue economic and social reforms. A summary of output scoring is as follows:

Output 1 (60%): Relevant and high-quality organisational support delivered to beneficiaries – Score A
- 58 projects (target 59 by March 2020) assessed as satisfactory. Embedded advisers have included the Special Adviser to the President on the Ease of Doing Business (see Box below), technical advice to the Chief Trade Negotiator and the Managing Director of the Rural Electrification Agency; and the Green Bonds Adviser.
- Beneficiary feedback has been satisfactory with projects scoring on average 94% on relevance and 90% on quality, well above the log frame thresholds (90% and 80% respectively). Several projects drove major reforms on behalf of their principals, despite the challenging context they are working in.

Output 2 (40%): Relevant, high-quality policy research, studies and consultation products – Score A
- 42 projects (against a target of 44 by March 2020) have been assessed as satisfactory at implementation/completion stage, with a number of projects under this output exceeding expectations. This included support leading to the adoption of a simplified export procedure that addressed a major obstacle to doing business.
- Beneficiary feedback has been positive with projects scoring on average 93% on Relevance and 86% on quality (against targets of 90% and 80%).

The intended outcome of PDF 2 is that Nigeria’s reformers or champions of change use increased capacity and evidence to enable them to pursue vital economic and social reform. The programme has contributed to significant change in the areas of business environment reform, trade policy and green bonds as well as in infrastructure as PDF II took up the slack in the gap between NIAF programmes.

However, the effect of the context in which the programme operated in 2019 has been a lower number of transformational wins that PDF can support than could have been the case. Under PDF I, the administration pursued a smaller number of large, potentially high impact reforms projects such as the setup of the Nigerian Sovereign Investment Authority (NSIA) and YouWiN! Under PDF II, while the context has become even more challenging, there have been some significant policy developments supported by the project. .. During the last year, delays in cabinet appointments and a lack of clarity in economic policy direction means requests to DFID under PDF II have been for assistance on a higher number of smaller sized projects.

Programmatically, the major part of this year has focused on opportunities for consolidating support in areas of success and areas that are not highly political where PDF II support could increase impact. Despite challenges in its operating context the independent review commissioned by DFIDN and this programme review, demonstrates that PDF II support has made an impact and continues to be valued by beneficiaries. There are some instances of transformational impacts materialising over the last year, especially Nigeria’s signing of the African Continental Free Trade Agreement, progress on the World Bank’s Ease of Doing Business rankings, and follow-on issuances of green bonds.

The theory of change in the business case is still valid – careful vetting of requests to support reform with advice and studies can influence policy outcomes positively. However, risks to this ToC anticipated at the business case stage heightened during the year. An assumption was that “The new Federal Government of Nigeria appoints Cabinet, settles in and works efficiently (Policy direction setting, policy formulation and implementation) in a timely way”. This risk materialised but actions such as updating political economy analyses to gauge where support could still be effective, contributed to continued progress during 2019. These included support to business environment reforms, signing of the African Continental Free Trade Area (AfCFTA), better audits by the Office of the Auditor General for the Federation (OAuGF) and further progress on the issuance of a sequel green bond. Box 1 below summarises how PDF II puts its ToC into practice to achieve change, using the example of support to business environment reforms. (Other examples are in Section C, Progress Towards Outcomes.)

Box 1: Supporting Business Environment Reforms / PDF II provided two advisers to this work stream – one of which is a Senior Special Assistant to the President on Industry Trade and Investment, who heads the Presidential Enabling Business Environment Council (PEBEC) Secretariat. Drawing on the extra-Ministerial authority of the Office of the Vice President, the Senior Special Assistant provided advice and coordination across key agencies on trade and investment interventions to make doing business easier and more attractive in Nigeria. The Senior Special Assistant was a focal point for government ministries, departments, and agencies, and helped to build understanding and synergies so they could support and implement the required reforms. / This embedded adviser also became an active participant in several important bodies that oversee and influence Nigeria’s business climate: The Economic Management Team, the Nigerian Office of Trade Negotiation, the Trade Policy Advisory Council, the National Economic Council, and the Federal Executive Council – the highest economic policy platform in Nigeria. The adviser also facilitated closer links between the VP and PDF II so that the aims and objectives of both OVP and PDF were more closely aligned. PDF II also provided support through a Technical Assistant to help organise advocacy meetings with key stakeholder groups and prepare documentation. This adviser also undertook data analysis and literature reviews to help develop an evidence base to guide the reform process. The evidence was packaged into strategic information products, including progress reports, policy reviews and impact assessments. / PDF’s support in conjunction with other DFID Nigeria and HMG Prosperity Fund programmes including in partnership with the World Bank, helped Nigeria move up 15 places to the 131st position in the 2020 World Bank’s ‘Ease of Doing Business’ index. The country was also recognised – for the second time in three years on the 2020 Index – as one of the 10 most reformed economies in the world.

Feedback and an independent evaluation conducted last year suggest that the programme has provided beneficiaries with the capability to deliver impact. Feedback from beneficiaries collected by the programme records that the support provided by PDF to beneficiaries is appreciated and has provided beneficiaries with capability to deliver impact during their terms in office. Beneficiaries on average scored PDF II support 94% on relevance and 88% on quality. This is corroborated in interviews under this annual review with beneficiaries including in OVP, OAuGF and NIPC. The independent review concluded the following:

“PDF has been a highly visible programme which has given HMG [Her Majesty’s Government] the opportunity to influence evidence-based policy making by the Nigerian government. It has enabled DFID to leverage their competitive advantage as a donor of choice in Nigeria. This observation was made by a large number of respondents during the interviews for this review. The support through PDF II was considered to be effective. There was significant praise for how the support was instrumental in achieving important outcomes, in many instances, in a relatively short period.

“… The counterfactual of PDF support is difficult to establish, however beneficiary feedback indicates that majority of initiatives would not have been as effective, or gone further in implementation, without the PDF support.”

This annual review judges that PDF continues to represent VFM based on the proposition in the business case. Requests from government are screened to support policy formulation including assessments of the political economy and whether better outcomes could be achieved a different way. Robust systems are then used to identify and retain quality consultants, to negotiate fee rates (including use of a cap to ensure this major driver of costs is sourced economically) and compare fee rates with comparator programmes (as envisaged in the business case). The deliberate focus in the Trade Policy workstream to work with micro, small and medium-scale enterprises within which women and the poor are represented is an example of how all activities are required to consider equity considerations. The independent VFM review of PDF II during the last year found the PMU had an appropriate way of reporting success stories across the portfolio of small-scale projects where the impacts are often indirect (demonstrating effectiveness). The review monetised the benefits of results linked to PDF concluding that it is highly likely that PDF projects represent value for money for the investment.

Programme management systems in DFID and in DAI have underpinned good commercial and financial performance even though monthly spend variances have been high in recent months. The PMU has remained compliant with the contract amended in October 2018. Financial performance measured by timely submission of invoices and variation between forecast and actual spend was generally satisfactory taking the year as a whole, though with monthly significant variations especially in recent months due to slower than anticipated pick-up in programme activities following elections.

The programme retains its ‘medium’ risk rating due to the mitigating actions taken to handle uncertainty around elections, although exiting the programme presents delivery and reputational risks that will need to be managed closely. The programme anticipated the contextual risk that time would be needed to gauge the appetite for a new government to draw on PDF resources to support implementing its economic plans. While the delay in appointments was longer than anticipated, political economy analyses helped the PMU identify areas where PDF II was engaged and where progress would likely be sustained. In advance of closure on March 2020, PDF II faces delivery risks; decisions need to be taken with beneficiaries on whether to continue embedded advisers beyond March 2020 by transferring to the bridge programme, Champions of Change.

Recommendations for the year ahead

Identifying activities to support in last three months
- PDF has done well to consolidate on opportunities which were identified from its political economy analyses. Its support to the current administration on business environment reforms, climate financing and rural electrification has yielded significant fruit. The same politically-aware approach should continue to identify where activities can have the greatest chance of catalysing reforms in the remainder of the programme.
- Fiscal pressures are increasing and there is limited fiscal space for necessary human capital or physical capital investments. PDF II interventions such as support to the Efficiency Unit in the Ministry of Finance, Budget and National Planning, were highly relevant. With the limited amount of time and resources left, PDF should explore opportunities to influence the debate on other fiscal issues, especially domestic resource mobilisation.
- Nigeria is developing medium and long-term economic growth plans during the first half of 2020. Building on discussions with the OVP and Ministry of Finance, DFID should explore studies to support higher investment and competitiveness needed for long term growth in Nigeria.
- The programme has done well to provide support on environment related issues via the support to the green bonds programme and other areas of technical assistance to the Ministry of Environment in the past. As the programme winds down, it should support development of other DFID work to identify other avenues available to bring climate change to the forefront of policy discussions in Nigeria.

Follow-on to PDF II
- PDF II concludes in March 2020. DFID should manage expectations of beneficiaries on the scope for continuing existing support and starting new programmes through the bridge facility that will follow.
- A substantive successor programme to PDF II (beyond the bridge programme) should consider whether to revise the Theory of Change and implementation approach. The Project Completion Review for PDF II should consider aspects of its design including:
  - DFID advisory and programme staff time required in PDF II on designing ToRs and on quality assurance of some outputs and whether this can be limited to strategy and oversight;
  - Balance between responsive TA to meet requests from reformers with specific advisers/studies where opportunities open, and more substantial institutional strengthening;
  - Alternative or complementary delivery channels e.g. targeted TA and research through IFIs that supports Nigeria to unlock IFI grant and loans in support of transformational reforms.

Acronyms

AfCFTA	African Continental Free Trade Area
CBN	Central Bank of Nigeria
CoP	Non-Oil Export Community of Practice
CTN	Chief Trade Negotiator
DAI	DAI Global, LLC (implementing contractor for PDF II)
DFID	Department for International Development
EA	Embedded advisers (PDF-funded consultants supporting government)
EBES	Enabling Business Environment Secretariat (assists MDAs to implement the reform agenda of PEBEC)
FEC	Federal Executive Council
FGN	Federal Government of Nigeria
HMG	Her Majesty’s Government
IMF	International Monetary Fund
MDAs	Ministries, departments and agencies
NEPC	Nigerian Export Promotion Council
NEXIM	Nigerian Export-Import Bank
NIAF	Nigeria Infrastructure Advisory Facility. There have been three DFID NIAF projects: ‘NIAF 1’ and ‘NIAF 2’, and the recently started UK-NIAF
NIPC	Nigerian Investment Promotion Commission
NOTN	Nigerian Office for Trade Negotiations
NXP	A statutory document to be completed by exporters
OAuGF	Office of the Auditor General for the Federation
OVP	Office of the Vice President
PDF	Policy Development Facility
PEA	Political economy analysis
PEBEC	Presidential Enabling Business Environment Council
PEA	Political economy analysis
PERL	Partnership to Engage Reform and Learn – a DFID governance programme
PMU	PDF II’s Programme Management Unit
PAC	Public Accounts Committee
ToC	Theory of change
ToRs	Terms of reference
VFM	Value for money
WTO	World Trade Organisation

## B: DETAILED OUTPUT SCORING

Output Title	Relevant and high-quality PDF II organisational support delivered to beneficiaries
Output number per LF		1	Output Score	A
Impact weighting (%):		60%	Impact weighting % revised since last AR?	N
Risk Rating		Moderate	Risk Revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of projects assessed as executed satisfactorily (as planned) or better during implementation	59	On Track: As of the time of this review, PDF II had 58 projects assessed as satisfactory at implementation/Completion stage. A number of projects have helped drive major reforms on behalf of their beneficiaries.
Beneficiary, user perceptions of relevance and quality of PDF II funded organisational support	Relevance: 90% / Quality: 80%	Achieved: Beneficiary feedback has been satisfactory with projects scoring on average 94% on relevance and 90% on quality, well above the log frame thresholds.
Number of instances where beneficiaries/EAs say that PDF II-supported data and analysis has directly influenced any of the 5 stages of policy formulation	MDAs, NASS, CSOs: 10	Achieved (in 2017): 57 in the year under review.
[note] There are no log frame milestones for 2019, as the programme will end in less than 4 months, therefore this assessment is against the 2020 milestones. In addition, the programme’s log frame was revised so that rather than each individual embedded adviser counting as a “project”, embedded advisers would be grouped according to thematic areas/clusters. This did not impact the scoring methodology of the project, however.
[note] In the year under review, 2 projects under Output 1 (One in the OVP and the Ministry of Works Power and Housing) were assessed as unsatisfactory during implementation. Though they technically met the beneficiaries’ approval, they were assessed by PDF II as not having met the desired objectives/standards, and so have not been included in Indicator 1.1.

Provide supporting narrative for the score

Under this output, technical assistance is provided to beneficiaries to support development and implementation of economic and social policies. Most of the projects are in the form of embedded advisers – specialist advisers who support the work of ministries, departments and agencies (MDAs), often with excellent access to ministers and to decision-making bodies. Output 1 scores an ‘A’. Four out of a target of five projects have been assessed as satisfactory and beneficiary feedback has been strong.

At the time of this review, PDF II has a total of 71 projects. Of these, 8 are ongoing projects, and 63 have been completed/closed (including 10 projects inherited from PDF I which were completed and archived during the Inception Phase of PDF II). This translates into 121 Embedded Advisers each with contracts ranging from three months to a year. A list of institutions and policy areas supported is in Table 1 at the end of this section. The changes in the configuration of the economic team has contributed to a delay in identifying where the new government would request support.

The PMU collects feedback from beneficiaries and scores the ‘Number of instances where PDF has supported data and analysis which has directly influenced any of the five stages of policy formulation’. This is one source of evidence on whether PDF’s approach remains important in influencing policy. The feedback scores have been exceeded targets which is a good indicator that the advice provided is appropriate and good quality. The annual review involved meetings to garner feedback from several key beneficiaries including in the OVP, OAuGF, the Rural Electrification Agency and NIPC which confirmed the value of the inputs from advisers, for instance in activities like preparing policy briefs, building capacity of senior staff and performing specialist tasks. An independent impact assessment confirmed this conclusion (see Progress Against Outcome section, Section C below).

PDF’s political economy analysis was updated early in 2019 to inform programming decisions in light of elections up until the end of the programme. PEA revealed that some areas of work are likely to be more immune to electoral politics. Also given the relatively short period between the federal elections and programme closure, the PEA led to a focus on consolidating wins made over the life of the programme to date. The PMU reviewed its support to the Nigerian government in conjunction with the DFID team, assessed likely areas where support could make an impact and focused on them. The remainder of this section details progress in seven policy areas.

Business Environment reforms continue to make impact: Given the high-profile nature of the work done in this area, the global implications on Nigeria’s rankings and more importantly the signalling to the business community, PDF continued to support PEBEC with two embedded advisers with the results outlined in Box 1. During this year, the advisers worked on the third iteration of 60-day National Action Plans to deepen business environment reforms on domestic and international trade, migration, electricity, starting a business, paying taxes and more.

Rural Electrification Agency (REA): Commissioning of Projects under the Energising Economies Initiative: The Nigerian government is advancing its policy on accelerating access to power, by electrifying economic clusters through its Energising Economies Initiative being implemented by the REA. The Energising Economies Initiative is private sector driven, but the agency – with the support of PDF embedded advisers – provides project management, legal, regulatory and transactional support for pilot projects. These projects include the 1.45MW Sura shopping complex Independent Power Project which will provide power to 1047 shops of which 620 are currently in use. Since the project kicked-off over 700 generators have been decommissioned thereby reducing the harmful greenhouse emissions and noise pollution.

In the on-grid power sector, the National Control Centre for Transmission Commission of Nigeria required technical support to develop the power market: An embedded adviser developed models for on-grid the National Control Centre to enable grid operators accurately model the incremental impact of newly built substation and transmission lines on the national grid. This measure improves grid management, reducing incidences of system collapse and improving voltage quality. Other infrastructure projects which have been completed are the Oriade/Ilashe community and Nnamdi Azikiwe Mausoleum and Library. These projects are considered strategic because these communities which never had power supply previously but are now connected either through on–grid or off-grid initiatives.

Signing the Africa Continental Free Trade Agreement (AfCFTA). The AfCFTA was signed by Nigeria in July 2019 with support of the adviser embedded in the Nigerian Office for Trade Negotiation (NOTN). In addition, engagements of PDF II’s Trade Policy work stream supported the signing of the AfCFTA. The Trade Policy work stream (described fully under Output 2 below) engaged with trade and investment stakeholders such as the Manufacturers Association of Nigeria and other Government stakeholders enlightening them on the importance of signing and implementation of the AfCFTA for Nigeria. Some of these stakeholders such as the Manufacturers Association of Nigeria formed a part of the Presidential Committee on Impact and Readiness Assessment of the AfCFTA, which recommended the signing of the AfCFTA. The agreement was signed in July 2019 after these engagements. The embedded adviser in NOTN was also instrumental in implementing key aspects of AfCFTA and World Trade Organisation (WTO) agreements; these included setting up a Nigerian trade remedy mechanism for anti-dumping and safeguards under the AfCFTA and WTO Agreements.

Follow-on issue of green bonds: PDF supported the successful pilot issue of a N10.69bn green bond in December 2017. A PDF embedded adviser has provided further technical support in the development of a coordinating framework to guide key agencies such as the Debt Management Office, Office of the Accountant General of the Federation (OAuGF) and Ministry of Environment for effective monitoring of the use of proceeds of the funds via a green bond account. The proceeds of the pilot bond have been invested in the Renewable Energy Micro-Utility and Energizing Education Program. The bond finances 15% of the total cost of these projects and implementation of the projects has commenced as the contractors have been mobilized to site. PDF also supported a follow-on bond issue. The target date of end-2018 could not be met but the issuance was finally achieved for N15n in June 2019.

Reforms and technology innovations at the Public Accounts Committee (PAC) of the National Assembly: PDF has supported the drive to review and present PAC Reports from 2010 to 2014, for the first time in ten years; and the 2010 audit report has been considered and adopted by the House of Reps. These represent significant milestones at the Assembly as the outcomes of the reports feed into investigation by the Economic and Financial Crimes Commission, the Nigerian Police and Independent Corrupt Practices Commission for prosecution of offenders. EAs supported the production of PAC Newsletter, the printing of End of Assembly Report and the 2011 – 2014 PAC Reports. An EA also supported the House of Representatives Public Accounts Committee (PAC) speed up the review of audited reports once transmitted from the OAuGF to MDAs by moving from a manual system of operation to a fully digitised facility. The EA also helped attract additional support (21 computers) to the PAC of the House of Assembly, helping complete the digital facility by raising the number of computers from 4 to 25 and attracting hands-on training for staff and Committee members.
[note] For full story, please see link to PDF II Result Product on the website https://www.pdfnigeria.org/pac/.

Introducing technology to improve government procurement processes: A new accountability and transparency platform named 'Price Checker' has been introduced with support of the PDF’s embedded advisory support to the Ministry of Finance. Price Checker is a web-based platform designed, developed and installed to aid the procurement process, for use by MDA officers engaged in budgeting, procurement, internal audit, etc. It enables vendors of non-customised goods to upload their product details – prices, models, features and other specifications on the platform for use by staff of MDAs for their various tasks as mentioned above, including carrying out market surveys, price analysis, etc. The website was created by Galaxy Backbone and the platform formally handed over to the Bureau for Public Procurement for implementation.

Lessons identified this year, and recommendations for the year ahead linked to this output

- DFID Nigeria is setting up a bridge programme to ensure a that there is some support to reform champions of within the Nigerian government beyond March 2020. The bridge programme will begin in January, Priorities to smooth the transition include:
  - Provide all relevant information to the implementing agency for the bridge programme to effectively support decisions on which high-level embedded advisers should be on-boarded;
  - Manage expectations on beneficiaries, explaining the process for deciding which EAs will continue under the bridge programme.
- With the limited amount of time and resources left, PDF should explore opportunities to influence the debate on other fiscal issues, especially domestic resource mobilisation.

Table 1: Overview of areas of technical assistance by MDA during 2019
Federal Ministry, Department & Agency	Areas of Technical Assistance	Number of EAs
State House (Office of the Vice President – OVP & Chief of Staff – CoS)	Economic Advisory Council	7
	Economic Advisory Board	11
	Economic Matters	1
	Job Creation & Youth Employment	1
	Policy and Delivery Unit
	Internally Displaced Persons (IDPs)	1
	Communication, Digital & New Media
	Advisory Power Team Cross-sectional Support
	Nigeria Asset Decision Support System (NADSS)
	Rural Electrification Agency & Power Sector Recovery Plan	1
	Energising Education & Regulation Programme Implementation Support	1
	Industry Trade & Investment (EBES)	2
Ministry of Industry, Trade and Investment (MITI)	Special Advisers on Investment & Strategic Communications	1
	Direct Investor Summit 2018 & Sector Summaries	1
Ministry of Foreign Affairs (MFA)	Senior Adviser on Trade & Investment issues
	Technical Assistance on Economic Diplomacy Initiative
Ministry of Finance (MoF)	Chief of Staff, Support to Efficiency Unit, Economic Reforms	1
	Technical Assistance on Improving Tax Compliance in Nigeria	1
	Special Assistant on Key MSMEs financing Initiatives	1
	PPP Unit Coordinator & Project Adviser
Ministry of Planning & Budget (MBP)	Monitoring & Evaluation, Media, Policy & Planning Advisers	1
	Humanitarian Coordination Group
Ministry of Health (MoH)	Universal Health Coverage Agenda: One PHC Per Ward & Rapid Results Initiative
Ministry of Environment (MoE)	Special Adviser & Support to the Implementation of the UNEP report on Ogoni Clean up
	Communications Adviser
	Climate Finance Advisor (Green Bonds)	1
Ministry of Agriculture & Rural Development (FMARD)	Project Management Advisor	1
	Studies on Addressing Agricultural Finance Constraints, Assessing Capacity needs at FMARD, & Youth Unemployment in Agriculture
	Support to Transforming Nigeria’s Livestock Industry
Ministry of Solid Minerals (MSM)	Delivery Unit /Technical Adviser
Nigeria Extractive Industries Transparency Initiative (NEITI)	Policy, Planning & Strategy	6
Nigeria Sovereign Investment Authority (NSIA)	Technical, Communications, & Health Investment Advisor	1
	Technical Assistance & Investment Decision support for the Nigeria Infrastructure fund
Office of the Auditor General for the Federation (OAuGF)	National Audit Office Partnership
	Technical Advisor & Project Management of the OAuGF Reform Initiatives	2
Central Bank of Nigeria (CBN)	Technical Support on Energy (Power) matters	1
Federal Ministry of Power, Works, and Housing (MoPWH)	Chief of Staff & Project Management Unit Support
	Policy, Roads, Urban Development & Housing, Energising Education, & Emergency Generation
	Performance Monitoring & Communications
Nigeria Office for Trade Negotiations (NOTN)	Technical Assistance	1
	Training on Trade Policy
National Assembly (NASS)	Technical Support to the Chairman, House of Representatives Public Accounts Committee (PAC)	1

Output Title	Relevant and high-quality PDF II policy research, explorative studies and consultation products delivered to beneficiaries
Output number per LF		2	Output Score	A
Impact weighting (%):		40%	Impact weighting % revised since last AR?	No
Risk Rating		Moderate	Risk Revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Number of projects assessed as executed satisfactorily (as planned) or better during implementation	44	On Track: As of the time of this review, 37 projects assessed as satisfactory at implementation/Completion stage (none unsatisfactory. Work such as that leading to the automation of the exporters’ proceeds form will lead to very significant benefits.
Beneficiary, user perceptions of relevance and quality of PDF II-supported policy studies and events	Relevance: 90% / Quality: 80%	Achieved: Beneficiary feedback has been positive with projects scoring on average 93% on Relevance and 86% on quality, above the log frame thresholds.
Number of instances where beneficiaries/EAs say that PDF II-supported data and analysis has directly influenced any of the 5 stages of policy formulation	MDAs, NASS, CSOs: 7	Achieved: 25
[note] There are no log frame milestones for 2019, but at the programme will end in less than 4 months, this assessment is against the March 2020 milestones. The weighting for Output 2 has been kept at 40% as this still reflects its importance for the programme as whole even though it overstates the relative level of effort between outputs 1 and 2 in the year covered by this annual review.

Provide supporting narrative for the score

Under this output, PDF delivers tailored studies and reports for beneficiaries and disseminates their findings. This output also includes work streams such as on Trade Policy that are like sub-projects – events and reports that engage a range of stakeholders likely to achieve specific economic reform outcomes. Output 2 is scored an ‘A’. Four studies were completed satisfactorily during the year under review and the target of six high quality studies before March 2020 is on track. The successful workstream on non-oil trade, however, is not adequately reflected in the logframe and merits.

Since the inception of the programme, PDF II has taken on a total of 101 projects under Output 2. Of these, 5 are in pipeline, 87 are closed (completed) projects, and 9 are ongoing. During the last year, due to financial constraints, DFID Nigeria decided not to start any further studies in order to preserve budget for embedded advisers. Only a limited number of projects were commissioned along with an allocation for the Trade Workstream and for knowledge management activities. Following a review of key economic priorities under the new administration and discussions with potential beneficiaries, PDF has identified a small number of studies to undertake in the last few months of the programme.

The main activities under Output 2 this year have been: 1) two activities under the Trade Policy work stream (simplifying a bureaucratic process for exporters and taking forward the Non-Oil Exporters Community of Practice); and 2) a study to further scope the potential for a diaspora fund in Nigeria.

The Trade Policy Workstream began in November 2016 with the objective of opening up the Nigerian policy discourse to underserved small and medium exporters and potentially other new voices so that new evidence can be introduced to support exports. This PDF II initiative strengthens alternative (or under-represented) voices so that they can feed into the long-term policy process. The outcome objective was that stronger, more influential and sustainable exporters and their representative groups emerge and participate more in dialogue on trade policy.

Specifically, PDF provides evidence for these target groups to engage in policy discourse, convene the groups and support their dialogue with policy makers (such as the Enabling Business Environment Secretariat (EBES), Nigeria Export Promotion Council (NEPC), the Federal Ministry of Trade and Investment, NOTN) through events. Major successes that have been achieved during the last year with activities in previous years as well as 2019/20 have been: A) supporting exporter stakeholders to engage in dialogue through the Non-oil Export Community of Practice; and B) the automation of an export processing form.

A) Non-oil Export Community of Practice: PDF II supported development of the Non-Oil Export Community of Practice (CoP) to coordinate advocacy and capacity strengthening activities in three major areas of impact: access to finance, access to markets, and trade policy. To build influence, relationships were established with various stakeholders including EBES, Nigerian Economic Summit Group, NOTN, the South East Chamber of Commerce, the Organisation of Women in International Trade, the National Assembly Business Environment Roundtable, Nigerian Export-Import Bank (NEXIM), NEPC etc.

PDF II also established the Exporter Dialogue (ED) Series as a platform for enabling underrepresented export-oriented voices to engage with and influence Nigeria’s Trade policy. At the first Exporter Dialogue event, the NXP form was identified as a major challenge for non-oil exporters (see below). This issue together with the evidence from an earlier PDF Study (called the Exporter Experience Study) were fed back to PEBEC and followed up. Since then there have been several dialogues designed to address Nigeria’s trade policies and business environment. The issues distilled from the dialogues centred a on poor knowledge of international trade protocols and agreements (such as the AfCFTA), and the need for formalisation of trade across land borders to ECOWAS markets. The exporter dialogues have gained so much prominence that the Corporate Affairs Commission was also present at a dialogue to provide on the spot registration of businesses. Also, beneficiaries have confirmed that the Nigerian government has at different times used the dialogue to disseminate information directly to the exporters and receive feedback, and that PDF’s capacity building efforts has helped identify gaps they had in their services to exporters and continues to feed into the National Action Plans of EBES.

The Community of Practise has grown in prominence to the extent that it has been invited to critique policy documents: to review regulations of the National Agency for Food and Drug Administration and Control; to serve as the voice of exporters on the NEPC Board; NEXIM has invited CoP to attend the Bankers Committee meeting representing the private sector; and the National Assembly Business Environment Roundtable has invited the CoP to review bills currently working their way through the legislature. To guarantee sustainability beyond PDF II, efforts are now underway to formalize the CoP and create a non-profit organisation, to be called the Coalition of Non-Oil Exporters.

Supporting the automation of export processes: On June 6 2017, the Central Bank of Nigeria (CBN) sent out a notice and external memo enforcing the requirement that all shipments from Nigeria had to be accompanied by an NXP form – a statutory document to be completed by all exporters that specifies the foreign exchange earnings from exporting. This was an existing provision of Nigeria’s foreign exchange manual but the requirement was not enforced. All bills of lading were required to have the number of the form NXP endorsed on it.

The Trade Policy work stream had already been engaging with non-oil exporters to understand the real challenges that they face in the sector particularly regarding export of their products. An initial study titled ‘Exporters Experience’ was also commissioned a few months ahead of the CBN notice. Discussions with Exporters via PDF’s Trade Policy work stream revealed that enforcing use of the NXP form was a major obstacle to exporting; involving completing six copies of the form, going in person between different branches of the exporters’ banks (local and at ports or in Lagos) need to be completed and submitted to the exporters’ banks who the exporters’ and delays of several weeks. The result was that physical inspections of exports would be delayed including for perishable goods.

During the next year successive dialogue events with non-oil exporters in Lagos and PDF experts’ engagement with banks led to two major recommendations: 1) to train commercial bankers on the NXP process and 2) to automate the NXP process (this had the additional benefit of increasing of the process). Subsequently, the PDF team supported the capacity building of banks in understanding export financing and engaged the EBES with relevant government and private sector stakeholders on the digitization and automation of the NXP process in February 2019. Then on 28 October 2019, the CBN introduced web-based forms for commercial exports (‘e-Form NXP’) to phase out the hard copy version. This saves time and financial costs. Eliminating undue human contact also creates more transparency; every exporter is required to obtain a Tax Identification Number, ensures that accurate taxes and levies are paid, and businesses entitlement to exemption is tracked digitally, removing scope for discretion.
[note] At one of PDF’s exporter dialogues, 18 bank representatives were in attendance.
[note] How PEBEC Is Improving Trade Across Borders in Nigeria, ProShare Nigeria < https://www.proshareng.com/news/Doing%20Business%20in%20Nigeria/How-PEBEC-Is-Improving-Trade-Across-Borders-in-Nigeria/44093>

Nigeria Diaspora Study and Development of Nigeria Diaspora Fund. In July 2017, PDF II commissioned a study to understand the patterns of diaspora remittances and the potential for optimising remittances for development impact and economic growth. The study indicated key information and patterns that should be considered if the country is to harness investment from diaspora. The study report was initially disseminated online, and later at a formal event with key private sector stakeholders especially financial services, investment and private equity firms and policy makers in November 2018. One of the aims of the dissemination event was to nudge private sector financial services and investment companies to use the study findings to develop and market financial products that will meet diaspora investment needs. Following the dissemination, two requests for technical assistance for projects that would attract diaspora investment into the country were received from private sector practitioners. One of the requests, the design and development of the Nigeria Diaspora Fund, is currently being taken forward. The findings are to be a global public good especially for Nigerian financial services firms to continue to explore opportunities to raise investments in country.

Lessons identified this year, and recommendations for the year ahead linked to this output

The Economic Development Team has identified numerous studies relevant for Nigeria’s current political and economic context. Some areas identified are understanding policy development on climate change in country, domestic resource mobilisation, supporting structural transformation and so on. The PMU should initiate and bring such studies to close during the programme’s tenure.

Continue to explore opportunities to raise awareness on the studies delivered to beneficiaries over its lifespan. In addition, the PMU should ensure that it has an adequate archiving system in place to ensure that key reports are available for DFID use beyond the life of the programme.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

The intended outcome of PDF II is that Nigeria’s reformers or champions of change use increased capacity and evidence to enable them to pursue vital economic and social reforms. The diagram below illustrates PDF II’s theory of Change. A request for support comes from a policy initiator, often government, but also other stakeholders that can influence policies and its implementation. This support should either support better policy formulation, tackle constraints to implementing it – both technical and political obstacles. DFID and the PMU then screen requests against criteria, such as whether they are feasible and UK support can make a difference. If the decision is made to support a request the expertise is provided – e.g. advisors, reports, processes bringing together stakeholders – and DFID/HMG looks for opportunities to promote reforms in discussions with government. If successful, new policies and their effective implementation should improve the prospects for inclusive growth.

This annual review considers the theory of change (ToC) set out in the business case to remain valid. However, some risks to delivery which were anticipated while drafting the ToC heightened during the year. These concerned political factors following elections and a reconfiguration of economic policy responsibilities between arms of government. One key assumption related to the ToC is that; “the new Federal Government of Nigeria appoints Cabinet, settles in and works efficiently (Policy direction setting, policy formulation and implementation) in a timely way”. After the 2015 election, transition committees were set up to ensure smooth implementation between outgoing and incoming ministers. There was a delay in ministerial appointments in 2015 and again in 2019 when the new cabinet was not in place until August 2019. This meant that it is taking longer to ramp up the programme than anticipated. Despite the heightened risk, PDF II supported key achievements over the last year such as Business environment Reforms, signing of the AfCFTA, better audits by the OAuGF and further progress on a follow-up green bond.

PDF supports a large number of departments; this responsiveness is a strength anticipated in the business case, but also means that there is no main docking point between DFID and government on government and DFID are getting best value from PDF. PDF helps strengthen policy formulation and implementation through the selection of activities which are cross-checked against criteria, through careful preparation of TORs, through selection of individuals consults and their monitoring. Advisers have sometimes been concentrated in ministries and there is a dialogue with beneficiaries (such as with the Chief Economic Adviser, NSIA or the Auditor General) on how decisions on groups of advisers can support improving policy making. DFID discusses the impact of advisers periodically with beneficiaries to understand whether the support is having the impact it should be. By design, PDF is able to cover a wide range of sectors. The cost of this flexibility to be able to be responsive is that there is no single point in government for the programme to discuss performance and whether PDF is delivering all it could to government. This is a consideration for future programmes.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

This annual review looks at progress towards outcome indicators for programme end in March 2020: the number of instances when beneficiaries can demonstrate that PDF II support directly influenced any of the 5 stages of policy formulation should be 17. Records from the programme indicate that over 50 instances were validated by beneficiaries. Relative to PDF I, this reflects the nature of support provided under PDF II which has been for smaller financial scale pieces of support. Requests to DFID under PDF II have been for assistance on a higher number of smaller sized projects. This is an issue for the Project Completion Report to explore in further detail, exploring for instance whether this reflects the Nigerian government’s current approach to economic policy or design and perception of PDF’s technical support.

Outcome indicator 2 requests “A rating of a sample of instances when PDF II support contributed to implementation of vital social and economic reforms”. The programme has provided eight instances (seven of which were also validated by the programme’s independent VFM review) showing that the support provided to the Federal Government of Nigeria (FGN) has generated a number of positive outcomes important to Nigeria’s poverty-reduction agenda. These include:
[note] Four instances were highlighted under PDF 1

- Improving Nigeria’s business environment—to support the development of small- and medium-sized businesses and to spur the national economy;
- Supporting a national job creation strategy focused on Nigeria’s growing technology sector.
- Boosting the export potential of non-oil businesses and enterprises;
- Supporting the Nigerian Sovereign Investment Authority (NSIA)—to boost investor confidence and channel investments into critical development projects;
- Issuing green bonds—to support sustainable development and secure Nigeria’s climate commitments;
- Extending an affordable and reliable supply of renewable power to hard-to-reach rural communities;
- Improving the efficiency of spending and overheads—freeing more funds for public services;
- Laying the foundations of a more effective auditing system to enhance accountability across government.

Examples of three major areas of work where PDF supported good outcomes for Nigeria (in addition to the Doing Business success described in the Summary above) were: A) supporting Nigeria’s signing of the Africa Continental Free Trade Area (AfCFTA); B) preparation for Nigeria to issue a first and second green bond; and C) providing continuity in DFID’s support to Nigeria’s infrastructure policy and planning.

Support to the Nigeria Office for Trade Negotiation and Nigeria (NOTN) in signing AfCFTA: PDF supported the Economic Advisory Board which makes recommendations to the Special Adviser to the President on Economic Matters. The Board made a recommendation on coordinating Nigeria’s Trade policy which led to the creation of the NOTN headed by the Chief Trade Negotiator (CTN), late Ambassador Chiedu Osakwe. PDF II supported the setup of the Office by providing research materials to its library, training on trade policy and negotiation for its staff, and a Technical Assistant to the Chief Trade Negotiator, who was designated Deputy Chief Trade Negotiator for Nigeria. The TA focused on drafting the AfCFTA and on trade remedies for Nigeria (legitimate measures to protect domestic industries, e.g. anti-dumping). The development of the AfCFTA was hit when the CTN was recalled before signing; the CTN had championed the AfCFTA, drafting parts of the agreement along with counterparts from the other countries. Over the following year the CTN undertook a nationwide consultation supported by PDF, after which Nigeria signed up to the agreement in July 2019. The AfCFTA will create the world's largest free trade area (comprising 1.2 billion people with a combined gross domestic product of $2.5 trillion) and will potentially lead to a 60% boost in intra-African trade by 2022.

PDF II supported Nigeria to plan, develop and issue the first ever sovereign green bond in Africa; the bonds are now financing climate-smart initiatives, supporting the country’s climate commitments, and driving a new emphasis on pro-poor green development. During the last two years, a PDF II EA has supported the Ministry of Environment develop policies and strategies to operationalize green bonds. The EA prepared guidelines and criteria for identifying green projects in line with standards for the use of proceeds from green bonds that will be verified independently in the future. The EA was central to unlocking World Bank assistance which included support for a green bond advisory group and a green bond technical advisory team. The EA convened meetings between the advisory group, capital market operators and Nigeria’s Debt Management Office. A Green Bond Secretariat was eventually formed and major development partners committed funds. The World Bank made an initial release of N125 million to support technical and administrative processes; and following the success of the pilot green bond initiative in 2018 approved a further N500 million to support the issuance of additional bonds and supervise projects funded during the pilot.

Between early 2017and September 2019] PDF provided continuity in UK’s support to Nigeria’s infrastructure development between the conclusion of NIAF 2 and the mobilisation of the new UK-NIAF programme. Technical support included assistance to the Rural Electrification Agency and to the Transmission Company of Nigeria. Activities also included political economy analyses of Nigeria’s infrastructure planning and financing strategies which will feed into UK-NIAF enabling a quicker start to the new DFID programme, as well as the work of other development partners. This continuity has helped maintain relationships built up over the past eight years of the previous programmes (NIAF 1 & 2) with GoN.

As envisaged in the business case, other DFID programmes to support Nigeria have benefited through PDF explorative studies and advisers. PDF supported DFID’s response to the farmer herder conflict by recruiting a well-qualified adviser who has been involved in the drafting of the National Livestock Transformation Plan. This Plan is now live and being implemented at the state level. PDF has also worked alongside PERL to support the passage of the Audit Bill which would enshrine the independence of the Office of the Auditor General of the Federation. The Audit bill was passed by both houses of the national legislature but was not assented to by the President. In its last few months, PDF is undertaking a study on governance of climate and environmental issues in Nigeria which will support government and DFID on future climate initiatives.

Explain major changes to the logframe in the past year

In line with recommendation of the 2018 annual review, logframe milestones were reviewed and revised at the output level to reflect the change in project counting methodology to highlight thematic clusters rather than each project counting as a standalone. In addition, the logframe was also revised to reflect the change in mix of activities, especially the addition of infrastructure support during the year which had not been envisaged in programme design while leaving flexibility to respond to the needs of the new government after 2019 elections. This decision was taken in March 2019 and the revised logframe approved in September 2019.

Describe any planned changes to the logframe as a result of this review

N/A

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year

PDF is an example of a programme providing national level policy advice and technical assistance to promote pro-growth policies – a potential ‘great buy’ if the conditions are right and implementation is strong. DFID’s own assessment of development ‘best buys’ for economic development, identifies national level policy advice and technical assistance to promote pro-growth policies as a potential ‘great buy’. This typically requires heavy engagement by skilled and long-term advisors and can be delivered by DFID advisors working with partner governments, technical assistance, or intensive policy-oriented research partnerships. PDF aims to demonstrate this VFM case. Out of PDF’s portfolio, while not all interventions are expected to be game-changing, the overall portfolio should demonstrate sufficient results to justify the overall cost of the programme. PDF’s highest potential value for money (VFM) comes from some of its relatively small-scale interventions out of a large portfolio unlocking major reforms.

The VFM of PDF is achieved by robust programme management systems that maximise the chances of interventions achieving their objectives and doing so within the overall budget and within the agreed cost ceilings for specific types of expenditures, especially fee rates. When a policy maker within the Nigerian government requests support on policy formulation, DFID responds as described in the ToC by evaluating the feasibility and political economy around the request in conjunction with the following questions: Is implementation possible? Can providing a solution help meet DFID’s objectives? can PDF provide a critical contribution? If the responses are positive, the programme may support.

The impact of advisers is routinely reviewed between DFID, PMU and beneficiaries; this interaction leads to decisions on stopping adviser posts where they are no longer needed, but also addressing potential risks in such close working between DFID and government. While monitoring and evaluation of technical assistance is undertaken primarily by third-party contractor, DFID undertakes regular reviews to make sure the balance of support across Nigerian government remains high value. The efficacy of DFID’s portfolio of interventions has been reviewed twice over the last year and strategic conversations around the support held with the OVP in March 2019, May 2019 and September 2019. The result has been a minimisation of embedded advisers; of 24 infrastructure advisers, on 2 highly strategic ones were retained under PDF in March 2019. In addition, from 52 non-infrastructure advisers, there are 12 left on PDF books. Ad-hoc meetings are scheduled with beneficiaries to address developments which may have significant reputational impact on DFID. In instances where embedded advisers work in sensitive areas, ToRs are developed to ensure that sensitive information is not reported back to the PMU with annual reviews or more frequent discussions providing the opportunity to sense-check the support to beneficiaries.

The programme must be strategically selective on interventions to implement as it is limited by annual budgetary allocations. Therefore, there are instances where the programme would decline a request for support, or revise the terms of reference associated with some support to achieve the desired outputs.

The business case proposed quantitative and qualitative methods to assess economy and effectiveness in particular during implementation to ensure the programme continues to represent VFM and these have been undertaken through routine monitoring and in the independent VFM review. For the economy dimension of VFM, the business case suggested a review of the average cost of embedded advisers and daily cost of expertise brought in for policy studies and research (vis-à-vis benchmarks). In addition, case studies around major policies that have been introduced with support from PDF II with quantifiable benefits where possible should be undertaken to highlight effectiveness. Details are in the descriptions of the following summaries against the ‘four Es’.

Economy: As envisaged during the design of the programme, the primary cost driver for PDF II remains the fee rate of the technical expertise it deploys. A strict cap for embedded advisers fee remains £6,250 per month; through proactive negotiations, PDF II has managed to attract and retain skilled technical experts despite inflation, although there have been instances where the programme simply could not afford the preferred expert. In May 2019, a cap of £800 on daily fee rates was introduced, with any rates above this requiring additional review by DFIDN prior to approval. PDF has operated within this rate since this was effected.

A recent independent VFM review of PDF II found the programme to be delivering economically. Taking other DFID Nigeria programmes and other development partner programmes as benchmarks the review noted:
[note] Bayaz, Guilden (2019): Value for Money Assessment of the Policy Development Facility

PDF II fee rates of consultants have been at similar levels to other DFID Nigeria programmes (based on information from programmes such as FOSTER [DFID’s support to Oil and Gas sector reforms], Deepening Democracy and the Federal Public Administration Reform programme [which] have been referred to. The latter two programmes ended in 2016).

The same review founds that while management costs were difficult to assess because of different accounting practices between programmes, it suggested management costs were being managed reasonably:

In terms of management costs, it is difficult to compare to other programmes because Facility staff costs are also part of those. The Managed Fund fee which was set at 3.5% (actuals show 3% in expenditure reporting) does not appear to be too high, considering that there is no mark up on the EAs by the Facility service provider. As a comparison, World Bank charges 7% in management fees on its Trust Funds.

Efficiency: DFID’s definition of efficiency is focused on the relationship between inputs and outputs (i.e., technical efficiency): How well do we or our agents convert inputs into outputs? (DFID, 2011, p.4). To ensure that there is a maximum likelihood of delivery to standards required by beneficiaries, project ToRs are carefully designed to document agreed deliverables and required skill sets. In addition, technical expertise is vetted to ensure it can deliver to the ToR outputs by reviewing consultants’ CVs and where required, interviewing prospective candidates. Where the beneficiary identifies a preferred candidate, and PDF II has concerns with delivery, this is flagged with the beneficiary and a recruitment recommendation made based on the requirements set out on the ToR. In addition, beneficiary feedback is obtained at various intervals to ensure contractors are delivering agreed outputs and contractor payments are tied to confirmation that outputs are delivered in line with the agreed ToR.
[note] DFID (2011), DFID’s Approach to Value for Money

Effectiveness: PDF The independent VFM review prepared case studies of success stories from PDF’s portfolio of small-scale projects – such as those summarised for business environment, trade policy and green bonds in this annual review. The VFM review also monetised where feasible realised or potential benefits of policies supported by PDF projects. Table 2 at the end of this section compares the costs incurred by PDF on individual projects, as well as total cost of PDF so far, with the benefits it has likely achieved or contributed to. This comparison demonstrates that it is highly likely that PDF projects represented value for money for DFID’s investment. For instance, support to improve the Efficiency Unit in the Ministry of Finance contributed to FGN making savings estimated at over £0.5 billion; benefits will continue to accrue in the future from the introduction of e-Procurement supported by PDF. PDF support for rural electrification helped unlock over £400 million of World Bank and African Development Bank funding for Nigeria. Beneficiary feedback collected in the report supported this view. A number of examples were provided by beneficiaries and other respondents, such as PDF support to OAuGF coming at a critical time to support modernisation of the process for auditing federal accounts and the quality of support for business environment reform.

Equity: PDF II requires embedded advisers or consultants to always consider the gender and equity impacts as they embark on any project. In fact, gender and equity impacts are built into ToRs for consideration at the design stage of every intervention. This enables the programme, beneficiaries and embedded advisers to consider equity impacts and where possible quantify these impacts at the inception and implementation of the programme. One example is the deliberate focus by the Trade Policy workstream on Micro Small and Medium-Sized Enterprises within which women and the poor are strongly represented. PDF’s support to the Job Creation Unit also helped encourage female applicants to the Npower programme (38% of successful applicants are women). A recent dialogue on women’s participation in inclusive growth also raised awareness on gender constraints on female participation in economic activities in Nigeria. In addition, studies funded by PDF II where primary research is conducted are required to have gender markers in order to provide evidence that can used to improve targeting of interventions (e.g. the Middle Class Study).

Explain whether and why the programme should continue from a VFM perspective, based on its own merits and in the context of the wider portfolio

Based on feedback from beneficiaries collected by the programme and in this review, the programme should continue because the support provided by PDF to beneficiaries has provided them with capability to deliver impact during their term in office within acceptable costs. Beneficiaries on average scored PDF II support 94% on Relevance and 89% on quality, above log frame thresholds. The independent assessment of the program observed that:

There was significant praise for how the support was instrumental in achieving important outcomes, in many instances, in a relatively short period. The study went on to state that, “the counterfactual of PDF support is difficult to establish, however beneficiary feedback indicates that majority of initiatives would not have been as effective, or gone further in implementation, without the PDF support. Many examples of this were provided by beneficiaries and other respondents.

Successful PDF initiatives involve a combination of effective advisers/high quality reports and strong institutional ownership and supportive policy environment for the policy area supported. Of the eight instances the programme has provided to highlight its effectiveness, the independent impact assessment and annual review meetings indicate that interventions on the efficiency unit, supporting the REA, support to the Auditor Generals, non-oil exports and business environment reflect strong leadership/effectiveness of the technical assistance provided by PDF. In these instances, PDF has provided embedded advisers who are highly qualified and have nurtured relationships across the Nigerian government to drive reforms. Other interventions such as those on job creation reflect a favourable policy environment as the government recognised the country’s jobs deficit as a key challenge to its development agenda. Finally, interventions on green bonds reflect strong MDA leadership and strong technical assistance computed with a favourable policy environment as mobilising finance is imperative.

The PDF programme also aligns well with other DFID programmes and with the new Africa Strategy to address long-term issues that matter most for Africa’s prosperity. The programme supports policy makers who can make an impact on inclusive growth, trade, and economic partnerships (via research and technical support to the OVP, the Ministry of Budget and Planning, senior economic advisers to the President, the Finance Minister and more). The programme also supports climate change and natural resource management via technical advice to the Ministry of Environment and supports stability within Nigeria via support on DFID’s North-East interventions.

Table 2: Summary of Realised and Potential Benefits from PDF

Benefit Description	Quantified/ Monetised	Realised	Potential
Savings on public expenditure (recurrent and capital)	Through: / Efficiency Unit engagement / Cost reduction on 2nd Niger Bridge project	£508m / £140m	Large potential through Efficiency Unit initiatives like e-procurement, etc. Significant return considering the initiatives cost around £150k from PDF II Managed Fund budget.
Investment in social Infrastructure	NSIA current social portfolio on schools and hospitals. / Here, the higher-level benefits would be accrued from better education and health outcomes but we don’t know the extent and likelihood of these yet. Global evidence shows that investing in social infrastructure in Africa provides significant returns.	£56m
Contribution to Job Creation	Around 12,100 jobs (REA and YouWin). / Monetary value of a job is extremely difficult to calculate, and depends on context, country, sector, etc. however, benefits of a job far exceed an annual wage income.		Plenty more jobs can be linked to PDF funded initiatives. The exact number is to be determined through tracer studies (by PDF or by Government of Nigeria).
Environmental benefits	Through: / -Green Bonds engagement, funding solar energy and forestry projects / -REA support (not monetised) / Environmental benefits of REA programmes likely to be good through use of solar, and cancellation of diesel generators. Can be monetised further through avoided emissions approach, in the near future.	£23m fund value fully taken up. / In addition, this is expected to have job creation and tax generation related impacts, according to the brief prepared for the Debt Management Office.	£32m through second sovereign green bond expected to be issued by the end of May 2019. / Further, private green bonds issued, for example the £32m Access Bank bond.
Leveraging further funding (for example from other development partners) for Government projects/ initiatives.	REA work on Energising Education phase I.	£427m / (total for phases 2 and 3, from WB and African Development Bank respectively)

E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation

Overall risk rating: The overall risk remains Moderate for PDF II which continues to reflect the uncertainty about the political environment for reforms, challenges to delivery and reputational risks. The programme complies with DFID’s guidance on maintaining risk register and proactively managing risk. DFID and the PMU instituted regular catch-ups where emerging risks were flagged and actions to mitigate them discussed.

The major current risk on the programme relates to the External Context; there is insufficient political and managerial leadership including capacity to drive through wider organisational reforms in ministries, departments and agencies. An emerging risk to reflect in the next update of the risk register is the delivery risk that programme closure in March 2020 results in important activities halting. Mitigating this risk will require a strategy to discuss with beneficiaries and to ensure the bridge programme provides continuity. A summary of the major categories of risks based on the latest risk register is as follows:

External Context: The main risks relating to government commitment include: [Risk C1 in risk register] legislation supported by PDF II not being passed, or insufficient budgets being approved to enable their implementation; [C2] insufficient leadership and capability to drive through the wider organisational reforms in MDAs to support evidence-based policy implementation; and [C3] the new government does not appoint new Cabinet quickly and move to implementation. These risks have been mitigated by using a strong political economy lens to identify areas where reforms were likely to continue as they were regarded as less politically contentious (such as business environment reforms). Furthermore, the PMU raises awareness among EAs of the importance of identifying key civil servants besides their principals who will act as enablers for their reform initiatives. After mitigation, these risks are mostly classed as having Moderate risk.

Delivery: The only active delivery risk is the longstanding risk that PDF backs individuals/ institutions that are unable or unwilling to pursue policy and implementation reform [D1]. The programme has established mechanisms for adapting to the reform environment, working with other DFID/donor programmes where relevant and finding solutions to help build the capabilities of the MDAs to achieve project goals. A proposed new delivery risk for 2020 under programme closure is that PDF exit is proactively managed; this will include managing the expectations of beneficiaries about what the bridge programme can deliver and also ensuring continuity of advisers in cases where the same consultants would ideally transfer from PDF to the bridge programme. This is identified as a Reputational risk in the register.

Reputational: An ongoing risk is that comments are attributed to DFID which may harm the UK's Government relationship with Nigerian counterparts [R1] or that public positions or actions taken by DFID funded embedded advisers have a negative impact on DFID. To mitigate this risk the PMU makes all report reports public and staff avoid providing comments to the media. Where embedded advisers are not directly managed by the programme, regular performance reviews are held with beneficiaries, and taking prompt action if problems are identified.

Safeguards: The only live safeguarding risk concerns support to FGN’s jobs initiatives [S3] – the safeguarding of people employed through government job creation programmes. The mitigating risk is that ToRs for advisers working on assignments related to jobs and infrastructure prevent risks arising.

Update on partnership principles

The programme does not use the Partnership Principles as formal conditionality in programming as no UK aid money goes directly to the Government of Nigeria. However, greater resources will be directed to those institutions that demonstrate greater commitment to the partnership principles. For instance, institutions committed to improving poverty reduction may be highly considered when determining the level of technical assistance that the programme provides. This will be used alongside political economy analysis of where job creation and poverty alleviation is likely to be championed within the Nigerian government.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues

The PDF II programme as implemented by the PDU remains compliant with the terms of the contract as amended in October 2018. PDF II did not have any commercial-related challenges during the period under review. DFID is currently tendering a bridging intervention (“Champions of Change”) which is expected to commence operations before PDF II ends and a successor programme is approved and mobilised.

Financial performance of the programme during the period under review was broadly satisfactory based on DFID’s measurement of financial performance i.e. meeting forecasted spend and timely submission of monthly invoices. Although the programme has consistently submitted monthly invoices on or before the 15th of the following month as required, it has recorded significant monthly variances between forecast and actual spend as shown below from September 2018 to October 2019. Although the variance period average was only 1% - and year-end budgets accurate - the highs and lows reflect the programme’s challenges with forecasting. This was partly due to the slow engagement of MDAs since the elections and the implementation of new programmes. This meant that PDF would not need to operate in areas it historically has. The programme’s spend was significantly higher in March 2019 as the programme wound down non-critical infrastructure projects to reposition itself for demands post the election period. Post March-2019, the programme worked with the assumption that there would be an increased demand by MDAs for technical advisory support once the new cabinet was in place following the 2019 elections. DFID and the programme agreed to put on hold some Output 2 projects (i.e. research) in order to accommodate these requests should they be made.

Month	Sep-18	Oct-18	Nov-18	Dec-18	Jan-19	Feb-19	Mar-19	Apr-19	May-19	Jun-19	Jul-19	Aug-19	Sep-19	Oct-19
% Variance	-26%	21%	3%	1%	-11%	8%	31%	0%	-2%	1%	23%	-7%	-2%	-27%

No independent programme audit was conducted for this period under review as the Programme is due to end by March 2020 and a Programme Completion Report (PCR) is due by June 2020. For this reason a waiver was secured to conduct the independent programme audit in time for PCR. The independent programme audit (August 2018 – December 2019) is currently being contracted and is due to be conducted in January and February 2020.

The results of the previous programme audit covering the period August 2017 to July 2018, were very satisfactory as no material issues were raised. Recommendations from the audit have also been adequately addressed. The Service Provider’s last annual audited statements for the period ended December 2018 has been shared with DFID and has no key issues or concerns.

Date of last narrative financial report(s)	November 2019
Date of last Annual Audited Statement (s) – PDF/DAI	December 2018

G: MONITORING, EVIDENCE & LEARNING

Monitoring

The team for the annual review (AR) included DFID Nigeria’s current Senior Responsible Officer or SRO (Economic Adviser), the future SRO from January 2020 (Senior Economic Adviser) and programme manager and officer. The AR involved meetings with beneficiaries and embedded advisers, and also drew on the impact assessment and VFM studies commissioned following the last AR. Meetings were held with the Deputy Chief of Staff to the Vice President, the Auditor General (Office of the Auditor General for the Federation), Chief Executive of the NIPC, senior staff of the Rural Electrification programme, and others. Conversations with the beneficiaries highlighted the relevance of PDF’s support and the recognition that the programme’s technical assistance has helped their ability to deliver on key policy issues.

During the year, the PDU holds conversations regularly with embedded advisers, and periodically with the beneficiaries or beneficiary representatives. DFID and the PDU discuss issues on a weekly basis in addition to holding six monthly reviews where risks and opportunities are highlighted.

Evidence

As described in the VFM discussion above, PDF is an example of a potential ‘great buy’ programme which aims to unlock reforms that deliver very high returns when effective by improving the prospects for por-poor growth. Any individual effort will be high risk but a few high impact successes are necessary to make the overall portfolio and project approach worthwhile. Success depends on there being reform champions for DFID to work with, and a strong delivery partnership between DFID staff and implementing partners.

The information and cases studies gathered and prepared on PDF’s support to policy formulation constitute evidence that a number of programme activities have worked in the way set out in the theory of change and achieved meaningful results. Total number of instances counting PDF’s support on the stages of policy formulation cited in this year alone is 57 for Output 1 (defined as relevant and high quality PDF II organisational support delivered to beneficiaries), and 6 for Output 2 (relevant and high quality PDF II policy research, explorative studies and consultation products delivered to beneficiaries). Over the year, case studies around major policies that have been introduced/implemented with support from PDF II reveal that the PDF II funded embedded advisors’ contributions were key to the success of the project. Some key examples include the Energizing Economies project which is providing power to Sura Market in Lagos and Ariaria market in Aba. The Office of the Vice President and the Ministry of Power, Works and Housing responded positively on the contributions of the embedded advisors, developing the EEI initiative and its transaction matrix. Others include the business environment reforms, green bonds and AfCFTA.

Learning

At the inception of PDF II, a monitoring and Knowledge Management/Learning (KM) system was set up. The KM system which draws on formal reports from EAs and consultants. It has enabled PDF II to capture key learning and evidence and to ensure that EAs work more collaboratively and learn from each other. The tools that aid learning on the programme include:

1. Interim and exit interviews conducted for EAs; these help to reveal process learning as well as shed more light on achievements, lessons, risks and mitigation measures;
2. Annual reviews and beneficiary feedback where a sample of PDF II’s Output 1 projects active in the year are reviewed to assess the extent to which outcomes have been achieved and if beneficiaries still find the support relevant and informs the shape of future support;
3. PDF PMU’s internal assessment of projects against relevance and quality criteria. The beneficiaries are also required to carry out a similar assessment for each EA;
4. Anecdote Circles: a recent introduction, one Anecdote Circle was held in April 2019 where EAs came together to share experiences on ‘proud moments and sustaining gains’;
5. Semi-formal networking and learning events: two semi-formal events were held in December 2018 and July 2019. These provided EAs, DFID Advisers and other colleagues across HMG, and other programmes to share experiences and lessons based on EAs’ achievements.

Progress on recommendations from previous reviews

The programme implemented all recommendations from the last annual review. Please see Table 3 below.
Table 3: Progress On 2018 Annual Review Recommendations
	S/N	AR 2018 / Recommendation	Management Response	Progress
	1	PDF II should explore areas where it is already providing support, selection criteria for which should be to improve the productivity of what will be done regardless of who wins the 2019 elections. Examples include: / Modernising the Public Accounts Committee in a way that avoids discontent politically about take up of the PAC reports; / Bringing skills to bear on the mechanics of how to implement social protection programmes in conjunction with other DFID Programmes (such as the Child Development Grant Programme). / The Programme should explore other areas beyond the aforementioned areas, where PDF is already providing support	PDF will consult with existing beneficiaries and DFID, on areas including but not limited to the above, where the efficiency of PDF II support might be improved that will not be so politically sensitive. To start this process, we will: / Identify “politically neutral” areas of support and suggest ways to improve productivity internally; and / Take our conclusions to consult with DFID and those responsible for implementing the reforms	Achieved / PDF Consulted with current beneficiaries (EBES, NIPC, OAuGF, NASS, FBDS etc.) and deemed the following areas as sufficiently “politically neutral”, to enable improved productivity: / Optimising Diaspora/Nigeria's Middle-class investment, / Franchising / Ease of Doing Business, / Modernisation of PAC / OAuGF / In addition, implementation of Social Intervention programmes was explored further with DFID, and it was decided that given current financial challenges, action would be on hold and PDF II would only consider specific request from the relevant DFID team should they arise. / Having consulted, the following activities/outputs aimed at improving productivity in the selected areas have been undertaken: / Dissemination event for the Diaspora study held in November 2018. It was well attended, raised interest of private sector fund development and management institutions, and led to a request for support on the development of a Nigeria Diaspora Fund. A project developing the business case is about to commence and is expected to be delivered by December 2019. / The Nigeria Middle Class Study has been completed and it is expected to complement current work on optimising investment and private sector development by the LINKS Programme. / PDF II supported a roundtable discussion on the development of the 2019 Franchise agenda for Nigeria, and matchmaking conference in November 2018. The events saw the launch of a private sector led franchise association and the franchise institute of Nigeria. Additional support on institutionalising both the association, the institute, and other interventions have been requested from PDF, but were placed on hold due to lack of funds. Also collaborations are currently ongoing on raising the profile of the need for Franchise specific fund from the BoI. A BoI director was invited to the seventh Exporter Dialogue (ED7), which also had a presentation from a representative from the Franchise space. The issue was raised and addressed, with recommendations made to financial institutions. / PDF II has supported the development of Practice Notes for LACIAC and training of their staff, as well as training for MSMEs on dispute arbitration mechanisms. In line with recommendations of the Franchising study and dissemination event on dispute resolution, this will go a long way to supporting franchising and other MSMEs. Further work is planned over the coming months to support LACIAC in providing free Arbitration Clinics to MSMEs. / Request from EBES for McKinsey support was considered and after much of the projects preparation work was completed, the project had to be dropped in January 2019 due to lack of funds. / PDF through the Trade Policy Workstream continues to support EBES in areas of common interest such as the Apapa Port Grid Lock. PDF II also continues to provide TA to the EBES through the SSA on Industry Trade and Investment. / The refurbishment and upscaling of the House of Representatives’ Public Accounts Committee was completed, and the 2010 – 2014 backlog of Auditor General’s reports were published in April 2019. PDF Continues to support the PAC on the 2015 &2016 reports and transition to a new PAC in the 9th Parliament.

	2		PDF II will commission a research towards aggregating jobs supported across all PDF II projects. In addition, this will include areas where it is evident that the private sector has had adequate time to respond to FGN-led initiatives, and have led to further jobs created (i.e. indirect jobs). The research design will be associated with clear objectives, specific research questions and an associated methodology. Insights gained by this research will reveal employment gains and how these are differentiated by men and women. The methodology to be developed will be informed by guidance provided by the DCED results measurement standard on defining net additional jobs and estimating attributable changes.	Achieved / ToRs for the research on aggregation of jobs created as a result of PDF support was developed and shared with DFID for comments in March 2019. Following review, consultants’ procurement was concluded in August and the Study commenced in September. / The study has been completed and the report is undergoing review and finalisation processes.

3	3	Draw up Value for Money case studies that focus on assessing and attributing the effectiveness of specific interventions such as support to the Efficiency Unit and the Ministry of Environment on the origination of Green Bonds by the next annual review.	PDF II will initiate research into suitable methodologies for assessing attribution of the effectiveness of its intervention. The methodology will be shared with DFID following which necessary steps to carry out the assessments will be taken. In addition to the above examples, PDF II will identify other interventions in order to take the opportunity of showcasing the value of PDF II support. Bearing in mind the nature of PDF II interventions, for each case, the assessment will aim to address the 4 dimensions of value for money, in order to provide a balanced assessment. We envisage the scope of the assessments’ enquiries will look at the consequences of, for example, efficiency gains and the value of issuing green bonds, and who realises these. Results from these analyses will inform the value of the second outcome indicator - a rating of a sample of instances when PDF II support contributed to implementation of vital social and economic reforms.	Achieved / Research on suitable methodology for assessing attribution by PDF was completed and a ToR for the research commissioning was developed. / Identification of key areas for the research case studies was also concluded and incorporated into the ToR. Areas identified include: / Efficiency Unit, / Green Bonds, / Energising Economies, / OAuGF Support. / Consultants were procured in August 2019, and as of the time of this report the study has been completed and the report is undergoing review and finalisation processes.

Policy Recommendations	4	To periodically take a step back, to review the roster of Embedded Advisors on a case by case basis, in order to reprioritize areas of engagement given champions of change in the run up to the elections and within the new administration	PDF II will carry out an internal review the roster of EAs in Jan 2019, in relation to champions of change and current government priorities,and present the findings and conclusions to DFID in early February 2019. This analysis will be repeated in May 2019, soon after the new administration begins, and its implications. In this respect, the criteria will be defined by the priorities of the new administration. It may be the case that such criteria are informed by the results of a preceding analysis of the political economy.	Achieved (and ongoing) / The first review took place in early January 2019 and recommendations on EA projects and handling strategy with FGN were presented to DFID. This informed DFID’s decisions on management of the financial stretch following further extensions to infrastructure contracts. / A second review to determine estimated underspend from all on-going projects was carried out in March 2019. This will inform decisions on management of PDF’s core projects beyond May 2019. / Periodic reviews continue to be held as part of proactive financial management.

	5	Look to revise its logical framework to ensure that milestones are realistic.	Revisions to milestones, and necessarily targets for 2020, will focus at Output level, specifically indicators 1.1, 1.3, 2.1 & 2.3. They will be submitted to DFID.	Achieved / The review of output milestones commenced in Feb 2019. / Proposal on revised milestones were shared with DFID. After feedback from DFID, PDF II updated the proposed Logframe output milestones following a further submission, the review was concluded with new milestones agreed in September 2019.

	6	PDF should review and determine the implications of the change in the counting methodology to provide clarity on what may and may not be comparable (with PDF I) under Output 1.	A review of the change, and the implications of this, will be conducted with a recommendation on comparability of Output 1 between phases submitted to DFID	Achieved / Review process commenced in February 2019 and concluded that the best way forward to enable comparison with PDF I would be to keep relevant project and programme information in the two formats for use as appropriate. / This has now been done and the two sets of data are available upon request.

	7	Implementing DAIE’s Quality Assurance policy on project close down	PDF will conduct an initial review of the DAI QA Policy on close down and develop and implement a Programme close down plan by end of Q2 FY2019/20	Achieved (and ongoing) / Initial review of DAI-E QA policy on project closure was done in November 2018. / Further discussion of close down was held with DAI-E during APMU visit to HO in February 2019 / APMU close down planning workshop held in November 2019. This will feed into updates on Programme close out. / A Close-out activities schedule covering all relevant activities including reporting and Audit has been agreed with DFID and is being implemented.

Programme Recommendations	8	Determining ways of managing the sustainability of the changes achieved through PDF II’s support across beneficiary MDAs, the OVP and the Trade Policy Workstream’s Community of Practice. The areas of focus will be selected in consultation with beneficiary institutions.	A number of products have been identified as critical for ensuring that results, lessons, and resources from PDF II are sustained and available to future programmes	Achieved (and ongoing) / KM Team commenced documentation of results and tracer studies in key areas in Q12019. / As part of EA annual reviews, lessons learnt were collated with focus on delivery and sustainability. These will be developed as part of PDF II Legacy Products by Scriptoria. This is currently on-going. / Potential institutions to be invited to showcase gains and sustainability mechanisms at close out event include: / NSIA, / OAuGF / REA / Efficiency Unit