ADDENDUM TO BUSINESS CASE

SUMMARY INFORMATION
Project Name	Political Settlements Research Programme
Country or region targeted	Worldwide
Type of cost extension (if applicable)	Costed extension
Original project budget	£4.4 million
Original project start and end dates	01/04/2014
Cost extension value (if applicable)	£2.2 million
New project end date (if applicable)	30/03/21
Business Case Quest Document No.	https://ec.vault.dfid.gov.uk/otcs/cs.exe?func=ll&objId=8534256&objAction=viewheader

INFORMATION
What is the project’s purpose?
The Political Settlements Research Programme is a contract for £4.4m over four years (2015-19). We propose that the programme is extended by a further £2.2m for two additional years (2020-2021). PSRP provides research and expertise on peace and political settlements and how international actors can best contribute to ending violent conflict. / PSRP is one of our flagship conflict research programmes, achieving ‘A+’ in the last 2 annual reviews. It is considered both practical and operationally relevant by DFID HQ and country offices, other government departments and the international community. / PSRP’s research and researchers are in high demand: PSRP is providing comparative research and expertise to the UN, EU and OECD on policy, such as the UN Secretary General’s “Sustaining Peace Agenda”, and in practice such as through advice to the UN mediator’s office on Yemen. / PSRP’s work is practical. PSRP expertise has informed or improved DFID / HMG engagements on peace processes covering: Columbia, Afghanistan, Syria, Cyprus, Kosovo and Yemen. PSRP provides research and expertise direct to Ambassadors, Special Envoys (e.g. for the Great Lakes, South Sudan and Afghanistan), mediators (including at the UN) and domestic actors working towards peace. PSRP also provides rapid advice to country teams during complex changes to political processes e.g. Zimbabwe, Lebanon and Yemen and delivers popular seminars and public events. / PSRP’s purpose is: to enable more effective interventions that address conflict risks and promote stable and pro-poor institutions. PSRP focusses on understanding and overcoming political barriers to peace and development and promoting initiatives that are more likely to succeed. / DFID sought feedback on PSRP's research ahead of this extension proposal. All feedback has been positive. Explicit requests for an extension were provided by country teams (Yemen, Afghanistan, South Sudan, Syria and Afghanistan); DFID and FCO policy teams, including CHASE; FCO Research Analysts and Ambassadors; and the Stabilisation Unit. / Performance to date / PSRP has surpassed targets for publications publishing 11 articles in peer-reviewed journals, 5 book chapters, 21 briefing papers, 33 research reports, and 59 blogs to date. The launch of the Peace Agreements Database (PA-X) in 2018 has been recognised as a ground breaking tool for comparative research and for those trying to end armed conflict. It contains over 1500 documents from over 150 peace processes over the last 50 years. New data is also being developed on amnesties. / The peace agreements database is a noteworthy accomplishment, with remarkable breadth. It will serve as an invaluable resource for scholars, groups impacted by violent conflict seeking a greater voice in peace processes, and individuals charged with mediating disputes. The knowledge the database provides may foster political settlements that are more inclusive and more sustainable. / US Ambassador (former) Carey Cavanaugh / I found the database a really helpful source – much more so than other resources available. First of all, it’s clear and easy to use. Second, it instantly provides a comprehensive set of results. That’s invaluable when we quickly need to provide concrete examples and precedents to our policy customers in the FCO.” HMG official using database. / This database will be an important resource, not just for high-level mediators and parties to conflicts, but also to the wider range of civic participants who seek to influence talks processes and press for greater inclusion. Having access to such a breadth of data on peace processes will mean that practitioners will have a firmer foundation for the choices they make. / Jonathan Cohen, Executive Director, Conciliation Resources, http://www.c-r.org / International Development Act (Gender Equality) 2014 / PSRP meets the requirement to consider gender equality in its research. It has published major contributions on how gender is considered- and the role of women- in peace processes and on conflict-related violence against women. / This includes comparative research across Liberia, Timor-Leste and Northern Ireland and makes recommendations about how the international community could address these more effectively. PSRP research also finds that wider efforts to end conflict, improve security and demobilise combatants can also have important benefits for reducing domestic violence. / UN Women is examining the gendered dimensions of peace agreement implementation, drawing on the PSRP gender and peace agreement database. This follows PSRP’s contribution to the UN’s 15-year review of Security Council resolution 1325, and the Secretary General’s Report on Women, Peace and Security last year (2017).
What is the objective of the cost extension or other changes?
The objective of the proposed cost and time extension is to build upon PSRP’s achievements thus far; testing and refining the programme’s most important findings whilst continuing to provide high quality public good research, and expertise to DFID country offices, FCO Ambassadors, Special Envoys and international policy makers at the UN, in Europe and at the OECD. / This research is in line with HMG’s Strategic Defence and Security Review which identified peace processes and reducing conflict as a core objective. / PSRP’s research is already informing DFID country diagnostics and strategic directions work on conflict, security and justice. Further developing PSRP’s evidence-based framework will enable HMG to tailor the most effective interventions for each context, and understand how political constraints can best be tackled to reduce violence and conflict. / The goal of the extension is to move PSRP’s outputs from the analytical into the operational by developing tailored country peace process support for 6 countries, drawing on comparative research from the database. These will also outline indicators for monitoring implementation in progress. This will enable HMG to: / Manage complex trade-offs with better evidence on likely peace process outcomes; / Understand and deal with ‘set backs’ ’including where there is an absence of national peace processes in intractable conflicts; / Work collaboratively in a complex and changeable global context of interventions. / PSRP will deliver the following outputs to help DFID meet these goals and objective: / Deepen data and comparative research, and further test and refine findings, drawing on the peace agreements database. The research will focus specifically on implementation arrangements, where there is strong DFID and HMG demand. / Build International policy engagement with International institutions to support the UN Secretary General’s Sustaining Peace Agenda as it turns to implementation over the next two years, with the OECD and European partners. / Evidence based advice (provided rapidly when events require) to DFID teams working on peace agreements or political changes e.g. Syria, Yemen and Burma teams on ceasefires or Zimbabwe and Lebanon on leadership changes. / Risks / PSRP has a detailed risk matrix and regularly reviews risks with partners. Risks to PSRP’s research programme have been highest when field work has been undertaken in challenging conflict situations. Risks reduced to ‘moderate’ when field work was completed. PSRP’s proven approach mitigates delivery risks (fieldwork delay, slow analysis, slow writing) whilst their strong networks mean that the research produced is likely to be relevant to both policy and academic interests. We assess that the risk rating for the extension will remain moderate.
What is the additional and total support the UK will Provide?
The proposed extension is for an extra £2.2 m over 2 years (added to the current contract of £4.4m over 4 years). This will bring DFID’s total investment to £6.6m by 2021. / DFID and PSRP have agreed that the extension will focus on areas where there is potential to generate the most powerful insights and policy and where demand is highest – such as Ceasefires; Peace Process Implementation mechanisms; and local agreements and their impact on national processes. / These priorities directly reflect demand from users, beneficiaries, and partners, including from DFID country offices.
What are the expected results?
The extension will build on the results framework in PSRP’s logframe, adding further milestones and further refining the strategy set out in the original Business Case. The outputs and detail below build on a proposal and budget provided by PSRP for the extension. DFID negotiated with PSRP to refine the scope of the proposal, to ensure it is operationally relevant and meets HMG needs and to ensure vfm. / Output I: The Peace Agreements Database and innovating digital technology for peace. / The peace agreements database has established Edinburgh University as a leader in the UK ‘peace-tech’ field. PSRP will develop further innovation through the extension, including: / Convening technology-providers with organisations working on conflict and violence data to further innovation in monitoring, research, and analysis. / Use ‘text mining’ methods on peace agreement texts and other tools to explore new methods in experimental research. / Explore development of a mobile app to aid interactive visualisation of peace negotiation options. / Output II: Research Publications / High quality research (measured in terms of number of working papers, peer reviewed journal articles, and citations) on the following topics (further details in Annexe A). / • Ceasefires / • Peace Process Implementation mechanisms / • Sequencing and trade- offs in peace processes / • Interim Transitions, power-sharing and inclusion / • local agreements and their impact on national processes; / • The roles of domestic military and political power-holders directly engaged in conflict (at local, sub-state and national levels) / • The role of social and civic groups, including those who are not aligned with the main conflict groupings; / • The role of international actors and organisations who intervene. / Output III: Uptake / Uptake is measured in terms of number of formal meetings with policy makers at which research is presented, web traffic data, media engagement, DFID country office engagement and policy focused events. This will include: / Support to those engaged in/with countries with ongoing violent conflicts (e.g. HMG officials, Mediators, UN, other international organisations and civil society partners). / PSRP will develop medium to long term evidence-based trajectories for peace processes based on the above research. This will include thematic papers drawing comparatively across peace processes, but also be responsive to specific issues and needs in each country context. It will also include papers directly addressing how innovation in sequencing, local agreements, and agreement implementation might address conflict. / Evidence will be relevant to a range of processes, but targeted in particular at: Ethiopia-Ogaden, Myanmar, South Sudan, Syria, Yemen and Afghanistan. / PSRP will use in-house capacity, experts with significant experience of peace processes (including those deployed in conflict settings), and research, to provide a forward support function to UN and HMG teams. Existing research will feed directly into peace processes and will draw back new data and material for PSRP researchers to analyse. / Further uptake from the research conducted to date. Outreach to further inform research design and questions, and to disseminate findings, would build on the existing demand from the OECD, UN (UN Women, UNDPA, and UNHDR), EU Mediation network, Nordic Women’s Mediators Network, and HMG. However, further links would be built with civil society groups in-country, through our partners CR and International IDEA. / Continue PSRP’s proven rapid advice service to DFID and HMG. This is responsive to teams’ questions and feeds into PSRP’s research strategy. PSRP often writes up rapid responses as public good policy briefs. Forward-deployed consultants would enable PSRP to better anticipate and prepare for issues which arise in the field. / On approval of the extension we would negotiate new milestones and delivery targets with PSRP, based on the existing Logframe.
What is the approach to implementation?
Management Structure and Governance / PSRP’s core team will continue into the extension period. PSRP’s Director is well regarded by FCO Research Analysts working on multi-lateral conflict. Her rapid advice on the Cyprus peace process informed the position of senior members of the FCO. When the Columbia peace deal looked under threat, due to an elected new administration, the parties cited her book and research on the legal status of the agreement to prevent it from collapsing. Feedback cites the high quality of her advice to colleagues working on Syria, Yemen, Zimbabwe, Lebanon and South Sudan, among others. / PSRP needs to maintain its existing staff capacity at the University of Edinburgh if it is to further develop PSRP’s highest-performing elements and ensure the legacy of the database beyond the end of the extension period (2021). / This next phase of work will have a clear operational component, bringing in experts who are able to translate research into practice and develop long term plans for each country, drawing on the comparative research available through the database. / Three partners will be retained from the original consortium: Conciliation Resources, International IDEA and the Austrian Study Centre for Peace and Conflict Resolution. (Their roles are outlined in section. These are high performing partners who have been retained to undertake the following roles. / Conciliation Resources will facilitate joint analysis from its London base; support uptake in the UK, and with civil society partners; plus consultancy inputs relating to Ethiopia-Ogaden and Afghanistan (see below). / International IDEA will support uptake at UN Head Quarters and in the MENA region. / ASPR will continue uptake work in Europe, with OECD and with DFID South Sudan. / PSRP will continue to work with ISS on uptake of the research completed in phase 1 but will not be implementing new research as part of the extension. / The research budget has been halved and therefore other consortium partners will not be continued. These include: The Rift Valley Institute and The Transitional Justice Institute (TJI) University of Ulster. Both partners performed well and completed agreed research plans. / In response to growing demand from country offices, PSRP will deliver diverse uptake activities including: rolling context analysis, cross-sector seminars, political analysis training and advice, and where possible embed key researchers for short spans of time in country offices or with UN Mediators in order to observe the day-to-day practice of peace processes. / The established PSRP management structure, steering committee and advisory board will be retained for the extension, but with a revised membership that reflects the new scaled down consortium. / Value for Money (VfM) / PSRP is a proven, highly effective research programme that bridges the divide between academic research and operational needs. There is a high DFID demand for further research and engagement, which paves the way for future uptake and impact. / Uptake and impact are the most potent drivers of VfM in social research as relatively small research input costs can translate into changes in policy and practice. These can have profound real world impacts (e.g. more effective peace agreements), and make HMG’s large operational investments to be more effective. Extending PSRP’s current contract to fund further research, and scale up uptake and impact activities, therefore offers good VfM. / The Core Management Team ensures VfM across the programme, with a focus on both quality and cost. Cost savings are found each year and PSRP has a good budget to expenditure ratio. PSRP has attracted additional funding from the British Academy, UN and ESRC, which has reduced unit costs. PSRP has also reduced travel and venue costs by using new technology to communicate with partners or by using UoE premises pro bono. / A detailed budget has been provided by PSRP. Key costs in the extension will be: / Retaining the core University of Edinburgh (UoE) staff members working on the peace agreements database and research. / Extending the current development officer role to full time and adding a new communications role to support the uptake work in the final two years. / Additional input days of computer and design technology support to co-development innovative tools and products from the database. / Retaining three of the current consortium partners: Conciliation Resources; International IDEA, and the Austrian Study Centre for Peace and Conflict Resolution (ASPR): / All three partners have recognised country experts and research capability that are complementary to the database. / Four consultant roles to provide the forward support to country-level mediation and peace processes in Yemen, Syria, Burma, Ethiopia-Ogaden and South Sudan. / Costs for uptake workshops, travel, and design and print of publications. / Costs for responsible closure at the end of the two years. This will involve future-proofing the database, and archiving the PSRP website and publications. / The extension will ensure further value for money from the original PSRP investment as the research will be based upon an established network and proven approach to research delivery and quality management. / PSRP’s significant set-up costs will not be required in the extension phase, allowing the proportion of funding dedicated to primary research (i.e. over and above core team salaries and communications, uptake and other activities) to rise from 38% to 53%. / DFID will monitor the programme in line with logframe, quarterly and Annual Reviews. / PSRP’s performance on VfM is strong. The expected programme costs were set out in the contract and work plan are in line with expectations. The Financial Regulations of the University of Edinburgh provide a strong framework and include a range of value for money provisions on, amongst other areas, procurement, travel and subsistence.
Describe any key changes to the original business case?
The proposed extension remains within the scope the original Business Case and Terms of Reference. The only significant change is the shift from analytical towards operationally focused research as well as a focus on the highest performing aspects of PSRP’s work. / There is already provision under the Terms of Reference to extend the contract by up to one year. Considerably added value will however be achieved by continuing the programme beyond this timeframe to enable the policy and uptake work with country offices and the UN to take place (Outputs 2 and 3). This is where policy demand is highest and where the greatest value from the extension could be achieved. The time lines for the country peace processes and the UN and OECD policy processes require research and uptake to continue into 2021. If only one year was approved the extension would have to focus on the peace agreements database analysis only (Output 1) which would severely reduce the likely impact and value of the extension.

Annex A / Summary of Programmes for Extension (PSRP Phase2) / Ceasefires and inclusion: PA-X has revealed the extensive practice of developing and implementing ceasefires. PSRP has already published an outline of the different elements that can be included in ceasefires and how they are put together. This will be developed into a more detailed tool kit for practioners. The outline is already being used by DFID teams in Yemen, Burma and Syria and is sought by other actors, for example, PSRP met with US National Security Agency representatives to discuss mechanisms for monitoring ceasefires remotely. / Systematic analysis of global ceasefire patterns is a gap in the literature. PSRP’s extension will address this by developing a dedicated ‘sub’ database of ceasefires. / Accompanying research will explore the following questions: / Who negotiates ceasefires: army chiefs, with or without what command authorisation; what civilian levels / international brokers are involved? What is the overlap with humanitarian issues? / How are women or other citizen groups involved, and how do they get access? / How and when do ceasefires set pathways for how the conflict is to be resolved, and what actors will be understood to be key to its resolution, and how inclusion more generally is addressed? / What monitoring mechanisms do ceasefires put in place? / What is good practice in terms of designing a ceasefire that works? / Interim Transitions, power-sharing and inclusion: PSRP research has already revealed the complexity of interim transitions. This work would produce an extended report/ journal article on interim transitions, and related responsive work on power-sharing options. In particular it would look at: / Modalities for legally ‘constituting’ the interim transition, and decisions over who is included; / Staging and sequencing of the transition; / The agendas for transitional governments, and the relationship to civic processes; / How these arrangements tend to fall apart, and why, and Options for putting them back together again: tent widening, new civic processes, alternative processes / Local agreements, Sub-national processes, and National Processes. / In exploring the relationship between local and national peace processes PA-X research has revealed diverse different types of local agreements and how they take shape. These have received little attention to date in global comparative research. PSRP will explore how these local agreements come about and what role they play in relation to national peace. Some initial case studies indicate that they are critical to national peace (Autessere 2010, on DRC). Building on an initial paper produced by PSRP for the Oslo Forum for Mediators, PSRP will explore: / What sorts of ‘local agreement’ are signed in peace processes, and why? / Who initiates and what type of actor is involved? / When and how do they relate to the sequencing of wider national peace efforts? / What types of conflict do they arise in, and at what stage?? / What do these agreements typically include, what is their particular character? / How sustainable are they? / Implementation challenges and inclusion. / PSRP’s existing research indicates that implementation of peace agreements, and in particular the transition from ‘elite inclusion’ (horizontal inclusion) to ‘broader social inclusion’ (vertical inclusion) is very difficult to achieve. The breakdown of peace agreements forms a major challenge for conflict prevention. PSRP will disseminate these findings and refine research on measuring implementation of agreements. This will likely include the following: / Role of Constitutional/Supreme Courts in making or breaking peace settlements: the international community often supports a strong independent judiciary as part of its ‘rule of law’ commitments. However, judges in the early stage of a post-conflict or post-transition scenario play a quite different role in either consolidating the political settlement and its new commitments to inclusion, or re-negotiating it, or even acting as ‘spoilers’. / This project would build on existing PA-X research which identified all settings where a court has been invited to strike down or amend a peace settlement. The ‘Edinburgh Dialogues’ mechanism with International IDEA (which has produced influential reports for PSRP) will convene leading judges from relevant Courts to discuss and document the peculiarities of these cases. / Peace agreement monitoring: peace agreements often introduce third party monitoring. Yet, there has been little appraisal of the options that exist for this, how effective they are, and whether there are concepts of good practice which could be applied more routinely. / The project will commission papers from leading experts in the global south, and from people involved in monitoring implementation. These will aim to improve understanding of monitoring options, their relative strengths and weaknesses, types of international support needed, and models of good practice. PSRP will explore how political-military actors, civic actors, and international actors are involved in monitoring arrangements. / Continuing measurement work and dissemination: PSRP will continue to disseminate existing research and in particular to promote the innovative measurement tools and methodologies that it has applied during phase 1 of the research.