Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Yemen Social Fund for Development (SFD)
Programme Value: £100,000,000		Review Date: January 2017
Programme Code: 201427	Start Date: 10/05/2010	End Date: 31/12/ 2017

Summary of Programme Performance
Year	2011	2012	2013	2014	2015	2016	2017
Programme Score	n/a	A	A	A	A	A
Risk Rating	High	High	Medium	Medium	Medium	Severe

Summary of progress and lessons learnt since last review

Introduction

At the end of 2015, and following dialogue with key donors including DFID and the World Bank, SFD decided to extend its Phase IV by two years (January 2016-December 2017). This review therefore covers the first year of the extension.

This review was completed by the 31st January 2016 as required by DFID’s programme management rules, in the midst of a major ongoing humanitarian crisis and open conflict in Yemen. The review is based on: the Social Fund for Development’s (SFD’s) two Progress Reports (Sept 2015-March 2016; and April-September 2016) as well as end year budget and result figures; information provided in regular dialogue throughout the year; periodic exchanges with other donors; and on-going dialogue through the year and in the preparation of this Annual Review (AR).

Summary of Progress and Lessons Learnt

Cumulatively, between January 2011 and September 2016, SFD has completed 4,730 projects, with a cost of about USD 661 million; not including SFD’s operation expenses and studies and evaluations cost. The estimated number of people who directly benefited from these interventions and from creating access to services is about 7.36 million, of whom 3.98 million were women. During the same period, completed and ongoing projects have generated temporary employment of about 31.4 million workdays across all sectors.

There had been a steady increase in the number of active field projects during April-July 2016, when the number of active projects reached 433. In August 2016, however, some projects were completed and some donors (such as the Islamic Development Bank) suspended disbursement leading to projects being paused. This resulted in a drop of the number of active projects. According to the progress report, DFID support represents the largest share of these active projects (about 38 percent) followed by the World Bank through UNDP (19 percent), and the German government through KfW (18 percent).
Given the ongoing active conflict, SFD have continued to operate under very difficult working conditions though there have been improvements. The Taiz Branch Office (BO) has remained closed throughout due to the on-going conflict in the city with the project portfolio managed by the Ibb BO. Certain key staff (notably the Heads of the M&E, and the Education, Health and Social Protection Units) have continued to work remotely from third countries. On the other hand, the head of the Water and Environment Unit was able to return to Sana’a. Following relocation in 2015 of headquarters staff to a safer, temporary office in Sana’a, SFD were also able to move back to their main building.

Other major challenges have included concerns around the stability of the banking sector, funding (including the recent suspension of Arab Fund and Islamic Development Bank funding due to the Government of Yemen falling behind in arrears to both organisations) and an expansion of needs for the services SFD provides due to the deteriorating humanitarian situation. SFD has remained resilient and have responded in a flexible and pragmatic manner to these challenges. They have adapted their existing risk management strategies and used their local knowledge and networks to deliver where conditions and funding have allowed. Along with this increase in active projects one of those most positive developments over the last year has been a much improved funding situation for the organisation. A new World Bank emergency programme (channelled via UNDP) for USD$35 million became operational in August, with new funding also coming from the German and Dutch governments, and agreements for US and EU funding from 2017 onwards. Most significantly, up to $180million in further support was agreed by the World Bank in January 2016.

Despite the positive funding outlook SFD only received $55.9 million in 2016 compared to the originally expected amount of $210 million and later revised forecast of $97 million. There are two key lessons to be learned here:
1. In retrospect, even the medium case budget scenario was highly optimistic and a more realistic (but still challenging) scenario would have been the low case one.
2. SFD should have proactively informed its donor partners of the funding shortfall and the effect this would have on its results for 2016.

The coming year will be an important one for SFD as it enters the second - and final - year of extended Phase IV and as Yemen (unfortunately) appears to be settling into a protracted crisis characterised by active conflict, increasing fragmentation and significantly worsened living conditions for the great majority of the Yemeni population. SFD, in dialogue with its donor partners, will need to decide on the way forward. A meeting with partners will be held in early March in Amman.

Summary of recommendations for the next year

For SFD	For DFID
Strategy
Sustain and increase current donor support through demonstration of strong performance. Work towards unlocking suspended donor funds	Promote funding to SFD, be it unlocking suspended funding, encouraging sustained and increased support from existing donors and encouraging new donors
Submit plans for SFD’s operations beyond 2017 by June 2017 to allow donors sufficient time for planning ahead of 2018	Push for an SFD plan/strategy for 2018 and beyond at the March 2017 SFD-donor meeting
Programme Management
Demonstrate to DFID effective communication and application of fraud policies to downstream partners	Ensure SFD are effectively communicating their fraud policies to downstream partners, enact a sample check process on procurement and tender documents, and further explore SFD’s financial delivery chain to identify potentially weak areas
Provide DFID with a sample of downstream due diligence assessments	Undertake an effectiveness review on a sample of due diligence assessments of SFD partners
Continue positive cooperation with DFID’s Independent Monitoring Programme, including implementing recommendations of the WASH study and any recommendations arising from new study on LIWP	Continue to make the best use of the Independent Monitoring Programme to gain assurance of delivery of SFD’s work. / Agree with SFD a system for sharing results of IM studies with other donors to build confidence and help drive improvements in SFD practice. / Seek to better understand other donors’ monitoring regimes, including use of Independent Monitoring, and to co-ordinate on and share lessons from these
SFD to significantly improve format and content of 6-monthly reports to include: i) include standalone targets and results for annual reporting period; ii) analysis of results, including explanation of funding allocations over the period; and iii) more narrative on wider context. / SFD should explore with donors whether a switch to bi-annual calendar year reporting (January-June; July-December) would be more effective
	In consultation with the Statistics and Results Adviser, to review the framework and methodology we use to measure SFD’s performance and implement a revised framework in time for the next review.
SFD should update DFID on their relationship with local authorities and stakeholders with respect to planning for construction, rehabilitation and handover of facilities.
SFD should update DFID on how it calculates its education enrolment results in the context of internal population movements which have greatly increased over the past year.
	Understand the control regime that donors as well as UNDP (manager of various donor programmes with SFD) are applying to their funding, including their use of independent monitoring. We should align our control regimes to provide maximum assurance and avoid duplication
	DFID should continue to continue to monitor the micro-finance sector in Yemen as well as progress in use and scaling up of mobile phone banking. This requires continued monitoring of the Small and Microenterprise (SME) sector. / DFID should increase its engagement with SFD’s Small and Microenterprise Development Unit (SMED) and the Small and Microenterprise Promotion Services (SMEPS) / DFID officials should continue to engage with the IFC on issues affecting the private sector, banking system and MFIs
Share findings of community-level surveys on SFD operations
	DFID should review the effectiveness of SFD’s engagement with the humanitarian sector and vice versa, and seek to increase understanding of SFD’s role and activities within the international community
Remain alert to the potential for increased attempts at aid diversion and/or political interference due to new funding coming on stream and, with other donors at the upcoming donor meetings in Amman, discuss additional controls that can be developed. Measures to avoid organisational overstretch should also be agreed.
Both parties should ensure increased regular communication, including technical discussions with sectoral staff and greater tracking of output progress throughout the year
Governance
SFD to continue to regularly update on status of Board of Directors		Discuss governance issues, including role and status of the Board of Directors, at the March 2017 SFD-donor meeting in Amman. Continue to keep SFD’s governance structures under review
Financial Management
Both parties should continue to closely monitor the status of the Yemeni banking and financial system in order to mitigate any developing risks
Ensure that all financial assurance documents (i.e. annual audit statements) are received by donors in a timely manner	Ensure a clear and reliable payment forecast is given to SFD at the beginning of the new Financial Year to enable SFD to plan effectively

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Business Case
DevTracker Link to Log frame:	Log frame

Wider Context

Yemen’s conflict has lasted nearly two years with the humanitarian situation continuing to deteriorate, now ranking amongst one of the most serious in the world. The UN estimates that 21.2 million people – over 80% of the population – are in need of humanitarian assistance. Severe food insecurity has become widespread in Yemen with more than half of the population living in ‘crisis’ or ‘emergency’ levels of food insecurity and WFP warning that, as of January 2017, there are only 3 months of wheat stock, and 3.5 months of sugar stock, left in the country. The conflict continues to hamper the provision of basic services, with the health system overstretched and the recent outbreak of cholera leading to 180 confirmed cases and 15,468 suspected cases. The Social Welfare Fund (the government’s cash transfer programme) has not made payments to its’ 8 million beneficiaries (among the poorest in the country) since early 2015. The United Nations Humanitarian Coordinator for Yemen has stated that over 10,000 have been killed in the conflict and over 2 million people are internally displaced. In response to the crisis, the UK has committed £103 million in humanitarian funding for 2016/17.

The ongoing conflict has also continued to lead to economic deterioration. Yemen is now at risk of an economic collapse which will severely exacerbate the humanitarian crisis and cause lasting structural damage to the economy. According to the International Monetary Fund (IMF), Yemen's economy shrank by more than any other country in 2015 (-28%).

Peace talks continue to be a top priority, with a political solution being the only way to bring long-term stability to Yemen and end the conflict. The UK has continued to strongly support the work of UN Special Envoy, Ismail Ould Cheikh Ahmed, and his efforts in working with all parties to bring about peace in Yemen. The latest round of formal peace talks took place during the summer of 2016 in Kuwait with the international diplomatic emphasis currently being on ensuring all parties to the conflict renew their commitment to the Cessation of Hostilities, engage constructively with the UN-established De-escalation and Coordination Committee and return to negotiations so that the conflict can be resolved.

Funding

At the end of 2015, in consultation with its donor partners, SFD decided to extend its current Phase IV (2011-2015) by two years (Jan 2016-Dec 2017). The extension proposal includes three possible funding scenarios and SFD decided to base their plans on a “medium case” scenario with a budget of $453 million of which $419 million was for projects. For 2016, the budget for programmes amounted to approximately $210 million. This was predicated, among other things, on the assumption that funds from donors such as the World Bank, Saudi Fund and Kuwait Fund would be unsuspended. In retrospect, the unsuspension of these funds was premised on an overly hopeful assumption that the conflict would abate and that Yemen would enter a phase of early recovery. In recognition that these funds were not going to be unsuspended, SFD revised down their Results Framework 2016 milestones in May 2016 on the basis of an expected $97 million being received for 2016. However by December 2016, SFD had only received just under $56 million, representing 27% of total funds originally planned and 57.5% of funds as revised in the May 2016 Results Framework. Scoring in this Annual Review has proportionally taken into account this funding deficit.

Furthermore, with the exception of DFID’s funding, funds available were mostly earmarked to LIWP (cash for works), water, health and education.  Because DFID contribution is un-earmarked, SFD were able to flexibly allocate across sectors as needed. We note that DFID’s first disbursement came on stream almost halfway through the year (in April 2016). Lastly, SFD have not proactively informed its donor partners (including DFID) on the effect the funding shortfall would have on its results for 2016. Donors should be kept regularly updated on this next year.

Since the last Annual Review (completed in January 2016), SFD’s funding outlook has improved overall. In September 2015, following the suspension of World Bank and Gulf funding, SFD’s active projects dropped to a low of 93 (a major reduction if compared to an average of around a 700 in more stable years). That figure reached a high of 284 in March 2016 but subsequently dropped slightly to 238 (worth $62 million) at the time of report due to the suspension of Islamic Development Bank and Arab Fund funding as a result of the Government of Yemen falling in arrears on its regular debt repayments to these organisations for historical lending for development-focused projects. This overall improvement has been the result of both continued and new funding streams. A new World Bank emergency programme (channelled via UNDP) for $35 million became operational in August, with the Germans and Dutch governments continuing to fund SFD with large-scale support, Germany, for example, signing agreements for two new projects worth €10 million in November.

The outlook for 2017 and beyond also appears brighter. A two-year, $6m USAID grant (through UNDP) started operations in January 2017 and on 13 December 2016, the EU committed €32 million to Yemen mainly supporting SFD. Most notably up to $180 million in further support could also be provided by the World Bank (up until August 2019) as an extension of their emergency project. The latter however is subject to the Government of Yemen not falling in arrears on debt repayments to the World Bank, and is something we will be monitoring.

Operations

The improved funding situation means that operationally, despite a lot of challenges in the field, the trajectory is looking cautiously positive. Spend is accelerating across the organisation and is now up to $5m a month. Between March - September 2016, 44 new projects with an estimated cost of USD 15.2 million, had been approved.

SFD continue to be active in all 22 governorates though not all districts in each governorate. In their latest progress report, they calculated that there were districts with some degree of accessibility problems in nearly half (10 out of 22) of governorates: of the 333 districts in Yemen, 20 were completely inaccessible, 24 were partially inaccessible, and 18 had difficult access for a total of 172 districts. The governorates with the highest concentration of accessibility problems (expressed as a percentage of their districts) were: Sa’adah (86%), Al Jawf (75%) and Taiz (65%); these are followed by Al-Baidha (55%) and Al-Dhale (44%).

As covered above, the ongoing conflict has meant that SFD have continued to operate under very difficult working conditions. The Taiz Branch Office (BO) has remained closed due to the on-going conflict in the city with the project portfolio managed by the Ibb BO. Certain key staff (notably the Heads of the M&E and the Health, Education and Social Protection Units) have continued to work remotely from third countries.

DFID’s programme of support

DFID’s current programme of support to the Yemen Social Fund for Development (SFD) (£100m to SFD’s Phase IV 2011-2015) was originally planned to end on 31 December 2015. However the sharp escalation of the conflict in March 2015 had a significant impact on SFD’s ability to operate and our original planned disbursement schedule. In response to the crisis and following consultations with DFID, the World Bank and other donors, in late 2015 SFD decided to extend Phase IV by two years (1 January 2016 - 31 December 2017). Accordingly, we agreed to an initial 12 month, no-cost extension of our support to 31 December 2016.

We have made three disbursements this financial year (£3 million in April, £4 million in September and £1.5 million in December) totalling £8.5 million. At the end of this financial year, £3.14 million of committed funds will remain outstanding from our £100 million commitment to SFD and we have agreed a further no cost extension to 31 December 2017. We intend, subject to Ministerial approval, to agree new additional funding to keep our support at least at current levels in 2017-18. In line with our commitment to ensure the survival of key institutions for the resilience and recovery of Yemen, we will develop plans to continue to support SFD, subject to Ministerial approval, with a multi-year programme of support for 2018 onwards.

Assurance

DFID undertook a Due Diligence Assessment on SFD in April 2016 which concluded that the organisation has the capacity and capability to deliver DFID support. A separate, EU-commissioned assessment by the independent auditors Grant Thornton likewise concluded earlier this year that SFD has the processes and oversight in place to manage EU funds.

DFID Yemen’s Independent Monitoring Programme continues to provide third-party assurance on the delivery of SFD’s work and has so far verified two sets of SFD-supported projects (in Al-Mahra Governorate and a selection of projects on water and sanitation). These exercises confirmed that SFD is delivering the intended projects and identified areas for operational improvement which SFD have followed up on. A further study on SFD’s Labour Intensive Works Programme (LIWP) has been designed and field work will commence in February 2016 with a report expected in April 2016.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

This has been another very challenging year for SFD. The prospects of a peace deal are slim while the humanitarian crisis has deepened. Furthermore, as noted above, SFD received only 57% of the funding expected under the medium case budget scenario. Nonetheless, SFD has continued to show resilience and has been able to continue activities in most parts of the country. Despite the challenges, we judge overall progress towards the outcome to be broadly on track.

Overall output score and description - A: Outputs met expectation
We have scored SFD an A for 2016 in light of the limited funding received. As noted above, SFD revised down their Results Framework 2016 milestones in May 2016 on the basis of an expected $97 million being received for 2016. However by December 2016, they had only received just under $56 million, representing 57.5% of funds expected. Scoring in this Annual Review has proportionally taken into account this funding deficit (as set out in the far right hand column of the detailed output scoring tables). SFD did not proactively articulate the implications of funding shortfall for results delivery throughout the year meaning that the scoring process has been complicated and time consuming. It will be critical for SFD to actively communicate the implications of any funding shortfall in 2017 and keep donors informed of in year progress so that performance can be effectively tracked.
Output	Weighting	Score
Community and Local Development Program: Basic services improved	70%	A
Small and Micro Enterprises Development Program: Economic opportunities created	5%	A+
Labour Intensive Works Program: Reduced vulnerability for the poor	20%	B
Capacity Building: Stakeholders capable and empowered	5%	C
Overall	100%	A

Key lessons and actions

SFD’s Strategy Paper for extending Phase IV noted the deep humanitarian crisis and a desire to contribute to the humanitarian effort whilst retaining SFD’s mandate as a development organisation with a mandate to operate across the country. The strategy was also premised on the hope that Yemen would be on a more positive trajectory by the second year of the extension. Unfortunately this has not been the case, with Yemen entering into a protracted crisis (conflict, humanitarian, political). As set out above, this continues to pose operational challenges in terms of access and increased caseload. The longer the conflict continues the more SFD’s resilience as an institution will be tested.

In many respects, however, SFD’s position has greatly improved in 2016. New funding, an increase in the number of active projects and the continuation of operations despite the ongoing conflict, mark major achievements given the concerns last year about the future outlook for SFD and the ongoing deterioration of the operating context. SFD’s flexible approach and proactive risk mitigation measures have been critical in achieving this, helping them remain active in an extremely challenging context. DFID and SFD engagement with current and potential donors, as well as regular DFID payments each quarter, has also been helpful in improving the funding situation for SFD.

DFID’s sustained support for SFD as well as regular messaging about SFD to the international community has helped maintain interest in SFD. Time spent lobbying the World Bank to find creative solutions for resuming funding to SFD as well as briefing the United States (who had never funded SFD before) have resulted in concrete support for SFD. While labour-intensive, these efforts have been well spent.

Similarly, regular and frequent dialogue with SFD has been mutually beneficial: it has informed our understanding of the situation on the ground and SFD’s understanding of our own operating context; and has allowed exchange of ideas on the way forward. The one important gap is that SFD have not regularly and explicitly communicated to DFID the concrete implications of reduced funding on achievement of its targets.

Quality of reporting, after improvements in 2014 and the early part of 2015, has steadily dropped in 2016. Delivery of the last progress report (covering April-Sept 2016) was delayed until early December and SFD’s response to DFID’s questions sent at the end of December arrived a week before the deadline for this Annual Review. We recommend that reporting and broader M&E be tabled at the March 2017 SFD-donor meeting in Amman, and also that DFID review the framework and methodology used to measure and track SFD’s performance with a view to agreeing and implementing a revised framework in time for the next review.

The conflict – and the subsequent suspension of World Bank disbursements to Yemen - has meant that the annual, formal Joint Donor Performance Review (JDRs) (co-hosted by the World Bank and SFD) have not been possible. The last SFD-donor meeting was held in Amman in November 2015 and, although not a formal review, was immensely useful. DFID advocated for a meeting in 2016 but due to logistical and resource constraints this was not possible. A meeting will now be held in early March 2017 in Amman.

In its extension proposal, SFD noted that during the emergency phase it would work closely with the humanitarian agencies who would take the lead in responding to the needs of IDP populations, with SFD assisting in building temporary or longer-term structures to ensure access to improved water sources, adequate sanitation facilities, and education and recreational spaces for children. SFD participates in the UN Cluster system, specifically in the Health, Protection, Nutrition and Education clusters. Midway through the extension, it is now opportune to review this collaboration and identify what is working and any gaps.

Significant challenges remain. These can be broken down into two categories: 1) operational performance and management, and; 2) long-term strategy.

Operational performance and management

Whilst SFD’s proactive management of emerging risks (such as the measures taken with banks to mitigate the consequences of any cash crisis) and securing of significant funding should be applauded SFD also need to continue to ensure that operational performance and management is continually improved. SFD seems to have struggled with reporting this year and, after improvements in 2015, have reverted back to a format which is primarily based on quantitative data and limited analysis. This makes it difficult to assess progress on substantive issues such as gender mainstreaming and quality of targeting among others, and to understand reasons behind given results. Furthermore, the six-monthly reports are not aligned with the calendar year.

On the DFID side, the challenges of remote management should be acknowledged. It is now over two years since DFID staff have been based in country. The longer this situation continues the greater the loss of institutional and contextual knowledge will be. The forthcoming SFD-donor meeting is a good opportunity to deepen relationships and understanding however this cannot be a substitute. An increased schedule of engagement, including the proposed sectoral or thematic meetings with specific units will help somewhat, as will the regular calls with SFD Branch Offices .

Long-term strategy

SFD has now entered the second and last year of the extension to Phase IV and needs to develop a strategy for 2018 and beyond, in discussion and agreement with its partners. Among a number of substantive issues, SFD will need to consider: i) its’ role in context of the ongoing humanitarian emergency and the challenge of collaboration / coordination with humanitarian actors whilst retaining independent and neutral mandate; ii) the most appropriate measures to respond to what is now a protracted crisis and long-term conflict which has exacerbated pre-existing, deep-seated vulnerabilities; iii) the impact of the ongoing conflict; iv) funding; v) staff retention; vi) its’ politically neutral mandate; and vii) relationship with GoY in general and via the SFD Board.

Wirth respect to funding specifically, although new funding (including the $180 million of World Bank Additional Financing to the Emergency Crisis Response Project approved in July 2016 via UNDP approved by the World Bank Board on 17/01/2016) looks to have secured the short-to-medium term financial future of SFD, SFD needs to develop a funding strategy for the longer-term including what is realistic and achievable given that they did not receive the planned for budget under the medium-case scenario.

Has the logframe been updated since the last review?

Yes. SFD updated their Results Framework (RF) to cover the two additional years (2016 and 2017). As our Logframe is a subset of SFD’s RF, we have added new 2016 targets for the extended programme. No indicators or weightings have been changed. For institutional memory, we have retained those indicators whose activities were either completed in previous years (2.2 and 2.3) or did not start as planned (3.1 and 3.3 which SFD decided to deprioritise when conflict started in favour of short-term workfare assistance i.e. cash for works):

- Output Indicator 2.2: Enabling Environment: Credit bureau legislation/regulation submitted to Government
- Output Indicator 2.3: Enabling Environment: Code of Conduct regarding Consumer Protection adopted by Yemen Microfinance Network
- Output Indicator 3.1: Number of people directly benefiting from multi-year workfare assistance in rural areas (not operating in urban areas)
- Output Indicator 3.3: Number of working days employment created under workfare assistance program for: Multi-year activities in rural areas

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Community and Local Development Program: Basic services improved
Output number per LF		1	Output Score	A
Risk:		Severe	Impact weighting (%):	70
Risk revised since last AR?		N	Impact weighting % revised since last AR?	No

Indicator(s)		2016 Milestones	Achieved 2015	Achieved 2016	% of target reached	Revised Milestone[1] / % reached	Score
1.1 Education access: Number of classrooms constructed or rehabilitated	Cumulative	10,498	9,157	9,715	(93%)
	In Year	1,341		558	(42%)	771 / 72%	C
1.2 Education quality: Number of formal teachers trained (8 days training, sex disaggregated)	Cumulative	232 male, / 226 female	232 male / 226 female	264 male / 226 female	107%
	In Year	0		32 male / 0 female	No target set: unexpected increase	No target set : unexpected increase	A
1.3 Rural roads access: Total length of roads improved/built (km)	Cumulative	1,348	1,168[2]	1,306	97%
	In Year	180		138	77%	103 / / 126%	A+
1.4 Number of people provided with access to improved water sources (within 30 mins walking distance or less)	Cumulative	981,426	774,251	941,801	96%
	In Year	207,175		167,550	86%	119,126 / 141%	A+
1.5 Sanitation access: Number of people with access to improved sanitation facilities	Cumulative	323,955	232,725	279,232	86%
	In Year	91,230		46,507	51%	52,457 / 89%	B
1.6 Number of Primary Health Care workers qualified (3 year qualification)	Cumulative	296 male / 242 female	266 male / 220 female	271 male / 274 female	101%
	In Year	30 male / 22 female		5 male / 54 female	113%	30 / / 203%	A++
[1] Based proportionately on the £59 million of funding actually received by December 2016, (only 57% of the expected amount when the 2016 milestones were set).
[2] Incorrectly reported by SFD in 2015 as having achieved1,723.

Key Points

As can be seen from the results above, with the exception of indicator 1.6, SFD has delivered less than planned against the 2016 targets. This would have scored SFD a B (Outputs moderately did not meet expectation). As this underperformance is mainly due to the fact that SFD received just under 60% of the expected funding, our judgment is that we should measure performance against reduced milestones for 2016 (shown in the fifth column of the table above and based on proportional reductions in line with the funding shortfall). Under this scenario, on balance we have awarded SFD an A (met expectations).
SFD reports that they are members of the Health, Protection, Nutrition and Education Clusters, the coordination mechanisms for emergency responses. They are sharing their data and information as well as drawing on humanitarian data to inform their delivery as well as progress reporting. This is welcome as it is important that SFD and the humanitarian community mutually interact and coordinate. SFD had highlighted this interface in their Phase IV extension proposal. It is recommended that DFID: 1) find out from SFD more detail on how this is working in practice; and 2) in parallel, ask the DFID Yemen Humanitarian Team to assess via their linkages to clusters coordinators the nature of SFD’s engagement as well as whether and how cluster coordinators are proactively ensuring SFD participation.

Education
As set out in SFD’s extension proposal, in a conflict context it is essential to work towards protecting education opportunities for children as well as to help create a somewhat more stable environment for children who are living such difficult circumstances. This is a sound approach though requires close coordination with local authorities as well as with humanitarian partners. SFD notes that it is a member of the Education Cluster and reports regular participation in its meetings. It also communicates with education emergency groups via WhatsApp where members get updated about MoE circulars and decisions and latest activities of civil society organizations
Since start of Phase IV in 2011 and as of September 2016, a total of 1,049 projects were completed and handed over to the Ministry of Education (MoE) with a total number of 6,638 new classrooms and 2,907 rehabilitated. During the period April-September, 32 infrastructure projects were completed with a total cost of USD 8.4 million.
Roads
The 2015 target was 1,300km and SFD reported achieving 1,723; this led to DFID scoring SFD as overachieving in last year’s Annual Review. However, the March-Sept 2016 progress report contains a footnote explaining that the figure of 1,723 included completed, under implementation and planned projects while the number of actual completed projects was in fact 1,168. This is problematic as it means SFD underperformed on this indicator in 2015. SFD noted that a footnote in the March-September 2015 report had explained what the figure represented and that they would only be able to provide a final figure in the March 2016 report. While DFID may have been missed this during the 2015 Annual Review, SFD should ensure to only put actually achieved results in the achieved columns of their Results Framework: if a figure is not available the achieved box should be left blank with a footnote explaining the absence of data.

Water and Sanitation

The latest progress report notes that in the period April-Sept 2016, 43 water projects entered completion phase. It also notes that 270 projects under implementation were suspended due to funding shortfall. The amount needed to implement, complete, and close these projects is significant (USD 86.7 million).In the same period, four sanitation projects entered completion phase while, due to a funding shortfall, 21 projects have been suspended, with an amount of USD 1.8 million needed to implement and close them.
Our Independent Monitoring verification study of SFD’s work on water and sanitation undertaken in late 2015/early 2016 identified a number of issues with the recording of data on sanitation projects and made a number of recommendations for improvements. In particular, since initiation of sanitation projects is contingent upon a completed water project (because a water supply is needed for sanitation activities), the study recommended that the Management Information System (MIS) accurately record completed water projects. SFD have responded proactively for example by creating new modules in their MIS. SFD has been rolling out improvements over the course of 2016. DFID will monitor their application via regular dialogue with SFD, including a catch up call on progress with their Head of Unit in March 2016.

In their latest progress report, SFD have flagged the challenges of capturing and recording the longer-term impact of completed water projects on the lives of the people as expressed via health, education, and economic status. The Water and Environment Unit has committed to develop guidelines for collecting and recording in the MIS information on indicators such as :
- number of students and absenteeism (classes and days) to be included in pre- and post- intervention survey format (impact on education):
- water fetching time, before and after intervention (time and efforts saved for women and girls):
- average expenses for treating family members for water borne diseases during a given period, before and after intervention (for health impact):
SFD will also train staff and consultants on how to collect and enter the data in the MIS. Health
SFD have overachieved their combined target for Output Indicator 1.6 and, when disaggregated by sex, have respectively over and underachieved on women and men trained. More widely, they have continued to construct, rehabilitate and furnish health facilities and centres.

Summary of responses to issues raised in previous annual reviews (where relevant)
Last year’s review recommended that SFD should ensure any decisions to build or rehabilitate education or health infrastructure be based on clear agreements for maintenance with relevant stakeholders. This has become ever more important given that such decisions will be partly determined by the conflict context and party by the current status of local authorities. SFD report that they continue to coordinate with local authorities and stakeholders. However at this half way stage it would be opportune to review, together with other donors. It is recommended that this be placed on the agenda at the March 2017 SFD-donor meeting in Amman.

The last review also recommended that DFID should monitor implementation in its regular meetings with SFD. We have continued to do so via our regular meetings with SFD, our IMP and periodic exchanges with other donors. However, we recognise that we may need more in depth discussions on specific sectors and also that we should seek to increase information sharing about performance with other donors.

Recommendations

While this output continues to be key, we recommend reviewing its weighting given that the LIWP output has become an area of increased focus by SFD and we expect it to continue to be so in the near future.

DFID should increase the level of engagement and dialogue with SFD and structure it around specific sector issues to allow for focussed and more technical discussion of performance.

SFD should update DFID on their relationship with local authorities and stakeholders with respect to planning for construction and rehabilitation of facilities. as well as handover

SFD should update DFID on how it calculates its education enrolment results in the context of internal population movements which have greatly increased over the past year.

Output Title	Small and Micro Enterprises Development Program: Economic opportunities created
Output number per LF		2	Output Score	A+
Risk:		Severe	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	No

Indicator(s)		Milestone 2016	Achieved 2015	Achieved 2016	% of target reached	Revised Milestone[3] / % reached	Score
2.1 Outreach Number of active borrowers: / - % female / - Number of additional branches in rural areas	In Year	90,000 Female - 50% Rural - 0	93,297 / Female - 71% / Rural – 0	90,416 / Female - 46% / Rural - 0	100% / 92%	51,750 / 174%	A+
2.4 Financial Sustainability: Number of MFIs that are financially sustainable	Cumulative	0	0	2	No target set: unexpected increase
	In Year	0		2	No target set: unexpected increase	No target set / unexpected increase	A+
[3] Based proportionately on the £59 million of funding actually received by December 2016, (only 57% of the expected amount when the 2016 milestones were set).

Key Points

Since March 2015 the microfinance sector has faced many challenges and these have continued in 2016. The rise of liquidity issues in the banking system has made it difficult for MFIs to disburse larger amounts of loans due liquidity limits set by banks. SFD report that the pace of work of the SMED Unit has steadily increased during 2016. SMED has continued to monitor its partner micro-finance institutions (MFIs) and to provide them financial and technical assistance. During the reporting period, disbursements have continued at a reasonable pace. Loans to partnering MFIs have reached a total amount of YER 800 million (equal to about USD 3.2 million[4]). A rescheduling plan for MFIs who defaulted on loan repayments to SFD during 2015 due to the conflict) has been put in place and, as of September 2016, all have had their loans rescheduled with most making regular repayments. Despite the crisis, MFIs are continuing to lend, except for Al-Awa'el MF in Taiz where armed clashes continue to disrupt operations, and have demonstrated a remarkable resilience and adaptability (discussed in the Project Completion Review for DFID Programme ‘Building Yemen's Investment Climate 2013-16’).
[4] 1 USD = YER 250 according to the official exchange rate set by the Yemen Central Bank.
SMED has also continued to work on a number of initiatives aimed at reviving the MF sector. The establishment of a Loan Guarantee Programme that would share the risk with MFIs when lending to those who do not have sufficient guarantees, is underway and a managing director has been hired. Preparatory work for the Takaful Fund (meant to refund all SME owners who have lost their businesses and homes due to the ongoing armed conflict, or have suffered death or physical injury) is at advanced stages: an operational and policy manual has been approved and, in preparation for compensation, SMED has been liaising with MFIs to collect all the cases. This offers some semblance of reassurance to some of those affected by the conflict.
Mobile phone banking in Yemen has become operational through Al Kureimi Islamic Microfinance Bank (one of the MFIs that SFD helped establish and works with). The Central Bank of Yemen gave final approval in July 2016 after testing was successful. Several MFIs have already subscribed to the service through Al Kureimi, and are expected to make wider use of it.
With respect to Output Indicator 2.1, SFD has over-reached its target of 90,000 which was lower than the previous year, because the economic situation has forced many potential borrowers away, or forced some borrowers to default. The target for Output Indicator 2.4 was zero. As above, the indicators have had to adjust to reflect the current crisis: from the end of 2014 to September 2016, the proportion of MFI’s portfolio classed as ‘at risk’ has increased from less than 5% to 54.6%. This feeds into a broader concern about the banking sector, which entered the crisis with a loan book that was highly vulnerable to defaults: according to the IMF, around 22% of bank loans were not being properly serviced by their customers. But the majority of MFIs have adapted to the new environment by offering different products and shifting the focus of their operations to rural and agriculture finance. SMED’s work therefore remains important to maintain the sector’s resilience and support activity that can still continue. Nevertheless, in a post-conflict scenario, donors may face a very different microfinance sector, necessitating a more strategic, systemic and wide reaching approach to donor support.
We have overall scored this output an A (achieved expectations).
Summary of responses to issues raised in previous annual reviews (where relevant)

Last year’s Annual Review suggested a more strategic, systemic and wide reaching approach to donor support for the microfinance sector in a post-conflict scenario might be needed in the near future. It noted that SFD’s SMED had been laying the ground for a number of post-conflict initiatives for reviving the microfinance sector, including a Credit Guarantee Fund and supporting solidarity funds, and had produced a concept policy paper on capitalization of MFIs. The Annual Review further recommended that DFID should maintain active policy engagement with Yemeni institutions on these issues, and that DFID’s Economic Advisor should continue to develop relationships with SMED and SMEPS, both to support SFD’s current operations as well as to consider initiatives for the SME and microfinance sectors in the future. In doing this, DFID should incorporate lessons identified through its (closing) ‘Building Yemen’s Investment Climate programme

As reported above, SFD has made excellent progress on the abovementioned measures. DFID has continued to develop relationships both with SFD (SMED and SMEPS) as well as with other actors in Yemen.

Recommendations

DFID should continue to continue to monitor the state of the micro-finance sector in Yemen as well as the progress in use and scaling up of mobile phone banking. This necessarily requires continued monitoring of Yemen’s SME sector – a sector which, according to ILO employment data – appears to be operating increasingly informally.

DFID should further intensify its engagement with SFD (SMED and SMEP). DFID officials should also continue to engage with the International Finance Corporation (IFC), who remain engaged with issues affecting the private sector, banking system and MFIs.

Output Title	Labour Intensive Works Program: Reduced vulnerability for the poor
Output number per LF		3	Output Score	B
Risk:		Severe	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)		2016 Milestones	Achieved 2015	Achieved 2016	% of target reached	Revised Milestone[5] / % reached	Score
3.2 Number of people directly benefiting from short term workfare assistance in / - rural areas / - urban areas	Cumulative	Rural - 798,712 Urban - 479,571	Rural - 648,712 / Urban - 409,571	Rural - 725,617 / Urban - 426,026	91% / 89%
	In Year	Rural - 150,000 / Urban – 70,000		Rural - 76,905 / Urban - 16,455	51% / 24%	86,250 / 89% / 40,250 / 41%	C
3.4 Number of working days employment created under workfare assistance program for: / - Short term activities in rural areas / - Short term activities in urban areas	Cumulative	Rural - 10,000,000 Urban - 2,000,000	Rural – 9,000,000 / Urban - 1,800,000	Rural – 10,200,000 / Urban - 1,860,000	102% / 93%
	In Year	Rural - 1,000,000 / Urban - 200,000		Rural – 1,200,000 / Urban - 60,000	120% / 30%	575,000 / 209% / 115,000 / 52%	A+
3.5 Land: Total area of agricultural rehabilitated terraces and land (hectares)	Cumulative	4,741	4,441	4,579	97%
	In Year	300		138	46%	173 / / 80%	B
[5] Based proportionately on the £59 million of funding actually received by December 2016, (only 57% of the expected amount when the 2016 milestones were set).

Key Points
SFD have continued to prioritise short-term cash for work during this first year of the extension to Phase IV. They have sought to enhance its role in response to the ongoing crisis and to provide assistance to the largest potential number of displaced households. To extend its coverage, SFD has reduced the wage rate per family per 50 days worked from $700 to $500. This mechanism also serves to ensure self-targeting within benefiting communities. SFD is also delivering 85 percent of wages through banking services’ providers.

The LIWP has been significantly boosted by the activation in October 2016 of the World Bank’s Emergency Support Project channelled via UNDP of which $35 million is allocated for SFD. Of this amount, the majority is for LIWP.
We have scored this output as a B (Outputs moderately did not meet expectation)

There are two issues going forward:
1. As Yemen has entered into a protracted crisis, SFD should now review whether short-term cash for work interventions are still the best approach. Longer-term cash for works opportunities could be a more appropriate measure to help build household and community resilience but this needs to be assessed against other factors such a need and available resources
2. The wage rate is an important component of targeting and SFD have already adjusted it. In the context of ever increasing household and community vulnerability and given that SFD have entered the second year of the extension, SFD should now discuss with donors their approach to setting wage rates including any adjustments and related implications for resourcing as well as targeting

Summary of responses to issues raised in previous annual reviews (where relevant)
In last year’s review, we had recommended that SFD provide regular assessments of the feasibility of multi-year LIWP. Throughout the year, they have maintained the view that short-term cash for works continue to be the correct strategy.

Recommendations
- Given the increasing priority given to LIWP, DFID to review whether the logframe’s impact weighting rating is still correct
- SFD to update donors on its current thinking regarding short and long-term cash for works including targeting methodology. This should be placed on the agenda for the March 2017 meeting in Amman

Output Title	Capacity Building: Stakeholders capable and empowered
Output number per LF		4	Output Score	C
Risk:		Severe	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	No

Indicator(s)		2016 Milestones	Achieved 2015	Achieved 2016	% of target reached	Revised Milestone[6] / % reached	Score
4.1 Number of people trained in M&E, participatory methods, planning or other strategic information management (disaggregated by male, female and Local Authority (LA) members trained on Empowerment and Local Development programme	Cumulative	Male: 1,007 / Female: 782	Male: 887 Female: 702	Male: 887 / Female: 702	88% / 90%
	In Year	Male: 120 / Female: 80		Male: 0 / Female: 0	0% / 0%	69, 0% / 46, 0%	C
4.2 Number of village councils in pilot areas which are functioning effectively: / - meeting regularly / - wide participation (sex disaggregated) / - initiate self-help initiatives	Cumulative	4,283	3,983	4,316	101%
	In Year	300		333	111%	173, 192%	A+
4.3 Organisation supported / - Number of NGOs supported / - Number of local authorities supported / - Number of Community-Based Organisations formed	Cumulative	NGOs: 66 / LAs: 80 CBOs: 1,982	NGOs: 55 / LAs: 50 CBOs: 1,832	NGOs: 55 / LAs: 50 CBOs: 1,832	83% / 63% / 92%
	In Year	NGOs: 11 / LAs: 30 CBOs: 150		NGOs: 0 / LAs: 0 CBOs: 0	0% / 0% / 0%	6, 0% / 17, 0% / 86, 0%	C
[6] Based proportionately on the £59 million of funding actually received by December 2016, (only 57% of the expected amount when the 2016 milestones were set).

Key Points

SFD provides capacity building and organisational support to a wide range development partners at the local level. In the face of funding problems, SFD have chosen to prioritise other sectors so no there has been little or no progress against the main indicators. We agree with this approach.

The exception is the progress on Output Indicator 4.2 which has been good. This likely reflects the positive cumulative effect of SFD’s long-term work with local communities in establishing VCC. Indeed, the knock-on effect of this work is evidenced in the fact that Village Cooperative Councils (VCC) supported by SFD have continued to play an active role in self-help humanitarian and relief initiatives. SFD report that in the period March-September 2016, 921 self-help initiatives were implemented in 32 districts of 13 governorates with a total estimated cost of YER 234,138,893 (about $937,000) totally funded and implemented by communities.

We have scored this output a C (Outputs did not meet expectation).

Summary of responses to issues raised in previous annual reviews (where relevant)
NA

Recommendations

The upcoming SFD-donor meeting in Amman (March 2017) offers a good opportunity to discuss the performance of this output with SFD, including understanding its relative prioritisation compared to other outputs (such as water and health) where funding has been earmarked by other donors.

SFD should reconsider the measurement indicators of these outputs in order to capture quality and not just quantity and keep DFID updated on the status of this sector throughout 2017, including in their progress reports.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

SFD have now completed 4,730 projects at a cost of $661 million during their Phase IV. The estimated number of people directly benefiting from these interventions is 7.36 million, of which 3.98m are female. Completed and ongoing projects have generated 31.4 million person days of temporary employment. For a country with a population of only 27 million, SFD investments therefore continue to have a major impact on the country’s non-oil economy and particularly on the lives of the most vulnerable.

During the last year the deteriorating political, economic and security context in Yemen has continued to have a significant impact on SFD’s key cost drivers, as it has for many other institutions and individuals in Yemen. Whilst prices for key goods such as fuel and construction materials have moderated from some of the worst levels seen at the end of 2015, they continue to eat into SFD’s operational budgets. According to the World Food Programme, for example, the average price of wheat flour and diesel have consistently been 20-30% higher than pre-crisis levels during the six months to September 2016. Underneath this headline data, we see substantial variations in prices - Taiz is a particular hotspot for high prices - which will have contributed to cost variations in the work being done by SFD. As long as the conflict continues, critical cost drivers such as fuel will continue to challenge SFD operations.

Last year’s Annual Review cited funding pressures as the biggest challenge to SFD’s performance. With the increased number of new projects (to 238 as of September 2016) due to new funding and the prospect of significant additional new funding from the World Bank and others on the horizon this challenge has significantly reduced over the last year. As highlighted in the previous Annual Review SFD had enacted cost-saving measures such as cutting staff numbers by 20% and reducing salaries across the organisation by 15%. Due to the improved funding situation SFD have now been able to reverse the reductions in salaries; a move we support as it ensures the retention of key staff.

VfM performance compared to the original VfM proposition in the business case

When considering the VfM of DFID’s contribution to SFD, this Review applies the ‘3E’ principles: Economy, Efficiency, and Effectiveness. Following from the last review, DFID have considered the merits of different VFM indicators - the most relevant are discussed below alongside a qualitative discussion:

Economy: the operating costs associated with managing the Fund were originally set at 6.4% of total costs, which is positive compared with other mechanisms that pool donor funds (UN rates are typically set at 8%). The actual annual allocation in 2015, however, (according to the latest annual accounts) was 9.9%. This is a significant increase on the actual allocation for 2014 (3.2%). The reason for this increase is the significant reduction of funds available for SFD in 2015 (due to major donors suspending funding on the outbreak of the conflict). Likewise, SFD’s annual accounts also allow us to measure the project officer wage bill as a percentage of the total works and goods budget, giving us some idea of the relationship between input and output costs at a project level: between 2014 and 2015, the wage bill remained broadly unchanged, but the reduction in the overall budget meant the bill represented 4.4% of the total works budget, comparing to 1.1% in 2014.
The above is symptomatic of a general challenge on SFD’s ability to deliver economy of scale as central operating costs will remain stable in the face of the number of active projects dropping. This primarily raises questions on the scale of SFD operations: overall outgoings in 2015, for example, were only 27.5% of outgoings in 2014. The significant amounts of new funding coming on stream in 2016 should improve the overall assessment as the balance between operating costs and delivery returns to something more akin to 2014.

Efficiency: The last review highlighted the efficiency benefits of SFD as a means to pool and coordinate donor support to Yemen, but that suspended donor funding would represent a challenge. In 2016, that issue remains: aside from positive news of significant new funding coming from the World Bank, UNDP, EU, US and Germans (with lobbying and expertise on SFD being provided by DFID), widespread support to SFD remains constrained. The recent suspension of Arab Fund and Islamic Development Bank funding (due to the Government of Yemen falling behind in its arrears to both organisations) is a new concern, whilst other Gulf funding continues to remain locked. (Overall the active donor pool dropped from 21 in 2015 to 18 in 2016). Crucially, we do not see a growth in separate independent development projects that are not coordinated with others. The merits of SFD as an efficient mechanism to pool donor resources for development therefore remain.
Efficiency is also affected by the geographical laydown of projects, and the local level drivers affecting it. For example, Self-help Initiatives Implemented by Village Cooperative Councils (VCC) cost substantially more, on average, in Taiz than Ibb and Hajja.

Effectiveness can be measured by assessing progress against targets. Whilst in some areas, for example cash-for-work, progress has been strong many targets were not met in 2016. This is due to the deficit in funding SFD received in other donor funding over the year. Given that a total of $55.9 million was disbursed compared to the originally expected $205 million (27%) we calculate that had SFD received the full amount of funding the majority of targets would have been over-achieved.

Assessment of whether the programme continues to represent value for money

In line with the above measurements SFD’s value for money performance is considered satisfactory in comparison to the original VfM proposition in the business case, particularly given the context within which it is operating. DFID and SFD should, however, pay specific attention to SFD’s operating costs: if the above figure of 9.9% does not drop back in 2016/7, investigation and appropriate follow up action will be needed. Likewise, whilst SFD will highly likely remain the best value for money intervention of its type for Yemen, we should expect continued cost pressures for as long as the crisis continues. DFID and SFD should also consider ways of monitoring the economy and efficiency of work at a project level, which are both easy to collect and informative for example:

- Typical consultancy day rates
- #km of rural roads built per 1,000 workdays
- Total area of agricultural rehabilitated land and terraces (Hectares) per 1,000 workdays

Quality of financial management

SFD has continued its historically strong financial management track record this year. It received an unqualified opinion by the independent, external auditor (as it has done since its establishment 1997). Furthermore all disbursements by the Islamic Development Bank are individually audited before another payment is issued. SFD have also been subject to a DFID Due Diligence Assessment which concluded that SFD has the capacity and processes in place to effectively manage donor funds. An internal EU-commissioned assessment by the independent auditors Grant Thornton also reached a similar conclusion.

SFD’s automated, multicurrency/multi-donor financial management system allows SFD to track and record each transaction made across the organisation. SFD Branch Offices and HQ also regularly undertake sample checks on payments.

Though the state of the banking system in Yemen continues to deteriorate, SFD currently reports that all local banks with which it has accounts are still functioning and are safe and feasible. DFID should continue to watch the status of the banking system within Yemen closely to mitigate developing risks, as well as the ability of donors to get funding to SFD in Yemen through the international banking system. We have continued to successfully make payments to SFD this year though we are aware of others experiencing issues with transferring funds and there is a significant risk that we could experience difficulties transferring funds in future. Our payments are made directly from our bank account in the UK to an assigned DFID-SFD bank account in the Commercial Bank of Yemen. At no point do funds pass through the Central Bank of Yemen. We are confident in SFD’s management of these funds and receive financial expenditure statements before each new payment.

Date of last narrative financial report	December 2016
Date of last audited annual statement	October 2016

E: RISK (½ page)

Overall risk rating: Severe

Overview of programme risk

Yemen remains a challenging operating environment with high risks for delivery across the DFID Yemen portfolio. Major risks to the delivery of SFD’s work include: a) external interference in projects; b) funds not being used as intended; c) donor funding being further suspended due to the conflict, and; d) the conflict negatively effecting operational delivery and staff safety. SFD have remained adaptive to challenges: recently, for example, they secured assurances from their banks that SFD will be treated as a priority customer in any situation of cash shortages. This risk is most prominent under the cash-for-work programmes as SFD must use cash for beneficiaries (whereas commercial suppliers can be paid electronically). A further emerging risk could be the additional new $180m World Bank finance. Whilst this is a positive development it could potentially bring increased political attention and could mean attempts at aid diversion and/or interference are more likely.

Outstanding actions from risk assessment

As above, action should be continued in the following areas:

Banking: SFD and DFID should continue to closely monitor the status of the Yemeni banking and financial system in order to mitigate any developing risks.

Unsuspending funding: DFID should continue to promote funding to SFD, including through unlocking long-term suspended Gulf funding and lobbying partners to pay off Government of Yemen debts which would keep open World Bank and Islamic Development Bank funding. SFD should sustain and increase current donor support through demonstration of strong performance.

Interference and Capacity Overstretch: SFD and DFID should remain alert to the potential for increased attempts at aid diversion and/or interference due to new funding coming on stream and, with other donors at the upcoming donor meetings in Amman, discuss additional controls that can be developed.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

SFD's Phase IV was originally due to run between 2011 and 2015, with the UK’s £100 million commitment being provided by 31 December 2015. Following the outbreak of the conflict in early 2015 SFD, in consultation with donors, planned for a two-year crisis response extension period (2016 - 2017) in order to best continue delivering development goals whilst remaining adaptable to the crisis. The duration of DFID’s support has now been extended to match this two year period. Plans for SFD’s operations beyond 2017 (whether a new ‘Phase V’ or a further emergency extension) will need to be submitted over the coming months to allow donors sufficient time for planning ahead of 2018. DFID will push for this at the next annual SFD-donor meeting, planned for February 2017.

Performance of partnership (s)

SFD’s proactive management of risk, achievement of results and delivery of Value for Money (VfM) mean that the organisation continues to perform as a trusted partner, respected by the international community and able to consistently secure new funding from a variety of donors over the last year. Whilst SFD’s performance has been strong, continued emphasis should be placed on donors receiving timely reporting and assurance documents. On the other side it must be recognised that commercial performance would be improved through DFID ensuring that a clearer and more reliable payment forecast is given to SFD at the beginning of the new financial year.

 Asset monitoring and control

N/A. DFID does not control or claim ownership of SFD assets. This is due to the un-earmarked nature of our support.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

DFID’s core funding includes support to SFD’s Monitoring and Evaluation Unit. This Unit serves two stated primary objectives: a) supporting accountability to the Government of Yemen and donors, and;
b) Supporting internal learning and development. The unit tracks the progress of sub-projects under implementation and SFD conducts annual project and community-level surveys to obtain beneficiary feedback. SFD do not, however, include summaries or sample cases in their six-monthly reporting which would provide greater donor assurance. DFID will ask for a section including this to be added to the next six-monthly report.

Monitoring progress throughout the review period

Following a previous focus on conducting three utilisation surveys between 2014 and 2015 (as covered in last year’s Annual Review) SFD’s Monitoring and Evaluation Unit focussed on monitoring the impact of the conflict on their work in 2016 through monitoring their accessibility across Yemen and damaged projects. According to the latest reporting the number of inaccessible districts decreased to 20 (out of a total of 333 in Yemen) by October 2016, compared to 35 districts in March 2016. The governorates most affected by access issues for SFD were Sana’a (with 15% of districts recorded as inaccessible), Amran (14%) and Hajjah (10%).

We continue to monitor SFD's performance through our Independent Monitoring Programme (IMP). Earlier this year a verification study of SFD's WASH interventions confirmed delivery of work, with strong performance in the targeting and quality of water provision projects. The study did, however, record several reporting issues that were leading to over-reporting and ineffective targeting (for sanitation projects). These issues were primarily the result of gaps in SFD’s Management Information System which they are now working to solve. SFD have also pro-actively identified a series of other follow up actions as a result of the study; we will monitor these to assure they are implemented. A study of the SFD's Labour Intensive Works Programme (LIWP) is planned to start field work in early 2016. This will provide a wealth of information on one of the key areas of focus of SFD’s interventions.

Review Process

This Annual Review was completed by the SRO (Social Development Adviser) and Programme Manager, with technical inputs from the Economic Adviser, through a desk-based review. The data for the review is based largely on narrative and financial reports provided by SFD on a six-monthly and quarterly basis respectively, and subject to discussion and scrutiny by DFID staff. The AR has been quality assured by DFID Yemen’s Statistics and Results Adviser.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against VfM measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process