Programme Completion Review

Title: Ethiopia Portfolio Assurance Programme Phase II (EPAP II)
Final Programme Spend £ (full life): £300,999.55	Review Date:	June 2021
Programme Code: 300436	Start Date: November 2017	End Date: / March 2021

Summary of Programme Performance

Year	2018	2019	2021
Programme Score	B	A	A
Residual Risk Exposure Rating	Minor	Minor	Minor

DevTracker Link to Business Case (and any addendum):	Click Here
DevTracker Links to all logframes used during programme lifetime:	Click Here

Acronyms:

AR: Annual Review of programme
BC: Business Case
BRE: Building Resilience in Ethiopia Programme
DFID: UK’s Department for International Development (now part of FCDO)
EPAP II: Ethiopia Portfolio Assurance Programme (Phase II)
FA: Financial Aid to the Government of Ethiopia
FCDO-E: Foreign, Commonwealth and Development Office Ethiopia
FACE: Financial Accountability and Anti-Corruption Committee of FCDO Ethiopia
FAQ: Frequently Asked Questions
FPbC: Family Planning by Choice Programme
FRA: Fiduciary Risk Assessment
GEFA: Global Evaluation Framework Agreement
GEQIP-E: General Education Quality Improvement for Equity Programme
GoE: Government of Ethiopia
IPE: IPE Global Limited
MoF: Ethiopian Ministry of Finance
MoU: Memorandum of Understanding
NGO: Non-Governmental Organisation
PDEL: Programme Delivery Excellence Lead Team
PET: Public Expenditure Tracking
OpEx: Operational Excellence Team (former name of PDEL)
ODA: Official Development Assistance
R&M: Refugee and Migration Programme
SET: Supporting Ethiopia’s Transition
SEED: Supporting Election for Ethiopia’s Democracy System
SMT: Senior Management Team (of former DFID Ethiopia)
SRO: Senior Responsible Owner
ToR: Terms of Reference
TLs: Team Leaders
UNDP: United Nations Development Programme
VFM: Value for Money

A. Summary and Overview (1-2 pages)

Description of the programme and what it has achieved [1/2 page]

The Ethiopia Portfolio Assurance Programme Phase 2 (EPAP II) focused on providing increased assurance and strengthening FCDO-E’s ability to identify, understand, address, and manage delivery, reputational, safeguarding and fiduciary risks at programme and portfolio levels. EPAP II was a successor of Ethiopia Portfolio Assurance Programme (EPAP I) and built on the achievements and lesson learnt from EPAP I. It was designed to complement and supplement several initiatives, which FCDO-E already has in place by: ​
​
- commissioning in-depth reviews of the highest risk elements of our portfolio, ensuring there are robust governance, management and financial controls to mitigate fiduciary risk; ​
- conducting targeted cash flow tracking reviews;
- supporting staff in interpreting finance and assurance reports and adequate follow up​; and
- maintaining capability to respond to emerging risk areas.

The expected impact of the programme is to improve efficiency and effectiveness of FCDO’s investment in Ethiopia by ultimately ensuring that funds are reaching to their intended beneficiaries. EPAP II’s outcome was to support improved financial risk management and governance structure of implementing partners of FCDO-E.

The programme was led by Programme Delivery Excellence Lead (PDEL) team (formerly the OpEx Team) in FCDO-E and delivered by IPE Global Ltd (IPE), as per the contract signed in November 2018. EPAP II was extended by 18 months from the original Business Case life time, with a new end date of 20 November 2021, with no additional financing to offset procurement delays. Subsequently, FCDO Ministers decided that the programme should be closed earlier on 13 March 2021 due to an ODA prioritisation exercise that was undertaken following the outbreak of Covid-19.

Overall, the programme is judged to have met expectations and has been scored ‘A’. All of EPAP II’s outputs have been met despite a very difficult operating context, including internal conflicts in Ethiopia, COVID-19, procurement delays and internal challenges within FCDO-E to put forward programmes to be reviewed. During the life of the programme, full risk reviews of five programmes and an anti-corruption study were completed, where key risks were identified alongside recommendations to address these. In addition, more than six audited financial statements and interim financial reports from NGOs receiving funding through accountable grants, private sector firms delivering their work through contracts, GoE and multilaterals that FCDO has MoUs with were reviewed to inform EPAP II’s capability building output (to develop tailored trainings and various useful tools for FCDO-E staff). During the time of implementation, EPAPII provided assurances on the high-risk elements of a total programming of £388m by FCDO-E.

Major lessons learned, evidence generated and recommendations [1/2 page]

Procurement timing: Once the business case was approved in 2017, there were procurement delays that affected the start of the inception phase. This meant that there were limited deliverables in the first year of the programme. The time it takes to conclude procurement processes to appoint an implementing partner should not be underestimated by any new programme.

Lack of ownership from FCDO-E programme delivery teams and resourcing: At times, FCDO-E programme delivery teams showed limited interest in seeking support from EPAP II by putting forward programmes for reviews to enable the identification of and mitigation of risks (primarily due to competing priorities they have and workload issues). This contributed to delays in starting of reviews. Further, programme teams did not always follow up on and track progress on findings in a timely manner. Senior Leaders and programme Teams need to proactively follow up on and use the finding and recommendations from EPAP reviews more to enhance their delivery and inform their future decisions. Additionally, initiatives such as EPAP II should in the future consider providing additional internal resources to support the reviews (e.g. in central teams such as PDEL).

How this report was conducted [1 paragraph]

This report is based on a combination of partner reporting for each of their reviews and capacity building sessions/tools, the logframe, business case and minutes from periodic meetings. Information from the two annual reviews (AR 2018 and 2019) were also used where still relevant. In addition, data collection tools were prepared using a web-based survey method called ‘Survio’ to assess EPAP II’s performance against two output indicators.

Actions following approval of this report [1-2 paragraphs]

No further follow up action is required on finances and asset disposals, as all outstanding payments have already been made to IPE and no assets were procured for the programme. However, as part of building up on the outputs of EPAP II to increase FCOD-E’s ability to manage programme related risks, PDEL will monitor progress on recommendations from the risk reviews and disseminate lesson learnt.

## B: Theory of Change and Outcome Assessment (1-2 pages)

	Starting point	Final result
Budget	£1,000,000	£300,399.55
Timeframe	2.5 years / (November 2017- March 2020)	3.5 years / (November 2017- March 2021)
Outcomes	Outcome: Improved financial, risk management and governance structures of implementing partners of FCDO-E. / Outcome Indicator 1: EPAP leads to strengthening of systems and processes. / Outcome Indicator 2: Increased evidence base to make better funding decisions.	High risk areas identified for five programmes and recommendations made to address these, including undertaking Public Expenditure Tracking for a programme delivered through a Financial Aid support to GoE. / The effectiveness of existing anti-corruption interventions of GoE was also assessed through a study to support FCDO-E’s policy development in this area. / Two capacity building sessions were delivered to all programme delivery staff in FCDO-E alongside the development of four tools, to enhance their knowledge on interpreting audited and non-audited financial statements and managing fiduciary risks.

Overall assessment of programme outcomes, sustainability and VfM [1/2 – 1 page]

Outcomes
The assessment of outcomes shows that EPAP II had a positive result on improving financial, risk management and governance structures of implementing partners of FCDO-E. This was achieved through identifying and assessing high risk areas of five selected programmes:

  - Refugee and Migration Programme (R&M)
  - Family Planning by Choice Programme (FPbC)
  - General Education Quality Improvement for Equity Programme (GEQIP-E)
  - Supporting Ethiopia’s Transition (SET)
  - Supporting Election for Ethiopia’s Democracy System (SEED)

EPAP II also funded a study that assessed the effectiveness of existing anti-corruption interventions of Government of Ethiopia (GoE) and this enhanced the knowledge of FCDO-E to inform its policy making and Fiduciary Risk Assessment (FRA).

These outputs have contributed to providing increased assurance that UK taxpayers’ funds are spent prudently, each contributing to the attainment of EPAP II’s outcomes. From the survey questionnaire sent to programme delivery teams whose programme were reviewed, 71.4% of the respondents felt that the overall output of the EPAP II risk reviews were of high quality and that the outcome of the review was helpful to their delivery. This is slightly higher than the 70% target set. Also 100% of the respondents expressed that the capacity building sessions were useful and contributed to improved risk management.

Overall Spend Performance

Total spend performance for EPAP II was only 30% of the total budget allocated to the programme. This variance originated due to the following reasons:

1. procurement delays at the start of the programmes, which impacted the inception and programme implementation timelines;
2. Covid-19 and internal conflicts during the first full year of implementation brought slippages on programme reviews as well as limited international travel against the delivery plan, leading to low spend on expenses;
3. the high staff turnover rate from IPE also resulted in key personnel changes and a reduction on daily fee rates for some consultants; and
4. due to the ODA prioritisation exercise following the outbreak of Covid-19, it was decided that the programme should be closed early (by eight months) – this decision also meant that consideration for a ‘no-cost time extension’ were not feasible.
The overall financial performance for the programme was as follows:

Implementing Year	Revised Budget (£)	Actual spend (£)	Variance (£)	Variance (%)
2017/18	0.00	0.00	0.00	0
2018/19	0.00	0.00	0.00	0
2019/20	153,169.42	153,169.42	0.00	0
2020/21	846,830.58	147,230.13	699,600.45	83%
Total	1,000,000.00	300,399.55	699,600.45	70%

Sustainability
To sustain the gains from EPAP II, programme teams and senior leaders need to ensure that all key findings and recommendations from the programme risk reviews and the anti-corruption study are followed up. Importantly they should be used as key sources of evidence to manage risk at a portfolio level and for design of new BCs. PDEL team will have an important role in ensuring this.

EPAP II’s outputs will also continue to provide broader value to FCDO-E teams through analysing the findings and applying these to similar programmes as well as applying the tools produced to enhance the capability of programme delivery teams. For example, the standard audit ToRs and audit checklists have already been used as part of commissioning external audit.

Due to the ODA prioritisation exercise, the programme came to an end early. It is unlikely that an EPAP III will be developed. Teams need to ensure that they reserve sufficient budgets in their programmes to enable risk reviews like that of EPAP II in the future.

VFM
Economy measures relate to the independent, professional oversight and quality assurance that is gained from IPE. This has worked well, given the review findings provide additional credibility to existing assurance mechanisms already in place in programmes, recommending improvements in numerous areas.
Since the start of the programme, the cost drivers were mainly consultancy fees, economy class travel, subsistence and accommodation expenses for the international/local specialist per the business case. Costed workplans were put in place throughout the programme implementation. IPE also shared sample costed-work plans that ensured that specific costs against all deliverables were outlined and agreed clearly before payments were made.
Efficiency gains were made by having a standalone programme with centralised management in PDEL because it:
- allowed a single point of management for a single supplier;
- enabled more focused quality assurance and lesson learning, for FCDO and Programme implementing partners; and
- ensured the application of consistent standards, methodologies, and reporting formats across all the design, field work and review reports
Full risk review of the five programmes and the anti-corruption study costed FCDO £0.3m (i.e. an average £38k per review) providing assurance against around £388 million programming. In other words, every £1 investment in EPAP II has provided assurance against £1,463.23 worth of programming, representing good value for money.

The overall effectiveness of this programme is demonstrated by the improved programme delivery in FCDO-E and its implementing partners and the reduction in delivery, fiduciary, safeguarding and reputation risks. Each finding highlighted areas of weakness within our implementing partners. The EPAP II reports allowed FCDO-E programme teams to make informed decisions on the risk levels facing their programmes. They also enabled teams to determine appropriate control and assurance mechanisms for each programme. Through individual action plans to follow up on all accepted recommendations, each team is also able to address shortcomings, minimising risk to the UK’s and other partners’ investments. EPAP II also has wider and unquantifiable benefits of demonstrating FCDO-E’s commitment to optimise VFM and accountability, which goes beyond the benefits to the individual programmes that were reviewed.
All the reviewed programmes considered safeguarding risks through assessing partner organisations’ policies and principles. Recommendations in these areas increased compliance, enabling the better protection of vulnerable groups including women and girls. For instance, the R&M, SET and SEED reviews identified key risks, recommending better adherence to safeguarding policy and suggested capacity building training for the implementing partners’ staff. This promotes increased equity in FCDO’s programmes, which in turn contributes to an increased VFM.
Summarise the programme’s theory of change and results framework, including any changes to outcome indicators. [1/2 – 1 page]

The theory of change in the original business case (illustrated in the above diagram) did not change during the implementation of the programme. Ahead of the start of each review, IPE developed a risk-based work plan, methodologies, and approaches (using the criteria set for selection of programmes for review). This has been accomplished by reviewing business cases, logframes, progress reviews and audit reports of the selected programmes. The evidence from the various desk reviews, field visits and meetings as well as capacity building training led to identifying key risks and recommendations for improved control design and operating effectiveness and enhanced accountability of implementing partners and FCDO-E. The identification of key risks such as delivery, fiduciary and safeguarding risks that were not observed by previous audit reports and periodic reviews contributed to improved efficiency and effectiveness of FCDO-E investments. Therefore, we can conclude that the inputs and outputs contributed to the achievement of the outcomes and impact.

## C: Detailed Output Assessment (Output 1)

Output 1	Inception phase successfully completed
Output Score	A
Impact weighting (%)	0	Impact weighting revised since last AR?	Yes, down

Output Indicator	Starting Target	Final Logframe Target	Final Result Achieved
1.1. Portfolio level consideration undertaken to agree selection of programmes for review	-	-	- Approach to programme selected presented to Financial Accountability and Anti-Corruption Committee of FCDO Ethiopia (FACE) and the whole FCDO-E Team, and agreed. / - Three programmes (one from each team) have been selected and agreed for screening in year 1 review / Met expectation: A
1.2. Programme specific work undertaken	-	-	Methodologies for reviews developed and Risk of two programmes initiated / Met expectation: A

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]

      1. Portfolio level consideration undertaken to agree selection of programmes for review and Programme specific work undertaken.

To decide on the approaches the EPAP II reviews should take, a working group was established to gather feedback on key risks from each team, followed by a consultation of the senior leadership and all programme teams. Five key criteria for the selection of programmes were agreed:

1. Governance and management structures within partners and their robustness
2. Partners capacity to deliver
3. Delivery structure (this could be both complexity of the delivery chain and/or a programme having a combination of different aid delivery modalities)
4. Programmes which operate in an environment highly exposed to corruption
5. The high-risk rating in a programme (e.g. this could be delivery, fiduciary)

Additional factors were also agreed to be considered, including safeguarding risks, size and end date of programmes, and previous audits and reviews including EPAP I. In the first instance, four programmes (as per output indicator 1.1) were nominated (FPbC, GEQIP-E, R&M and BRE) and desk reviews were undertaken through reviewing of business cases, progress reports, logframes and interview of implementing partners to identify key areas of concerns. Subsequently, it was decided that risk reviews of two of these programmes (FPbC and R&M) would be undertaken. In addition to the desk reviews, field visits in two regions (Amhara and Tigray) and interviews with key stakeholders held.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme [1-2 paragraphs]

The reviews identified key risks and suggested solutions to strengthen implementing partners capacity for better programme delivery and fiduciary risk management approaches and therefore enhancing efficiency and effectiveness of the investment in these programmes (the assessment for this was covered in detail in the last EPAP II AR). The inception phase was economical, as IPE Global used the local office focal person (which was a free resource) for various tasks and meetings and standard contracting rates for desk reviews and field visits. The risk review approaches considered safeguarding polices and principles that contributed to increased equity.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

There were two key lessons learnt at the inception phase:

Limited capacity of programme implementing partners (due to vacancies or absence of key personnel) to deliver agreed objectives: this has been communicated to FCDO-E programme teams as a key lesson to increase assurances across the portfolio.

Absence of ratings in the risk findings and associated recommendations posed a challenge to FCDO-E and implementing partners on how to prioritise findings and gain maximum benefits quickly through addressing issues. From the Learning IPE took from the first-year reviews, it suggested rating all findings in the recent reviews (e.g. critical, high, major ratings for risk findings and high, medium, low for prioritisation of recommendations).

## C: Detailed Output Assessment (Output 2)

Output 2	Quality reports and effective action plans established and managed in accordance with identified needs within the FCDO portfolio
Output Score	A
Impact weighting (%)	80%		Impact weighting revised since last AR?	Yes, Up

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
2.1. Number of risk reviews completed for addressing key risks		Five reviews completed	Five reviews completed	Five Programmes’ risk reviews completed, identified key risks and recommendations to address the risks - Met Expectation: A
2.2.% of members of FCDO-E's programme teams (whose programmes were reviewed) agree that the risk reviews were of high quality and helpful to their programme delivery		80% 'agree' or 'agree strongly'	70% 'agree' or 'agree strongly'	71.4% of those surveyed ‘agreed' or 'agreed strongly' risk reviews were helpful to their programme delivery – Met expectation: A
2.3. % of EPAP Review recommendations received / agreed by programme teams		80% of recommendation accepted	80% of recommendation accepted	83% of the recommendation were accepted by programme teams - Met expectation: A
2.4. Action plans established and monitored by SRO's (e.g. in delivery plans, stand-alone trackers).		100% of accepted recommendations included in action plans and monitored	100% of received recommendations included in action plans and monitored	100% of the recommendations are included in individual programme delivery plans and in a central tracker - Met expectation: A

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]

2.1. Number of risk reviews completed for addressing key risks

In total, five reviews were undertaken during the life of the programme. All the reports for the programmes identified key risks with recommendations on ways to improve the existing governance and organisational structures, financial management systems, address delivery risks as well as fiduciary risk management that contributed to increased assurance for the efficient use of resources and effective use of UK investment.

The study that assessed GoE’s intervention on anti-corruption in Ethiopia was conducted through interviewing 15 institutions. Its key findings suggested ways to better manage and control corruption and informed internal policy making within FCDO-E.

2.2. Percentage (%) of members of FCDO-E's programme team (whose programmes are reviewed) agree that the risk reviews were of high quality and helpful to their programme delivery

Out of the total respondents for the survey questionnaires, 71.4% agreed that the risk reviews were of high quality and helpful to their programme delivery despite these reviews being undertaken during highly challenging times – this was marginally above the 70% target. The feedback also revealed that the anti-corruption study contributed to a broader office fiduciary risk assessment.

2.3-2.4 Percentage (%) of EPAP Review recommendations received / agreed by programme teams and action plans established and monitored by SRO's (e.g. in delivery plans, stand-alone trackers).

The reports for all six risk reviews (including the anti-corruption study) have been shared with programme delivery teams and 83% of total recipients confirm that they agreed with the final recommendations (only some recommendations were not accepted by FPbC programme team). A stand-alone tracker was developed and progress for previous reviews (FPbC and R&M) were followed up by PDEL. The tracker is being updated for the recent reviews (GEQIP-E, SEED & SET) to monitor progress teams are making on implementing the recommendations from the EPAP II reviews.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme [1-2 paragraphs]

The cost of major inputs such as field visits, consultancy fees etc. have reduced since the last AR due to travel restrictions for international consultants and high turnover on key personnel of IPE (previous key personnel were changed in 2020/2021 with new ones that had lower daily fees). In addition, one of the consortium members, BDO, which is a UK based firm, did not take part in the programme review and instead a local consortium partner led on financial elements of reviews – this contributed to some cost savings too, enhancing economy. That said, the overall output was achieved as planned due to the adaptive approach that IPE adopted. Full risk reviews of the five programmes and an anti-corruption study cost FCDO £0.3m (average £38k per review) providing assurance against around £388 million programming in total. In other words, every £1 investment in EPAP II has provided assurance against £1,463.23 worth of programming, representing good value for money.

All the reviews considered safeguarding risks through reviewing safeguarding principles, procedures and approaches and identifying key risks and suggesting solutions to ensure vulnerable groups including women and girls are protected that contributed to increased equity.

Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

The overall feedback from FCOD-E programme teams (according to the survey undertaken) revealed that IPE generated numerous concrete recommendation that teams can take forward with partners (including the GoE and other donors), to mitigate potential risks to programme delivery.

There are three key areas for consideration for similar initiatives such as EPAP II risk reviews in the future:

Importance of local presence of consortium partners: Covid-19 and internal conflicts impacted on IPE’s ability to undertake the programme reviews based on the original timelines. Due to travel restriction, the core IPE team in India could not join the field visits and most of the work they accomplished was based on desk reviews. While this posed a delivery risk, IPE were able to mitigate this by deploying consultants from their local office in Addis and made increased use of their local consortium partner – this also meant that the review benefited from experts who understood the local context very well.

Some of the reviews took longer than the initial work plan agreed with IPE due to unavailability of implementing partners for interview and securing time from FCDO-E programme teams to engage in the review process. In some instances, both groups did not prioritise the risk reviews (e.g. due to under-staffing and workload issues). Agreeing priorities in advance could mitigate this occurring again for future reviews.

Key findings and recommendations for some programme reviews were perceived as originating from small sample size studies and this affected some programme teams’ confidence to ‘buy-in’ to the suggested recommendation strongly (this is based on feedback from the survey). Forming a consensus on sample sizes that need to be used with programme teams early, taking into account cost implications, would have helped to tackle this perception head-on.

## C: Detailed Output Assessment (Output 3)

Output 3	Enhanced capability within FCDO Ethiopia to manage programme risks.
Output Score	A+
Impact weighting (%)	20%		Impact weighting revised since last AR?	Yes, Up

Output Indicator		Starting Target	Final Logframe Target	Final Result Achieved
3.1 Review of sample reports from various partner organisations to assess robustness and make recommendations for improvement		-	At least 6 reports reviewed. Assessment report produced.	A combination of reports (both audited and non-audited financial statements) from 6 programmes were reviewed. Assessment report produced. / Met Expectation: A
3.2 Build capability of staff through delivering training and sharing of lessons. % of staff who find the capability building useful.		-	At least 1 capability building session held. 70% or more find this useful.	Two capability building sessions delivered. 100% of participants found this useful. / Exceed Expectation: A+
3.3 Number of tools developed to help improve reporting by partners and staff capability to assess these.		-	Two Tools produced	Four tools developed. / Exceeded Expectation: A+

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score. [1/2 page]

3.1 Review of sample reports from various partner organisations to assess robustness and make recommendations for improvement

IPE reviewed audited and non-audited financial statements from programmes delivered through all types of aid modalities (contracts, financial aid to GoE, multilateral funding, accountable grants) from six programmes: these were the LIFT Programme (DAI contract), SAPHE (GoE-SDG pooled fund), CSSP (delivered by the British Council), the new WASH programme (MoF), BRE (UNICEF component) and GEQIP-E (delivered by the World Bank). The review involved analysing the audit findings, financial report components and audit recommendations. It aimed to develop tailored capacity building sessions by using the samples as case studies and identity potential areas for improvement from partners reporting. IPE also reviewed key documents (business cases, agreements with partners, reporting schedules and delivery plans) of the programmes to come up with their recommendations.

3.2 - 3.3 Build capability of staff through delivering training and sharing of lessons. % of staff who find the capability building useful and number of tools developed to help improving reporting.

Prior to designing the capability building session, IPE prepared a survey to all programme delivery staff to understand the different levels of knowledge on interpreting audited and non-audited financial statements. Using the survey results and the sample reports as case studies (as explained in 3.1), two workshops were delivered. These mainly focused on recommendations on how to interpret audited and non-audited financial statements and sharing of lessons from the case studies to enhance the capability of programme teams. The second survey conducted after the sessions showed that 100% of the respondents found the capability building sessions useful.

Based on the feedback from the two surveys and the learning material from the capacity building sessions, IPE developed four tools to help programme delivery team better interpret financial reports and become ‘intelligent consumers’ of reports from partners:

1. a ‘checklist’ of all the key contents of a key report and what teams should check
2. a list of FAQs to clarify the key technical contents that frequently appear in reports.
3. a sample reporting template for multi-laterals to better support teams in analysing budget to spend performance and inform the decision of disbursements.
4. a quick reference/guide to FCDO-E commissioned audits and standard audit ToR have also been issued to enhance the capability of programme teams and for better fiduciary risk management.
Lessons learned through this output, and recommendations for future programming [1-2 paragraphs]

All the session slides, checklists, quick guides and standard audit ToR were shared across the whole FCDO-E team to be used for future reference and contributed to enhancing the knowledge of all staff.

There are four areas for consideration for similar initiatives in the future:

The assessment from the sample reports that IPE collected showed that there are different types of reports (e.g. in terms of content or size) that FCDO-E receives from implementing partners. There are potential opportunities to streamline reporting from partners to simplify the information FCDO-E receives and enhance FCDO-E’s ability to review reports.

The 100% satisfaction score from the feedback received following the capability building sessions shows that there is potentially more appetite for continuous capability building sessions that would enhance the capability of programme teams.

Feedback from participants showed that learning some of the technical areas individually may at times be a challenge. Therefore, practical exercises and group discussions could further enhance participants learning.

SROs involvement in the capability sessions was relatively lower than programme management staff. This reflects the different roles within FCDO. In future tailored learning should be provided to SROs to encourage their deeper involvement.

D: Risk [½ - 2 pages]

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance. [1/2 page]

The overall risk rating throughout the duration of the programme was maintained at ‘minor’ and was within FCDO-E’s risk appetite. The programme risk register reflected risks across the six categories as previously defined by FCDO (reputational, operational, context, delivery, safeguarding and fiduciary). Risk was managed through the risk register on FCDO’s Aid Management Platform (AMP). This was regularly reviewed, updated through regular discussions with IPE and quarterly risk meetings, including identification of new risk. In addition, all risks in the register had mitigation measures in place that were continuously monitored.

The key risks in the last year related to early closure of EPAP II and the programme not achieving its intended objectives because of this. This was mitigated by holding discussions with partners to come up with a clear plan for delivery, revising milestones in the EPAP II logframe in a realistic manner and amending the EPAPII contract.

Other key risks with major and moderate residual risk ratings were as follows:

COVID-19 pandemic and security situation (Context risk): These led to travel restrictions and social distancing that hindered face-to-face meetings with key partners and field visits related to reviews.

Mitigation actions: IPE actively engaged their local office representatives and consortium members to ease travel around Ethiopia. Travel advice from the British Embassy was also shared with partners and PDEL assisted with facilitating visits.

Delay in programme selection for review due to Covid-19 and challenges with Programme Teams engaging in reviews (Delivery risk): this continued to be a key risk in both years of delivery, as it led to difficulties in delivering the programme due to shift on programme priorities and few programmes being out forward to be reviewed by EPAP II.

Mitigation actions: the EPAP II team in PDEL continually underscored the importance of risk reviews to programme teams, explaining their benefits and updates were provided at the FACE meeting. It also challenged programme teams both on inclusion and exclusion of programmes from reviews. These approaches largely helped mitigate the risk.
E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency. [1 page]

Performance of partners and FCDO, notably on commercial and financial issues

The programme disbursed £300,999.55 out of the approved £1,000,000 (30%). This was expected due to the delay in starting the programme and early closure of the programme. EPAP II was able to deliver all its objectives within this reduced budget, at a reduced cost than initially planned (economy) and efficiently due to its and consortium partners presence in Ethiopia.

EPAP II had two ‘no cost extensions’ amendments: The first was in 2019 to extend the end-date of the programme (till November 2021) to compensate the procurement delay at the start of the programme. The second amendment was in 2020 for change in key personnel and to effect Ministers decision to close the programme 8 months earlier than planned, as a result of the ODA prioritisation following the outbreak of the Covid-19 outbreak.

Performance of partnerships

IPE and its consortium partners delivered all expected outputs in line with agreed workplans and IPE had a very good working relationship with the EPAP II team in PDEL, and within the consortium members. There were regular bi-monthly progress monitoring meetings between FCDO-E and IPE, to discuss progress against the agreed work plan, risks, finances, compliance with FCDO-E rules, status of field visits for selected programmes and reviews and timely submission of quality reports and audits.

Challenges included one of the consortium members, BDO’s, failure to take part in the programme implementation as planned as well as high staff turnover in IPE, leading to an increased pressure on IPE. Additionally, Covid-19 significantly contributed to delays in undertaking the programme risk reviews and field visits as compared to the initial agreed workplan. Despite these challenges, IPE worked together with FCDO-E and its consortium partners to ensure all reviews were delivered before the end date of the programme.

Programme-level approach to monitoring and evaluation [1/2 page]

There was rigorous monitoring throughout the programme across all programme reviews and capacity building activities, including:

- a detailed report upon completion of inception phase,
- EPAP II team’s review of methodologies and work plans in collaboration with programme team,
- ToRs for each review/ study and methodology papers that set out the approach IPE would take on each project, enabling monitoring of progress,
- progress reports,
- regular meeting with partner to discuss issues and risks, and comprehensive reports of risk review.

A survey was also undertaken to gather evidence, by collecting feedback from FCDO-E programme delivery teams. The survey assessed whether the EPAP II reviews added value to programmes risk management approaches, enhanced capabilities of programme team as well partners’ capacity. Further, close follow up on the recommendations of reviewed programmes were assessed to ensure that improvements were made.

Date of last narrative financial report	N/A – invoices were sent to FCDO-E for approval in line with agreed workplans	Date of last audited annual statement	N/A