ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	UK Nigeria Infrastructure Advisory Facility
Country or region targeted	Nigeria
Type of cost extension (if applicable)	None
Original project budget	£80m
Original project start and end dates	Set up 15 May 2017 / Contract start 14 October 2019 / Initial contract end 13 October 2023 / Financial project end 13 April 2024
Cost extension value (if applicable)	Separate addendum for CDEL
New project end date (if applicable)	New end date: 12 April 2027
Business Case Vault Document No.	11768538

INFORMATION
What is the project’s purpose?
Enhanced management and planning of climate smart infrastructure development / Removed: “at the federal level and in the North-East Nigeria” / Added: “and planning” and “of climate smart”
What is the objective of the cost extension or other changes?
The main changes are to put climate (including energy transition) at the heart of the infrastructure development in line with UK Government ambition (and increased Nigerian ambition), with UK International Climate Finance being a main source of funding. / An addendum covering the £10m CDEL addition is being done separately as it will need more approvals/processing and this addendum needs processing earlier to give clarity for the existing technical assistance supplier. / The end date is being adjusted to allow for loading of the CDEL on to systems and tendering of a monitoring contract for both RDEL and CDEL. / There are also some adjustments reflecting changes in the security and political situation in Nigeria since the 2015 Business case and ODA prioritisation exercises in 2021-22. / These are explained in more detail below.
What is the additional and total support the UK will provide?
The only additional support is the CDEL which is in a separate addendum as it needs more work and approvals.
What are the expected results?
New results inserted in italics / Improved infrastructure and planning in Nigeria, including: - / Successful completion of Nigeria's power sector reforms, with a contract- based market operating sustainably, including reforming the Transmission Company of Nigeria (TCN) / A transformational improvement in way public money is spent on the Federal Road Network (FRN) with a reformed Federal Road Maintenance Agency (FERMA) using a UKNIAF developed Road Asset Management System (RAMS) to prioritise investments, factoring climate issues as a priority and greatly strengthened budgeting and project management capability. / Substantially improved processes for the wider capital budget. Aim is for all projects to be assessed for economic, social, climate change and environmental impacts with ability to attract climate finance prioritised - and decisions to prioritise on political grounds being exceptional and taken with knowledge of opportunity costs. [The BEIS PACT programme is taking over funding some of this through UKNIAF’s contractor in 21-22 and 22-23 due to FCDO budget reductions but this may come back into NIAF in later years, depending on BEIS/FCDO budget mergers.] / A significant pipeline (target $2bn) of climate smart Public Private Partnerships (PPPs) will have reached financial close with UKNIAF support, and Nigeria will have substantially improved processes for developing and assessing infrastructure. / The leverage of public and private climate finance will be measured for the PPP work - ICF KPIs 11 and 12. / The programme will also seek to track some potential Greenhouse Gas emissions avoided through their work and people made more resilient to climate change (ICF indicators KPIs 6 and 4). / ICF Transformational Change indicator KPI 15 will be used to measure the success in sustainable capacity building in the key institutions. / Removed results / Unbundling of TCN into a separate systems operator ­– removed due to budget / Broader large-scale capacity building of more institutions – this will now focus on a narrower group of institutions e.g. regulator, transmission company, roads and a narrower set of areas e.g. support to TCN cannot cover all areas and PPP capacity building will be constrained. / UKNIAF will have improved the timeliness and quality of at least £500 million of Nigerian Government and multilateral reconstruction spending in Borno and Yobe. Unfeasible due to worsened security situation. / Privatisation of National Integrated Power Plants complete and TCN concessioned / These may remain in public hands and not be privatised before 2026. / The PPP pipeline of $3bn - reduced to $2bn / Results are also being moved to later, recognising the fact that due to the budget reductions in 20-21,22-22 and most likely 22-23 the programme is not going to achieve results as envisaged, including delayed implementation of the Power Sector Reform Plan and the reduced traction with Federal Nigerian Government. A revised logframe has been drawn up and submitted.
What is the approach to implementation?
TetraTech International (previously named WYG) is implementing the main contract after winning the open competitive tender in 2019. It conducted an extended inception phase until early 2020, then was immediately asked to pivot towards Covid response e.g. in its work on roads, and its allocation was reduced considerably in 2020 as a result of ODA prioritisation so some work was put on hold. Covid also affected Nigerian Federal Government infrastructure budgets (Nigeria is oil dependent) and ability to focus. The 2021-2022 financial allocation to Tetra Tech was also reduced from planned £18m to £4.1m. This means a narrower focus within components and some reduced targets long term given the lead times with infrastructure planning. The contract is 4+2 years, starting in 2019. / There will be a separate contract (including potentially advisory and fund management contracts) for the 2021-22 £10m CDEL – which it is proposed to allocate to an existing fund as either a grant or first loss facility. This will be managed in line with the ProF rules around Development Capital. See separate Business Case addendum which will follow. / An FCDO Adviser will be programme funded and seconded to Tetra Tech, with external facing focus .The adviser will help liaison with the significant number of Ministries, agencies and States, development partners, facilitate COP26 energy transition work and thereafter on climate finance engagement including with other development partners, multilaterals, CDC and Infracredit, facilitating bridging the gap between the Technical Assistance and the investments. This will improve the overall impact of the programme. / There is regular liaison with the energy donor working group and government counterparts. Some other donors are able to step in on some of the off-grid energy work for example or decarbonisation. / Further, HMG’s BEIS (Business Energy and Industrial Strategy Department) has agreed to fund some of NIAF’s proposed work. The work with the Ministry of Finance around climate smart infrastructure planning which NIAF started in 21-22 but stopped due to budget can continue via Tetra Tech but through the PACT (Partnership for Accelerated Transition Programme). While the NIAF contract will be used, FCDO will act solely as a conduit and manager for supervising the finance. The performance and results (and final spend) will be reported through the PACT programme.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
Putting climate change at the heart of most activities. / The original Business Case included in it some elements of climate change, namely mainstreaming climate into infrastructure planning and reducing gas flaring. The inception phase strengthened this by adding “facilitating achievement of Nigeria’s NDCs (Nationally Determined contributions)” into the Theory of Change. / From 2021-2022, in line with increased UK and Nigeria ambition on climate change, it will become a key part of all UKNIAF components and the theory of change, including facilitating energy transition away from fossil fuels and general decarbonisation, as well as infrastructure being more resilient to floods and greater heat and helping people cope with the impacts of climate change. / International Climate Fund (ICF) funding / The programme will therefore have International Climate Finance as the main element of its funding. The results indicators will include ICF indicators -in particular mobilisation of climate finance, institutional transformational change and GHG emissions. / There is an additional £10m ICF CDEL which will be used to de-risk or bridge the viability gap of impactful climate infrastructure e.g. off grid energy access or clean cooking initiatives, leveraging large amounts of private finance and we plan to monitor improved energy access through this. It will likely be deployed into a fund with Infracredit, a Private Infrastructure Development Group entity in Nigeria. See separate Business Case Addendum. / Removal of North East component / The 2015 Business case assumed continued stability in the North East and that NIAF could advise the Nigerian Government and donor around rebuilding infrastructure. In practice the situation in Borno and Yobe is unsuitable for this as Boko Haram and Islamic State have gained territory and made both States too unstable for large scale investments. Donor and Nigerian government funds are focussed on humanitarian support. It is therefore proposed to remove this component permanently as this situation is not likely to change and it’s a logical approach given the overall budget reduction for UKNIAF. / Combining capital budgets and PPP components into Infrastructure Financing / These were separate components but there is significant overlap, especially as Nigeria’s fiscal situation makes PPPs often the only viable option and both have similar budgeting and planning skills requirements. They are therefore combined into one component. This work will mainstream climate priorities into infrastructure planning and seek to leverage climate finance for projects. / State emphasis for PPPs / The original business case assumed greater budgets and buy in at the Federal level for competitive tenders, including in departments such as the Ministry of Transport on areas such as railway lines and airports. In practice the Ministry of Transport has been focussed only on single source export finance projects with China for railways and airports. The Federal government is also unlikely to achieve large infrastructure projects between now and elections (in 2023 but focus is already shifting), so the PPP plans have shifted to State level projects where Governors have more stability. The careful choice of States reflects FCDO priority ones and ones with good track records or potential of treating commercial investors well as well as ones which have viable pipeline projects that development or climate financiers are willing to support e.g. Kaduna, Kano, Nasarawa, Edo, Ekiti, Ogun, Lagos. A mutual accountability framework is already in place with Kaduna and similar steps will be taken in other states. / Revised components and proportions of spend / The programme spend will shift to reflect traction with the Nigerian government, any sourcing from ICF/climate finance and focus of other donors or programmes e.g. BEIS programming. / Likely revised proportions are: - / RDEL / Tetra Tech Contract maximum is £72.8m: - / Power 20-35% / Roads 15- 30% - a large proportion of Federal Government budget (not all counting as ICF) / Infrastructure Financing 20-35% / Programme funded adviser, monitoring contract, audit – 2 to 5% / CDEL £10m - the details of this spend will be in a separate addendum to follow / Monitoring / A contract for monitoring, incorporating the Technical Review Panel (TRP) envisaged in the business case and contract will be tendered shortly, now the freeze on contracts is lifted. It will have less staff, reflecting the budget reduction and given Covid travel and quarantine issues, work will be remote as far as possible. The proposal is for a team lead to visit country and energy, infrastructure, roads and climate specialists remotely twice a year. This will also influence the decision on whether to offer the 2-year contract extension – decision point mid-2022. / The planned mid -term evaluation foreseen in the Business case will not occur due to budgets but also the fact that the work has been cut back so there is less justification to review (TRP will provide written reports which will give some independence. The appropriateness of an end term broader review/evaluation will be reassessed along with the contract extension decision and depending on funding. / Value for money framework / Tetra Tech’s payments link to performance under Economy and Effectiveness indicators. There is a robust arrangement to benchmark input costs every 6 months. / Effectiveness is harder to measure during the programme as this is mostly qualitative work, with any quantitative results arriving late in the programme and further this is an adaptive programme – see ODI analysis on assessing VfM in adaptive programmes. The assessment of qualitative work is time-consuming, requires technical expertise (which was lacking) and has been difficult but will be done with the assistance of the Technical Review Panel. / The interim PRO (Team Lead of Ec Dev team) has assessed that UKNIAF work and Task Orders in the energy space were (often at the demand of ministries) overly focussed on producing longwinded academic think piece documents which risked not leading to institutional change and often lacked a reality check with Nigeria’s politics and reduced budget situation. Deliverables are therefore shifting to being more user friendly and focussed on what practical changes can be achieved and on disseminating/raising the willpower/traction for such change, using FCDO and other donors’ influencing powers. / A key piece of work from the downscaling is how to capture value from the work abruptly abandoned at the end of the financial year with the ODA cuts e.g. UKNIAF assessed how to unbundle TCN or what NBET (Nigeria’s bulk purchaser) could do on contract reforms and analysed off grid policy procedures for Rural Electrification Agency. This work was not then followed up on, especially since the instructions that we could not communicate externally between February and end May limited the ability to do handovers or workshops for broader donors before the individual expert consultants left. The plan is to use the sector leads to do some handover/lessons. / Gender and equity / Evidence is women benefit more from provision of power, transport and water than men. The programme has also built into systems designing infrastructure for the poor and women. The roads assessments focussed on prioritising routes for food security for example. / Revised Theory of Change incorporating climate / This theory of change reflects the narrower focus of counterpart institutions as well as mainstreaming climate more clearly. / This table does not replace the more extensive risk register but aims to show how risks link in with the Theory of Change above. / Assumption Risk and chance of materialising Consequence of risk materialising and mitigation / Continued traction with Nigerian Government counterparts, including on power sector reform and roads legislation and climate MEDIUM to HIGH / Deterioration with elections nearing – FGN becomes less willing to take difficult reform decisions which may be politically unpopular. Market reforms in power sector and energy transition (which requires private capital to take risk) becomes less viable. / Pivoted some work e.g. PPPs to States. / Could shift funding further away from difficult reforms and to easier entities. This will deliver some results although less transformational. / The previous work on roads legislation risks being wasted if the legislation is not passed. / Security does not further deteriorate to make PPP work in some states unviable MEDIUM likelihood / Further deterioration Kaduna was changed to red by FCDO for security in May 2021 but this should be manageable. Other lower risk states included in programme to spread the risk. / Borno and Yobe already removed. / Funding available for implementing roadworks LOW If FGN funding is reduced (it is currently about **% of Nigeria’s budget) then this will affect quantum and timing of results in the road sector. / Ultimately, we could withdraw support. / World Bank has funding for implementation of power sector databases LOW / As envisaged in existing loan instrument. The data design and collection work would need shifting to a cruder, cheaper database potentially which could be more easily procured. / Programme re-design assumes a 20% year on year RDEL increase from 21-22 – assuming GNI increase and increased ICF spend available for country offices. MEDIUM A further funding reduction would affect the results produced and require another revisit to the logframe. / Staffing availability in FCDO to supervise HIGH and already materialised issue of lack of full time PRO for UKNIAF. Less value for money due to reduced ability to supervise programme and nimbleness of pivots. / Programme funding an adviser will provide critical support to the PRO including technical expertise. / END